## RABillBrowse_projwise6385909120
Project RA Bill
GANGA DHAM TOWERS
Bill Date From 01/04/2010 To 30/04/2023
Page 1 of 1
Total Records: 35601 Records 1 To 35601
Project | WO NO | RABill Sr.No | RA Bill Date | Cont Bill No | Contractor | Executed_By | Voucher_No | TASK | Labour_Name | Qty | Unit | Rate | PS % | Retention_Amt | Total_RetRelease | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Total Amount | Status | Credits | Debits | TDS_Amt | Due Date
GANGA DHAM TOWERS | 843 | 102904 | 30 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2439 | A East Side 27th to 31th Floor | Glazing / Facad Work (M) | 2030.1968 | Sq.Ft | 823 | 100 | 0 | 0 | 1670852 | IGST 18% I/P RD | 300753.36 | 1971605.36 | 1971605.36 | Approved | 0 | 0 | 0 | 30 Mar 2023
GANGA DHAM TOWERS | 843 | 102903 | 30 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2438 | A West Side 21st to 26th Floor | Glazing / Facad Work (M) | 3659.0037 | Sq.Ft | 537 | 100 | 0 | 0 | 1964885 | IGST 18% I/P RD | 353679.3 | 2318564.3 | 2318564.3 | Approved | 0 | 0 | 0 | 30 Mar 2023
GANGA DHAM TOWERS | 1431 | 102865 | 29 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2428 | B North Side 11th To 15th Floor | Glazing / Facad Work (M) | 349.73 | Sq.Ft | 537 | 100 | 4695.13 | 0 | 187805 | IGST 18% I/P RD | 33804.9 | 221609.9 | 221609.9 | Approved | 0 | 0 | 0 | 29 Mar 2023
GANGA DHAM TOWERS | 843 | 102862 | 18 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2432 | A West Side 6th to 10th Floor | Glazing / Facad Work (M) | 3059.9907 | Sq.Ft | 537 | 100 | 0 | 0 | 1643215 | IGST 18% I/P RD | 295778.7 | 1938993.7 | 1938993.7 | Approved | 0 | 0 | 0 | 18 Mar 2023
GANGA DHAM TOWERS | 1431 | 102861 | 10 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2421 | B South Side 11th To 15th Floor | Glazing / Facad Work (M) | 1896.1453 | Sq.Ft | 537 | 100 | 25455.75 | 0 | 1018230 | IGST 18% I/P RD | 183281.4 | 1201511.4 | 1201511.4 | Approved | 0 | 0 | 0 | 10 Mar 2023
GANGA DHAM TOWERS | 843 | 102860 | 06 Mar 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2433 | A North Side 27th to 31th Floor | Glazing / Facad Work (M) | 2982.8384 | Sq.Ft | 823 | 100 | 0 | 0 | 2454876 | IGST 18% I/P RD | 441877.68 | 2896753.68 | 2896753.68 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1431 | 102859 | 08 Feb 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2437 | B North Side 1st To 5th Floor | Glazing / Facad Work (M) | 2649.7579 | Sq.Ft | 537 | 100 | 35573 | 0 | 1422920 | IGST 18% I/P RD | 256125.6 | 1679045.6 | 1679045.6 | Approved | 0 | 0 | 0 | 08 Feb 2023
GANGA DHAM TOWERS | 1431 | 102858 | 08 Feb 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2422 | B North Side 16th To 20th Floor | Glazing / Facad Work (M) | 2727.4544 | Sq.Ft | 537 | 100 | 36616.08 | 0 | 1464643 | IGST 18% I/P RD | 263635.74 | 1728278.74 | 1728278.74 | Approved | 0 | 0 | 0 | 08 Feb 2023
GANGA DHAM TOWERS | 1431 | 102857 | 02 Feb 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2423 | B North Side 11th To 15th Floor | Glazing / Facad Work (M) | 2648.3818 | Sq.Ft | 537 | 100 | 35554.53 | 0 | 1422181 | IGST 18% I/P RD | 255992.58 | 1678173.58 | 1678173.58 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1431 | 102856 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2424 | B East Side 27th To 31st Floor | Glazing / Facad Work (M) | 1782.7448 | Sq.Ft | 823 | 100 | 0 | 0 | 1467199 | IGST 18% I/P RD | 264095.82 | 1731294.82 | 1731294.82 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102855 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2434 | A West Side 27th to 31th Floor | Glazing / Facad Work (M) | 1748.2224 | Sq.Ft | 823 | 100 | 0 | 0 | 1438787 | IGST 18% I/P RD | 258981.66 | 1697768.66 | 1697768.66 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 1431 | 102854 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2425 | B North Side 21st To 26th Floor | Glazing / Facad Work (M) | 2487.3892 | Sq.Ft | 537 | 100 | 33393.2 | 0 | 1335728 | IGST 18% I/P RD | 240431.04 | 1576159.04 | 1576159.04 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102853 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2431 | A North Side 27th to 31th Floor | Glazing / Facad Work (M) | 960.6707 | Sq.Ft | 823 | 100 | 0 | 0 | 790632 | IGST 18% I/P RD | 142313.76 | 932945.76 | 932945.76 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 1431 | 102852 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2420 | B North Side 6th To 10th Floor | Glazing / Facad Work (M) | 2424.46 | Sq.Ft | 537 | 100 | 32548.38 | 0 | 1301935 | IGST 18% I/P RD | 234348.3 | 1536283.3 | 1536283.3 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 1431 | 102851 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2426 | B North Side 27th To 31st Floor | Glazing / Facad Work (M) | 1586.0158 | Sq.Ft | 823 | 100 | 0 | 0 | 1305291 | IGST 18% I/P RD | 234952.38 | 1540243.38 | 1540243.38 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 1431 | 102850 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2427 | B North Side 27th To 31st Floor | Glazing / Facad Work (M) | 1598.6768 | Sq.Ft | 823 | 100 | 0 | 0 | 1315711 | IGST 18% I/P RD | 236827.98 | 1552538.98 | 1552538.98 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102849 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2435 | A East Side 27th to 31th Floor | Glazing / Facad Work (M) | 1581.9684 | Sq.Ft | 823 | 100 | 0 | 0 | 1301960 | IGST 18% I/P RD | 234352.8 | 1536312.8 | 1536312.8 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102848 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2430 | A West Side 27th to 31th Floor | Glazing / Facad Work (M) | 1635.2211 | Sq.Ft | 823 | 100 | 0 | 0 | 1345787 | IGST 18% I/P RD | 242241.66 | 1588028.66 | 1588028.66 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102847 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2429 | A South Side 27th to 31th Floor | Glazing / Facad Work (M) | 1712.452 | Sq.Ft | 823 | 100 | 0 | 0 | 1409348 | IGST 18% I/P RD | 253682.64 | 1663030.64 | 1663030.64 | Approved | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 843 | 102846 | 31 Jan 2023 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED |  | A South Side 27th to 31th Floor | Glazing / Facad Work (M) | 1696.6841 | Sq.Ft | 823 | 100 | 0 | 0 | 1396371 | IGST 18% I/P RD | 251346.78 | 1647717.78 | 1647717.78 |  | 0 | 0 | 0 | 31 Jan 2023
GANGA DHAM TOWERS | 699 | 99351 | 29 Apr 2023 |  | SUSHANT ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 234 | D Bldg Lift Pit Waterproofing (L) | RCC Buffer Columns-BC | 4 | No. | 800 | 100 | 80 | 0 | 3200 | CGST 0% URD I/P | 0 | 3200 | 3200 | Approved | 0 | 0 | 32 | 29 Apr 2023
GANGA DHAM TOWERS | 1564 | 99350 | 29 Apr 2023 |  | JAY GANESH ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 241 | STP Pumproom internal Plaster Work | Internal Plaster DCW | 927.83 | Sq.Ft | 15 | 100 | 347.94 | 0 | 13917.45 | CGST 0% URD I/P | 0 | 13917.45 | 13917.45 | Approved | 0 | 0 | 501 | 29 Apr 2023
GANGA DHAM TOWERS | 1564 | 99350 | 29 Apr 2023 |  | JAY GANESH ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 241 | Pumproom Brickwork,Plaster work 6" | 6" Brick Work | 176 | Sq.Ft | 18 | 100 | 79.2 | 0 | 3168 | CGST 0% URD I/P | 0 | 3168 | 3168 | Approved | 0 | 0 | 501 | 29 Apr 2023
GANGA DHAM TOWERS | 1564 | 99350 | 29 Apr 2023 |  | JAY GANESH ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 241 | STP Pumproom External Plater | External Plaster DCW | 1227.4 | Sq.Ft | 25 | 100 | 767.13 | 0 | 30685 | CGST 0% URD I/P | 0 | 30685 | 30685 | Approved | 0 | 0 | 501 | 29 Apr 2023
GANGA DHAM TOWERS | 1564 | 99350 | 29 Apr 2023 |  | JAY GANESH ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 241 | Pumproom Brickwork,Plaster work 6" | Patli Mkt - R.Ft | 118.73 | R.Ft | 20 | 100 | 59.37 | 0 | 2374.6 | CGST 0% URD I/P | 0 | 2374.6 | 2374.6 | Approved | 0 | 0 | 501 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2004 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2504 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2603 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2501 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2503 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2601 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2502 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2602 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2604 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2503 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2603 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2602 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 803 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2601 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2601 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 901 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2602 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2501 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2604 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2604 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2502 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 1601 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 1901 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2502 Chemical & IPS Waterproofing | IPS W/P | 434.492 | Sq.Ft | 11 | 100 | 477.94 | 0 | 4779.41 | CGST 0% URD I/P | 0 | 4779.41 | 4779.41 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2504 Chemical & IPS Waterproofing | IPS W/P | 422.94 | Sq.Ft | 11 | 100 | 465.23 | 0 | 4652.34 | CGST 0% URD I/P | 0 | 4652.34 | 4652.34 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2602 Chemical & IPS Waterproofing | IPS W/P | 434.492 | Sq.Ft | 11 | 100 | 477.94 | 0 | 4779.41 | CGST 0% URD I/P | 0 | 4779.41 | 4779.41 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2604 Chemical & IPS Waterproofing | IPS W/P | 422.94 | Sq.Ft | 11 | 100 | 465.23 | 0 | 4652.34 | CGST 0% URD I/P | 0 | 4652.34 | 4652.34 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2601 Chemical & IPS Waterproofing | IPS W/P | 414.2475 | Sq.Ft | 11 | 100 | 455.67 | 0 | 4556.72 | CGST 0% URD I/P | 0 | 4556.72 | 4556.72 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2603 Chemical & IPS Waterproofing | IPS W/P | 344.4035 | Sq.Ft | 11 | 100 | 378.84 | 0 | 3788.44 | CGST 0% URD I/P | 0 | 3788.44 | 3788.44 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 101 Chemical & IPS Waterproofing | IPS W/P | 414.2475 | Sq.Ft | 11 | 100 | 455.67 | 0 | 4556.72 | CGST 0% URD I/P | 0 | 4556.72 | 4556.72 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 401 | 99330 | 29 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 202 | A 2503 Chemical & IPS Waterproofing | IPS W/P | 344.4035 | Sq.Ft | 11 | 100 | 378.84 | 0 | 3788.44 | CGST 0% URD I/P | 0 | 3788.44 | 3788.44 | Approved | 0 | 0 | 576 | 29 Apr 2023
GANGA DHAM TOWERS | 184 | 99329 | 28 Apr 2023 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 150 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 1 | No. | 1000000 | 20 | 0 | 0 | 200000 | C+S GST 18% I/P RD | 36000 | 236000 | 236000 | Approved | 0 | 0 | 20000 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lobbby Flooring | Vitrified Flooring -Bco | 647 | Sq.Ft | 45 | 100 | 727.88 | 0 | 29115 | C+S GST 18% I/P RD | 5240.7 | 34355.7 | 34355.7 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | Dado Work - BC | 30 | Sq.Ft | 70 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 634 | 99323 | 28 Apr 2023 |  | R K INTERIOR | R K INTERIOR | EV - 426 | A 26th Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 3658 | 28 Apr 2023
GANGA DHAM TOWERS | 45 | 99321 | 27 Apr 2023 |  | NILIMA BHOSEKAR | NILIMA BHOSEKAR | EV - 164 | Landscape Consultancy | Landscape Consultancy. | 0.4 | No. | 2500000 | 5 | 0 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 30000 | 27 Apr 2023
GANGA DHAM TOWERS | 45 | 99321 | 27 Apr 2023 |  | NILIMA BHOSEKAR | NILIMA BHOSEKAR | EV - 164 | Landscape Consultancy | Landscape Consultancy. | 1 | No. | 2500000 | 10 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 0 | 30000 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Structural Platform - C RCC Consultancy | RCC Consultancy | 4613.98 | Sq.Ft | 6 | 100 | 0 | 0 | 27683.88 | C+S GST 18% I/P RD | 4983.1 | 32666.98 | 32666.98 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Structural Platform - A RCC Consultancy | RCC Consultancy | 4613.98 | Sq.Ft | 6 | 100 | 0 | 0 | 27683.88 | C+S GST 18% I/P RD | 4983.1 | 32666.98 | 32666.98 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Structural Platform - B RCC Consultancy | RCC Consultancy | 2783.57 | Sq.Ft | 6 | 100 | 0 | 0 | 16701.42 | C+S GST 18% I/P RD | 3006.26 | 19707.68 | 19707.68 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Entrance Gate details | Consultancy Charges | 1 | No. | 25000 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Meditation Hall RCC Consultancy | RCC Consultancy | 1683 | Sq.Ft | 5.25 | 100 | 0 | 0 | 8835.75 | C+S GST 18% I/P RD | 1590.44 | 10426.19 | 10426.19 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Tower A OHWT RCC Consultancy | RCC Consultancy | 61900 | Ltrs | 0.15 | 100 | 0 | 0 | 9285 | C+S GST 18% I/P RD | 1671.3 | 10956.3 | 10956.3 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | STP (36 KLD Capacity) RCC Consultancy | RCC Consultancy | 36000 | Ltrs | 0.15 | 100 | 0 | 0 | 5400 | C+S GST 18% I/P RD | 972 | 6372 | 6372 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | Tower C OHWT RCC Consultancy | RCC Consultancy | 61900 | Ltrs | 0.15 | 100 | 0 | 0 | 9285 | C+S GST 18% I/P RD | 1671.3 | 10956.3 | 10956.3 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 419 | 99320 | 27 Apr 2023 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 310 | EWS Building OHWT RCC Consultancy | RCC Consultancy | 32500 | Ltrs | 0.15 | 100 | 0 | 0 | 4875 | C+S GST 18% I/P RD | 877.5 | 5752.5 | 5752.5 | Approved | 0 | 0 | 13475 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2501 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 10 | No. | 150 | 100 | 150 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2604 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2603 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2503 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2601 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2602 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2502 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2503 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2501 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2504 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2504 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 401 | 99316 | 27 Apr 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA |  | A 2501 Chemical & IPS Waterproofing | IPS W/P | 436 | Sq.Ft | 11 | 100 | 479.6 | 0 | 4796 | CGST 0% URD I/P | 0 | 4796 | 4796 |  | 0 | 0 | 243 | 27 Apr 2023
GANGA DHAM TOWERS | 1443 | 99304 | 26 Apr 2023 |  | AQUARIUS WATERPROOFING | AJAY KUMAR GUPTA | EV - 151 | EWS STP - Int. Chemical Waterproofing+Ghotai Plaster | Screeding W/P-BCo | 388 | Sq.Ft | 15 | 100 | 582 | 0 | 5820 | CGST 0% URD I/P | 0 | 5820 | 5820 | Approved | 0 | 0 | 982 | 26 Apr 2023
GANGA DHAM TOWERS | 1443 | 99304 | 26 Apr 2023 |  | AQUARIUS WATERPROOFING | AJAY KUMAR GUPTA | EV - 151 | EWS STP - Int. Chemical Waterproofing+Ghotai Plaster | Chemical Waterproofing (M+L).Sq.ft | 2655.26 | Sq.Ft | 22 | 100 | 5841.57 | 0 | 58415.72 | CGST 0% URD I/P | 0 | 58415.72 | 58415.72 | Approved | 0 | 0 | 982 | 26 Apr 2023
GANGA DHAM TOWERS | 1443 | 99304 | 26 Apr 2023 |  | AQUARIUS WATERPROOFING | AJAY KUMAR GUPTA | EV - 151 | EWS STP - Int. Chemical Waterproofing+Ghotai Plaster | Cement Ghotai Plaster | 2267.33 | Sq.Ft | 15 | 100 | 3401 | 0 | 34009.95 | CGST 0% URD I/P | 0 | 34009.95 | 34009.95 | Approved | 0 | 0 | 982 | 26 Apr 2023
GANGA DHAM TOWERS | 1444 | 99296 | 26 Apr 2023 |  | AQUARIUS WATERPROOFING | AJAY KUMAR GUPTA | EV - 382 | EWS STP External Waterproofing Work | Membrane Horizontal Waterproofing (M) | 294.1176 | Sq.Ft | 34 | 100 | 0 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 0 | 26 Apr 2023
GANGA DHAM TOWERS | 1567 | 99286 | 25 Apr 2023 |  | AAKAAR INDUSTRIES | AAKAAR INDUSTRIES | EV - 361 | Tower C Debris chute system - 1 Mtrs | Debris Chute system (M+L) | 11 | Mtrs | 1925 | 100 | 0 | 0 | 21175 | C+S GST 18% I/P RD | 3811.5 | 24986.5 | 24986.5 | Approved | 0 | 0 | 212 | 25 Apr 2023
GANGA DHAM TOWERS | 901 | 99279 | 24 Apr 2023 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 278 | Tower C Safety Net | Safety Net Fixing- SO | 15601.8519 | Sq.Ft | 2.7 | 100 | 1053.13 | 0 | 42125 | C+S GST 18% I/P RD | 7582.5 | 49707.5 | 49707.5 | Approved | 0 | 0 | 508 | 24 Apr 2023
GANGA DHAM TOWERS | 901 | 99279 | 24 Apr 2023 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 278 | Tower C Safety Net | Safety Net Removing- SO | 6456.2963 | Sq.Ft | 1.35 | 100 | 0 | 0 | 8716 | C+S GST 18% I/P RD | 1568.88 | 10284.88 | 10284.88 | Approved | 0 | 0 | 508 | 24 Apr 2023
GANGA DHAM TOWERS | 145 | 99253 | 21 Apr 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 138 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 21 Apr 2023
GANGA DHAM TOWERS | 145 | 99252 | 21 Apr 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 139 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 21 Apr 2023
GANGA DHAM TOWERS | 145 | 99251 | 21 Apr 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 137 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 21 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 2603 Gypsum Plaster | Gypsum on Wall (M) | 2931.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259 | C+S GST 5% I/P RD | 512.96 | 10771.96 | 10771.96 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 2404 Gypsum Plaster | Gypsum on Wall (M) | 1062 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3717 | C+S GST 5% I/P RD | 185.86 | 3902.86 | 3902.86 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 2504 Gypsum Plaster | Gypsum on Wall (M) | 3299 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.5 | C+S GST 5% I/P RD | 577.32 | 12123.82 | 12123.82 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 2604 Gypsum Plaster | Gypsum on Wall (M) | 3299 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.5 | C+S GST 5% I/P RD | 577.32 | 12123.82 | 12123.82 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 703 Gypsum Plaster | Gypsum on Wall (M) | 1162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 4067 | C+S GST 5% I/P RD | 203.36 | 4270.36 | 4270.36 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 2503 Gypsum Plaster | Gypsum on Wall (M) | 2931.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259 | C+S GST 5% I/P RD | 512.96 | 10771.96 | 10771.96 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 303 Gypsum Plaster | Gypsum on Wall (M) | 2931.16 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259.06 | C+S GST 5% I/P RD | 512.96 | 10772.02 | 10772.02 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 394 | 99244 | 20 Apr 2023 |  | A K INTERIOR CONTRACTOR | SWASTIK MARBLE WORKS | EV - 73 | A Bldg Flat No. 304 Gypsum Plaster | Gypsum on Wall (M) | 3299.12 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.92 | C+S GST 5% I/P RD | 577.34 | 12124.26 | 12124.26 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 302 Gypsum Plaster | Gypsum on Wall (M) | 3443.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12052.36 | C+S GST 5% I/P RD | 602.62 | 12654.98 | 12654.98 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 701 Gypsum Plaster | Gypsum on Wall (M) | 1688 | Sq.Ft | 3.5 | 100 | 0 | 0 | 5908 | C+S GST 5% I/P RD | 295.4 | 6203.4 | 6203.4 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 2602 Gypsum Plaster | Gypsum on Wall (M) | 3443.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12051 | C+S GST 5% I/P RD | 602.56 | 12653.56 | 12653.56 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 2501 Gypsum Plaster | Gypsum on Wall (M) | 3523 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.5 | C+S GST 5% I/P RD | 616.52 | 12947.02 | 12947.02 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 802 Gypsum Plaster | Gypsum on Wall (M) | 714 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2499 | C+S GST 5% I/P RD | 124.96 | 2623.96 | 2623.96 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 2601 Gypsum Plaster | Gypsum on Wall (M) | 3523 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.5 | C+S GST 5% I/P RD | 616.52 | 12947.02 | 12947.02 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 2502 Gypsum Plaster | Gypsum on Wall (M) | 1057.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3700 | C+S GST 5% I/P RD | 185 | 3885 | 3885 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 392 | 99243 | 20 Apr 2023 |  | J K INTERIOR | SWASTIK MARBLE WORKS | EV - 71 | A Bldg Flat No. 301 Gypsum Plaster | Gypsum on Wall (M) | 3523.05 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.68 | C+S GST 5% I/P RD | 616.54 | 12947.22 | 12947.22 | Approved | 0 | 0 | 0 | 20 Apr 2023
GANGA DHAM TOWERS | 694 | 99242 | 20 Apr 2023 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 79 | B GF Podium Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 2618 | Sq.Ft | 4 | 100 | 261.8 | 0 | 10472 | C+S GST 18% I/P RD | 1884.96 | 12356.96 | 12356.96 | Approved | 0 | 0 | 105 | 20 Apr 2023
GANGA DHAM TOWERS | 389 | 99238 | 19 Apr 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 72 | Loading / Unloading Expenses | Unloading of tiles. | 8 | Metric Tonnes | 260 | 100 | 0 | 0 | 2080 | CGST 0% URD I/P | 0 | 2080 | 2080 | Approved | 0 | 0 | 0 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 34 | 100 | 51.04 | 0 | 2041.63 | CGST 0% URD I/P | 0 | 2041.63 | 2041.63 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 24 | 100 | 26.16 | 0 | 1046.3 | CGST 0% URD I/P | 0 | 1046.3 | 1046.3 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | CGST 0% URD I/P | 0 | 521.42 | 521.42 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.494 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1115.86 | CGST 0% URD I/P | 0 | 1115.86 | 1115.86 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | CGST 0% URD I/P | 0 | 941.54 | 941.54 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.11 | Sq.Ft | 24 | 100 | 25.87 | 0 | 1034.64 | CGST 0% URD I/P | 0 | 1034.64 | 1034.64 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.503 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1116.07 | CGST 0% URD I/P | 0 | 1116.07 | 1116.07 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Dry Balcony dado | Dado BC | 80.361 | Sq.Ft | 28 | 100 | 56.25 | 0 | 2250.11 | CGST 0% URD I/P | 0 | 2250.11 | 2250.11 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Master Toilet dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | CGST 0% URD I/P | 0 | 3732.62 | 3732.62 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Parents Toilet dado | Dado BC | 77.931 | Sq.Ft | 28 | 100 | 54.55 | 0 | 2182.07 | CGST 0% URD I/P | 0 | 2182.07 | 2182.07 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Children Toilet Dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | CGST 0% URD I/P | 0 | 3732.62 | 3732.62 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Parents Toilet dado | Dado BC | 95.436 | Sq.Ft | 28 | 100 | 66.81 | 0 | 2672.21 | CGST 0% URD I/P | 0 | 2672.21 | 2672.21 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | CGST 0% URD I/P | 0 | 2453.47 | 2453.47 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | CGST 0% URD I/P | 0 | 1708.06 | 1708.06 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | CGST 0% URD I/P | 0 | 979.27 | 979.27 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 24 | 100 | 73.1 | 0 | 2923.99 | CGST 0% URD I/P | 0 | 2923.99 | 2923.99 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 36 | 100 | 117.63 | 0 | 4705.13 | CGST 0% URD I/P | 0 | 4705.13 | 4705.13 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Dry Balcony dado | L Groove - BCV | 3.834 | R.Ft | 20 | 100 | 1.92 | 0 | 76.68 | CGST 0% URD I/P | 0 | 76.68 | 76.68 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Staff Toilet dado | L Groove - BCV | 21.933 | R.Ft | 20 | 100 | 10.97 | 0 | 438.66 | CGST 0% URD I/P | 0 | 438.66 | 438.66 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Parents Toilet dado | L Groove - BCV | 21.996 | R.Ft | 20 | 100 | 11 | 0 | 439.92 | CGST 0% URD I/P | 0 | 439.92 | 439.92 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Children Toilet Dado | L Groove - BCV | 38.7 | R.Ft | 20 | 100 | 19.35 | 0 | 774 | CGST 0% URD I/P | 0 | 774 | 774 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Powder Toilet dado | L Groove - BCV | 32.238 | R.Ft | 20 | 100 | 16.12 | 0 | 644.76 | CGST 0% URD I/P | 0 | 644.76 | 644.76 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2004 Master Toilet dado | L Groove - BCV | 38.61 | R.Ft | 20 | 100 | 19.31 | 0 | 772.2 | CGST 0% URD I/P | 0 | 772.2 | 772.2 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 31.5 | 100 | 17.74 | 0 | 709.6 | CGST 0% URD I/P | 0 | 709.6 | 709.6 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 31.5 | 100 | 29.56 | 0 | 1182.48 | CGST 0% URD I/P | 0 | 1182.48 | 1182.48 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 31.5 | 100 | 36.01 | 0 | 1440.46 | CGST 0% URD I/P | 0 | 1440.46 | 1440.46 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 551 | 99231 | 19 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 144 | A 2503 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 31.5 | 100 | 36.01 | 0 | 1440.46 | CGST 0% URD I/P | 0 | 1440.46 | 1440.46 | Approved | 0 | 0 | 431 | 19 Apr 2023
GANGA DHAM TOWERS | 1530 | 99230 | 19 Apr 2023 |  | SURESH KUMAR MURALIDHAR | SURESH KUMAR MURALIDHAR | EV - 153 | Departmental Labour for Material shifting, Cleaning | Male Coolie | 12 | No. | 550 | 100 | 0 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 77 | 19 Apr 2023
GANGA DHAM TOWERS | 1530 | 99230 | 19 Apr 2023 |  | SURESH KUMAR MURALIDHAR | SURESH KUMAR MURALIDHAR | EV - 153 | Departmental Labour for Material shifting, Cleaning | Male Coolie | 2 | No. | 550 | 100 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 77 | 19 Apr 2023
GANGA DHAM TOWERS | 1546 | 99225 | 18 Apr 2023 |  | SURESH KUMAR MURALIDHAR | SURESH KUMAR MURALIDHAR | EV - 77 | B Flat No 302 Gypsum Plaster removing work- - 1 Flat | Gypsum Removing work-BRE | 1 | Flat | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 0 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 594 | 99223 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 61 | Commercial Building Architectural Consultancy | Architectural Consultancy | 21036 | Sq.Ft | 30 | 5 | 0 | 0 | 31554 | C+S GST 18% I/P RD | 5679.72 | 37233.72 | 37233.72 | Approved | 0 | 0 | 41878 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 15 | 0 | 0 | 215208.31 | C+S GST 18% I/P RD | 38737.5 | 253945.81 | 253945.81 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 15 | 0 | 0 | 215208.31 | C+S GST 18% I/P RD | 38737.5 | 253945.81 | 253945.81 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 9896 | Sq.Ft | 144.98 | 10 | 0 | 0 | 143472.21 | C+S GST 18% I/P RD | 25825 | 169297.21 | 169297.21 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 19792 | Sq.Ft | 144.98 | 10 | 0 | 0 | 286944.42 | C+S GST 18% I/P RD | 51650 | 338594.42 | 338594.42 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior Consultancy Amenity and Club house rate differance | Interior Designing Consultancy Rate Diff | 19792 | Sq.Ft | 144.98 | 10 | 0 | 0 | 286944.42 | C+S GST 18% I/P RD | 51650 | 338594.42 | 338594.42 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 21779.8 | Sq.Ft | 50 | 10 | 0 | 0 | 108899 | C+S GST 18% I/P RD | 19601.82 | 128500.82 | 128500.82 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 21779.88 | Sq.Ft | 50 | 15 | 0 | 0 | 163349.1 | C+S GST 18% I/P RD | 29402.84 | 192751.94 | 192751.94 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 10890 | Sq.Ft | 50 | 10 | 0 | 0 | 54450 | C+S GST 18% I/P RD | 9801 | 64251 | 64251 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 21779.8 | Sq.Ft | 50 | 10 | 0 | 0 | 108899 | C+S GST 18% I/P RD | 19601.82 | 128500.82 | 128500.82 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 10890 | Sq.Ft | 50 | 10 | 0 | 0 | 54450 | C+S GST 18% I/P RD | 9801 | 64251 | 64251 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 21779.8 | Sq.Ft | 50 | 10 | 0 | 0 | 108899 | C+S GST 18% I/P RD | 19601.82 | 128500.82 | 128500.82 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 10890 | Sq.Ft | 50 | 10 | 0 | 0 | 54450 | C+S GST 18% I/P RD | 9801 | 64251 | 64251 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 83 | 99222 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 65 | Interior design of amenity area & club house | Interior Designing Consultancy | 10890 | Sq.Ft | 50 | 10 | 0 | 0 | 54450 | C+S GST 18% I/P RD | 9801 | 64251 | 64251 | Approved | 0 | 0 | 257298 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | C Architectural Consultancy | Architectural Consultancy | 274382 | Sq.Ft | 25 | 5 | 0 | 0 | 342977.5 | C+S GST 18% I/P RD | 61735.96 | 404713.46 | 404713.46 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | A Architectural Consultancy | Architectural Consultancy | 273853 | Sq.Ft | 25 | 5 | 0 | 0 | 342316.25 | C+S GST 18% I/P RD | 61616.92 | 403933.17 | 403933.17 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | B Architectural Consultancy | Architectural Consultancy | 176055 | Sq.Ft | 25 | 5 | 0 | 0 | 220068.75 | C+S GST 18% I/P RD | 39612.38 | 259681.13 | 259681.13 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | C Architectural Consultancy | Architectural Consultancy | 233579.04 | Sq.Ft | 25 | 25 | 0 | 0 | 1459869 | C+S GST 18% I/P RD | 262776.42 | 1722645.42 | 1722645.42 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | C Architectural Consultancy | Architectural Consultancy | 274382 | Sq.Ft | 25 | 5 | 0 | 0 | 342977.5 | C+S GST 18% I/P RD | 61735.96 | 404713.46 | 404713.46 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | A Architectural Consultancy | Architectural Consultancy | 273853 | Sq.Ft | 25 | 5 | 0 | 0 | 342316.25 | C+S GST 18% I/P RD | 61616.92 | 403933.17 | 403933.17 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | C Architectural Consultancy | Architectural Consultancy | 207948.8 | Sq.Ft | 25 | 5 | 0 | 0 | 259936 | C+S GST 18% I/P RD | 46788.48 | 306724.48 | 306724.48 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | A Architectural Consultancy | Architectural Consultancy | 273852.8 | Sq.Ft | 25 | 5 | 0 | 0 | 342316 | C+S GST 18% I/P RD | 61616.88 | 403932.88 | 403932.88 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | A Architectural Consultancy | Architectural Consultancy | 267434.4 | Sq.Ft | 25 | 5 | 0 | 0 | 334293 | C+S GST 18% I/P RD | 60172.74 | 394465.74 | 394465.74 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | B Architectural Consultancy | Architectural Consultancy | 176055 | Sq.Ft | 25 | 5 | 0 | 0 | 220068.75 | C+S GST 18% I/P RD | 39612.38 | 259681.13 | 259681.13 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | B Architectural Consultancy | Architectural Consultancy | 176055 | Sq.Ft | 25 | 5 | 0 | 0 | 220068.75 | C+S GST 18% I/P RD | 39612.38 | 259681.13 | 259681.13 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | Parking Area Architectural Consultancy | Architectural Consultancy | 375128.41 | Sq.Ft | 10 | 5 | 0 | 0 | 187564.21 | C+S GST 18% I/P RD | 33761.56 | 221325.77 | 221325.77 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | Parking Area Architectural Consultancy | Architectural Consultancy | 375128 | Sq.Ft | 10 | 5 | 0 | 0 | 187564 | C+S GST 18% I/P RD | 33761.52 | 221325.52 | 221325.52 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 19 | 99221 | 18 Apr 2023 |  | METAPHORS | METAPHORS | EV - 62 | Parking Area Architectural Consultancy | Architectural Consultancy | 375128.41 | Sq.Ft | 10 | 5 | 0 | 0 | 187564.21 | C+S GST 18% I/P RD | 33761.56 | 221325.77 | 221325.77 | Approved | 0 | 0 | 498990 | 18 Apr 2023
GANGA DHAM TOWERS | 389 | 99220 | 18 Apr 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 68 | Loading / Unloading Expenses | Unloading of GYpsum- | 12 | Metric Tonnes | 200 | 100 | 0 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 0 | 18 Apr 2023
GANGA DHAM TOWERS | 1552 | 99207 | 17 Apr 2023 |  | SURESH KUMAR MURALIDHAR | SURESH KUMAR MURALIDHAR | EV - 92 | B Blgd Gypsum Removing For Kutch | Chipping & Grinding | 4 | Flat | 3500 | 100 | 350 | 0 | 14000 | CGST 0% URD I/P | 0 | 14000 | 14000 | Approved | 0 | 0 | 140 | 17 Apr 2023
GANGA DHAM TOWERS | 1545 | 99206 | 17 Apr 2023 |  | SURESH KUMAR MURALIDHAR | SURESH KUMAR MURALIDHAR | EV - 76 | A Bldg Gypsum removing for kutch - 1 No. | Chipping & Grinding | 8 | Flat | 3500 | 100 | 700 | 0 | 28000 | CGST 0% URD I/P | 0 | 28000 | 28000 | Approved | 0 | 0 | 280 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 22.106 | R.Ft | 45 | 100 | 24.87 | 0 | 994.77 | C+S GST 18% I/P RD | 179.06 | 1173.83 | 1173.83 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 80.213 | R.Ft | 45 | 100 | 90.24 | 0 | 3609.59 | C+S GST 18% I/P RD | 649.72 | 4259.31 | 4259.31 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 10 | R.Ft | 45 | 100 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 17 | R.Ft | 45 | 100 | 19.13 | 0 | 765 | C+S GST 18% I/P RD | 137.7 | 902.7 | 902.7 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 29 | R.Ft | 45 | 100 | 32.63 | 0 | 1305 | C+S GST 18% I/P RD | 234.9 | 1539.9 | 1539.9 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Master Bed Marble Flooring | Italian Marble Champher & Polish | 11 | R.Ft | 45 | 100 | 12.38 | 0 | 495 | C+S GST 18% I/P RD | 89.1 | 584.1 | 584.1 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 41.972 | R.Ft | 45 | 100 | 47.22 | 0 | 1888.74 | C+S GST 18% I/P RD | 339.98 | 2228.72 | 2228.72 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 10 | R.Ft | 45 | 100 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 10 | R.Ft | 45 | 100 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 34.769 | R.Ft | 45 | 100 | 39.12 | 0 | 1564.61 | C+S GST 18% I/P RD | 281.62 | 1846.23 | 1846.23 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 24 | R.Ft | 45 | 100 | 27 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Master Bed Marble Flooring | Italian Marble Champher & Polish | 46.83 | R.Ft | 45 | 100 | 52.68 | 0 | 2107.35 | C+S GST 18% I/P RD | 379.32 | 2486.67 | 2486.67 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Master Bed Marble Flooring | Italian Marble Champher & Polish | 14 | R.Ft | 45 | 100 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.83 | R.Ft | 35 | 100 | 40.98 | 0 | 1639.05 | C+S GST 18% I/P RD | 295.02 | 1934.07 | 1934.07 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 14 | R.Ft | 35 | 100 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 22.106 | R.Ft | 35 | 100 | 19.34 | 0 | 773.71 | C+S GST 18% I/P RD | 139.26 | 912.97 | 912.97 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 26 | R.Ft | 35 | 100 | 22.75 | 0 | 910 | C+S GST 18% I/P RD | 163.8 | 1073.8 | 1073.8 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 34.769 | R.Ft | 35 | 100 | 30.42 | 0 | 1216.92 | C+S GST 18% I/P RD | 219.04 | 1435.96 | 1435.96 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 24 | R.Ft | 35 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 11 | R.Ft | 35 | 100 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 10 | R.Ft | 35 | 100 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 20.202 | R.Ft | 35 | 100 | 17.68 | 0 | 707.07 | C+S GST 18% I/P RD | 127.28 | 834.35 | 834.35 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 37.31 | R.Ft | 35 | 100 | 32.65 | 0 | 1305.85 | C+S GST 18% I/P RD | 235.06 | 1540.91 | 1540.91 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 37.31 | R.Ft | 35 | 100 | 32.65 | 0 | 1305.85 | C+S GST 18% I/P RD | 235.06 | 1540.91 | 1540.91 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 403 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 35 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 10 | R.Ft | 35 | 100 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 402 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 62.958 | R.Ft | 35 | 100 | 55.09 | 0 | 2203.53 | C+S GST 18% I/P RD | 396.64 | 2600.17 | 2600.17 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99203 | 17 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 78 | A 404 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 38.6595 | R.Ft | 35 | 100 | 33.83 | 0 | 1353.08 | C+S GST 18% I/P RD | 243.56 | 1596.64 | 1596.64 | Approved | 0 | 0 | 307 | 17 Apr 2023
GANGA DHAM TOWERS | 551 | 99202 | 17 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 84 | A 2603 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 27.5 | 100 | 106.17 | 0 | 4246.61 | C+S GST 18% I/P RD | 764.38 | 5010.99 | 5010.99 | Approved | 0 | 0 | 42 | 17 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 402 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 147.455 | Sq.Ft | 35 | 100 | 129.02 | 0 | 5160.93 | C+S GST 18% I/P RD | 928.96 | 6089.89 | 6089.89 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 402 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 400.967 | Sq.Ft | 35 | 100 | 350.85 | 0 | 14033.85 | C+S GST 18% I/P RD | 2526.1 | 16559.95 | 16559.95 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 404 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 60.796 | Sq.Ft | 35 | 100 | 53.2 | 0 | 2127.86 | C+S GST 18% I/P RD | 383.02 | 2510.88 | 2510.88 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 195.196 | Sq.Ft | 35 | 100 | 170.8 | 0 | 6831.86 | C+S GST 18% I/P RD | 1229.74 | 8061.6 | 8061.6 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 403 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 80.128 | Sq.Ft | 35 | 100 | 70.11 | 0 | 2804.48 | C+S GST 18% I/P RD | 504.8 | 3309.28 | 3309.28 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 236.356 | Sq.Ft | 35 | 100 | 206.81 | 0 | 8272.46 | C+S GST 18% I/P RD | 1489.04 | 9761.5 | 9761.5 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 404 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 84.176 | Sq.Ft | 35 | 100 | 73.65 | 0 | 2946.16 | C+S GST 18% I/P RD | 530.3 | 3476.46 | 3476.46 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 402 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 93.695 | Sq.Ft | 35 | 100 | 81.98 | 0 | 3279.33 | C+S GST 18% I/P RD | 590.28 | 3869.61 | 3869.61 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 403 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 57.632 | Sq.Ft | 35 | 100 | 50.43 | 0 | 2017.12 | C+S GST 18% I/P RD | 363.08 | 2380.2 | 2380.2 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 641 | 99199 | 15 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 81 | A 402 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 127.715 | Sq.Ft | 35 | 100 | 111.75 | 0 | 4470.03 | C+S GST 18% I/P RD | 804.6 | 5274.63 | 5274.63 | Approved | 0 | 0 | 519 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Westside 25th Floor Texture Painting | Scaffolding/Gondola work | 191.1429 | Sq.Ft | 3.5 | 100 | 16.73 | 0 | 669 | C+S GST 18% I/P RD | 120.42 | 789.42 | 789.42 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Eastside 26th Floor Texture Painting | Scaffolding/Gondola work | 191.1429 | Sq.Ft | 3.5 | 100 | 16.73 | 0 | 669 | C+S GST 18% I/P RD | 120.42 | 789.42 | 789.42 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Eastside 25th Floor Texture Painting | Scaffolding/Gondola work | 191.1429 | Sq.Ft | 3.5 | 100 | 16.73 | 0 | 669 | C+S GST 18% I/P RD | 120.42 | 789.42 | 789.42 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Westside 26th Floor Texture Painting | Scaffolding/Gondola work | 191.1429 | Sq.Ft | 3.5 | 100 | 16.73 | 0 | 669 | C+S GST 18% I/P RD | 120.42 | 789.42 | 789.42 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Westside 26th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Northside 25th Floor Texture Painting | Texture Paint (L) | 219.3103 | Sq.Ft | 7.25 | 100 | 39.75 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Northside 25th Floor Texture Painting | Texture Paint (L) | 219.3103 | Sq.Ft | 7.25 | 100 | 39.75 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Northside 26th Floor Texture Painting | Texture Paint (L) | 219.3103 | Sq.Ft | 7.25 | 100 | 39.75 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Westside 25th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Eastside 26th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 1199 | 99194 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 141 | B Northside 26th Floor Texture Painting | Texture Paint (L) | 219.3103 | Sq.Ft | 7.25 | 100 | 39.75 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 178 | 15 Apr 2023
GANGA DHAM TOWERS | 372 | 99193 | 15 Apr 2023 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 574 | B Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 79.3742 | Sq.Ft | 155 | 100 | 0 | 0 | 12303 | C+S GST 18% I/P RD | 2214.54 | 14517.54 | 14517.54 | Approved | 0 | 0 | 203 | 15 Apr 2023
GANGA DHAM TOWERS | 372 | 99193 | 15 Apr 2023 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 574 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50 | Sq.Ft | 160 | 100 | 0 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 203 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Northside 25th Floor Texture Painting | Texture Paint (M) | 219.3103 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Westside 25th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Northside 26th Floor Texture Painting | Texture Paint (M) | 219.3103 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Northside 26th Floor Texture Painting | Texture Paint (M) | 219.3103 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Westside 26th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Eastside 26th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Northside 25th Floor Texture Painting | Texture Paint (M) | 219.3103 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1590 | C+S GST 18% I/P RD | 286.2 | 1876.2 | 1876.2 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 1200 | 99191 | 15 Apr 2023 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 165 | B Eastside 25th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 0 | 15 Apr 2023
GANGA DHAM TOWERS | 372 | 99190 | 15 Apr 2023 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 311 | B Bldg Terrace Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 176.8984 | Sq.Ft | 175.174 | 100 | 0 | 0 | 30988 | C+S GST 18% I/P RD | 5577.84 | 36565.84 | 36565.84 | Approved | 0 | 0 | 310 | 15 Apr 2023
GANGA DHAM TOWERS | 272 | 99189 | 15 Apr 2023 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 312 | A Bldg Terrace Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 75.968 | Sq.Ft | 181.3 | 100 | 0 | 0 | 13773 | C+S GST 18% I/P RD | 2479.14 | 16252.14 | 16252.14 | Approved | 0 | 0 | 551 | 15 Apr 2023
GANGA DHAM TOWERS | 272 | 99189 | 15 Apr 2023 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 312 | A Bldg Terrace Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 227.8985 | Sq.Ft | 181.3 | 100 | 0 | 0 | 41318 | C+S GST 18% I/P RD | 7437.24 | 48755.24 | 48755.24 | Approved | 0 | 0 | 551 | 15 Apr 2023
GANGA DHAM TOWERS | 537 | 99175 | 14 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 123 | A 2502 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 31.5 | 100 | 30.52 | 0 | 1220.75 | CGST 0% URD I/P | 0 | 1220.75 | 1220.75 | Approved | 0 | 0 | 178 | 14 Apr 2023
GANGA DHAM TOWERS | 537 | 99175 | 14 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 123 | A 2502 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 44 | R.Ft | 80 | 100 | 88 | 0 | 3520 | CGST 0% URD I/P | 0 | 3520 | 3520 | Approved | 0 | 0 | 178 | 14 Apr 2023
GANGA DHAM TOWERS | 537 | 99175 | 14 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 123 | A 2502 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 103.131 | R.Ft | 80 | 100 | 206.26 | 0 | 8250.48 | CGST 0% URD I/P | 0 | 8250.48 | 8250.48 | Approved | 0 | 0 | 178 | 14 Apr 2023
GANGA DHAM TOWERS | 537 | 99175 | 14 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 123 | A 2502 Master Bed Marble Flooring | Italian marble Skirting - BCo | 60.21 | R.Ft | 80 | 100 | 120.42 | 0 | 4816.8 | CGST 0% URD I/P | 0 | 4816.8 | 4816.8 | Approved | 0 | 0 | 178 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Parents Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.125 | R.Ft | 22.5 | 100 | 2.32 | 0 | 92.81 | C+S GST 18% I/P RD | 16.7 | 109.51 | 109.51 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Master Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 3.9975 | R.Ft | 22.5 | 100 | 2.25 | 0 | 89.94 | C+S GST 18% I/P RD | 16.18 | 106.12 | 106.12 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Powder Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 2.9325 | R.Ft | 22.5 | 100 | 1.65 | 0 | 65.98 | C+S GST 18% I/P RD | 11.88 | 77.86 | 77.86 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Parents Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.125 | R.Ft | 22.5 | 100 | 2.32 | 0 | 92.81 | C+S GST 18% I/P RD | 16.7 | 109.51 | 109.51 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Powder Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 2.9325 | R.Ft | 22.5 | 100 | 1.65 | 0 | 65.98 | C+S GST 18% I/P RD | 11.88 | 77.86 | 77.86 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Parents Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.125 | R.Ft | 22.5 | 100 | 2.32 | 0 | 92.81 | C+S GST 18% I/P RD | 16.7 | 109.51 | 109.51 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Children Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.6875 | R.Ft | 22.5 | 100 | 2.64 | 0 | 105.47 | C+S GST 18% I/P RD | 18.98 | 124.45 | 124.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Master Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 3.9975 | R.Ft | 22.5 | 100 | 2.25 | 0 | 89.94 | C+S GST 18% I/P RD | 16.18 | 106.12 | 106.12 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Powder Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 2.9325 | R.Ft | 22.5 | 100 | 1.65 | 0 | 65.98 | C+S GST 18% I/P RD | 11.88 | 77.86 | 77.86 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Children Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.6875 | R.Ft | 22.5 | 100 | 2.64 | 0 | 105.47 | C+S GST 18% I/P RD | 18.98 | 124.45 | 124.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Master Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 3.9975 | R.Ft | 22.5 | 100 | 2.25 | 0 | 89.94 | C+S GST 18% I/P RD | 16.18 | 106.12 | 106.12 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Children Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.6875 | R.Ft | 22.5 | 100 | 2.64 | 0 | 105.47 | C+S GST 18% I/P RD | 18.98 | 124.45 | 124.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Master Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 3.57 | Sq.Ft | 40 | 100 | 3.57 | 0 | 142.8 | C+S GST 18% I/P RD | 25.7 | 168.5 | 168.5 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Children Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 40 | 100 | 2.32 | 0 | 92.7 | C+S GST 18% I/P RD | 16.68 | 109.38 | 109.38 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Parents Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 4.3425 | Sq.Ft | 40 | 100 | 4.34 | 0 | 173.7 | C+S GST 18% I/P RD | 31.26 | 204.96 | 204.96 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Parents Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 4.3425 | Sq.Ft | 40 | 100 | 4.34 | 0 | 173.7 | C+S GST 18% I/P RD | 31.26 | 204.96 | 204.96 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Powder Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 40 | 100 | 2.32 | 0 | 92.7 | C+S GST 18% I/P RD | 16.68 | 109.38 | 109.38 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Powder Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 40 | 100 | 2.32 | 0 | 92.7 | C+S GST 18% I/P RD | 16.68 | 109.38 | 109.38 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Master Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 3.57 | Sq.Ft | 40 | 100 | 3.57 | 0 | 142.8 | C+S GST 18% I/P RD | 25.7 | 168.5 | 168.5 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Children Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 40 | 100 | 2.32 | 0 | 92.7 | C+S GST 18% I/P RD | 16.68 | 109.38 | 109.38 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Parents Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 4.125 | R.Ft | 45 | 100 | 4.64 | 0 | 185.63 | C+S GST 18% I/P RD | 33.42 | 219.05 | 219.05 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Powder Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 2.9325 | R.Ft | 45 | 100 | 3.3 | 0 | 131.96 | C+S GST 18% I/P RD | 23.76 | 155.72 | 155.72 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Powder Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 2.9325 | R.Ft | 50 | 100 | 3.67 | 0 | 146.63 | C+S GST 18% I/P RD | 26.4 | 173.03 | 173.03 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Parents Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 4.125 | R.Ft | 50 | 100 | 5.16 | 0 | 206.25 | C+S GST 18% I/P RD | 37.12 | 243.37 | 243.37 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Children Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.75 | R.Ft | 50 | 100 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Master Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.9975 | R.Ft | 45 | 100 | 4.5 | 0 | 179.89 | C+S GST 18% I/P RD | 32.38 | 212.27 | 212.27 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Master Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.9975 | R.Ft | 50 | 100 | 5 | 0 | 199.88 | C+S GST 18% I/P RD | 35.98 | 235.86 | 235.86 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Powder Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 2.9325 | R.Ft | 50 | 100 | 3.67 | 0 | 146.63 | C+S GST 18% I/P RD | 26.4 | 173.03 | 173.03 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Children Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.75 | R.Ft | 45 | 100 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Parents Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 4.125 | R.Ft | 45 | 100 | 4.64 | 0 | 185.63 | C+S GST 18% I/P RD | 33.42 | 219.05 | 219.05 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Parents Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 4.125 | R.Ft | 45 | 100 | 4.64 | 0 | 185.63 | C+S GST 18% I/P RD | 33.42 | 219.05 | 219.05 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Children Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.75 | R.Ft | 50 | 100 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Children Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.75 | R.Ft | 45 | 100 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Powder Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 2.9325 | R.Ft | 45 | 100 | 3.3 | 0 | 131.96 | C+S GST 18% I/P RD | 23.76 | 155.72 | 155.72 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Parents Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 4.125 | R.Ft | 50 | 100 | 5.16 | 0 | 206.25 | C+S GST 18% I/P RD | 37.12 | 243.37 | 243.37 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Master Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.9975 | R.Ft | 50 | 100 | 5 | 0 | 199.88 | C+S GST 18% I/P RD | 35.98 | 235.86 | 235.86 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Master Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.9975 | R.Ft | 45 | 100 | 4.5 | 0 | 179.89 | C+S GST 18% I/P RD | 32.38 | 212.27 | 212.27 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Children Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.75 | R.Ft | 45 | 100 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Master Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 3.9975 | R.Ft | 45 | 100 | 4.5 | 0 | 179.89 | C+S GST 18% I/P RD | 32.38 | 212.27 | 212.27 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Powder Toilet Counter wash Basin | Italian Marble Zero Joint-BCo | 2.9325 | R.Ft | 45 | 100 | 3.3 | 0 | 131.96 | C+S GST 18% I/P RD | 23.76 | 155.72 | 155.72 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Parents Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 4.3425 | Sq.Ft | 35 | 100 | 3.8 | 0 | 151.99 | C+S GST 18% I/P RD | 27.36 | 179.35 | 179.35 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Children Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Powder Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Powder Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Master Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 3.57 | Sq.Ft | 35 | 100 | 3.12 | 0 | 124.95 | C+S GST 18% I/P RD | 22.5 | 147.45 | 147.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 201 Children Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Powder Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Parents Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 4.3425 | Sq.Ft | 35 | 100 | 3.8 | 0 | 151.99 | C+S GST 18% I/P RD | 27.36 | 179.35 | 179.35 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Children Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 2.3175 | Sq.Ft | 35 | 100 | 2.03 | 0 | 81.11 | C+S GST 18% I/P RD | 14.6 | 95.71 | 95.71 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 401 Master Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 3.57 | Sq.Ft | 35 | 100 | 3.12 | 0 | 124.95 | C+S GST 18% I/P RD | 22.5 | 147.45 | 147.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Master Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 3.57 | Sq.Ft | 35 | 100 | 3.12 | 0 | 124.95 | C+S GST 18% I/P RD | 22.5 | 147.45 | 147.45 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 601 Parents Toilet Counter wash Basin | Italian Marble Mirror Polish- BCo | 4.3425 | Sq.Ft | 35 | 100 | 3.8 | 0 | 151.99 | C+S GST 18% I/P RD | 27.36 | 179.35 | 179.35 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Powder Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 2.9325 | R.Ft | 25 | 100 | 1.83 | 0 | 73.31 | C+S GST 18% I/P RD | 13.2 | 86.51 | 86.51 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Parents Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.125 | R.Ft | 25 | 100 | 2.58 | 0 | 103.13 | C+S GST 18% I/P RD | 18.56 | 121.69 | 121.69 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Powder Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 2.9325 | R.Ft | 25 | 100 | 1.83 | 0 | 73.31 | C+S GST 18% I/P RD | 13.2 | 86.51 | 86.51 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Children Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.6875 | R.Ft | 25 | 100 | 2.93 | 0 | 117.19 | C+S GST 18% I/P RD | 21.1 | 138.29 | 138.29 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Master Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 3.9975 | R.Ft | 25 | 100 | 2.5 | 0 | 99.94 | C+S GST 18% I/P RD | 17.98 | 117.92 | 117.92 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Master Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 3.9975 | R.Ft | 25 | 100 | 2.5 | 0 | 99.94 | C+S GST 18% I/P RD | 17.98 | 117.92 | 117.92 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 701 Parents Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.125 | R.Ft | 25 | 100 | 2.58 | 0 | 103.13 | C+S GST 18% I/P RD | 18.56 | 121.69 | 121.69 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 641 | 99174 | 14 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 362 | A 901 Children Toilet Counter wash Basin | Italian Marble Edge Polish- BCo | 4.6875 | R.Ft | 25 | 100 | 2.93 | 0 | 117.19 | C+S GST 18% I/P RD | 21.1 | 138.29 | 138.29 | Approved | 0 | 0 | 77 | 14 Apr 2023
GANGA DHAM TOWERS | 1179 | 99156 | 13 Apr 2023 |  | AMAN ENTERPRISES | AMAN ENTERPRISES | EV - 313 | C Roller Compaction work | Roller- BC | 1.375 | Day | 4000 | 100 | 0 | 0 | 5500 | CGST 0% URD I/P | 0 | 5500 | 5500 | Approved | 0 | 0 | 55 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Westside 26th floor External Texture Painting | Texture Paint (M) | 424 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Northside 25th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Northside 26th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Westside 25th floor External Texture Painting | Texture Paint (M) | 424 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A South side 25th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A South side 26th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Eastside 25th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 845 | 99155 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 116 | A Eastside 26th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 1464 | 99154 | 13 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 93 | A Opening Railing For Safety 26th To 31st Floor | Hold Fast Patti- DSP | 180 | No. | 5 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 57 | 13 Apr 2023
GANGA DHAM TOWERS | 1464 | 99154 | 13 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 93 | A Opening Railing For Safety 26th To 31st Floor | Plumbing Nails (M+L) | 4 | Kgs | 12 | 100 | 1.2 | 0 | 48 | C+S GST 18% I/P RD | 8.64 | 56.64 | 56.64 | Approved | 0 | 0 | 57 | 13 Apr 2023
GANGA DHAM TOWERS | 1464 | 99154 | 13 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 93 | A Opening Railing For Safety 26th To 31st Floor | Fabrication work (L) | 400 | Kgs | 12 | 100 | 120 | 0 | 4800 | C+S GST 18% I/P RD | 864 | 5664 | 5664 | Approved | 0 | 0 | 57 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Northside 26th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A South side 26th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Eastside 25th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Westside 26th floor External Texture Painting | Texture Paint (L) | 424 | Sq.Ft | 7.25 | 100 | 76.85 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Eastside 26th floor External Texture Painting | Scaffolding/Gondola work | 466.5714 | Sq.Ft | 3.5 | 100 | 40.82 | 0 | 1633 | C+S GST 18% I/P RD | 293.94 | 1926.94 | 1926.94 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A South side 26th floor External Texture Painting | Scaffolding/Gondola work | 403.7143 | Sq.Ft | 3.5 | 100 | 35.33 | 0 | 1413 | C+S GST 18% I/P RD | 254.34 | 1667.34 | 1667.34 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Eastside 25th floor External Texture Painting | Scaffolding/Gondola work | 151.1429 | Sq.Ft | 3.5 | 100 | 13.23 | 0 | 529 | C+S GST 18% I/P RD | 95.22 | 624.22 | 624.22 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Eastside 25th floor External Texture Painting | Scaffolding/Gondola work | 223.1429 | Sq.Ft | 3.5 | 100 | 19.53 | 0 | 781 | C+S GST 18% I/P RD | 140.58 | 921.58 | 921.58 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A South side 25th floor External Texture Painting | Scaffolding/Gondola work | 375.1429 | Sq.Ft | 3.5 | 100 | 32.83 | 0 | 1313 | C+S GST 18% I/P RD | 236.34 | 1549.34 | 1549.34 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Westside 26th floor External Texture Painting | Scaffolding/Gondola work | 360.5714 | Sq.Ft | 3.5 | 100 | 31.55 | 0 | 1262 | C+S GST 18% I/P RD | 227.16 | 1489.16 | 1489.16 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Westside 25th floor External Texture Painting | Scaffolding/Gondola work | 383.1429 | Sq.Ft | 3.5 | 100 | 33.53 | 0 | 1341 | C+S GST 18% I/P RD | 241.38 | 1582.38 | 1582.38 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Northside 26th floor External Texture Painting | Scaffolding/Gondola work | 358 | Sq.Ft | 3.5 | 100 | 31.33 | 0 | 1253 | C+S GST 18% I/P RD | 225.54 | 1478.54 | 1478.54 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 844 | 99153 | 13 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 143 | A Northside 25th floor External Texture Painting | Scaffolding/Gondola work | 388 | Sq.Ft | 3.5 | 100 | 33.95 | 0 | 1358 | C+S GST 18% I/P RD | 244.44 | 1602.44 | 1602.44 | Approved | 0 | 0 | 226 | 13 Apr 2023
GANGA DHAM TOWERS | 804 | 99152 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 148 | B-2001 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 804 | 99152 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 148 | B-2001 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 629 | 99151 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 89 | A 803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186.4 | R.Ft | 55 | 100 | 0 | 0 | 10252 | C+S GST 18% I/P RD | 1845.36 | 12097.36 | 12097.36 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 629 | 99151 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 89 | A 2303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 629 | 99151 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 89 | A 2303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 629 | 99151 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 89 | A 803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 352.008 | Sq.Ft | 55 | 100 | 0 | 0 | 19360.44 | C+S GST 18% I/P RD | 3484.88 | 22845.32 | 22845.32 | Approved | 0 | 0 | 0 | 13 Apr 2023
GANGA DHAM TOWERS | 805 | 99150 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 147 | B-2001 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 402 | 13 Apr 2023
GANGA DHAM TOWERS | 805 | 99150 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 147 | B-2001 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 402 | 13 Apr 2023
GANGA DHAM TOWERS | 632 | 99149 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 90 | A 2303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 295 | 13 Apr 2023
GANGA DHAM TOWERS | 632 | 99149 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 90 | A 803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352.008 | Sq.Ft | 20 | 100 | 176 | 0 | 7040.16 | C+S GST 18% I/P RD | 1267.22 | 8307.38 | 8307.38 | Approved | 0 | 0 | 295 | 13 Apr 2023
GANGA DHAM TOWERS | 632 | 99149 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 90 | A 2303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 295 | 13 Apr 2023
GANGA DHAM TOWERS | 632 | 99149 | 13 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 90 | A 803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 139.8 | R.Ft | 20 | 100 | 69.9 | 0 | 2796 | C+S GST 18% I/P RD | 503.28 | 3299.28 | 3299.28 | Approved | 0 | 0 | 295 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Tiling Below Wooden Flooring | Ceramic Flooring work | 163.332 | Sq.Ft | 27.5 | 100 | 112.29 | 0 | 4491.63 | CGST 0% URD I/P | 0 | 4491.63 | 4491.63 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 31.5 | 100 | 42.34 | 0 | 1693.63 | CGST 0% URD I/P | 0 | 1693.63 | 1693.63 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 31.5 | 100 | 35.09 | 0 | 1403.61 | CGST 0% URD I/P | 0 | 1403.61 | 1403.61 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 31.5 | 100 | 31.99 | 0 | 1279.44 | CGST 0% URD I/P | 0 | 1279.44 | 1279.44 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 31.5 | 100 | 30.89 | 0 | 1235.78 | CGST 0% URD I/P | 0 | 1235.78 | 1235.78 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 31.5 | 100 | 17.11 | 0 | 684.37 | CGST 0% URD I/P | 0 | 684.37 | 684.37 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 537 | 99148 | 13 Apr 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 124 | A 2502 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140.472 | Sq.Ft | 34 | 100 | 119.4 | 0 | 4776.05 | CGST 0% URD I/P | 0 | 4776.05 | 4776.05 | Approved | 0 | 0 | 156 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 20 | 100 | 17.49 | 0 | 699.48 | CGST 0% URD I/P | 0 | 699.48 | 699.48 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Children Toilet Dado | Dado BC | 61.713 | Sq.Ft | 20 | 100 | 30.86 | 0 | 1234.26 | CGST 0% URD I/P | 0 | 1234.26 | 1234.26 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 20 | 100 | 30.5 | 0 | 1220.04 | CGST 0% URD I/P | 0 | 1220.04 | 1220.04 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Parents Toilet dado | Dado BC | 77.931 | Sq.Ft | 20 | 100 | 38.97 | 0 | 1558.62 | CGST 0% URD I/P | 0 | 1558.62 | 1558.62 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 120.465 | Sq.Ft | 55 | 100 | 165.64 | 0 | 6625.58 | CGST 0% URD I/P | 0 | 6625.58 | 6625.58 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 531.801 | Sq.Ft | 55 | 100 | 731.23 | 0 | 29249.06 | CGST 0% URD I/P | 0 | 29249.06 | 29249.06 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Terrace Parapet Top Granite | Granite Sill-BCo | 17.1 | R.Ft | 50 | 100 | 21.38 | 0 | 855 | CGST 0% URD I/P | 0 | 855 | 855 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Master Bed Marble Flooring | Italian marble Skirting - BCo | 51.678 | R.Ft | 55 | 100 | 71.06 | 0 | 2842.29 | CGST 0% URD I/P | 0 | 2842.29 | 2842.29 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 38.682 | R.Ft | 55 | 100 | 53.19 | 0 | 2127.51 | CGST 0% URD I/P | 0 | 2127.51 | 2127.51 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 104.634 | R.Ft | 55 | 100 | 143.87 | 0 | 5754.87 | CGST 0% URD I/P | 0 | 5754.87 | 5754.87 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 28.422 | R.Ft | 55 | 100 | 39.08 | 0 | 1563.21 | CGST 0% URD I/P | 0 | 1563.21 | 1563.21 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Tiling Below Wooden Flooring | Ceramic Flooring work | 160.812 | Sq.Ft | 18 | 100 | 72.37 | 0 | 2894.62 | CGST 0% URD I/P | 0 | 2894.62 | 2894.62 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Children Toilet Dado | Dado BC | 133.308 | Sq.Ft | 18 | 100 | 59.99 | 0 | 2399.54 | CGST 0% URD I/P | 0 | 2399.54 | 2399.54 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Parents Toilet dado | Dado BC | 95.436 | Sq.Ft | 18 | 100 | 42.95 | 0 | 1717.85 | CGST 0% URD I/P | 0 | 1717.85 | 1717.85 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 18 | 100 | 39.43 | 0 | 1577.23 | CGST 0% URD I/P | 0 | 1577.23 | 1577.23 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1004 Master Toilet dado | Dado BC | 133.308 | Sq.Ft | 18 | 100 | 59.99 | 0 | 2399.54 | CGST 0% URD I/P | 0 | 2399.54 | 2399.54 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99147 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | JUBAIR AHMAD | EV - 122 | A 1304 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 136.791 | Sq.Ft | 55 | 100 | 188.09 | 0 | 7523.51 | CGST 0% URD I/P | 0 | 7523.51 | 7523.51 | Approved | 0 | 0 | 722 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Guest Toilet dado | Dado BC | 131.02 | Sq.Ft | 18 | 100 | 58.96 | 0 | 2358.36 | C+S GST 18% I/P RD | 424.5 | 2782.86 | 2782.86 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 404 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.889 | R.Ft | 650 | 100 | 46.95 | 0 | 1877.85 | C+S GST 18% I/P RD | 338.02 | 2215.87 | 2215.87 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Staff Toilet dado | Dado BC | 67.685 | Sq.Ft | 17 | 100 | 28.77 | 0 | 1150.65 | C+S GST 18% I/P RD | 207.12 | 1357.77 | 1357.77 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 2603 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 180.288 | Sq.Ft | 80 | 100 | 360.58 | 0 | 14423.04 | C+S GST 18% I/P RD | 2596.14 | 17019.18 | 17019.18 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 2603 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 439.191 | Sq.Ft | 80 | 100 | 878.38 | 0 | 35135.28 | C+S GST 18% I/P RD | 6324.36 | 41459.64 | 41459.64 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 2603 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 129.672 | Sq.Ft | 80 | 100 | 259.34 | 0 | 10373.76 | C+S GST 18% I/P RD | 1867.28 | 12241.04 | 12241.04 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Guest Toilet dado | Dado BC | 58.28 | Sq.Ft | 20 | 100 | 29.14 | 0 | 1165.6 | C+S GST 18% I/P RD | 209.8 | 1375.4 | 1375.4 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 17 | 100 | 15.95 | 0 | 638.16 | C+S GST 18% I/P RD | 114.86 | 753.02 | 753.02 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 551 | 99146 | 13 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 80 | A 803 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.89 | Sq.Ft | 17 | 100 | 10.58 | 0 | 423.13 | C+S GST 18% I/P RD | 76.16 | 499.29 | 499.29 | Approved | 0 | 0 | 681 | 13 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 30 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 30 | 12 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 30 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 30 | 12 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Fan Point | 11 | No. | 200 | 30 | 16.5 | 0 | 660 | C+S GST 18% I/P RD | 118.8 | 778.8 | 778.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Fan Point | 11 | No. | 200 | 30 | 16.5 | 0 | 660 | C+S GST 18% I/P RD | 118.8 | 778.8 | 778.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Fan Point | 9 | No. | 200 | 25 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Fan Point | 9 | No. | 200 | 30 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Fan Point | 9 | No. | 200 | 30 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 30 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 25 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 30 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 30 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 30 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 30 | 14.85 | 0 | 594 | C+S GST 18% I/P RD | 106.92 | 700.92 | 700.92 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 25 | 8.25 | 0 | 330 | C+S GST 18% I/P RD | 59.4 | 389.4 | 389.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 30 | 14.85 | 0 | 594 | C+S GST 18% I/P RD | 106.92 | 700.92 | 700.92 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | TV Point | 8 | No. | 220 | 30 | 13.2 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | TV Point | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | TV Point | 8 | No. | 220 | 30 | 13.2 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | TV Point | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | TV Point | 6 | No. | 220 | 25 | 8.25 | 0 | 330 | C+S GST 18% I/P RD | 59.4 | 389.4 | 389.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 25 | 3.13 | 0 | 125 | C+S GST 18% I/P RD | 22.5 | 147.5 | 147.5 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 30 | 21.61 | 0 | 864.3 | C+S GST 18% I/P RD | 155.58 | 1019.88 | 1019.88 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 30 | 27.64 | 0 | 1105.5 | C+S GST 18% I/P RD | 199 | 1304.5 | 1304.5 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 30 | 27.64 | 0 | 1105.5 | C+S GST 18% I/P RD | 199 | 1304.5 | 1304.5 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 30 | 21.61 | 0 | 864.3 | C+S GST 18% I/P RD | 155.58 | 1019.88 | 1019.88 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 25 | 18.01 | 0 | 720.25 | C+S GST 18% I/P RD | 129.64 | 849.89 | 849.89 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 30 | 1.5 | 0 | 60 | C+S GST 18% I/P RD | 10.8 | 70.8 | 70.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 30 | 1.5 | 0 | 60 | C+S GST 18% I/P RD | 10.8 | 70.8 | 70.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 30 | 1.5 | 0 | 60 | C+S GST 18% I/P RD | 10.8 | 70.8 | 70.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 30 | 1.5 | 0 | 60 | C+S GST 18% I/P RD | 10.8 | 70.8 | 70.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 30 | 6.53 | 0 | 261.3 | C+S GST 18% I/P RD | 47.04 | 308.34 | 308.34 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 30 | 6.53 | 0 | 261.3 | C+S GST 18% I/P RD | 47.04 | 308.34 | 308.34 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 30 | 7.54 | 0 | 301.5 | C+S GST 18% I/P RD | 54.28 | 355.78 | 355.78 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 30 | 7.54 | 0 | 301.5 | C+S GST 18% I/P RD | 54.28 | 355.78 | 355.78 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 601 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 25 | 6.28 | 0 | 251.25 | C+S GST 18% I/P RD | 45.22 | 296.47 | 296.47 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 25 | 8.13 | 0 | 325 | C+S GST 18% I/P RD | 58.5 | 383.5 | 383.5 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 30 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 30 | 76.5 | 0 | 3060 | C+S GST 18% I/P RD | 550.8 | 3610.8 | 3610.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 30 | 118.5 | 0 | 4740 | C+S GST 18% I/P RD | 853.2 | 5593.2 | 5593.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 25 | 63.75 | 0 | 2550 | C+S GST 18% I/P RD | 459 | 3009 | 3009 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 30 | 76.5 | 0 | 3060 | C+S GST 18% I/P RD | 550.8 | 3610.8 | 3610.8 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 30 | 118.5 | 0 | 4740 | C+S GST 18% I/P RD | 853.2 | 5593.2 | 5593.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 30 | 126 | 0 | 5040 | C+S GST 18% I/P RD | 907.2 | 5947.2 | 5947.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 30 | 79.5 | 0 | 3180 | C+S GST 18% I/P RD | 572.4 | 3752.4 | 3752.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 25 | 66.25 | 0 | 2650 | C+S GST 18% I/P RD | 477 | 3127 | 3127 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 30 | 79.5 | 0 | 3180 | C+S GST 18% I/P RD | 572.4 | 3752.4 | 3752.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 30 | 126 | 0 | 5040 | C+S GST 18% I/P RD | 907.2 | 5947.2 | 5947.2 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 25 | 6.88 | 0 | 275 | C+S GST 18% I/P RD | 49.5 | 324.5 | 324.5 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 30 | 8.25 | 0 | 330 | C+S GST 18% I/P RD | 59.4 | 389.4 | 389.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 30 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 30 | 8.25 | 0 | 330 | C+S GST 18% I/P RD | 59.4 | 389.4 | 389.4 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 401 Internal Electrical Work | Data Point | 7 | No. | 220 | 30 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 402 Internal Electrical Work | Data Point | 4 | No. | 220 | 30 | 6.6 | 0 | 264 | C+S GST 18% I/P RD | 47.52 | 311.52 | 311.52 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 102 Internal Electrical Work | Data Point | 4 | No. | 220 | 30 | 6.6 | 0 | 264 | C+S GST 18% I/P RD | 47.52 | 311.52 | 311.52 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 101 Internal Electrical Work | Data Point | 7 | No. | 220 | 30 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 399 | 99140 | 12 Apr 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 91 | B Bldg Flat No. 502 Internal Electrical Work | Data Point | 4 | No. | 220 | 25 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 585 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Sanitary Store Removing at 99 level | Metacolur Sheet Removing - DER | 1138 | Sq.Ft | 2.5 | 100 | 0 | 0 | 2845 | C+S GST 18% I/P RD | 512.1 | 3357.1 | 3357.1 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Store Making of Sanitory Store at 99 level | M.S. Door fixing-Dld. | 1 | No. | 800 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Sanitary Store Removing at 99 level | MS Pipe Removing | 241.26 | Kgs | 7 | 100 | 0 | 0 | 1688.82 | C+S GST 18% I/P RD | 303.98 | 1992.8 | 1992.8 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Sanitary Store Removing at 99 level | M.S. Door removing | 1 | No. | 400 | 100 | 0 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Store Making of Sanitory Store at 99 level | MS Pipe Fixing (L) | 31.17 | Kgs | 14 | 100 | 10.91 | 0 | 436.38 | C+S GST 18% I/P RD | 78.54 | 514.92 | 514.92 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1398 | 99138 | 12 Apr 2023 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 309 | Store Making of Sanitory Store at 99 level | Meta colour Sheet Fixing BC | 88 | Sq.Ft | 5 | 100 | 11 | 0 | 440 | C+S GST 18% I/P RD | 79.2 | 519.2 | 519.2 | Approved | 0 | 0 | 66 | 12 Apr 2023
GANGA DHAM TOWERS | 1148 | 99125 | 12 Apr 2023 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 88 | A 304 Glass Cubicle | Glass Cubical (M) | 1 | No. | 11340 | 100 | 0 | 0 | 11340 | C+S GST 18% I/P RD | 2041.2 | 13381.2 | 13381.2 | Approved | 0 | 0 | 0 | 12 Apr 2023
GANGA DHAM TOWERS | 1148 | 99125 | 12 Apr 2023 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 88 | A 304 Glass Cubicle | Glass Cubical (M) | 1 | No. | 11340 | 100 | 0 | 0 | 11340 | C+S GST 18% I/P RD | 2041.2 | 13381.2 | 13381.2 | Approved | 0 | 0 | 0 | 12 Apr 2023
GANGA DHAM TOWERS | 1148 | 99125 | 12 Apr 2023 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 88 | A 304 Glass Cubicle | Glass Cubical (M) | 1 | No. | 19740 | 100 | 0 | 0 | 19740 | C+S GST 18% I/P RD | 3553.2 | 23293.2 | 23293.2 | Approved | 0 | 0 | 0 | 12 Apr 2023
GANGA DHAM TOWERS | 1148 | 99125 | 12 Apr 2023 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 88 | A 304 Glass Cubicle | Glass Cubical (M) | 1 | No. | 10500 | 100 | 0 | 0 | 10500 | C+S GST 18% I/P RD | 1890 | 12390 | 12390 | Approved | 0 | 0 | 0 | 12 Apr 2023
GANGA DHAM TOWERS | 1147 | 99123 | 12 Apr 2023 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 87 | A 304 Glass Cubicle | Glass Cubical (L) | 1 | No. | 8460 | 100 | 211.5 | 0 | 8460 | C+S GST 18% I/P RD | 1522.8 | 9982.8 | 9982.8 | Approved | 0 | 0 | 85 | 12 Apr 2023
GANGA DHAM TOWERS | 1435 | 99116 | 11 Apr 2023 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 26 | MEDIA Flex printing | Star BackLit Flex Print | 970 | Sq.Ft | 65 | 100 | 0 | 0 | 63050 | C+S GST 18% I/P RD | 11349 | 74399 | 74399 | Approved | 0 | 0 | 4000 | 11 Apr 2023
GANGA DHAM TOWERS | 1435 | 99116 | 11 Apr 2023 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 26 | MEDIA Flex printing | Star Flex | 6224.2584 | Sq.Ft | 22 | 100 | 0 | 0 | 136933.68 | C+S GST 18% I/P RD | 24648.06 | 161581.74 | 161581.74 | Approved | 0 | 0 | 4000 | 11 Apr 2023
GANGA DHAM TOWERS | 1330 | 99112 | 11 Apr 2023 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 21 | Contract Labour Act Registration & Compliace | Registration of Company (RC) | 1 | No. | 98500 | 100 | 0 | 0 | 98500 | C+S GST 18% I/P RD | 17730 | 116230 | 116230 | Approved | 0 | 0 | 16950 | 11 Apr 2023
GANGA DHAM TOWERS | 1330 | 99112 | 11 Apr 2023 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 21 | Contract Labour Act Registration & Compliace | B.O.C.W. Act Registration &Compliance. | 1 | No. | 71000 | 100 | 0 | 0 | 71000 | C+S GST 18% I/P RD | 12780 | 83780 | 83780 | Approved | 0 | 0 | 16950 | 11 Apr 2023
GANGA DHAM TOWERS | 1497 | 99100 | 11 Apr 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 135 | Site Expenses | Site Expenses -SO | 0.0047 | Month | 30000 | 100 | 0 | 0 | 141 | CGST 0% URD I/P | 0 | 141 | 141 | Approved | 0 | 0 | 0 | 11 Apr 2023
GANGA DHAM TOWERS | 1497 | 99100 | 11 Apr 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 135 | Site Expenses | Site Expenses -SO | 0.3135 | Month | 30000 | 100 | 0 | 0 | 9405 | CGST 0% URD I/P | 0 | 9405 | 9405 | Approved | 0 | 0 | 0 | 11 Apr 2023
GANGA DHAM TOWERS | 473 | 99097 | 11 Apr 2023 |  | ARYA CONSULTANCY | ARYA CONSULTANCY | EV - 908 | Electricity Infrastructure | Elect Meters Installation (L)-UTI | 85.5 | No. | 3500 | 30 | 0 | 0 | 89775 | C+S GST 18% I/P RD | 16159.5 | 105934.5 | 105934.5 | Approved | 0 | 0 | 8978 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 1 | No. | 250 | 30 | 1.88 | 0 | 75 | C+S GST 18% I/P RD | 13.5 | 88.5 | 88.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Fan Point | 9 | No. | 250 | 30 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Fan Point | 9 | No. | 250 | 30 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 8 | No. | 250 | 30 | 15 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 30 | 31.88 | 0 | 1275 | C+S GST 18% I/P RD | 229.5 | 1504.5 | 1504.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 30 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 30 | 31.88 | 0 | 1275 | C+S GST 18% I/P RD | 229.5 | 1504.5 | 1504.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 30 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 30 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 30 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 30 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 30 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 30 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 30 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 30 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 30 | 99.38 | 0 | 3975 | C+S GST 18% I/P RD | 715.5 | 4690.5 | 4690.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 30 | 99.38 | 0 | 3975 | C+S GST 18% I/P RD | 715.5 | 4690.5 | 4690.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 30 | 97.5 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 30 | 33 | 0 | 1320 | C+S GST 18% I/P RD | 237.6 | 1557.6 | 1557.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 30 | 29.25 | 0 | 1170 | C+S GST 18% I/P RD | 210.6 | 1380.6 | 1380.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 30 | 33 | 0 | 1320 | C+S GST 18% I/P RD | 237.6 | 1557.6 | 1557.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 30 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 30 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 30 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 30 | 75 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 30 | 73.13 | 0 | 2925 | C+S GST 18% I/P RD | 526.5 | 3451.5 | 3451.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 30 | 75 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 30 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 30 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 30 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 4 | No. | 350 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 4 | No. | 350 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 3 | No. | 350 | 30 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 4 | No. | 350 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 5 | No. | 350 | 30 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 4 | No. | 350 | 30 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 30 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | TV Point | 6 | No. | 350 | 30 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | TV Point | 6 | No. | 350 | 30 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | TV Point | 6 | No. | 350 | 30 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 30 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 302 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 30 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 359 | 99096 | 11 Apr 2023 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 427 | A Bldg Flat No. 301 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 30 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 471 | 11 Apr 2023
GANGA DHAM TOWERS | 1146 | 99095 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 83 | B 102 NOC | Italian Marble Mirror Polish- BCo | 61.264 | Sq.Ft | 45 | 100 | 68.92 | 0 | 2756.88 | C+S GST 18% I/P RD | 496.24 | 3253.12 | 3253.12 | Approved | 0 | 0 | 28 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 704 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 802 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 802 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1902 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1802 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 0.1 | No. | 26015 | 40 | 26.02 | 0 | 1040.6 | C+S GST 18% I/P RD | 187.3 | 1227.9 | 1227.9 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 802 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26015 | 40 | 26.02 | 0 | 1040.6 | C+S GST 18% I/P RD | 187.3 | 1227.9 | 1227.9 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 2102 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 2102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 2102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1902 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1902 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 702 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1801 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26925 | 40 | 26.93 | 0 | 1077 | C+S GST 18% I/P RD | 193.86 | 1270.86 | 1270.86 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26925 | 40 | 26.93 | 0 | 1077 | C+S GST 18% I/P RD | 193.86 | 1270.86 | 1270.86 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26925 | 40 | 26.93 | 0 | 1077 | C+S GST 18% I/P RD | 193.86 | 1270.86 | 1270.86 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 2001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26925 | 40 | 26.93 | 0 | 1077 | C+S GST 18% I/P RD | 193.86 | 1270.86 | 1270.86 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1118 | 99094 | 11 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 94 | A 1901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.1 | No. | 26925 | 40 | 26.93 | 0 | 1077 | C+S GST 18% I/P RD | 193.86 | 1270.86 | 1270.86 | Approved | 0 | 0 | 704 | 11 Apr 2023
GANGA DHAM TOWERS | 1252 | 99093 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 82 | B 601 NOC | Italian Marble Mirror Polish- BCo | 109.548 | Sq.Ft | 45 | 100 | 123.24 | 0 | 4929.66 | C+S GST 18% I/P RD | 887.34 | 5817 | 5817 | Approved | 0 | 0 | 49 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 101 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 97.2 | Sq.Ft | 35 | 100 | 85.05 | 0 | 3402 | C+S GST 18% I/P RD | 612.36 | 4014.36 | 4014.36 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 263.824 | Sq.Ft | 35 | 100 | 230.85 | 0 | 9233.84 | C+S GST 18% I/P RD | 1662.1 | 10895.94 | 10895.94 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 402 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 107.768 | Sq.Ft | 35 | 100 | 94.3 | 0 | 3771.88 | C+S GST 18% I/P RD | 678.94 | 4450.82 | 4450.82 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 101 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 125.896 | Sq.Ft | 35 | 100 | 110.16 | 0 | 4406.36 | C+S GST 18% I/P RD | 793.14 | 5199.5 | 5199.5 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 602 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 107.768 | Sq.Ft | 35 | 100 | 94.3 | 0 | 3771.88 | C+S GST 18% I/P RD | 678.94 | 4450.82 | 4450.82 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 402 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 82.236 | Sq.Ft | 35 | 100 | 71.96 | 0 | 2878.26 | C+S GST 18% I/P RD | 518.08 | 3396.34 | 3396.34 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 402 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 263.824 | Sq.Ft | 35 | 100 | 230.85 | 0 | 9233.84 | C+S GST 18% I/P RD | 1662.1 | 10895.94 | 10895.94 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 602 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 82.236 | Sq.Ft | 35 | 100 | 71.96 | 0 | 2878.26 | C+S GST 18% I/P RD | 518.08 | 3396.34 | 3396.34 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 601 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 128.392 | Sq.Ft | 35 | 100 | 112.34 | 0 | 4493.72 | C+S GST 18% I/P RD | 808.86 | 5302.58 | 5302.58 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 401 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 125.896 | Sq.Ft | 35 | 100 | 110.16 | 0 | 4406.36 | C+S GST 18% I/P RD | 793.14 | 5199.5 | 5199.5 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 470 | Sq.Ft | 35 | 100 | 411.25 | 0 | 16450 | C+S GST 18% I/P RD | 2961 | 19411 | 19411 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 263.824 | Sq.Ft | 35 | 100 | 230.85 | 0 | 9233.84 | C+S GST 18% I/P RD | 1662.1 | 10895.94 | 10895.94 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 601 Living,Dining,Ent.Lobby | Italian Marble Mirror Polish- BCo | 460.268 | Sq.Ft | 35 | 100 | 402.73 | 0 | 16109.38 | C+S GST 18% I/P RD | 2899.68 | 19009.06 | 19009.06 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 401 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 78.772 | Sq.Ft | 35 | 100 | 68.93 | 0 | 2757.02 | C+S GST 18% I/P RD | 496.26 | 3253.28 | 3253.28 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 501 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 470 | Sq.Ft | 35 | 100 | 411.25 | 0 | 16450 | C+S GST 18% I/P RD | 2961 | 19411 | 19411 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 501 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 125.896 | Sq.Ft | 35 | 100 | 110.16 | 0 | 4406.36 | C+S GST 18% I/P RD | 793.14 | 5199.5 | 5199.5 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 470 | Sq.Ft | 35 | 100 | 411.25 | 0 | 16450 | C+S GST 18% I/P RD | 2961 | 19411 | 19411 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 401 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 97.2 | Sq.Ft | 35 | 100 | 85.05 | 0 | 3402 | C+S GST 18% I/P RD | 612.36 | 4014.36 | 4014.36 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 101 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 78.772 | Sq.Ft | 35 | 100 | 68.93 | 0 | 2757.02 | C+S GST 18% I/P RD | 496.26 | 3253.28 | 3253.28 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 102 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 82.236 | Sq.Ft | 35 | 100 | 71.96 | 0 | 2878.26 | C+S GST 18% I/P RD | 518.08 | 3396.34 | 3396.34 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 102 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 107.768 | Sq.Ft | 35 | 100 | 94.3 | 0 | 3771.88 | C+S GST 18% I/P RD | 678.94 | 4450.82 | 4450.82 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 501 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 78.772 | Sq.Ft | 35 | 100 | 68.93 | 0 | 2757.02 | C+S GST 18% I/P RD | 496.26 | 3253.28 | 3253.28 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 702 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 107.768 | Sq.Ft | 40 | 100 | 107.77 | 0 | 4310.72 | C+S GST 18% I/P RD | 775.92 | 5086.64 | 5086.64 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 470 | Sq.Ft | 40 | 100 | 470 | 0 | 18800 | C+S GST 18% I/P RD | 3384 | 22184 | 22184 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 701 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 97.2 | Sq.Ft | 40 | 100 | 97.2 | 0 | 3888 | C+S GST 18% I/P RD | 699.84 | 4587.84 | 4587.84 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 263.824 | Sq.Ft | 40 | 100 | 263.82 | 0 | 10552.96 | C+S GST 18% I/P RD | 1899.54 | 12452.5 | 12452.5 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 702 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 82.236 | Sq.Ft | 40 | 100 | 82.24 | 0 | 3289.44 | C+S GST 18% I/P RD | 592.1 | 3881.54 | 3881.54 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 812 | 99092 | 11 Apr 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 86 | B 701 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 125.896 | Sq.Ft | 40 | 100 | 125.9 | 0 | 5035.84 | C+S GST 18% I/P RD | 906.46 | 5942.3 | 5942.3 | Approved | 0 | 0 | 1918 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 401 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.2857 | R.Ft | 35 | 100 | 46.62 | 0 | 1865 | C+S GST 18% I/P RD | 335.7 | 2200.7 | 2200.7 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 201 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.2857 | R.Ft | 35 | 100 | 46.62 | 0 | 1865 | C+S GST 18% I/P RD | 335.7 | 2200.7 | 2200.7 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 601 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 39.24 | R.Ft | 35 | 100 | 34.34 | 0 | 1373.4 | C+S GST 18% I/P RD | 247.22 | 1620.62 | 1620.62 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 601 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.2857 | R.Ft | 35 | 100 | 46.62 | 0 | 1865 | C+S GST 18% I/P RD | 335.7 | 2200.7 | 2200.7 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 401 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 39.24 | R.Ft | 35 | 100 | 34.34 | 0 | 1373.4 | C+S GST 18% I/P RD | 247.22 | 1620.62 | 1620.62 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 201 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 39.24 | R.Ft | 35 | 100 | 34.34 | 0 | 1373.4 | C+S GST 18% I/P RD | 247.22 | 1620.62 | 1620.62 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 1101 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 35.55 | R.Ft | 40 | 100 | 35.55 | 0 | 1422 | C+S GST 18% I/P RD | 255.96 | 1677.96 | 1677.96 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 901 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 35.55 | R.Ft | 40 | 100 | 35.55 | 0 | 1422 | C+S GST 18% I/P RD | 255.96 | 1677.96 | 1677.96 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 701 Marble Window Sill | Italian Marble Mirror Polish.- BCo | 35.55 | R.Ft | 40 | 100 | 35.55 | 0 | 1422 | C+S GST 18% I/P RD | 255.96 | 1677.96 | 1677.96 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 701 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.275 | R.Ft | 40 | 100 | 53.28 | 0 | 2131 | C+S GST 18% I/P RD | 383.58 | 2514.58 | 2514.58 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 1101 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.275 | R.Ft | 40 | 100 | 53.28 | 0 | 2131 | C+S GST 18% I/P RD | 383.58 | 2514.58 | 2514.58 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 901 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 53.275 | R.Ft | 40 | 100 | 53.28 | 0 | 2131 | C+S GST 18% I/P RD | 383.58 | 2514.58 | 2514.58 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 401 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 42.9975 | R.Ft | 45 | 100 | 48.37 | 0 | 1934.89 | C+S GST 18% I/P RD | 348.28 | 2283.17 | 2283.17 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 201 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 42.9975 | R.Ft | 45 | 100 | 48.37 | 0 | 1934.89 | C+S GST 18% I/P RD | 348.28 | 2283.17 | 2283.17 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 601 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 42.9975 | R.Ft | 45 | 100 | 48.37 | 0 | 1934.89 | C+S GST 18% I/P RD | 348.28 | 2283.17 | 2283.17 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 701 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 42.9975 | R.Ft | 50 | 100 | 53.75 | 0 | 2149.88 | C+S GST 18% I/P RD | 386.98 | 2536.86 | 2536.86 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 641 | 99091 | 11 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 51 | A 1101 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 42.9975 | R.Ft | 50 | 100 | 53.75 | 0 | 2149.88 | C+S GST 18% I/P RD | 386.98 | 2536.86 | 2536.86 | Approved | 0 | 0 | 305 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 13 | 100 | 14.7 | 0 | 588.16 | C+S GST 18% I/P RD | 105.86 | 694.02 | 694.02 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 13 | 100 | 13.81 | 0 | 552.24 | C+S GST 18% I/P RD | 99.4 | 651.64 | 651.64 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 13 | 100 | 15.02 | 0 | 600.68 | C+S GST 18% I/P RD | 108.12 | 708.8 | 708.8 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 13 | 100 | 12.5 | 0 | 499.94 | C+S GST 18% I/P RD | 89.98 | 589.92 | 589.92 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 13 | 100 | 18.04 | 0 | 721.66 | C+S GST 18% I/P RD | 129.9 | 851.56 | 851.56 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Guest Toilet Dado - 1 No. | Dado BC | 168.732 | Sq.Ft | 28 | 100 | 118.11 | 0 | 4724.5 | C+S GST 18% I/P RD | 850.42 | 5574.92 | 5574.92 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Parents Toilet Dado - 1 No. | Dado BC | 68.121 | Sq.Ft | 28 | 100 | 47.68 | 0 | 1907.39 | C+S GST 18% I/P RD | 343.34 | 2250.73 | 2250.73 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Children Toilet 1 Dado - 1 No. | Dado BC | 36.792 | Sq.Ft | 28 | 100 | 25.75 | 0 | 1030.18 | C+S GST 18% I/P RD | 185.44 | 1215.62 | 1215.62 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Master Toilet Dado - 1 No. | Dado BC | 125.838 | Sq.Ft | 28 | 100 | 88.09 | 0 | 3523.46 | C+S GST 18% I/P RD | 634.22 | 4157.68 | 4157.68 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Parents Toilet Dado - 1 No. | Dado BC | 132.867 | Sq.Ft | 28 | 100 | 93.01 | 0 | 3720.28 | C+S GST 18% I/P RD | 669.66 | 4389.94 | 4389.94 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Children Toilet 2 Dado - 1 No. | Dado BC | 24.174 | Sq.Ft | 28 | 100 | 16.92 | 0 | 676.87 | C+S GST 18% I/P RD | 121.84 | 798.71 | 798.71 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Powder Toilet Dado - 1 No. | Dado BC | 96.129 | Sq.Ft | 28 | 100 | 67.29 | 0 | 2691.61 | C+S GST 18% I/P RD | 484.48 | 3176.09 | 3176.09 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Children Toilet 1 Dado - 1 No. | Dado BC | 171.153 | Sq.Ft | 28 | 100 | 119.81 | 0 | 4792.28 | C+S GST 18% I/P RD | 862.62 | 5654.9 | 5654.9 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Children Toilet 2 Dado - 1 No. | Dado BC | 153.162 | Sq.Ft | 28 | 100 | 107.21 | 0 | 4288.54 | C+S GST 18% I/P RD | 771.94 | 5060.48 | 5060.48 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Guest Toilet Dado - 1 No. | Dado BC | 35.604 | Sq.Ft | 28 | 100 | 24.92 | 0 | 996.91 | C+S GST 18% I/P RD | 179.44 | 1176.35 | 1176.35 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Master Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 28 | 100 | 59.81 | 0 | 2392.49 | C+S GST 18% I/P RD | 430.64 | 2823.13 | 2823.13 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 Powder Toilet Dado - 1 No. | Dado BC | 35.604 | Sq.Ft | 28 | 100 | 24.92 | 0 | 996.91 | C+S GST 18% I/P RD | 179.44 | 1176.35 | 1176.35 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 185.031 | Sq.Ft | 45 | 100 | 208.16 | 0 | 8326.4 | C+S GST 18% I/P RD | 1498.76 | 9825.16 | 9825.16 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 201 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 218.7 | Sq.Ft | 45 | 100 | 246.04 | 0 | 9841.5 | C+S GST 18% I/P RD | 1771.48 | 11612.98 | 11612.98 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 593.604 | Sq.Ft | 45 | 100 | 667.8 | 0 | 26712.18 | C+S GST 18% I/P RD | 4808.2 | 31520.38 | 31520.38 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 242.478 | Sq.Ft | 45 | 100 | 272.79 | 0 | 10911.51 | C+S GST 18% I/P RD | 1964.08 | 12875.59 | 12875.59 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 201 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 283.266 | Sq.Ft | 45 | 100 | 318.67 | 0 | 12746.97 | C+S GST 18% I/P RD | 2294.46 | 15041.43 | 15041.43 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 201 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 177.237 | Sq.Ft | 45 | 100 | 199.39 | 0 | 7975.67 | C+S GST 18% I/P RD | 1435.62 | 9411.29 | 9411.29 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2001 StaffToilet Dado - 1 No. | Dado BC | 122.706 | Sq.Ft | 24 | 100 | 73.62 | 0 | 2944.94 | C+S GST 18% I/P RD | 530.08 | 3475.02 | 3475.02 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 1502 Window Sill | Italian Marble Sill- BC- | 45.656 | R.Ft | 55 | 100 | 62.78 | 0 | 2511.08 | C+S GST 18% I/P RD | 452 | 2963.08 | 2963.08 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 1302 Window Sill- | Italian Marble Sill- BC- | 45.656 | R.Ft | 55 | 100 | 62.78 | 0 | 2511.08 | C+S GST 18% I/P RD | 452 | 2963.08 | 2963.08 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 1702 Window Sill- | Italian Marble Sill- BC- | 45.656 | R.Ft | 55 | 100 | 62.78 | 0 | 2511.08 | C+S GST 18% I/P RD | 452 | 2963.08 | 2963.08 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 1902 Window Sill- | Italian Marble Sill- BC- | 51.363 | R.Ft | 60 | 100 | 77.04 | 0 | 3081.78 | C+S GST 18% I/P RD | 554.72 | 3636.5 | 3636.5 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 2102 Window Sill | Italian Marble Sill- BC- | 51.363 | R.Ft | 60 | 100 | 77.04 | 0 | 3081.78 | C+S GST 18% I/P RD | 554.72 | 3636.5 | 3636.5 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Ceramic Tiling | Ceramic Flooring work | 320.904 | Sq.Ft | 13 | 100 | 104.29 | 0 | 4171.75 | C+S GST 18% I/P RD | 750.92 | 4922.67 | 4922.67 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 202 Window Sill- | Italian Marble Sill- BC- | 46.791 | R.Ft | 45 | 100 | 52.64 | 0 | 2105.6 | C+S GST 18% I/P RD | 379 | 2484.6 | 2484.6 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 201 Window Sill- | Italian Marble Sill- BC- | 77.346 | R.Ft | 45 | 100 | 87.01 | 0 | 3480.57 | C+S GST 18% I/P RD | 626.5 | 4107.07 | 4107.07 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 758 | 99090 | 11 Apr 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 85 | B 502 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 15 | 100 | 51.93 | 0 | 2077.25 | C+S GST 18% I/P RD | 373.9 | 2451.15 | 2451.15 | Approved | 0 | 0 | 1397 | 11 Apr 2023
GANGA DHAM TOWERS | 844 | 99074 | 10 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 140 | A Eastside 26th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 117 | 10 Apr 2023
GANGA DHAM TOWERS | 844 | 99074 | 10 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 140 | A South side 25th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 117 | 10 Apr 2023
GANGA DHAM TOWERS | 844 | 99074 | 10 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 140 | A Northside 25th floor External Texture Painting | Texture Paint (L) | 384 | Sq.Ft | 7.25 | 100 | 69.6 | 0 | 2784 | C+S GST 18% I/P RD | 501.12 | 3285.12 | 3285.12 | Approved | 0 | 0 | 117 | 10 Apr 2023
GANGA DHAM TOWERS | 844 | 99074 | 10 Apr 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 140 | A Westside 25th floor External Texture Painting | Texture Paint (L) | 424 | Sq.Ft | 7.25 | 100 | 76.85 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 117 | 10 Apr 2023
GANGA DHAM TOWERS | 1248 | 99073 | 10 Apr 2023 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD |  | B 201 NOC | Italian Marble Flooring - BCo | 156.393 | Sq.Ft | 45 | 100 | 175.94 | 0 | 7037.69 | C+S GST 18% I/P RD | 1266.78 | 8304.47 | 8304.47 |  | 0 | 0 | 141 | 10 Apr 2023
GANGA DHAM TOWERS | 540 | 99072 | 10 Apr 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 54 | A 701 NOC | Italian Marble Champher & Polish | 28.5 | R.Ft | 55 | 100 | 39.19 | 0 | 1567.5 | C+S GST 18% I/P RD | 282.16 | 1849.66 | 1849.66 | Approved | 0 | 0 | 16 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 701 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 46.755 | R.Ft | 50 | 100 | 58.44 | 0 | 2337.75 | C+S GST 18% I/P RD | 420.8 | 2758.55 | 2758.55 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A-1101 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Champher & Polish | 88.155 | R.Ft | 50 | 100 | 110.19 | 0 | 4407.75 | C+S GST 18% I/P RD | 793.4 | 5201.15 | 5201.15 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 201 Master Bed Marble Flooring | Italian Marble Champher & Polish | 49.215 | R.Ft | 45 | 100 | 55.37 | 0 | 2214.68 | C+S GST 18% I/P RD | 398.64 | 2613.32 | 2613.32 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 601 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 88.155 | R.Ft | 45 | 100 | 99.17 | 0 | 3966.98 | C+S GST 18% I/P RD | 714.06 | 4681.04 | 4681.04 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 601 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 11.0667 | R.Ft | 45 | 100 | 12.45 | 0 | 498 | C+S GST 18% I/P RD | 89.64 | 587.64 | 587.64 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 401 Master Bed Marble Flooring | Italian Marble Champher & Polish | 49.215 | R.Ft | 45 | 100 | 55.37 | 0 | 2214.68 | C+S GST 18% I/P RD | 398.64 | 2613.32 | 2613.32 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 201 Living,Dining,Passa. Flooring | Italian Marble Champher & Polish | 88.155 | R.Ft | 45 | 100 | 99.17 | 0 | 3966.98 | C+S GST 18% I/P RD | 714.06 | 4681.04 | 4681.04 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 201 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 11.0667 | R.Ft | 45 | 100 | 12.45 | 0 | 498 | C+S GST 18% I/P RD | 89.64 | 587.64 | 587.64 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 201 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 46.755 | R.Ft | 45 | 100 | 52.6 | 0 | 2103.98 | C+S GST 18% I/P RD | 378.72 | 2482.7 | 2482.7 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 401 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 46.755 | R.Ft | 45 | 100 | 52.6 | 0 | 2103.98 | C+S GST 18% I/P RD | 378.72 | 2482.7 | 2482.7 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 401 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 16.5111 | R.Ft | 45 | 100 | 18.57 | 0 | 743 | C+S GST 18% I/P RD | 133.74 | 876.74 | 876.74 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 401 Living,Dining,Passa. Flooring | Italian Marble Champher & Polish | 88.155 | R.Ft | 45 | 100 | 99.17 | 0 | 3966.98 | C+S GST 18% I/P RD | 714.06 | 4681.04 | 4681.04 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 601 Master Bed Marble Flooring | Italian Marble Champher & Polish | 49.215 | R.Ft | 45 | 100 | 55.37 | 0 | 2214.68 | C+S GST 18% I/P RD | 398.64 | 2613.32 | 2613.32 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 601 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 46.755 | R.Ft | 45 | 100 | 52.6 | 0 | 2103.98 | C+S GST 18% I/P RD | 378.72 | 2482.7 | 2482.7 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 201 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 11.0571 | R.Ft | 35 | 100 | 9.67 | 0 | 387 | C+S GST 18% I/P RD | 69.66 | 456.66 | 456.66 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 901 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 11.05 | R.Ft | 40 | 100 | 11.05 | 0 | 442 | C+S GST 18% I/P RD | 79.56 | 521.56 | 521.56 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 901 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 40 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 901 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 40 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 901 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 40 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 701 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 11.06 | R.Ft | 50 | 100 | 13.83 | 0 | 553 | C+S GST 18% I/P RD | 99.54 | 652.54 | 652.54 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A-1101 Guest Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 11.06 | R.Ft | 50 | 100 | 13.83 | 0 | 553 | C+S GST 18% I/P RD | 99.54 | 652.54 | 652.54 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 701 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 88.155 | R.Ft | 50 | 100 | 110.19 | 0 | 4407.75 | C+S GST 18% I/P RD | 793.4 | 5201.15 | 5201.15 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A-1101 Master Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 49.215 | R.Ft | 50 | 100 | 61.52 | 0 | 2460.75 | C+S GST 18% I/P RD | 442.94 | 2903.69 | 2903.69 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A-1101 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 46.755 | R.Ft | 50 | 100 | 58.44 | 0 | 2337.75 | C+S GST 18% I/P RD | 420.8 | 2758.55 | 2758.55 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 641 | 99071 | 10 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 53 | A 701 Master Bed Marble Flooring | Italian Marble Champher & Polish | 49.215 | R.Ft | 50 | 100 | 61.52 | 0 | 2460.75 | C+S GST 18% I/P RD | 442.94 | 2903.69 | 2903.69 | Approved | 0 | 0 | 543 | 10 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | ISMB 125 (L) -BCo | 750.49 | Kgs | 20 | 100 | 375.25 | 0 | 15009.8 | C+S GST 18% I/P RD | 2701.76 | 17711.56 | 17711.56 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(L) | 2974 | Kgs | 20 | 100 | 1487 | 0 | 59480 | C+S GST 18% I/P RD | 10706.4 | 70186.4 | 70186.4 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | ISMC 200 (L) | 3384.5 | Kgs | 20 | 100 | 1692.25 | 0 | 67690 | C+S GST 18% I/P RD | 12184.2 | 79874.2 | 79874.2 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | ISMB 200 (L) | 1865 | Kgs | 20 | 100 | 932.5 | 0 | 37300 | C+S GST 18% I/P RD | 6714 | 44014 | 44014 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | ISMB 150 (L) | 2676.71 | Kgs | 20 | 100 | 1338.36 | 0 | 53534.2 | C+S GST 18% I/P RD | 9636.16 | 63170.36 | 63170.36 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | MS Plate (L) | 1306.5 | Kgs | 20 | 100 | 653.25 | 0 | 26130 | C+S GST 18% I/P RD | 4703.4 | 30833.4 | 30833.4 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | 254.32 | Kgs | 20 | 100 | 127.16 | 0 | 5086.4 | C+S GST 18% I/P RD | 915.56 | 6001.96 | 6001.96 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | Chemical Fastner fixing (L) | 390 | No. | 80 | 100 | 780 | 0 | 31200 | C+S GST 18% I/P RD | 5616 | 36816 | 36816 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1447 | 99070 | 08 Apr 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 119 | Tower A Service Platform Fabrication Work | ISMB 250 (L) | 667.67 | Kgs | 20 | 100 | 333.84 | 0 | 13353.4 | C+S GST 18% I/P RD | 2403.62 | 15757.02 | 15757.02 | Approved | 0 | 0 | 3088 | 08 Apr 2023
GANGA DHAM TOWERS | 1296 | 99062 | 08 Apr 2023 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 37 | Miscellaneous expenses | Marketing Operating Expenses | 8.9733 | Month | 25000 | 8.33 | 0 | 0 | 18687 | C+S GST 0% I/P RD | 0 | 18687 | 18687 | Approved | 0 | 0 | 0 | 08 Apr 2023
GANGA DHAM TOWERS | 272 | 99061 | 08 Apr 2023 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 58 | A Bldg 36th slab (31st Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 6336 | Sq.Ft | 190 | 100 | 30096 | 0 | 1203840 | C+S GST 18% I/P RD | 216691.2 | 1420531.2 | 1420531.2 | Approved | 0 | 0 | 24077 | 08 Apr 2023
GANGA DHAM TOWERS | 1056 | 99051 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 419 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 874.92 | C+S GST 18% I/P RD | 157.48 | 1032.4 | 1032.4 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 1056 | 99051 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 419 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 1056 | 99051 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 419 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 1055 | 99050 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 418 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 1055 | 99050 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 418 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 1055 | 99050 | 08 Apr 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 418 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 874.92 | C+S GST 18% I/P RD | 157.48 | 1032.4 | 1032.4 | Approved | 0 | 0 | 52 | 08 Apr 2023
GANGA DHAM TOWERS | 272 | 99024 | 07 Apr 2023 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 573 | A Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 23.6901 | Sq.Ft | 171 | 100 | 0 | 0 | 4051 | C+S GST 18% I/P RD | 729.18 | 4780.18 | 4780.18 | Approved | 0 | 0 | 81 | 07 Apr 2023
GANGA DHAM TOWERS | 272 | 99024 | 07 Apr 2023 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 573 | A Bldg 27th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 23.6784 | Sq.Ft | 171 | 100 | 0 | 0 | 4049 | C+S GST 18% I/P RD | 728.82 | 4777.82 | 4777.82 | Approved | 0 | 0 | 81 | 07 Apr 2023
GANGA DHAM TOWERS | 641 | 99023 | 07 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 55 | A 1301 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 45 | 100 | 45.17 | 0 | 1806.98 | C+S GST 18% I/P RD | 325.26 | 2132.24 | 2132.24 | Approved | 0 | 0 | 159 | 07 Apr 2023
GANGA DHAM TOWERS | 641 | 99023 | 07 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 55 | A 1301 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 45 | 100 | 77.02 | 0 | 3080.7 | C+S GST 18% I/P RD | 554.52 | 3635.22 | 3635.22 | Approved | 0 | 0 | 159 | 07 Apr 2023
GANGA DHAM TOWERS | 641 | 99023 | 07 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 55 | A 1301 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 45 | 100 | 193.29 | 0 | 7731.45 | C+S GST 18% I/P RD | 1391.66 | 9123.11 | 9123.11 | Approved | 0 | 0 | 159 | 07 Apr 2023
GANGA DHAM TOWERS | 641 | 99023 | 07 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 55 | A 1301 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 45 | 100 | 71.2 | 0 | 2848.1 | C+S GST 18% I/P RD | 512.66 | 3360.76 | 3360.76 | Approved | 0 | 0 | 159 | 07 Apr 2023
GANGA DHAM TOWERS | 641 | 99023 | 07 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 55 | A 1301 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 9.474 | R.Ft | 45 | 100 | 10.66 | 0 | 426.33 | C+S GST 18% I/P RD | 76.74 | 503.07 | 503.07 | Approved | 0 | 0 | 159 | 07 Apr 2023
GANGA DHAM TOWERS | 1229 | 99022 | 07 Apr 2023 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 49 | B Fire Fighting Riser work | SITC GI Pipe C Class 150mm dia.(M+L) | 238 | Mtrs | 2700 | 80 | 12852 | 0 | 514080 | C+S GST 18% I/P RD | 92534.4 | 606614.4 | 606614.4 | Approved | 0 | 0 | 0 | 07 Apr 2023
GANGA DHAM TOWERS | 1229 | 99022 | 07 Apr 2023 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 49 | B Fire Fighting Riser work | SITC GI Pipe C Class 100mm dia.(M+L) | 60 | Mtrs | 1900 | 80 | 2280 | 0 | 91200 | C+S GST 18% I/P RD | 16416 | 107616 | 107616 | Approved | 0 | 0 | 0 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-2101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 520.752 | R.Ft | 20 | 100 | 260.38 | 0 | 10415.04 | C+S GST 18% I/P RD | 1874.7 | 12289.74 | 12289.74 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1401 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1601 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 520.752 | R.Ft | 20 | 100 | 260.38 | 0 | 10415.04 | C+S GST 18% I/P RD | 1874.7 | 12289.74 | 12289.74 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1401 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1601 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1366.974 | Sq.Ft | 20 | 100 | 683.49 | 0 | 27339.48 | C+S GST 18% I/P RD | 4921.1 | 32260.58 | 32260.58 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-1301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 805 | 99021 | 07 Apr 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 47 | B-2101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1366.974 | Sq.Ft | 20 | 100 | 683.49 | 0 | 27339.48 | C+S GST 18% I/P RD | 4921.1 | 32260.58 | 32260.58 | Approved | 0 | 0 | 1558 | 07 Apr 2023
GANGA DHAM TOWERS | 149 | 99020 | 07 Apr 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 46 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 323 | No. | 4 | 100 | 0 | 0 | 1292 | CGST 0% URD I/P | 0 | 1292 | 1292 | Approved | 0 | 0 | 0 | 07 Apr 2023
GANGA DHAM TOWERS | 149 | 99020 | 07 Apr 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 46 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 151 | No. | 4 | 100 | 0 | 0 | 604 | CGST 0% URD I/P | 0 | 604 | 604 | Approved | 0 | 0 | 0 | 07 Apr 2023
GANGA DHAM TOWERS | 149 | 99020 | 07 Apr 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 46 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 4000 | No. | 4 | 100 | 0 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 0 | 07 Apr 2023
GANGA DHAM TOWERS | 1501 | 99011 | 28 Mar 2023 |  | TALENTAX RENAISSANCE PRIVATE LIMITED | TALENTAX RENAISSANCE PRIVATE LIMITED | EV - 2388 | GST Consultancy | Professional Fees | 1 | Month | 11000 | 100 | 0 | 0 | 11000 | C+S GST 18% I/P RD | 1980 | 12980 | 12980 | Approved | 0 | 0 | 2200 | 28 Mar 2023
GANGA DHAM TOWERS | 1501 | 99011 | 28 Mar 2023 |  | TALENTAX RENAISSANCE PRIVATE LIMITED | TALENTAX RENAISSANCE PRIVATE LIMITED | EV - 2388 | GST Consultancy | Professional Fees | 1 | Month | 11000 | 100 | 0 | 0 | 11000 | C+S GST 18% I/P RD | 1980 | 12980 | 12980 | Approved | 0 | 0 | 2200 | 28 Mar 2023
GANGA DHAM TOWERS | 1496 | 99002 | 06 Apr 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 45 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 2 | No. | 5500 | 100 | 0 | 0 | 11000 | C+S GST 18% I/P RD | 1980 | 12980 | 12980 | Approved | 0 | 0 | 2860 | 06 Apr 2023
GANGA DHAM TOWERS | 1496 | 99002 | 06 Apr 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 45 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 1 | No. | 26000 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 2860 | 06 Apr 2023
GANGA DHAM TOWERS | 1496 | 99002 | 06 Apr 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 45 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 3 | No. | 26000 | 100 | 0 | 0 | 78000 | C+S GST 18% I/P RD | 14040 | 92040 | 92040 | Approved | 0 | 0 | 2860 | 06 Apr 2023
GANGA DHAM TOWERS | 1496 | 99002 | 06 Apr 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 45 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 2 | No. | 3500 | 100 | 0 | 0 | 7000 | C+S GST 18% I/P RD | 1260 | 8260 | 8260 | Approved | 0 | 0 | 2860 | 06 Apr 2023
GANGA DHAM TOWERS | 1496 | 99002 | 06 Apr 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 45 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 6 | No. | 3500 | 100 | 0 | 0 | 21000 | C+S GST 18% I/P RD | 3780 | 24780 | 24780 | Approved | 0 | 0 | 2860 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 401 Living,Dining,Passa. Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 35 | 100 | 150.33 | 0 | 6013.35 | C+S GST 18% I/P RD | 1082.4 | 7095.75 | 7095.75 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 401 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 35 | 100 | 59.9 | 0 | 2396.1 | C+S GST 18% I/P RD | 431.3 | 2827.4 | 2827.4 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 401 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 35 | 100 | 55.38 | 0 | 2215.19 | C+S GST 18% I/P RD | 398.74 | 2613.93 | 2613.93 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1101 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 40 | 100 | 63.29 | 0 | 2531.64 | C+S GST 18% I/P RD | 455.7 | 2987.34 | 2987.34 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 901 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 40 | 100 | 171.81 | 0 | 6872.4 | C+S GST 18% I/P RD | 1237.04 | 8109.44 | 8109.44 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1201 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 40 | 100 | 68.46 | 0 | 2738.4 | C+S GST 18% I/P RD | 492.92 | 3231.32 | 3231.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1201 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 40 | 100 | 63.29 | 0 | 2531.64 | C+S GST 18% I/P RD | 455.7 | 2987.34 | 2987.34 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1101 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 40 | 100 | 171.81 | 0 | 6872.4 | C+S GST 18% I/P RD | 1237.04 | 8109.44 | 8109.44 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1101 Guest Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 40 | 100 | 40.16 | 0 | 1606.2 | C+S GST 18% I/P RD | 289.12 | 1895.32 | 1895.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1201 Guest Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 40 | 100 | 40.16 | 0 | 1606.2 | C+S GST 18% I/P RD | 289.12 | 1895.32 | 1895.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 901 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 40 | 100 | 40.16 | 0 | 1606.2 | C+S GST 18% I/P RD | 289.12 | 1895.32 | 1895.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 901 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 40 | 100 | 63.29 | 0 | 2531.64 | C+S GST 18% I/P RD | 455.7 | 2987.34 | 2987.34 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A 901 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 40 | 100 | 68.46 | 0 | 2738.4 | C+S GST 18% I/P RD | 492.92 | 3231.32 | 3231.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1201 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 40 | 100 | 171.81 | 0 | 6872.4 | C+S GST 18% I/P RD | 1237.04 | 8109.44 | 8109.44 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 641 | 99001 | 06 Apr 2023 |  | R K INTERIOR | Kishan Enterprises | EV - 50 | A-1101 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 40 | 100 | 68.46 | 0 | 2738.4 | C+S GST 18% I/P RD | 492.92 | 3231.32 | 3231.32 | Approved | 0 | 0 | 519 | 06 Apr 2023
GANGA DHAM TOWERS | 1452 | 98991 | 05 Apr 2023 |  | OMKAR PRADEEP MANE | OMKAR PRADEEP MANE | EV - 8 | Professional Consultancy | Professional Fees | 1 | Month | 25000 | 100 | 0 | 0 | 25000 | C+S GST 18% RCM | 4500 | 29500 | 29500 | Approved | 0 | 0 | 2500 | 05 Apr 2023
GANGA DHAM TOWERS | 1383 | 98988 | 31 Mar 2023 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 2381 | Professional Consultancy (Finalcial) | Professional Fees | 0.9994 | Month | 116666.666 | 100 | 0 | 0 | 116600 | CGST 0% URD I/P | 0 | 116600 | 116600 | Approved | 0 | 0 | 11660 | 31 Mar 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 404 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.66 | No. | 26015 | 45 | 193.16 | 0 | 7726.46 | C+S GST 18% I/P RD | 1390.76 | 9117.22 | 9117.22 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.66 | No. | 26015 | 45 | 193.16 | 0 | 7726.46 | C+S GST 18% I/P RD | 1390.76 | 9117.22 | 9117.22 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 902 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3 | No. | 26015 | 45 | 87.8 | 0 | 3512.03 | C+S GST 18% I/P RD | 632.16 | 4144.19 | 4144.19 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 902 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 601 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.0067 | No. | 26925 | 45 | 2.03 | 0 | 81.18 | C+S GST 18% I/P RD | 14.62 | 95.8 | 95.8 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.66 | No. | 26925 | 45 | 199.92 | 0 | 7996.73 | C+S GST 18% I/P RD | 1439.42 | 9436.15 | 9436.15 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 601 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.66 | No. | 26925 | 45 | 199.92 | 0 | 7996.73 | C+S GST 18% I/P RD | 1439.42 | 9436.15 | 9436.15 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1603 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1603 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 203 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1503 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 503 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1703 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 203 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 403 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 403 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 45 | 261.42 | 0 | 10456.65 | C+S GST 18% I/P RD | 1882.2 | 12338.85 | 12338.85 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1503 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3 | No. | 23237 | 45 | 78.42 | 0 | 3137 | C+S GST 18% I/P RD | 564.66 | 3701.66 | 3701.66 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.0033 | No. | 23237 | 45 | 0.86 | 0 | 34.51 | C+S GST 18% I/P RD | 6.22 | 40.73 | 40.73 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 703 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 503 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1003 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.33 | No. | 23237 | 45 | 86.27 | 0 | 3450.69 | C+S GST 18% I/P RD | 621.12 | 4071.81 | 4071.81 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 1118 | 98986 | 05 Apr 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 146 | A 1003 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 853 | 05 Apr 2023
GANGA DHAM TOWERS | 272 | 98985 | 05 Apr 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 149 | A Bldg 36th slab (31st Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1826 | Sq.Ft | 190 | 100 | 8673.5 | 0 | 346940 | C+S GST 18% I/P RD | 62449.2 | 409389.2 | 409389.2 | Approved | 0 | 0 | 6939 | 05 Apr 2023
GANGA DHAM TOWERS | 372 | 98983 | 05 Apr 2023 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 118 | B Bldg. 36th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 5740 | Sq.Ft | 190 | 100 | 27265 | 0 | 1090600 | C+S GST 18% I/P RD | 196308 | 1286908 | 1286908 | Approved | 0 | 0 | 21812 | 05 Apr 2023
GANGA DHAM TOWERS | 389 | 98977 | 05 Apr 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1 | Loading / Unloading Expenses | Unloading of Tile Adhesive | 13 | Metric Tonnes | 200 | 100 | 0 | 0 | 2600 | CGST 0% URD I/P | 0 | 2600 | 2600 | Approved | 0 | 0 | 0 | 05 Apr 2023
GANGA DHAM TOWERS | 978 | 98975 | 04 Apr 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 44 | 53rd National Safety Week 2023 | Miscellaneous Expenses | 1 | No. | 12476 | 100 | 0 | 0 | 12476 | CGST 0% URD I/P | 0 | 12476 | 12476 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 1482 | 98965 | 04 Apr 2023 |  | RAHUL SHYAMKUMAR KHANDELWAL | RAHUL SHYAMKUMAR KHANDELWAL | EV - 2 | Company Secretary | Company Secretary charges | 1 | Month | 20000 | 100 | 0 | 0 | 20000 | CGST 0% URD I/P | 0 | 20000 | 20000 | Approved | 0 | 0 | 2000 | 04 Apr 2023
GANGA DHAM TOWERS | 1052 | 98963 | 04 Apr 2023 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 4 | Legal Consultancy - 1 No | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-2101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1366.974 | Sq.Ft | 55 | 100 | 0 | 0 | 75183.57 | C+S GST 18% I/P RD | 13533.04 | 88716.61 | 88716.61 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1401 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1601 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1366.974 | Sq.Ft | 55 | 100 | 0 | 0 | 75183.57 | C+S GST 18% I/P RD | 13533.04 | 88716.61 | 88716.61 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1601 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 520.752 | R.Ft | 55 | 100 | 0 | 0 | 28641.36 | C+S GST 18% I/P RD | 5155.44 | 33796.8 | 33796.8 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1401 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-1301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 804 | 98941 | 04 Apr 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 48 | B-2101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 520.752 | R.Ft | 55 | 100 | 0 | 0 | 28641.36 | C+S GST 18% I/P RD | 5155.44 | 33796.8 | 33796.8 | Approved | 0 | 0 | 0 | 04 Apr 2023
GANGA DHAM TOWERS | 1425 | 98940 | 04 Apr 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 52 | A 2303 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4667 | R.Ft | 45 | 100 | 14.03 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 11 | 04 Apr 2023
GANGA DHAM TOWERS | 1425 | 98940 | 04 Apr 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 52 | A 2203 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.47 | R.Ft | 45 | 100 | 14.03 | 0 | 561.15 | C+S GST 18% I/P RD | 101 | 662.15 | 662.15 | Approved | 0 | 0 | 11 | 04 Apr 2023
GANGA DHAM TOWERS | 940 | 98939 | 04 Apr 2023 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 43 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 04 Apr 2023
GANGA DHAM TOWERS | 1360 | 98938 | 04 Apr 2023 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 42 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 24 | 100 | 73.1 | 0 | 2923.99 | C+S GST 18% I/P RD | 526.32 | 3450.31 | 3450.31 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Terrace Parapet Top Granite | Granite Sill-BCo | 24.561 | R.Ft | 55 | 100 | 33.77 | 0 | 1350.86 | C+S GST 18% I/P RD | 243.16 | 1594.02 | 1594.02 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 55 | 100 | 29.23 | 0 | 1169.19 | C+S GST 18% I/P RD | 210.46 | 1379.65 | 1379.65 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 1904 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 55 | 100 | 29.23 | 0 | 1169.19 | C+S GST 18% I/P RD | 210.46 | 1379.65 | 1379.65 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2304 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 55 | 100 | 29.23 | 0 | 1169.19 | C+S GST 18% I/P RD | 210.46 | 1379.65 | 1379.65 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 55 | 100 | 29.23 | 0 | 1169.19 | C+S GST 18% I/P RD | 210.46 | 1379.65 | 1379.65 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2004 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 55 | 100 | 29.23 | 0 | 1169.19 | C+S GST 18% I/P RD | 210.46 | 1379.65 | 1379.65 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Marble Window Sill | Italian Marble Sill- BC- | 47.97 | R.Ft | 60 | 100 | 71.96 | 0 | 2878.2 | C+S GST 18% I/P RD | 518.08 | 3396.28 | 3396.28 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Marble Window Sill | Italian Marble Sill- BC- | 25.974 | R.Ft | 60 | 100 | 38.96 | 0 | 1558.44 | C+S GST 18% I/P RD | 280.52 | 1838.96 | 1838.96 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Marble Window Sill | Italian Marble Sill- BC- | 25.974 | R.Ft | 60 | 100 | 38.96 | 0 | 1558.44 | C+S GST 18% I/P RD | 280.52 | 1838.96 | 1838.96 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.939 | R.Ft | 24 | 100 | 9.56 | 0 | 382.54 | C+S GST 18% I/P RD | 68.86 | 451.4 | 451.4 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Terrace Vitrified Flooring | Vitrified Skirting BC | 36.513 | R.Ft | 28 | 100 | 25.56 | 0 | 1022.36 | C+S GST 18% I/P RD | 184.02 | 1206.38 | 1206.38 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Terrace Vitrified Flooring | Vitrified Skirting BC | 36.513 | R.Ft | 28 | 100 | 25.56 | 0 | 1022.36 | C+S GST 18% I/P RD | 184.02 | 1206.38 | 1206.38 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2104 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.889 | R.Ft | 800 | 100 | 57.78 | 0 | 2311.2 | C+S GST 18% I/P RD | 416.02 | 2727.22 | 2727.22 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2104 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 800 | 100 | 100.44 | 0 | 4017.6 | C+S GST 18% I/P RD | 723.16 | 4740.76 | 4740.76 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2104 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 800 | 100 | 100.44 | 0 | 4017.6 | C+S GST 18% I/P RD | 723.16 | 4740.76 | 4740.76 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 28 | 100 | 53.69 | 0 | 2147.8 | C+S GST 18% I/P RD | 386.6 | 2534.4 | 2534.4 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Children Toilet Dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | C+S GST 18% I/P RD | 671.88 | 4404.5 | 4404.5 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Children Toilet Dado | Dado BC | 61.713 | Sq.Ft | 28 | 100 | 43.2 | 0 | 1727.96 | C+S GST 18% I/P RD | 311.04 | 2039 | 2039 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Dry Balcony dado | Dado BC | 78.03 | Sq.Ft | 28 | 100 | 54.62 | 0 | 2184.84 | C+S GST 18% I/P RD | 393.28 | 2578.12 | 2578.12 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | C+S GST 18% I/P RD | 307.46 | 2015.52 | 2015.52 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Children Toilet Dado | Dado BC | 61.713 | Sq.Ft | 28 | 100 | 43.2 | 0 | 1727.96 | C+S GST 18% I/P RD | 311.04 | 2039 | 2039 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Children Toilet Dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | C+S GST 18% I/P RD | 671.88 | 4404.5 | 4404.5 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Master Toilet dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | C+S GST 18% I/P RD | 671.88 | 4404.5 | 4404.5 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 28 | 100 | 24.75 | 0 | 990.11 | C+S GST 18% I/P RD | 178.22 | 1168.33 | 1168.33 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | C+S GST 18% I/P RD | 441.62 | 2895.09 | 2895.09 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | C+S GST 18% I/P RD | 176.26 | 1155.53 | 1155.53 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Dry Balcony dado | Dado BC | 80.361 | Sq.Ft | 28 | 100 | 56.25 | 0 | 2250.11 | C+S GST 18% I/P RD | 405.02 | 2655.13 | 2655.13 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.869 | R.Ft | 800 | 100 | 97.38 | 0 | 3895.2 | C+S GST 18% I/P RD | 701.14 | 4596.34 | 4596.34 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.545 | R.Ft | 800 | 100 | 90.9 | 0 | 3636 | C+S GST 18% I/P RD | 654.48 | 4290.48 | 4290.48 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.869 | R.Ft | 800 | 100 | 97.38 | 0 | 3895.2 | C+S GST 18% I/P RD | 701.14 | 4596.34 | 4596.34 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 800 | 100 | 100.44 | 0 | 4017.6 | C+S GST 18% I/P RD | 723.16 | 4740.76 | 4740.76 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 800 | 100 | 100.44 | 0 | 4017.6 | C+S GST 18% I/P RD | 723.16 | 4740.76 | 4740.76 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.545 | R.Ft | 800 | 100 | 90.9 | 0 | 3636 | C+S GST 18% I/P RD | 654.48 | 4290.48 | 4290.48 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.959 | R.Ft | 800 | 100 | 99.18 | 0 | 3967.2 | C+S GST 18% I/P RD | 714.1 | 4681.3 | 4681.3 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.968 | R.Ft | 800 | 100 | 99.36 | 0 | 3974.4 | C+S GST 18% I/P RD | 715.4 | 4689.8 | 4689.8 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.968 | R.Ft | 800 | 100 | 99.36 | 0 | 3974.4 | C+S GST 18% I/P RD | 715.4 | 4689.8 | 4689.8 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.959 | R.Ft | 800 | 100 | 99.18 | 0 | 3967.2 | C+S GST 18% I/P RD | 714.1 | 4681.3 | 4681.3 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2104 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 800 | 100 | 53.1 | 0 | 2124 | C+S GST 18% I/P RD | 382.32 | 2506.32 | 2506.32 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.889 | R.Ft | 800 | 100 | 57.78 | 0 | 2311.2 | C+S GST 18% I/P RD | 416.02 | 2727.22 | 2727.22 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 800 | 100 | 53.1 | 0 | 2124 | C+S GST 18% I/P RD | 382.32 | 2506.32 | 2506.32 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 1804 Terrace Parapet Top Granite | Granite Sill-BCo | 21.258 | R.Ft | 50 | 100 | 26.57 | 0 | 1062.9 | C+S GST 18% I/P RD | 191.32 | 1254.22 | 1254.22 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 24 | 100 | 13.52 | 0 | 540.65 | C+S GST 18% I/P RD | 97.32 | 637.97 | 637.97 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.503 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1116.07 | C+S GST 18% I/P RD | 200.9 | 1316.97 | 1316.97 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 24 | 100 | 22.52 | 0 | 900.94 | C+S GST 18% I/P RD | 162.16 | 1063.1 | 1063.1 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.503 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1116.07 | C+S GST 18% I/P RD | 200.9 | 1316.97 | 1316.97 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.11 | Sq.Ft | 24 | 100 | 25.87 | 0 | 1034.64 | C+S GST 18% I/P RD | 186.24 | 1220.88 | 1220.88 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.494 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1115.86 | C+S GST 18% I/P RD | 200.86 | 1316.72 | 1316.72 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 24 | 100 | 26.16 | 0 | 1046.3 | C+S GST 18% I/P RD | 188.34 | 1234.64 | 1234.64 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | C+S GST 18% I/P RD | 93.86 | 615.28 | 615.28 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2203 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 24 | 100 | 22.52 | 0 | 900.94 | C+S GST 18% I/P RD | 162.16 | 1063.1 | 1063.1 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2204 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 41.265 | Sq.Ft | 24 | 100 | 24.76 | 0 | 990.36 | C+S GST 18% I/P RD | 178.26 | 1168.62 | 1168.62 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2303 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 24 | 100 | 13.52 | 0 | 540.65 | C+S GST 18% I/P RD | 97.32 | 637.97 | 637.97 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 551 | 98937 | 04 Apr 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 56 | A 2404 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 1243 | 04 Apr 2023
GANGA DHAM TOWERS | 1520 | 98917 | 01 Apr 2023 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 10 | HO Expenses Security Services | Security Services. | 12 | Month | 13000 | 8.33 | 0 | 0 | 12999.95 | C+S GST 18% RCM | 2340 | 15339.95 | 15339.95 | Approved | 0 | 0 | 130 | 01 Apr 2023
GANGA DHAM TOWERS | 837 | 98901 | 28 Mar 2023 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 2226 | DA Development Electrical work | Electrical Work (Labour)-rate diff.-BC | 1 | No. | 58505 | 100 | 1462.63 | 0 | 58505 | C+S GST 18% I/P RD | 10530.9 | 69035.9 | 69035.9 | Approved | 0 | 5620 | 585 | 28 Mar 2023
GANGA DHAM TOWERS | 1287 | 98899 | 28 Mar 2023 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2309 | B 2102 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 50.9091 | Sq.Ft | 55 | 100 | 70 | 0 | 2800 | C+S GST 0% I/P RD | 0 | 2800 | 2800 | Approved | 0 | 0 | 28 | 28 Mar 2023
GANGA DHAM TOWERS | 1377 | 98887 | 27 Mar 2023 |  | GREEN PLANET SOLUTION | GREEN PLANET SOLUTION | EV - 2301 | A Garbage Chute Collection System | Garbage Chute (Dry/Wet) | 1 | No. | 900000 | 30 | 0 | 0 | 270000 | C+S GST 12% I/P RD | 32400 | 302400 | 302400 | Approved | 0 | 0 | 5400 | 27 Mar 2023
GANGA DHAM TOWERS | 1337 | 98856 | 20 Mar 2023 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2211 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 1207 | 98854 | 20 Mar 2023 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2278 | Material Lift A - Material Lift Height Increase 25th to 31st | Erection work | 4.5 | Mtrs | 1200 | 100 | 0 | 0 | 5400 | C+S GST 18% I/P RD | 972 | 6372 | 6372 | Approved | 0 | 0 | 54 | 20 Mar 2023
GANGA DHAM TOWERS | 1437 | 98853 | 20 Mar 2023 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 2335 | PM Lift AMC in A & B Tower | PM Lift Height Extension | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 15 | 20 Mar 2023
GANGA DHAM TOWERS | 545 | 98852 | 20 Mar 2023 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 2336 | Tower B Lift Jumping (4th,9th,14th,19th &24th Floor) | Lift Jumping Work | 5 | No. | 1500 | 20 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 15 | 20 Mar 2023
GANGA DHAM TOWERS | 1208 | 98850 | 20 Mar 2023 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2279 | Material Lift B - Material Lift Height Increase 25th to 31st | Erection work | 6 | Mtrs | 1200 | 100 | 0 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 72 | 20 Mar 2023
GANGA DHAM TOWERS | 1364 | 98849 | 20 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2259 | B Cable Tray Ground Floor | MS Angle 50 x 50 x 5mm | 428.13 | Kgs | 12 | 100 | 128.44 | 0 | 5137.56 | CGST 0% URD I/P | 0 | 5137.56 | 5137.56 | Approved | 0 | 0 | 160 | 20 Mar 2023
GANGA DHAM TOWERS | 1364 | 98849 | 20 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2259 | A Cable Tray Ground Floor-(No.) | MS Angle 50 x 50 x 5mm | 679.9 | Kgs | 12 | 100 | 203.97 | 0 | 8158.8 | CGST 0% URD I/P | 0 | 8158.8 | 8158.8 | Approved | 0 | 0 | 160 | 20 Mar 2023
GANGA DHAM TOWERS | 1364 | 98849 | 20 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2259 | B Cable Tray Ground Floor | Fastner (M) - SOSB | 57 | No. | 20 | 100 | 0 | 0 | 1140 | CGST 0% URD I/P | 0 | 1140 | 1140 | Approved | 0 | 0 | 160 | 20 Mar 2023
GANGA DHAM TOWERS | 1364 | 98849 | 20 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2259 | A Cable Tray Ground Floor-(No.) | Fastner (M) - SOSB | 80 | No. | 20 | 100 | 0 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 160 | 20 Mar 2023
GANGA DHAM TOWERS | 1425 | 98847 | 20 Mar 2023 |  | Kishan Enterprises | MOHAN PARSHURAM YADAV | EV - 2265 | A 2503 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.47 | R.Ft | 45 | 100 | 14.03 | 0 | 561.15 | CGST 0% URD I/P | 0 | 561.15 | 561.15 | Approved | 0 | 0 | 6 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 41 | R.Ft | 80 | 100 | 82 | 0 | 3280 | CGST 0% URD I/P | 0 | 3280 | 3280 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 91.395 | R.Ft | 80 | 100 | 182.79 | 0 | 7311.6 | CGST 0% URD I/P | 0 | 7311.6 | 7311.6 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Master Bed Marble Flooring | Italian marble Skirting - BCo | 42 | R.Ft | 80 | 100 | 84 | 0 | 3360 | CGST 0% URD I/P | 0 | 3360 | 3360 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 36 | 100 | 106.13 | 0 | 4245.05 | CGST 0% URD I/P | 0 | 4245.05 | 4245.05 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 36 | 100 | 69.04 | 0 | 2761.45 | CGST 0% URD I/P | 0 | 2761.45 | 2761.45 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 36 | 100 | 117.63 | 0 | 4705.13 | CGST 0% URD I/P | 0 | 4705.13 | 4705.13 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 27.5 | 100 | 106.17 | 0 | 4246.61 | CGST 0% URD I/P | 0 | 4246.61 | 4246.61 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 34 | 100 | 30.06 | 0 | 1202.27 | CGST 0% URD I/P | 0 | 1202.27 | 1202.27 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 34 | 100 | 51.04 | 0 | 2041.63 | CGST 0% URD I/P | 0 | 2041.63 | 2041.63 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 34 | 100 | 44.58 | 0 | 1783.37 | CGST 0% URD I/P | 0 | 1783.37 | 1783.37 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Marble Window Sill | Italian Marble Sill- BC- | 17 | R.Ft | 80 | 100 | 34 | 0 | 1360 | CGST 0% URD I/P | 0 | 1360 | 1360 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 180.288 | Sq.Ft | 80 | 100 | 360.58 | 0 | 14423.04 | CGST 0% URD I/P | 0 | 14423.04 | 14423.04 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 439.191 | Sq.Ft | 80 | 100 | 878.38 | 0 | 35135.28 | CGST 0% URD I/P | 0 | 35135.28 | 35135.28 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 129.672 | Sq.Ft | 80 | 100 | 259.34 | 0 | 10373.76 | CGST 0% URD I/P | 0 | 10373.76 | 10373.76 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 103.896 | Sq.Ft | 34 | 100 | 88.31 | 0 | 3532.46 | CGST 0% URD I/P | 0 | 3532.46 | 3532.46 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 551 | 98846 | 20 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | MOHAN PARSHURAM YADAV | EV - 2313 | A 2503 Terrace Vitrified Flooring | Vitrified Flooring -BC | 118.863 | Sq.Ft | 34 | 100 | 101.03 | 0 | 4041.34 | CGST 0% URD I/P | 0 | 4041.34 | 4041.34 | Approved | 0 | 0 | 1038 | 20 Mar 2023
GANGA DHAM TOWERS | 1420 | 98820 | 20 Mar 2023 |  | JAY GANESH ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 2359 | D Bldg Scaffolding for Ext. Plaster | Lumpsum work- DCW | 0.3 | No. | 100000 | 100 | 750 | 0 | 30000 | CGST 0% URD I/P | 0 | 30000 | 30000 | Approved | 0 | 0 | 300 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1205 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 405 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 905 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1001 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 201 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 301 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 601 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 705 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1005 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1201 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1205 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 101 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 401 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 701 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 901 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 805 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 801 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1101 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 501 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 605 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 505 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1105 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1201 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 301 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 705 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 501 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 201 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1001 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 205 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 105 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 701 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 505 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 601 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 805 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1005 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 901 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 905 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 405 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 101 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1105 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 1101 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 605 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 305 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 801 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 798 | 98819 | 20 Mar 2023 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2268 | D 401 Counter for Wash Basin | Granite Counter (L) | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 540 | 20 Mar 2023
GANGA DHAM TOWERS | 695 | 98818 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2371 | B P2 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 2918 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10213 | C+S GST 5% I/P RD | 510.66 | 10723.66 | 10723.66 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 693 | 98817 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2370 | B P2 Podium Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 1195.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 4183 | C+S GST 5% I/P RD | 209.16 | 4392.16 | 4392.16 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 693 | 98817 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2370 | B P1 Podium Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 4050 | Sq.Ft | 3.5 | 100 | 0 | 0 | 14175 | C+S GST 5% I/P RD | 708.76 | 14883.76 | 14883.76 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D 12th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 616.45 | Sq.Ft | 9.5 | 100 | 0 | 0 | 5856.28 | C+S GST 5% I/P RD | 292.82 | 6149.1 | 6149.1 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D 8th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 489 | Sq.Ft | 9 | 100 | 0 | 0 | 4401 | C+S GST 5% I/P RD | 220.06 | 4621.06 | 4621.06 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D Main St.case Wall Gyp. Plaster 10th to 11th Fl. | Tikki Dhada (M) | 182.2222 | Sq.Ft | 9 | 100 | 0 | 0 | 1640 | C+S GST 5% I/P RD | 82 | 1722 | 1722 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D Fire St.case Wall Gyp. Plaster 3rd to 4th Fl. | Tikki Dhada (M) | 84 | Sq.Ft | 9 | 100 | 0 | 0 | 756 | C+S GST 5% I/P RD | 37.8 | 793.8 | 793.8 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D Fire St.case Wall Gyp. Plaster 9th to 10th Fl. | Tikki Dhada (M) | 404.87 | Sq.Ft | 9 | 100 | 0 | 0 | 3643.83 | C+S GST 5% I/P RD | 182.2 | 3826.03 | 3826.03 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 796 | 98816 | 20 Mar 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2369 | D Fire St.case Wall Gyp. Plaster Parking to 1st Fl. | Tikki Dhada (M) | 404.87 | Sq.Ft | 9 | 100 | 0 | 0 | 3643.83 | C+S GST 5% I/P RD | 182.2 | 3826.03 | 3826.03 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 697 | 98815 | 20 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2368 | D 202 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 597 | Sq.Ft | 9 | 100 | 0 | 0 | 5373 | C+S GST 5% I/P RD | 268.66 | 5641.66 | 5641.66 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 1314 | 98814 | 20 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2367 | D 1205 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 343.0526 | Sq.Ft | 9.5 | 100 | 0 | 0 | 3259 | C+S GST 5% I/P RD | 162.96 | 3421.96 | 3421.96 | Approved | 0 | 0 | 0 | 20 Mar 2023
GANGA DHAM TOWERS | 1338 | 98797 | 18 Mar 2023 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 2208 | HO Expensess (L) | Toner refilling | 11.85 | Month | 4000 | 8.33 | 0 | 0 | 3950 | CGST 0% URD I/P | 0 | 3950 | 3950 | Approved | 0 | 0 | 40 | 18 Mar 2023
GANGA DHAM TOWERS | 1337 | 98793 | 18 Mar 2023 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2209 | HO Expensess (L) | Printer Repairing- | 11.85 | Month | 8000 | 8.33 | 0 | 0 | 7900 | C+S GST 18% I/P RD | 1422 | 9322 | 9322 | Approved | 0 | 0 | 79 | 18 Mar 2023
GANGA DHAM TOWERS | 1337 | 98792 | 18 Mar 2023 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2210 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 80 | 18 Mar 2023
GANGA DHAM TOWERS | 1338 | 98791 | 18 Mar 2023 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 2207 | HO Expensess (L) | Toner refilling | 11.85 | Month | 4000 | 8.33 | 0 | 0 | 3950 | CGST 0% URD I/P | 0 | 3950 | 3950 | Approved | 0 | 0 | 40 | 18 Mar 2023
GANGA DHAM TOWERS | 1338 | 98790 | 18 Mar 2023 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 2206 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 18 Mar 2023
GANGA DHAM TOWERS | 1429 | 98789 | 18 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2256 | Sales office Fabrication work | MS Square Pipe (L) | 587.6 | Kgs | 12 | 100 | 176.28 | 0 | 7051.2 | CGST 0% URD I/P | 0 | 7051.2 | 7051.2 | Approved | 0 | 0 | 126 | 18 Mar 2023
GANGA DHAM TOWERS | 1429 | 98789 | 18 Mar 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2256 | Sales office Fabrication work | Meta colour Sheet Fixing BC | 1100 | Sq.Ft | 5 | 100 | 137.5 | 0 | 5500 | CGST 0% URD I/P | 0 | 5500 | 5500 | Approved | 0 | 0 | 126 | 18 Mar 2023
GANGA DHAM TOWERS | 1321 | 98788 | 18 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2307 | A Tower retaining wall plaster (99) | Single Coat Plaster (L) | 3852.33 | Sq.Ft | 25 | 100 | 2407.71 | 0 | 96308.25 | CGST 0% URD I/P | 0 | 96308.25 | 96308.25 | Approved | 0 | 0 | 1598 | 18 Mar 2023
GANGA DHAM TOWERS | 1321 | 98788 | 18 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2307 | B Tower retaining wall plaster (99) | Single Coat Plaster (L) | 1401.26 | Sq.Ft | 25 | 100 | 875.79 | 0 | 35031.5 | CGST 0% URD I/P | 0 | 35031.5 | 35031.5 | Approved | 0 | 0 | 1598 | 18 Mar 2023
GANGA DHAM TOWERS | 1321 | 98788 | 18 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2307 | A & B Tower retaining wall plaster (99) | Single Coat Plaster (L) | 1139.13 | Sq.Ft | 25 | 100 | 711.96 | 0 | 28478.25 | CGST 0% URD I/P | 0 | 28478.25 | 28478.25 | Approved | 0 | 0 | 1598 | 18 Mar 2023
GANGA DHAM TOWERS | 389 | 98773 | 17 Mar 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2196 | Loading / Unloading Expenses | Unloading of tiles. | 16 | Metric Tonnes | 260 | 100 | 0 | 0 | 4160 | CGST 0% URD I/P | 0 | 4160 | 4160 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2104 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 1304 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 1904 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2104 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 1904 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 2403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 632 | 98770 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2357 | A 1304 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1396 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 1304 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2104 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 1904 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 1304 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 1904 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2104 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 629 | 98769 | 17 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2358 | A 2404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 12th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 7th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 11th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 6th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 5th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 9th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 8th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | CGST 0% URD I/P | 0 | 723.87 | 723.87 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 12th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9.5 | 100 | 0 | 0 | 4685.02 | CGST 0% URD I/P | 0 | 4685.02 | 4685.02 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 5th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 246.58 | Sq.Ft | 9 | 100 | 55.48 | 0 | 2219.22 | CGST 0% URD I/P | 0 | 2219.22 | 2219.22 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 797 | 98768 | 17 Mar 2023 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 2262 | D 11th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9 | 100 | 110.96 | 0 | 4438.44 | CGST 0% URD I/P | 0 | 4438.44 | 4438.44 | Approved | 0 | 0 | 164 | 17 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 504 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 904 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 905 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 901 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 103 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 501 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 404 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 702 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 902 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 903 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 805 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 103 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1004 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 505 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 602 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 304 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1002 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 105 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 205 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 104 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 201 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 301 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 303 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1001 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 204 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 803 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 101 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1005 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 801 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 704 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 705 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 202 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 601 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 305 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 604 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 603 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 605 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 502 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 302 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 503 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 701 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 402 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 403 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 102 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 401 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 703 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 405 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 804 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1003 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 203 GI Louver | Galv. Louver (M) | 11.625 | Sq.Ft | 295 | 100 | 0 | 0 | 3429.38 | C+S GST 18% I/P RD | 617.28 | 4046.66 | 4046.66 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1102 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1104 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 302 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 804 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1103 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 101 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1101 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 305 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 405 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 704 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 1105 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 105 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 205 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 102 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 104 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 802 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 502 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 704 | 98748 | 16 Mar 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 2252 | D 904 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 905 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 604 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 701 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 203 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 603 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 201 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 105 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1001 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1002 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 205 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1005 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 605 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 402 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 404 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 704 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 302 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1003 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 102 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 104 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 101 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 503 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 505 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 702 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 304 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 804 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 502 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 803 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 305 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 601 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 602 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 902 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 805 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 303 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 901 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 301 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 405 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 504 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 703 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 904 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 501 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 103 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 204 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 202 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1004 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 705 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 801 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 401 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 403 GI Louver | Galv. Louver (L) | 11.625 | Sq.Ft | 30 | 100 | 8.72 | 0 | 348.75 | C+S GST 18% I/P RD | 62.78 | 411.53 | 411.53 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1103 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 305 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1004 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1102 GI Folding Door | Galv. Folding Door Fixing | 56.83 | Sq.Ft | 30 | 100 | 42.62 | 0 | 1704.9 | C+S GST 18% I/P RD | 306.88 | 2011.78 | 2011.78 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 102 GI Folding Door | Galv. Folding Door Fixing | 39.6667 | Sq.Ft | 30 | 100 | 29.75 | 0 | 1190 | C+S GST 18% I/P RD | 214.2 | 1404.2 | 1404.2 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1101 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 104 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 704 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1104 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 205 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 804 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 405 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 302 GI Folding Door | Galv. Folding Door Fixing | 39.6 | Sq.Ft | 30 | 100 | 29.7 | 0 | 1188 | C+S GST 18% I/P RD | 213.84 | 1401.84 | 1401.84 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 904 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 103 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 1105 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 105 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 502 GI Folding Door | Galv. Folding Door Fixing | 39.6667 | Sq.Ft | 30 | 100 | 29.75 | 0 | 1190 | C+S GST 18% I/P RD | 214.2 | 1404.2 | 1404.2 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 705 | 98747 | 16 Mar 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 2297 | D 101 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 920 | 16 Mar 2023
GANGA DHAM TOWERS | 1496 | 98745 | 16 Mar 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2266 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 3 | No. | 26000 | 100 | 0 | 0 | 78000 | C+S GST 18% I/P RD | 14040 | 92040 | 92040 | Approved | 0 | 0 | 2080 | 16 Mar 2023
GANGA DHAM TOWERS | 1496 | 98745 | 16 Mar 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2266 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 1 | No. | 26000 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 2080 | 16 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 6th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 5th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 11th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 1st Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 8th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 10th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 7th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 9th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 6th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D Terrace Floor Lobby Ghadai work | Ghadai work- BCP | 161.03 | Sq.Ft | 2 | 100 | 32.21 | 0 | 322.06 | CGST 0% URD I/P | 0 | 322.06 | 322.06 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 3rd Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 10th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 4th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 8th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 12th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 7th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 2nd Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 9th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 813 | 98664 | 15 Mar 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 2304 | D 11th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 68 | 15 Mar 2023
GANGA DHAM TOWERS | 551 | 98663 | 15 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2305 | A 2303 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 103.896 | Sq.Ft | 28 | 100 | 72.73 | 0 | 2909.09 | C+S GST 18% I/P RD | 523.64 | 3432.73 | 3432.73 | Approved | 0 | 0 | 130 | 15 Mar 2023
GANGA DHAM TOWERS | 551 | 98663 | 15 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2305 | A 2303 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 28 | 100 | 36.72 | 0 | 1468.66 | C+S GST 18% I/P RD | 264.36 | 1733.02 | 1733.02 | Approved | 0 | 0 | 130 | 15 Mar 2023
GANGA DHAM TOWERS | 551 | 98663 | 15 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2305 | A 2303 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 130 | 15 Mar 2023
GANGA DHAM TOWERS | 551 | 98663 | 15 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2305 | A 2303 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 28 | 100 | 82.54 | 0 | 3301.7 | C+S GST 18% I/P RD | 594.3 | 3896 | 3896 | Approved | 0 | 0 | 130 | 15 Mar 2023
GANGA DHAM TOWERS | 551 | 98663 | 15 Mar 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2305 | A 2303 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 130 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 7th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 12th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 5th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 1st Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 9th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 10th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 2nd Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 1st Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 5th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 6th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 4th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 7th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 10th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 8th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 3rd Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 9th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 6th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 12th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D Terrace level Duct Paint | 1 Coat Primer (Water Base) (M) | 597.996 | Sq.Ft | 1 | 100 | 0 | 0 | 598 | C+S GST 18% I/P RD | 107.64 | 705.64 | 705.64 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 8th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 2nd Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 11th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 3rd Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 4th FloorCommon Lobby Duct Painting | 1 Coat Primer (Water Base) (M) | 515.286 | Sq.Ft | 1 | 100 | 0 | 0 | 515.29 | C+S GST 18% I/P RD | 92.76 | 608.05 | 608.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1462 | 98662 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2341 | D 11th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (M) | 564.687 | Sq.Ft | 1 | 100 | 0 | 0 | 564.69 | C+S GST 18% I/P RD | 101.64 | 666.33 | 666.33 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 12th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 4th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 7th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 6th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 12th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 4th FloorCommon Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 2nd Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 3rd Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 6th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 10th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 11th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 5th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 10th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 7th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 11th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 1st Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 1st Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D Terrace level Duct Paint | 1 Coat Primer (Water Base) (L) | 531.552 | Sq.Ft | 1 | 100 | 13.29 | 0 | 531.55 | C+S GST 18% I/P RD | 95.68 | 627.23 | 627.23 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 3rd Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 8th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 2nd Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 8th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 9th Floor Common Lobby Duct Painting | 1 Coat Primer (Water Base) (L) | 458.032 | Sq.Ft | 1 | 100 | 11.45 | 0 | 458.03 | C+S GST 18% I/P RD | 82.44 | 540.47 | 540.47 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 9th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1463 | 98661 | 15 Mar 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2340 | D 5th Floor Toilet Duct Painting | 1 Coat Primer (Water Base) (L) | 501.944 | Sq.Ft | 1 | 100 | 12.55 | 0 | 501.94 | C+S GST 18% I/P RD | 90.34 | 592.28 | 592.28 | Approved | 0 | 0 | 121 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 23.3 | Kgs | 78 | 100 | 0 | 0 | 1817.4 | C+S GST 18% I/P RD | 327.14 | 2144.54 | 2144.54 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 15.9 | Kgs | 78 | 100 | 0 | 0 | 1240.2 | C+S GST 18% I/P RD | 223.24 | 1463.44 | 1463.44 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 21.2 | Kgs | 78 | 100 | 0 | 0 | 1653.6 | C+S GST 18% I/P RD | 297.64 | 1951.24 | 1951.24 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1294 | 98660 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2310 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 10.6 | Kgs | 78 | 100 | 0 | 0 | 826.8 | C+S GST 18% I/P RD | 148.82 | 975.62 | 975.62 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1702 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1002 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1802 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 502 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 10.6 | Kgs | 31.2 | 100 | 8.27 | 0 | 330.72 | C+S GST 18% I/P RD | 59.52 | 390.24 | 390.24 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 21.2 | Kgs | 31.2 | 100 | 16.54 | 0 | 661.44 | C+S GST 18% I/P RD | 119.06 | 780.5 | 780.5 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 1293 | 98659 | 15 Mar 2023 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 2311 | B 1702 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 235 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1404 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1201 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1204 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1501 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1502 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1504 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1301 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1401 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1304 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1302 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1402 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1601 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 503 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1604 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1301 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1502 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1202 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1602 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 204 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1204 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 403 Terrace False Ceiling | Sherawood False Ceiling (L) | 118.863 | Sq.Ft | 42 | 100 | 124.81 | 0 | 4992.25 | C+S GST 18% I/P RD | 898.6 | 5890.85 | 5890.85 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1601 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1302 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1304 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 503 Terrace False Ceiling | Sherawood False Ceiling (L) | 118.863 | Sq.Ft | 42 | 100 | 124.81 | 0 | 4992.25 | C+S GST 18% I/P RD | 898.6 | 5890.85 | 5890.85 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1201 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 204 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1402 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1401 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1504 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1501 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1602 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1202 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1604 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 637 | 98658 | 15 Mar 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 2312 | A 1404 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1550 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1301 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1303 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1504 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1302 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1601 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1503 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1604 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1603 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1304 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1501 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1601 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 204 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1401 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1304 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1301 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1502 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1302 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1402 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 503 Terrace False Ceiling | Painting work (M+L) -BC | 118.863 | Sq.Ft | 35 | 100 | 0 | 0 | 4160.21 | C+S GST 18% I/P RD | 748.84 | 4909.05 | 4909.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1201 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1602 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1604 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1204 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1504 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1202 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 403 Terrace False Ceiling | Painting work (M+L) -BC | 118.863 | Sq.Ft | 35 | 100 | 0 | 0 | 4160.21 | C+S GST 18% I/P RD | 748.84 | 4909.05 | 4909.05 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1404 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 636 | 98657 | 15 Mar 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2269 | A 1501 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 701 | 98656 | 15 Mar 2023 |  | VEER BHADRA ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 2316 | D Lift Shaft Painting | Cement Paint (L)- BC | 5036 | Sq.Ft | 2 | 100 | 251.8 | 0 | 10072 | C+S GST 18% I/P RD | 1812.96 | 11884.96 | 11884.96 | Approved | 0 | 0 | 101 | 15 Mar 2023
GANGA DHAM TOWERS | 700 | 98655 | 15 Mar 2023 |  | VEER BHADRA ENTERPRISES (MATERIAL) | ANIL MAHTO ENTERPRISES | EV - 2315 | D Lift Shaft Painting | Cement Paint (M)- BC | 3158 | Sq.Ft | 2 | 100 | 0 | 0 | 6316 | C+S GST 18% I/P RD | 1136.88 | 7452.88 | 7452.88 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 700 | 98655 | 15 Mar 2023 |  | VEER BHADRA ENTERPRISES (MATERIAL) | ANIL MAHTO ENTERPRISES | EV - 2315 | D Lift Shaft Painting | Cement Paint (M)- BC | 3158 | Sq.Ft | 2 | 100 | 0 | 0 | 6316 | C+S GST 18% I/P RD | 1136.88 | 7452.88 | 7452.88 | Approved | 0 | 0 | 0 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 24 | 100 | 25.49 | 0 | 1019.52 | C+S GST 18% I/P RD | 183.52 | 1203.04 | 1203.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 24 | 100 | 27.15 | 0 | 1085.83 | C+S GST 18% I/P RD | 195.44 | 1281.27 | 1281.27 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 24 | 100 | 33.31 | 0 | 1332.29 | C+S GST 18% I/P RD | 239.82 | 1572.11 | 1572.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 24 | 100 | 23.07 | 0 | 922.97 | C+S GST 18% I/P RD | 166.14 | 1089.11 | 1089.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 24 | 100 | 23.07 | 0 | 922.97 | C+S GST 18% I/P RD | 166.14 | 1089.11 | 1089.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 24 | 100 | 13.08 | 0 | 523.15 | C+S GST 18% I/P RD | 94.16 | 617.31 | 617.31 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 24 | 100 | 12.03 | 0 | 481.25 | C+S GST 18% I/P RD | 86.62 | 567.87 | 567.87 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 24 | 100 | 12.03 | 0 | 481.25 | C+S GST 18% I/P RD | 86.62 | 567.87 | 567.87 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 24 | 100 | 27.72 | 0 | 1108.94 | C+S GST 18% I/P RD | 199.6 | 1308.54 | 1308.54 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 24 | 100 | 25.49 | 0 | 1019.52 | C+S GST 18% I/P RD | 183.52 | 1203.04 | 1203.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 24 | 100 | 13.08 | 0 | 523.15 | C+S GST 18% I/P RD | 94.16 | 617.31 | 617.31 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 24 | 100 | 27.15 | 0 | 1085.83 | C+S GST 18% I/P RD | 195.44 | 1281.27 | 1281.27 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 24 | 100 | 27.72 | 0 | 1108.94 | C+S GST 18% I/P RD | 199.6 | 1308.54 | 1308.54 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 24 | 100 | 33.31 | 0 | 1332.29 | C+S GST 18% I/P RD | 239.82 | 1572.11 | 1572.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 24 | 100 | 13.08 | 0 | 523.15 | C+S GST 18% I/P RD | 94.16 | 617.31 | 617.31 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 24 | 100 | 33.31 | 0 | 1332.29 | C+S GST 18% I/P RD | 239.82 | 1572.11 | 1572.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 24 | 100 | 32.2 | 0 | 1288.01 | C+S GST 18% I/P RD | 231.84 | 1519.85 | 1519.85 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 24 | 100 | 32.2 | 0 | 1288.01 | C+S GST 18% I/P RD | 231.84 | 1519.85 | 1519.85 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 24 | 100 | 32.2 | 0 | 1288.01 | C+S GST 18% I/P RD | 231.84 | 1519.85 | 1519.85 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 24 | 100 | 23.07 | 0 | 922.97 | C+S GST 18% I/P RD | 166.14 | 1089.11 | 1089.11 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 24 | 100 | 27.15 | 0 | 1085.83 | C+S GST 18% I/P RD | 195.44 | 1281.27 | 1281.27 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 24 | 100 | 25.49 | 0 | 1019.52 | C+S GST 18% I/P RD | 183.52 | 1203.04 | 1203.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Dry Balcony Dado - 1 No. | Dado BC | 73.242 | Sq.Ft | 28 | 100 | 51.27 | 0 | 2050.78 | C+S GST 18% I/P RD | 369.14 | 2419.92 | 2419.92 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 28 | 100 | 114.03 | 0 | 4561.2 | C+S GST 18% I/P RD | 821.02 | 5382.22 | 5382.22 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 28 | 100 | 114.03 | 0 | 4561.2 | C+S GST 18% I/P RD | 821.02 | 5382.22 | 5382.22 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 28 | 100 | 84.96 | 0 | 3398.22 | C+S GST 18% I/P RD | 611.68 | 4009.9 | 4009.9 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 28 | 100 | 41.54 | 0 | 1661.44 | C+S GST 18% I/P RD | 299.06 | 1960.5 | 1960.5 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Powder Toilet Dado - 1 No. | Dado BC | 34.893 | Sq.Ft | 28 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Parents Toilet Dado - 1 No. | Dado BC | 48.654 | Sq.Ft | 28 | 100 | 34.06 | 0 | 1362.31 | C+S GST 18% I/P RD | 245.22 | 1607.53 | 1607.53 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 28 | 100 | 31.24 | 0 | 1249.42 | C+S GST 18% I/P RD | 224.9 | 1474.32 | 1474.32 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 800 | 100 | 95 | 0 | 3800 | C+S GST 18% I/P RD | 684 | 4484 | 4484 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 28 | 100 | 96.94 | 0 | 3877.52 | C+S GST 18% I/P RD | 697.96 | 4575.48 | 4575.48 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 28 | 100 | 96.94 | 0 | 3877.52 | C+S GST 18% I/P RD | 697.96 | 4575.48 | 4575.48 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 28 | 100 | 96.94 | 0 | 3877.52 | C+S GST 18% I/P RD | 697.96 | 4575.48 | 4575.48 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 28 | 100 | 109.37 | 0 | 4374.97 | C+S GST 18% I/P RD | 787.5 | 5162.47 | 5162.47 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 28 | 100 | 35.72 | 0 | 1428.84 | C+S GST 18% I/P RD | 257.2 | 1686.04 | 1686.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 28 | 100 | 35.72 | 0 | 1428.84 | C+S GST 18% I/P RD | 257.2 | 1686.04 | 1686.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 28 | 100 | 41.54 | 0 | 1661.44 | C+S GST 18% I/P RD | 299.06 | 1960.5 | 1960.5 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 28 | 100 | 84.96 | 0 | 3398.22 | C+S GST 18% I/P RD | 611.68 | 4009.9 | 4009.9 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 28 | 100 | 109.37 | 0 | 4374.97 | C+S GST 18% I/P RD | 787.5 | 5162.47 | 5162.47 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Powder Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 28 | 100 | 59.81 | 0 | 2392.49 | C+S GST 18% I/P RD | 430.64 | 2823.13 | 2823.13 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 28 | 100 | 35.72 | 0 | 1428.84 | C+S GST 18% I/P RD | 257.2 | 1686.04 | 1686.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Parents Toilet Dado - 1 No. | Dado BC | 48.654 | Sq.Ft | 28 | 100 | 34.06 | 0 | 1362.31 | C+S GST 18% I/P RD | 245.22 | 1607.53 | 1607.53 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 28 | 100 | 31.24 | 0 | 1249.42 | C+S GST 18% I/P RD | 224.9 | 1474.32 | 1474.32 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 28 | 100 | 31.24 | 0 | 1249.42 | C+S GST 18% I/P RD | 224.9 | 1474.32 | 1474.32 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 28 | 100 | 114.03 | 0 | 4561.2 | C+S GST 18% I/P RD | 821.02 | 5382.22 | 5382.22 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 28 | 100 | 102.55 | 0 | 4101.8 | C+S GST 18% I/P RD | 738.32 | 4840.12 | 4840.12 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Powder Toilet Dado - 1 No. | Dado BC | 34.893 | Sq.Ft | 28 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 28 | 100 | 41.54 | 0 | 1661.44 | C+S GST 18% I/P RD | 299.06 | 1960.5 | 1960.5 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Powder Toilet Dado - 1 No. | Dado BC | 34.893 | Sq.Ft | 28 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Kitchen Dado - 1 No. | Dado BC | 75.717 | Sq.Ft | 28 | 100 | 53 | 0 | 2120.08 | C+S GST 18% I/P RD | 381.62 | 2501.7 | 2501.7 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 28 | 100 | 102.55 | 0 | 4101.8 | C+S GST 18% I/P RD | 738.32 | 4840.12 | 4840.12 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 28 | 100 | 109.37 | 0 | 4374.97 | C+S GST 18% I/P RD | 787.5 | 5162.47 | 5162.47 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Powder Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 28 | 100 | 59.81 | 0 | 2392.49 | C+S GST 18% I/P RD | 430.64 | 2823.13 | 2823.13 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 28 | 100 | 102.55 | 0 | 4101.8 | C+S GST 18% I/P RD | 738.32 | 4840.12 | 4840.12 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2102 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 28 | 100 | 84.96 | 0 | 3398.22 | C+S GST 18% I/P RD | 611.68 | 4009.9 | 4009.9 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 Powder Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 28 | 100 | 59.81 | 0 | 2392.49 | C+S GST 18% I/P RD | 430.64 | 2823.13 | 2823.13 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 800 | 100 | 95 | 0 | 3800 | C+S GST 18% I/P RD | 684 | 4484 | 4484 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 800 | 100 | 61.6 | 0 | 2464 | C+S GST 18% I/P RD | 443.52 | 2907.52 | 2907.52 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 800 | 100 | 116.6 | 0 | 4664 | C+S GST 18% I/P RD | 839.52 | 5503.52 | 5503.52 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 800 | 100 | 118.2 | 0 | 4728 | C+S GST 18% I/P RD | 851.04 | 5579.04 | 5579.04 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 750 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 750 | 100 | 109.31 | 0 | 4372.5 | C+S GST 18% I/P RD | 787.06 | 5159.56 | 5159.56 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 750 | 100 | 109.31 | 0 | 4372.5 | C+S GST 18% I/P RD | 787.06 | 5159.56 | 5159.56 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 750 | 100 | 110.81 | 0 | 4432.5 | C+S GST 18% I/P RD | 797.86 | 5230.36 | 5230.36 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 750 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1302 Window Sill- | Italian Marble Sill- BC- | 5.707 | R.Ft | 55 | 100 | 7.85 | 0 | 313.89 | C+S GST 18% I/P RD | 56.5 | 370.39 | 370.39 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Window Sill- | Italian Marble Sill- BC- | 5.707 | R.Ft | 55 | 100 | 7.85 | 0 | 313.89 | C+S GST 18% I/P RD | 56.5 | 370.39 | 370.39 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Window Sill | Italian Marble Sill- BC- | 5.707 | R.Ft | 55 | 100 | 7.85 | 0 | 313.89 | C+S GST 18% I/P RD | 56.5 | 370.39 | 370.39 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 2302 StaffToilet Dado - 1 No. | Dado BC | 122.805 | Sq.Ft | 24 | 100 | 73.68 | 0 | 2947.32 | C+S GST 18% I/P RD | 530.52 | 3477.84 | 3477.84 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1902 StaffToilet Dado - 1 No. | Dado BC | 122.805 | Sq.Ft | 24 | 100 | 73.68 | 0 | 2947.32 | C+S GST 18% I/P RD | 530.52 | 3477.84 | 3477.84 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Common Toilet Counter Wash Basin - 1 No. | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1502 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 750 | 100 | 110.81 | 0 | 4432.5 | C+S GST 18% I/P RD | 797.86 | 5230.36 | 5230.36 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 758 | 98654 | 15 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2343 | B 1702 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1793 | 15 Mar 2023
GANGA DHAM TOWERS | 1252 | 98636 | 13 Mar 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2280 | B 1001 NOC | PCC Work- BCo | 186.25 | Sq.Ft | 6 | 100 | 27.94 | 0 | 1117.5 | C+S GST 18% I/P RD | 201.16 | 1318.66 | 1318.66 | Approved | 0 | 0 | 11 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1301 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 45 | 100 | 106.22 | 0 | 4248.99 | C+S GST 18% I/P RD | 764.82 | 5013.81 | 5013.81 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1401 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 45 | 100 | 66.46 | 0 | 2658.56 | C+S GST 18% I/P RD | 478.54 | 3137.1 | 3137.1 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1301 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 45 | 100 | 396.56 | 0 | 15862.5 | C+S GST 18% I/P RD | 2855.26 | 18717.76 | 18717.76 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1302 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 45 | 100 | 69.39 | 0 | 2775.47 | C+S GST 18% I/P RD | 499.58 | 3275.05 | 3275.05 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1302 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 45 | 100 | 222.6 | 0 | 8904.06 | C+S GST 18% I/P RD | 1602.74 | 10506.8 | 10506.8 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1401 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 45 | 100 | 82.01 | 0 | 3280.5 | C+S GST 18% I/P RD | 590.5 | 3871 | 3871 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 45 | 100 | 396.56 | 0 | 15862.5 | C+S GST 18% I/P RD | 2855.26 | 18717.76 | 18717.76 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1302 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 45 | 100 | 90.93 | 0 | 3637.17 | C+S GST 18% I/P RD | 654.7 | 4291.87 | 4291.87 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1301 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 45 | 100 | 66.46 | 0 | 2658.56 | C+S GST 18% I/P RD | 478.54 | 3137.1 | 3137.1 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1401 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 45 | 100 | 106.22 | 0 | 4248.99 | C+S GST 18% I/P RD | 764.82 | 5013.81 | 5013.81 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1202 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 40 | 100 | 61.68 | 0 | 2467.08 | C+S GST 18% I/P RD | 444.08 | 2911.16 | 2911.16 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1202 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 40 | 100 | 80.83 | 0 | 3233.04 | C+S GST 18% I/P RD | 581.94 | 3814.98 | 3814.98 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1101 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 96.294 | Sq.Ft | 40 | 100 | 96.29 | 0 | 3851.76 | C+S GST 18% I/P RD | 693.32 | 4545.08 | 4545.08 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1102 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 40 | 100 | 80.83 | 0 | 3233.04 | C+S GST 18% I/P RD | 581.94 | 3814.98 | 3814.98 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1101 Living,Dining,Ent.Lobby | Italian Marble Mirror Polish- BCo | 345.201 | Sq.Ft | 40 | 100 | 345.2 | 0 | 13808.04 | C+S GST 18% I/P RD | 2485.44 | 16293.48 | 16293.48 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1202 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 40 | 100 | 197.87 | 0 | 7914.72 | C+S GST 18% I/P RD | 1424.64 | 9339.36 | 9339.36 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 40 | 100 | 197.87 | 0 | 7914.72 | C+S GST 18% I/P RD | 1424.64 | 9339.36 | 9339.36 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1102 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 40 | 100 | 61.68 | 0 | 2467.08 | C+S GST 18% I/P RD | 444.08 | 2911.16 | 2911.16 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 812 | 98635 | 13 Mar 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2344 | B 1101 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 40 | 100 | 72.9 | 0 | 2916 | C+S GST 18% I/P RD | 524.88 | 3440.88 | 3440.88 | Approved | 0 | 0 | 1119 | 13 Mar 2023
GANGA DHAM TOWERS | 1513 | 98634 | 13 Mar 2023 |  | PUNDLIK P MAHAJAN | OM ENGINEERING & SCIENTIFIC EQUIPMENTS | EV - 2302 | R & D Purpose | R & D Purpose | 0.035 | No. | 100000 | 100 | 0 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 35 | 13 Mar 2023
GANGA DHAM TOWERS | 1482 | 98630 | 11 Mar 2023 |  | RAHUL SHYAMKUMAR KHANDELWAL | RAHUL SHYAMKUMAR KHANDELWAL | EV - 2195 | Company Secretary | Company Secretary charges | 1 | Month | 20000 | 100 | 0 | 0 | 20000 | CGST 0% URD I/P | 0 | 20000 | 20000 | Approved | 0 | 0 | 2000 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 11th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 7th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 2nd Floor Lift Opening BBM/Plaste | Blockwork/ Plaster-BC | 0.44 | No. | 5000 | 100 | 55 | 0 | 2200 | C+S GST 0% I/P RD | 0 | 2200 | 2200 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 10th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 4th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 12th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 5th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 1st Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 6th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 8th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D Parking Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 9th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1306 | 98628 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2338 | D 3rd Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.4488 | No. | 5000 | 100 | 56.1 | 0 | 2244 | C+S GST 0% I/P RD | 0 | 2244 | 2244 | Approved | 0 | 0 | 291 | 11 Mar 2023
GANGA DHAM TOWERS | 1315 | 98621 | 11 Mar 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2288 | D Bldg. Service Lift Shaft Plaster work | External Plaster- BC | 3875.686 | Sq.Ft | 20 | 100 | 1937.84 | 0 | 77513.72 | CGST 0% URD I/P | 0 | 77513.72 | 77513.72 | Approved | 0 | 0 | 775 | 11 Mar 2023
GANGA DHAM TOWERS | 389 | 98603 | 09 Mar 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2123 | Loading / Unloading Expenses | Unloading of Tile Adhesive | 15.5 | Metric Tonnes | 200 | 100 | 0 | 0 | 3100 | CGST 0% URD I/P | 0 | 3100 | 3100 | Approved | 0 | 0 | 0 | 09 Mar 2023
GANGA DHAM TOWERS | 1513 | 98593 | 09 Mar 2023 |  | PUNDLIK P MAHAJAN | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2282 | R & D Purpose | R & D Purpose | 0.0851 | No. | 100000 | 100 | 0 | 0 | 8514 | C+S GST 18% I/P RD | 1532.52 | 10046.52 | 10046.52 | Approved | 0 | 0 | 170 | 09 Mar 2023
GANGA DHAM TOWERS | 1118 | 98592 | 09 Mar 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2300 | A 3001 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 47964 | 35 | 419.69 | 0 | 16787 | C+S GST 18% I/P RD | 3021.66 | 19808.66 | 19808.66 | Approved | 0 | 0 | 1276 | 09 Mar 2023
GANGA DHAM TOWERS | 1118 | 98592 | 09 Mar 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2300 | A 3003 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 41490 | 35 | 363.04 | 0 | 14521.5 | C+S GST 18% I/P RD | 2613.88 | 17135.38 | 17135.38 | Approved | 0 | 0 | 1276 | 09 Mar 2023
GANGA DHAM TOWERS | 1118 | 98592 | 09 Mar 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2300 | A 3002 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236 | C+S GST 18% I/P RD | 2922.48 | 19158.48 | 19158.48 | Approved | 0 | 0 | 1276 | 09 Mar 2023
GANGA DHAM TOWERS | 1118 | 98592 | 09 Mar 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2300 | A 3004 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236 | C+S GST 18% I/P RD | 2922.48 | 19158.48 | 19158.48 | Approved | 0 | 0 | 1276 | 09 Mar 2023
GANGA DHAM TOWERS | 372 | 98591 | 09 Mar 2023 |  | B & B ENTERPRISES | SURESH KUMAR MURALIDHAR | EV - 2354 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.3125 | Sq.Ft | 160 | 100 | 0 | 0 | 3250 | CGST 0% URD I/P | 0 | 3250 | 3250 | Approved | 0 | 0 | 33 | 09 Mar 2023
GANGA DHAM TOWERS | 272 | 98590 | 09 Mar 2023 |  | GOURI INFRA | SURESH KUMAR MURALIDHAR | EV - 2355 | A Bldg 34th slab (29th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 85.3947 | Sq.Ft | 190 | 100 | 405.62 | 0 | 16225 | CGST 0% URD I/P | 0 | 16225 | 16225 | Approved | 0 | 0 | 162 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | 6 AMP Plug point (Independent) | 38 | No. | 200 | 35 | 66.5 | 0 | 2660 | C+S GST 18% I/P RD | 478.8 | 3138.8 | 3138.8 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | 6 AMP Plug point (Independent) | 58 | No. | 200 | 35 | 101.5 | 0 | 4060 | C+S GST 18% I/P RD | 730.8 | 4790.8 | 4790.8 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Conduit Piping work- BC | 226.32 | R.Ft | 2.75 | 100 | 15.56 | 0 | 622.38 | C+S GST 18% I/P RD | 112.02 | 734.4 | 734.4 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Conduit Piping work- BC | 167.28 | R.Ft | 2.75 | 100 | 11.5 | 0 | 460.02 | C+S GST 18% I/P RD | 82.8 | 542.82 | 542.82 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Exhaust Fan Point | 6 | No. | 200 | 35 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Exhaust Fan Point | 7 | No. | 200 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B 31st Floor 3102 | 15 Amp Point for Inverter Point | 14 | No. | 220 | 35 | 26.95 | 0 | 1078 | C+S GST 18% I/P RD | 194.04 | 1272.04 | 1272.04 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B 31st Floor 3101 | 15 Amp Point for Inverter Point | 17 | No. | 220 | 35 | 32.73 | 0 | 1309 | C+S GST 18% I/P RD | 235.62 | 1544.62 | 1544.62 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Secondary Light Points (Looping) | 38 | No. | 67 | 35 | 22.28 | 0 | 891.1 | C+S GST 18% I/P RD | 160.4 | 1051.5 | 1051.5 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Secondary Light Points (Looping) | 60 | No. | 67 | 35 | 35.18 | 0 | 1407 | C+S GST 18% I/P RD | 253.26 | 1660.26 | 1660.26 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | 6 AMP Plug point (Dependent) | 40 | No. | 67 | 35 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | 6 AMP Plug point (Dependent) | 22.9851 | No. | 67 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Curtain Point | 12 | No. | 200 | 35 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Curtain Point | 16 | No. | 200 | 35 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 81 | No. | 200 | 35 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 63 | No. | 200 | 35 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Data Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3102 Internal Electrical work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 399 | 98589 | 09 Mar 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2299 | B Bldg Flat No. 3101 Internal Electrical work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 09 Mar 2023
GANGA DHAM TOWERS | 1296 | 98583 | 08 Mar 2023 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2178 | Miscellaneous expenses | Marketing Operating Expenses | 7.7128 | Month | 25000 | 8.33 | 0 | 0 | 16062 | C+S GST 0% I/P RD | 0 | 16062 | 16062 | Approved | 0 | 0 | 0 | 08 Mar 2023
GANGA DHAM TOWERS | 636 | 98549 | 08 Mar 2023 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 2306 | A 2304 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 08 Mar 2023
GANGA DHAM TOWERS | 637 | 98548 | 08 Mar 2023 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 2263 | A 2304 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 59 | 08 Mar 2023
GANGA DHAM TOWERS | 272 | 98547 | 08 Mar 2023 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2353 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 44.6773 | Sq.Ft | 181.3 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 261 | 08 Mar 2023
GANGA DHAM TOWERS | 272 | 98547 | 08 Mar 2023 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2353 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 99.2774 | Sq.Ft | 181.3 | 100 | 0 | 0 | 17999 | C+S GST 18% I/P RD | 3239.82 | 21238.82 | 21238.82 | Approved | 0 | 0 | 261 | 08 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 55.2 | Mtrs | 60.5 | 100 | 0 | 0 | 3339.6 | C+S GST 18% I/P RD | 601.12 | 3940.72 | 3940.72 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 24.3878 | Mtrs | 49 | 100 | 0 | 0 | 1195 | C+S GST 18% I/P RD | 215.1 | 1410.1 | 1410.1 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 48.5 | Mtrs | 345 | 100 | 0 | 0 | 16732.5 | C+S GST 18% I/P RD | 3011.86 | 19744.36 | 19744.36 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 48.5 | Mtrs | 355 | 100 | 0 | 0 | 17217.5 | C+S GST 18% I/P RD | 3099.16 | 20316.66 | 20316.66 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 530 | 98541 | 06 Mar 2023 |  | NEPTUNE ENGINEERS | S D ENTERPRISES | EV - 2283 | A 2002 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 55.2 | Mtrs | 15.5 | 100 | 0 | 0 | 855.6 | C+S GST 18% I/P RD | 154 | 1009.6 | 1009.6 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Northside 26th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 417.3333 | Sq.Ft | 1.5 | 100 | 15.65 | 0 | 626 | C+S GST 18% I/P RD | 112.68 | 738.68 | 738.68 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Northside 25th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 384.6667 | Sq.Ft | 1.5 | 100 | 14.43 | 0 | 577 | C+S GST 18% I/P RD | 103.86 | 680.86 | 680.86 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Eastside 25th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 384.6667 | Sq.Ft | 1.5 | 100 | 14.43 | 0 | 577 | C+S GST 18% I/P RD | 103.86 | 680.86 | 680.86 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Westside 25th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 424 | Sq.Ft | 1.5 | 100 | 15.9 | 0 | 636 | C+S GST 18% I/P RD | 114.48 | 750.48 | 750.48 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A South side 25th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 384.6667 | Sq.Ft | 1.5 | 100 | 14.43 | 0 | 577 | C+S GST 18% I/P RD | 103.86 | 680.86 | 680.86 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A South side 26th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 417.3333 | Sq.Ft | 1.5 | 100 | 15.65 | 0 | 626 | C+S GST 18% I/P RD | 112.68 | 738.68 | 738.68 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Eastside 26th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 417.3333 | Sq.Ft | 1.5 | 100 | 15.65 | 0 | 626 | C+S GST 18% I/P RD | 112.68 | 738.68 | 738.68 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Westside 26th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 417.3333 | Sq.Ft | 1.5 | 100 | 15.65 | 0 | 626 | C+S GST 18% I/P RD | 112.68 | 738.68 | 738.68 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Westside 25th floor External Texture Painting | Water Base Primer (L) | 424 | Sq.Ft | 1 | 100 | 10.6 | 0 | 424 | C+S GST 18% I/P RD | 76.32 | 500.32 | 500.32 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Westside 26th floor External Texture Painting | Water Base Primer (L) | 417 | Sq.Ft | 1 | 100 | 10.43 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Eastside 26th floor External Texture Painting | Water Base Primer (L) | 417 | Sq.Ft | 1 | 100 | 10.43 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Northside 25th floor External Texture Painting | Water Base Primer (L) | 385 | Sq.Ft | 1 | 100 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Northside 26th floor External Texture Painting | Water Base Primer (L) | 417 | Sq.Ft | 1 | 100 | 10.43 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A South side 25th floor External Texture Painting | Water Base Primer (L) | 385 | Sq.Ft | 1 | 100 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A South side 26th floor External Texture Painting | Water Base Primer (L) | 417 | Sq.Ft | 1 | 100 | 10.43 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1292 | 98520 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2285 | A Eastside 25th floor External Texture Painting | Water Base Primer (L) | 385 | Sq.Ft | 1 | 100 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 81 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Westside 25th floor External Texture Painting | Water Base Primer (M) | 424 | Sq.Ft | 1 | 100 | 0 | 0 | 424 | C+S GST 18% I/P RD | 76.32 | 500.32 | 500.32 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Eastside 25th floor External Texture Painting | Water Base Primer (M) | 385 | Sq.Ft | 1 | 100 | 0 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A South side 26th floor External Texture Painting | Water Base Primer (M) | 417 | Sq.Ft | 1 | 100 | 0 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A South side 25th floor External Texture Painting | Water Base Primer (M) | 385 | Sq.Ft | 1 | 100 | 0 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Northside 25th floor External Texture Painting | Water Base Primer (M) | 385 | Sq.Ft | 1 | 100 | 0 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Westside 26th floor External Texture Painting | Water Base Primer (M) | 417 | Sq.Ft | 1 | 100 | 0 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Eastside 26th floor External Texture Painting | Water Base Primer (M) | 417 | Sq.Ft | 1 | 100 | 0 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Northside 26th floor External Texture Painting | Water Base Primer (M) | 417 | Sq.Ft | 1 | 100 | 0 | 0 | 417 | C+S GST 18% I/P RD | 75.06 | 492.06 | 492.06 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Northside 26th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 417 | Sq.Ft | 2 | 100 | 0 | 0 | 834 | C+S GST 18% I/P RD | 150.12 | 984.12 | 984.12 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A South side 25th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 385 | Sq.Ft | 2 | 100 | 0 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Eastside 25th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 385 | Sq.Ft | 2 | 100 | 0 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Westside 26th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 417 | Sq.Ft | 2 | 100 | 0 | 0 | 834 | C+S GST 18% I/P RD | 150.12 | 984.12 | 984.12 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Northside 25th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 385 | Sq.Ft | 2 | 100 | 0 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A South side 26th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 417 | Sq.Ft | 2 | 100 | 0 | 0 | 834 | C+S GST 18% I/P RD | 150.12 | 984.12 | 984.12 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Westside 25th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 424 | Sq.Ft | 2 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 1295 | 98519 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2317 | A Eastside 26th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 417 | Sq.Ft | 2 | 100 | 0 | 0 | 834 | C+S GST 18% I/P RD | 150.12 | 984.12 | 984.12 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Northside 25th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Eastside 26th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A South side 25th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A South side 26th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Westside 25th floor External Texture Painting | Texture Paint (M) | 424 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Eastside 25th floor External Texture Painting | Texture Paint (M) | 384.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Northside 26th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 845 | 98518 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2286 | A Westside 26th floor External Texture Painting | Texture Paint (M) | 417.2414 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Northside 25th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Westside 25th floor External Texture Painting | Texture Paint (L) | 424 | Sq.Ft | 7.25 | 100 | 76.85 | 0 | 3074 | C+S GST 18% I/P RD | 553.32 | 3627.32 | 3627.32 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Northside 26th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Westside 26th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Eastside 26th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A Eastside 25th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A South side 25th floor External Texture Painting | Texture Paint (L) | 384.8276 | Sq.Ft | 7.25 | 100 | 69.75 | 0 | 2790 | C+S GST 18% I/P RD | 502.2 | 3292.2 | 3292.2 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 844 | 98517 | 06 Mar 2023 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2287 | A South side 26th floor External Texture Painting | Texture Paint (L) | 417.2414 | Sq.Ft | 7.25 | 100 | 75.63 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 235 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 1804 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 19.935 | R.Ft | 45 | 100 | 22.43 | 0 | 897.08 | CGST 0% URD I/P | 0 | 897.08 | 897.08 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 1404 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 19.935 | R.Ft | 45 | 100 | 22.43 | 0 | 897.08 | CGST 0% URD I/P | 0 | 897.08 | 897.08 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 501 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 15.507 | R.Ft | 45 | 100 | 17.45 | 0 | 697.82 | CGST 0% URD I/P | 0 | 697.82 | 697.82 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 1202 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 19.935 | R.Ft | 45 | 100 | 22.43 | 0 | 897.08 | CGST 0% URD I/P | 0 | 897.08 | 897.08 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 1304 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 15.507 | R.Ft | 45 | 100 | 17.45 | 0 | 697.82 | CGST 0% URD I/P | 0 | 697.82 | 697.82 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 1425 | 98516 | 06 Mar 2023 |  | Kishan Enterprises | JUBAIR AHMAD | EV - 2346 | A 1904 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 15.507 | R.Ft | 45 | 100 | 17.45 | 0 | 697.82 | CGST 0% URD I/P | 0 | 697.82 | 697.82 | Approved | 0 | 0 | 48 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 36 | 100 | 123.54 | 0 | 4941.65 | CGST 0% URD I/P | 0 | 4941.65 | 4941.65 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 36 | 100 | 100.04 | 0 | 4001.72 | CGST 0% URD I/P | 0 | 4001.72 | 4001.72 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 36 | 100 | 77.15 | 0 | 3086.1 | CGST 0% URD I/P | 0 | 3086.1 | 3086.1 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 36 | 100 | 67.09 | 0 | 2683.69 | CGST 0% URD I/P | 0 | 2683.69 | 2683.69 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 515.529 | Sq.Ft | 80 | 100 | 1031.06 | 0 | 41242.32 | CGST 0% URD I/P | 0 | 41242.32 | 41242.32 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 189.585 | Sq.Ft | 80 | 100 | 379.17 | 0 | 15166.8 | CGST 0% URD I/P | 0 | 15166.8 | 15166.8 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 164.205 | Sq.Ft | 80 | 100 | 328.41 | 0 | 13136.4 | CGST 0% URD I/P | 0 | 13136.4 | 13136.4 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 120.465 | Sq.Ft | 80 | 100 | 240.93 | 0 | 9637.2 | CGST 0% URD I/P | 0 | 9637.2 | 9637.2 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 34 | 100 | 51.85 | 0 | 2074.07 | CGST 0% URD I/P | 0 | 2074.07 | 2074.07 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 34 | 100 | 32.86 | 0 | 1314.27 | CGST 0% URD I/P | 0 | 1314.27 | 1314.27 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 34 | 100 | 62.54 | 0 | 2501.55 | CGST 0% URD I/P | 0 | 2501.55 | 2501.55 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 135.873 | Sq.Ft | 34 | 100 | 115.49 | 0 | 4619.68 | CGST 0% URD I/P | 0 | 4619.68 | 4619.68 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | CGST 0% URD I/P | 0 | 729.18 | 729.18 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | CGST 0% URD I/P | 0 | 497.7 | 497.7 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | CGST 0% URD I/P | 0 | 584.46 | 584.46 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Staff Toilet dado | L Groove - BCV | 14.607 | R.Ft | 20 | 100 | 7.3 | 0 | 292.14 | CGST 0% URD I/P | 0 | 292.14 | 292.14 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 537 | 98515 | 06 Mar 2023 |  | MONIKA ENTERPRISES | JUBAIR AHMAD | EV - 2345 | A 2502 Staff Toilet dado | Dado BC | 116.262 | Sq.Ft | 31.5 | 100 | 91.56 | 0 | 3662.25 | CGST 0% URD I/P | 0 | 3662.25 | 3662.25 | Approved | 0 | 0 | 1102 | 06 Mar 2023
GANGA DHAM TOWERS | 1052 | 98506 | 04 Mar 2023 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 2105 | Legal Consultancy - 1 No | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 04 Mar 2023
GANGA DHAM TOWERS | 1383 | 98498 | 04 Mar 2023 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 2106 | Professional Consultancy (Finalcial) | Professional Fees | 1 | Month | 116666.666 | 100 | 0 | 0 | 116666.67 | CGST 0% URD I/P | 0 | 116666.67 | 116666.67 | Approved | 0 | 0 | 11667 | 04 Mar 2023
GANGA DHAM TOWERS | 1452 | 98497 | 04 Mar 2023 |  | OMKAR PRADEEP MANE | OMKAR PRADEEP MANE | EV - 2107 | Professional Consultancy | Professional Fees | 1 | Month | 25000 | 100 | 0 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 2500 | 04 Mar 2023
GANGA DHAM TOWERS | 774 | 98492 | 04 Mar 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 2164 | B GF Parking Flooring Trimix work | Weld mesh fixing(L) BCo | 17161.31 | Sq.Ft | 1 | 100 | 429.03 | 0 | 17161.31 | CGST 0% URD I/P | 0 | 17161.31 | 17161.31 | Approved | 0 | 0 | 1716 | 04 Mar 2023
GANGA DHAM TOWERS | 774 | 98492 | 04 Mar 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 2164 | B GF Parking Flooring Trimix work | Trimix Work - BC | 17161.31 | Sq.Ft | 9 | 100 | 3861.29 | 0 | 154451.79 | CGST 0% URD I/P | 0 | 154451.79 | 154451.79 | Approved | 0 | 0 | 1716 | 04 Mar 2023
GANGA DHAM TOWERS | 1113 | 98491 | 04 Mar 2023 |  | HINDUSTAN MAINTENANCE COMPANY | PROFESSIONAL PAINTING PARTNER | EV - 2356 | A 901 Walls Satin Matt Paint | Oil base Primer-BC | 2876 | Sq.Ft | 1 | 100 | 71.9 | 0 | 2876 | CGST 0% URD I/P | 0 | 2876 | 2876 | Approved | 0 | 0 | 129 | 04 Mar 2023
GANGA DHAM TOWERS | 1113 | 98491 | 04 Mar 2023 |  | HINDUSTAN MAINTENANCE COMPANY | PROFESSIONAL PAINTING PARTNER | EV - 2356 | A 901 Walls Satin Matt Paint | Oil base Primer-BC | 2876 | Sq.Ft | 1 | 100 | 71.9 | 0 | 2876 | CGST 0% URD I/P | 0 | 2876 | 2876 | Approved | 0 | 0 | 129 | 04 Mar 2023
GANGA DHAM TOWERS | 1113 | 98491 | 04 Mar 2023 |  | HINDUSTAN MAINTENANCE COMPANY | PROFESSIONAL PAINTING PARTNER | EV - 2356 | A 901 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2876 | Sq.Ft | 1.25 | 100 | 89.88 | 0 | 3595 | CGST 0% URD I/P | 0 | 3595 | 3595 | Approved | 0 | 0 | 129 | 04 Mar 2023
GANGA DHAM TOWERS | 1113 | 98491 | 04 Mar 2023 |  | HINDUSTAN MAINTENANCE COMPANY | PROFESSIONAL PAINTING PARTNER | EV - 2356 | A 901 Walls Satin Matt Paint | Scrapping with 2nd Coat Putty | 2876 | Sq.Ft | 1.25 | 100 | 89.88 | 0 | 3595 | CGST 0% URD I/P | 0 | 3595 | 3595 | Approved | 0 | 0 | 129 | 04 Mar 2023
GANGA DHAM TOWERS | 804 | 98487 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2174 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378.14 | R.Ft | 55 | 100 | 0 | 0 | 20797.7 | C+S GST 18% I/P RD | 3743.58 | 24541.28 | 24541.28 | Approved | 0 | 0 | 0 | 04 Mar 2023
GANGA DHAM TOWERS | 804 | 98487 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2174 | B-1101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 347.168 | R.Ft | 55 | 100 | 0 | 0 | 19094.24 | C+S GST 18% I/P RD | 3436.96 | 22531.2 | 22531.2 | Approved | 0 | 0 | 0 | 04 Mar 2023
GANGA DHAM TOWERS | 804 | 98487 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2174 | B-1101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 911.316 | Sq.Ft | 55 | 100 | 0 | 0 | 50122.38 | C+S GST 18% I/P RD | 9022.02 | 59144.4 | 59144.4 | Approved | 0 | 0 | 0 | 04 Mar 2023
GANGA DHAM TOWERS | 804 | 98487 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2174 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 980.1273 | Sq.Ft | 55 | 100 | 0 | 0 | 53907 | C+S GST 18% I/P RD | 9703.26 | 63610.26 | 63610.26 | Approved | 0 | 0 | 0 | 04 Mar 2023
GANGA DHAM TOWERS | 805 | 98486 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2156 | B-1101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 260.45 | R.Ft | 20 | 100 | 130.23 | 0 | 5209 | C+S GST 18% I/P RD | 937.62 | 6146.62 | 6146.62 | Approved | 0 | 0 | 394 | 04 Mar 2023
GANGA DHAM TOWERS | 805 | 98486 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2156 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 394 | 04 Mar 2023
GANGA DHAM TOWERS | 805 | 98486 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2156 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 741 | Sq.Ft | 20 | 100 | 370.5 | 0 | 14820 | C+S GST 18% I/P RD | 2667.6 | 17487.6 | 17487.6 | Approved | 0 | 0 | 394 | 04 Mar 2023
GANGA DHAM TOWERS | 805 | 98486 | 04 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2156 | B-1101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 684.45 | Sq.Ft | 20 | 100 | 342.23 | 0 | 13689 | C+S GST 18% I/P RD | 2464.02 | 16153.02 | 16153.02 | Approved | 0 | 0 | 394 | 04 Mar 2023
GANGA DHAM TOWERS | 1433 | 98477 | 04 Mar 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 2188 | RMC 150m Pipe Line Rental Charges | Rental Charges. | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 18% I/P RD | 3960 | 25960 | 25960 | Approved | 0 | 0 | 5440 | 04 Mar 2023
GANGA DHAM TOWERS | 1433 | 98477 | 04 Mar 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 2188 | RMC Pump Per Month Rental Charges | Pump Hiring for RMC | 1 | Month | 250000 | 100 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 0 | 5440 | 04 Mar 2023
GANGA DHAM TOWERS | 968 | 98458 | 03 Mar 2023 |  | MAYUR ARTS & ENTERPRISES | PARTH ENTERPRISES | EV - 2258 | Safety Board Fabrication Work - 1 No. | MS Pipe (L) | 112 | Kgs | 12 | 100 | 0 | 0 | 1344 | CGST 0% URD I/P | 0 | 1344 | 1344 | Approved | 0 | 0 | 13 | 03 Mar 2023
GANGA DHAM TOWERS | 393 | 98457 | 03 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2250 | A Bldg Flat No. 301 Gypsum Plaster | Gypsum on Wall (L) | 341 | Sq.Ft | 4 | 100 | 34.1 | 0 | 1364 | C+S GST 18% I/P RD | 245.52 | 1609.52 | 1609.52 | Approved | 0 | 0 | 70 | 03 Mar 2023
GANGA DHAM TOWERS | 393 | 98457 | 03 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2250 | A Bldg Flat No. 402 Gypsum Plaster | Gypsum on Wall (L) | 300 | Sq.Ft | 4 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 70 | 03 Mar 2023
GANGA DHAM TOWERS | 393 | 98457 | 03 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2250 | A Bldg Flat No. 401 Gypsum Plaster | Gypsum on Wall (L) | 368 | Sq.Ft | 4 | 100 | 36.8 | 0 | 1472 | C+S GST 18% I/P RD | 264.96 | 1736.96 | 1736.96 | Approved | 0 | 0 | 70 | 03 Mar 2023
GANGA DHAM TOWERS | 393 | 98457 | 03 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2250 | A Bldg Flat No. 701 Gypsum Plaster | Gypsum on Wall (L) | 368 | Sq.Ft | 4 | 100 | 36.8 | 0 | 1472 | C+S GST 18% I/P RD | 264.96 | 1736.96 | 1736.96 | Approved | 0 | 0 | 70 | 03 Mar 2023
GANGA DHAM TOWERS | 393 | 98457 | 03 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2250 | A Bldg Flat No. 601 Gypsum Plaster | Gypsum on Wall (L) | 368 | Sq.Ft | 4 | 100 | 36.8 | 0 | 1472 | C+S GST 18% I/P RD | 264.96 | 1736.96 | 1736.96 | Approved | 0 | 0 | 70 | 03 Mar 2023
GANGA DHAM TOWERS | 149 | 98456 | 03 Mar 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2303 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3849 | No. | 4 | 100 | 0 | 0 | 15396 | CGST 0% URD I/P | 0 | 15396 | 15396 | Approved | 0 | 0 | 0 | 03 Mar 2023
GANGA DHAM TOWERS | 968 | 98455 | 03 Mar 2023 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2154 | Safety Boards / Flex Printing | Safety Posters (Flex Printing) | 31 | No. | 130 | 100 | 0 | 0 | 4030 | C+S GST 18% I/P RD | 725.4 | 4755.4 | 4755.4 | Approved | 0 | 0 | 40 | 03 Mar 2023
GANGA DHAM TOWERS | 1520 | 98438 | 02 Mar 2023 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 2139 | HO Expenses Security Services | Security Services. | 12 | Month | 13000 | 8.33 | 0 | 0 | 12999.95 | C+S GST 18% RCM | 2340 | 15339.95 | 15339.95 | Approved | 0 | 0 | 130 | 02 Mar 2023
GANGA DHAM TOWERS | 1497 | 98434 | 02 Mar 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2255 | Site Expenses | Site Expenses -SO | 0.0393 | Month | 30000 | 100 | 0 | 0 | 1179 | CGST 0% URD I/P | 0 | 1179 | 1179 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 1497 | 98434 | 02 Mar 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2255 | Site Expenses | Site Expenses -SO | 0.2432 | Month | 30000 | 100 | 0 | 0 | 7296 | CGST 0% URD I/P | 0 | 7296 | 7296 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 202 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1508 | Sq.Ft | 55 | 100 | 0 | 0 | 82940 | C+S GST 18% I/P RD | 14929.2 | 97869.2 | 97869.2 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 1301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 610 | Sq.Ft | 55 | 100 | 0 | 0 | 33550 | C+S GST 18% I/P RD | 6039 | 39589 | 39589 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 1201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 610 | Sq.Ft | 55 | 100 | 0 | 0 | 33550 | C+S GST 18% I/P RD | 6039 | 39589 | 39589 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 202 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 209.328 | R.Ft | 55 | 100 | 0 | 0 | 11513.04 | C+S GST 18% I/P RD | 2072.34 | 13585.38 | 13585.38 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 1301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 224.448 | R.Ft | 55 | 100 | 0 | 0 | 12344.64 | C+S GST 18% I/P RD | 2222.04 | 14566.68 | 14566.68 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 630 | 98422 | 02 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2247 | A 1201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 224.448 | R.Ft | 55 | 100 | 0 | 0 | 12344.64 | C+S GST 18% I/P RD | 2222.04 | 14566.68 | 14566.68 | Approved | 0 | 0 | 0 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 1301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 202 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1357.2 | Sq.Ft | 20 | 100 | 678.6 | 0 | 27144 | C+S GST 18% I/P RD | 4885.92 | 32029.92 | 32029.92 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 1201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 202 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156.996 | R.Ft | 20 | 100 | 78.5 | 0 | 3139.92 | C+S GST 18% I/P RD | 565.18 | 3705.1 | 3705.1 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 1201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 631 | 98421 | 02 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2246 | A 1301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 553 | 02 Mar 2023
GANGA DHAM TOWERS | 1360 | 98420 | 02 Mar 2023 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2151 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 02 Mar 2023
GANGA DHAM TOWERS | 1360 | 98419 | 02 Mar 2023 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2150 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 02 Mar 2023
GANGA DHAM TOWERS | 940 | 98418 | 02 Mar 2023 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2149 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Mar 2023
GANGA DHAM TOWERS | 940 | 98417 | 02 Mar 2023 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2152 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 1003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352.008 | Sq.Ft | 20 | 100 | 176 | 0 | 7040.16 | C+S GST 18% I/P RD | 1267.22 | 8307.38 | 8307.38 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 903 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352.008 | Sq.Ft | 20 | 100 | 176 | 0 | 7040.16 | C+S GST 18% I/P RD | 1267.22 | 8307.38 | 8307.38 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 1204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 443.346 | Sq.Ft | 20 | 100 | 221.67 | 0 | 8866.92 | C+S GST 18% I/P RD | 1596.04 | 10462.96 | 10462.96 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 903 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 139.8 | R.Ft | 20 | 100 | 69.9 | 0 | 2796 | C+S GST 18% I/P RD | 503.28 | 3299.28 | 3299.28 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 1204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156.051 | R.Ft | 20 | 100 | 78.03 | 0 | 3121.02 | C+S GST 18% I/P RD | 561.78 | 3682.8 | 3682.8 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 632 | 98408 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2159 | A 1003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 139.8 | R.Ft | 20 | 100 | 69.9 | 0 | 2796 | C+S GST 18% I/P RD | 503.28 | 3299.28 | 3299.28 | Approved | 0 | 0 | 317 | 01 Mar 2023
GANGA DHAM TOWERS | 1239 | 98407 | 01 Mar 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2339 | Tower C Podium Excavtion | Excavation by Bucket | 1208.939 | Cu.Mtrs | 357.5 | 100 | 0 | 0 | 432195.69 | C+S GST 18% I/P RD | 77795.22 | 509990.91 | 509990.91 | Approved | 0 | 0 | 6184 | 01 Mar 2023
GANGA DHAM TOWERS | 1239 | 98407 | 01 Mar 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2339 | Tower C Podium Excavtion | Excavation By Needle | 407.97 | Cu.Mtrs | 456.5 | 100 | 0 | 0 | 186238.31 | C+S GST 18% I/P RD | 33522.9 | 219761.21 | 219761.21 | Approved | 0 | 0 | 6184 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 903 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186.4 | R.Ft | 55 | 100 | 0 | 0 | 10252 | C+S GST 18% I/P RD | 1845.36 | 12097.36 | 12097.36 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 1003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186.4 | R.Ft | 55 | 100 | 0 | 0 | 10252 | C+S GST 18% I/P RD | 1845.36 | 12097.36 | 12097.36 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 1204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 208.068 | R.Ft | 55 | 100 | 0 | 0 | 11443.74 | C+S GST 18% I/P RD | 2059.88 | 13503.62 | 13503.62 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 903 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 469.344 | Sq.Ft | 55 | 100 | 0 | 0 | 25813.92 | C+S GST 18% I/P RD | 4646.5 | 30460.42 | 30460.42 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 1003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 469.344 | Sq.Ft | 55 | 100 | 0 | 0 | 25813.92 | C+S GST 18% I/P RD | 4646.5 | 30460.42 | 30460.42 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 629 | 98404 | 01 Mar 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2160 | A 1204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 591.128 | Sq.Ft | 55 | 100 | 0 | 0 | 32512.04 | C+S GST 18% I/P RD | 5852.16 | 38364.2 | 38364.2 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 1511 | 98402 | 01 Mar 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2352 | Rabbit shifting & cleaning work | Hyva Trips | 70 | Trips | 3500 | 100 | 0 | 0 | 245000 | C+S GST 18% I/P RD | 44100 | 289100 | 289100 | Approved | 0 | 0 | 2450 | 01 Mar 2023
GANGA DHAM TOWERS | 1512 | 98399 | 01 Mar 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2260 | Tower C Podium Cable Trench excavation | Excavation by Bucket | 27.135 | Cu.Mtrs | 357.5 | 100 | 0 | 0 | 9700.76 | C+S GST 18% I/P RD | 1746.14 | 11446.9 | 11446.9 | Approved | 0 | 0 | 159 | 01 Mar 2023
GANGA DHAM TOWERS | 1512 | 98399 | 01 Mar 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2260 | Tower C Podium Cable Trench excavation | Excavation By Needle | 13.56 | Cu.Mtrs | 456.5 | 100 | 0 | 0 | 6190.14 | C+S GST 18% I/P RD | 1114.22 | 7304.36 | 7304.36 | Approved | 0 | 0 | 159 | 01 Mar 2023
GANGA DHAM TOWERS | 1119 | 98398 | 01 Mar 2023 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 2284 | C Bldg 4th RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 4525.305 | Sq.Ft | 185 | 100 | 20929.54 | 0 | 837181.43 | C+S GST 18% I/P RD | 150692.66 | 987874.09 | 987874.09 | Approved | 0 | 0 | 16744 | 01 Mar 2023
GANGA DHAM TOWERS | 1119 | 98398 | 01 Mar 2023 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 2284 | C Bldg 4th RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 4525.2975 | Sq.Ft | 185 | 100 | 20929.5 | 0 | 837180.04 | C+S GST 18% I/P RD | 150692.4 | 987872.44 | 987872.44 | Approved | 0 | 0 | 16744 | 01 Mar 2023
GANGA DHAM TOWERS | 636 | 98396 | 01 Mar 2023 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 2162 | A 2204 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.6071 | Sq.Ft | 140 | 100 | 0 | 0 | 24865 | C+S GST 18% I/P RD | 4475.7 | 29340.7 | 29340.7 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 636 | 98396 | 01 Mar 2023 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 2162 | A 2201 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.6071 | Sq.Ft | 140 | 100 | 0 | 0 | 24865 | C+S GST 18% I/P RD | 4475.7 | 29340.7 | 29340.7 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 637 | 98394 | 01 Mar 2023 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 2161 | A 2204 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 134 | 01 Mar 2023
GANGA DHAM TOWERS | 637 | 98394 | 01 Mar 2023 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 2161 | A 2201 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 134 | 01 Mar 2023
GANGA DHAM TOWERS | 806 | 98392 | 01 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2248 | B-1102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1615.8 | Sq.Ft | 55 | 100 | 0 | 0 | 88869 | C+S GST 18% I/P RD | 15996.42 | 104865.42 | 104865.42 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 806 | 98392 | 01 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2248 | B-1202 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1615.8 | Sq.Ft | 55 | 100 | 0 | 0 | 88869 | C+S GST 18% I/P RD | 15996.42 | 104865.42 | 104865.42 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 806 | 98392 | 01 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2248 | B-1102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 557.25 | R.Ft | 55 | 100 | 0 | 0 | 30648.75 | C+S GST 18% I/P RD | 5516.78 | 36165.53 | 36165.53 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 806 | 98392 | 01 Mar 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2248 | B-1202 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 557.25 | R.Ft | 55 | 100 | 0 | 0 | 30648.75 | C+S GST 18% I/P RD | 5516.78 | 36165.53 | 36165.53 | Approved | 0 | 0 | 0 | 01 Mar 2023
GANGA DHAM TOWERS | 807 | 98390 | 01 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2249 | B-1102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1454.22 | Sq.Ft | 20 | 100 | 727.11 | 0 | 29084.4 | C+S GST 18% I/P RD | 5235.2 | 34319.6 | 34319.6 | Approved | 0 | 0 | 782 | 01 Mar 2023
GANGA DHAM TOWERS | 807 | 98390 | 01 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2249 | B-1202 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1454.22 | Sq.Ft | 20 | 100 | 727.11 | 0 | 29084.4 | C+S GST 18% I/P RD | 5235.2 | 34319.6 | 34319.6 | Approved | 0 | 0 | 782 | 01 Mar 2023
GANGA DHAM TOWERS | 807 | 98390 | 01 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2249 | B-1102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 501.525 | R.Ft | 20 | 100 | 250.76 | 0 | 10030.5 | C+S GST 18% I/P RD | 1805.5 | 11836 | 11836 | Approved | 0 | 0 | 782 | 01 Mar 2023
GANGA DHAM TOWERS | 807 | 98390 | 01 Mar 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2249 | B-1202 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 501.525 | R.Ft | 20 | 100 | 250.76 | 0 | 10030.5 | C+S GST 18% I/P RD | 1805.5 | 11836 | 11836 | Approved | 0 | 0 | 782 | 01 Mar 2023
GANGA DHAM TOWERS | 1180 | 98389 | 01 Mar 2023 |  | M.S. CONSTRUCTION | RAHIMAN ABDUL SHAIKH | EV - 2281 | A Terrace Scaffolding Work | Scaffolding work | 756 | Sq.Ft | 5.5 | 100 | 103.95 | 0 | 4158 | CGST 0% URD I/P | 0 | 4158 | 4158 | Approved | 0 | 0 | 42 | 01 Mar 2023
GANGA DHAM TOWERS | 1513 | 98384 | 28 Feb 2023 |  | PUNDLIK P MAHAJAN | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2165 | R & D Purpose | R & D Purpose | 0.086 | No. | 100000 | 100 | 0 | 0 | 8604 | C+S GST 18% I/P RD | 1548.72 | 10152.72 | 10152.72 | Approved | 0 | 0 | 172 | 28 Feb 2023
GANGA DHAM TOWERS | 1513 | 98383 | 28 Feb 2023 |  | PUNDLIK P MAHAJAN | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2163 | R & D Purpose | R & D Purpose | 0.1266 | No. | 100000 | 100 | 0 | 0 | 12660 | C+S GST 18% I/P RD | 2278.8 | 14938.8 | 14938.8 | Approved | 0 | 0 | 253 | 28 Feb 2023
GANGA DHAM TOWERS | 1444 | 98381 | 28 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2296 | EWS STP External Waterproofing Work | Membrane Horizontal Waterproofing (M) | 116.8529 | Sq.Ft | 34 | 100 | 0 | 0 | 3973 | C+S GST 18% I/P RD | 715.14 | 4688.14 | 4688.14 | Approved | 0 | 0 | 0 | 28 Feb 2023
GANGA DHAM TOWERS | 1444 | 98381 | 28 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2296 | EWS STP External Waterproofing Work | Membrane Vertical Waterproofing (M) | 934.725 | Sq.Ft | 40 | 100 | 0 | 0 | 37389 | C+S GST 18% I/P RD | 6730.02 | 44119.02 | 44119.02 | Approved | 0 | 0 | 0 | 28 Feb 2023
GANGA DHAM TOWERS | 1443 | 98380 | 28 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2293 | EWS STP External Waterproofing Work | Membrane Horizontal Waterproofing (L) | 116.8462 | Sq.Ft | 13 | 100 | 151.9 | 0 | 1519 | C+S GST 18% I/P RD | 273.42 | 1792.42 | 1792.42 | Approved | 0 | 0 | 155 | 28 Feb 2023
GANGA DHAM TOWERS | 1443 | 98380 | 28 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2293 | EWS STP External Waterproofing Work | Membrane Vertical Waterproofing (L) | 934.7333 | Sq.Ft | 15 | 100 | 1402.1 | 0 | 14021 | C+S GST 18% I/P RD | 2523.78 | 16544.78 | 16544.78 | Approved | 0 | 0 | 155 | 28 Feb 2023
GANGA DHAM TOWERS | 1407 | 98379 | 28 Feb 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 2218 | EWS STP RCC | RCC Work STP | 18277 | Ltrs | 3.75 | 100 | 1713.47 | 0 | 68538.75 | CGST 0% URD I/P | 0 | 68538.75 | 68538.75 | Approved | 0 | 0 | 1267 | 28 Feb 2023
GANGA DHAM TOWERS | 1407 | 98379 | 28 Feb 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 2218 | EWS STP Pump Room RCC Work | RCC Work - BC | 314.3081 | Sq.Ft | 185 | 100 | 1453.67 | 0 | 58147 | CGST 0% URD I/P | 0 | 58147 | 58147 | Approved | 0 | 0 | 1267 | 28 Feb 2023
GANGA DHAM TOWERS | 1496 | 98371 | 27 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2173 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Transport Charges | 3 | No. | 1200 | 100 | 0 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 48 | 27 Feb 2023
GANGA DHAM TOWERS | 1496 | 98371 | 27 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2173 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Transport Charges | 1 | No. | 1200 | 100 | 0 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 48 | 27 Feb 2023
GANGA DHAM TOWERS | 1520 | 98366 | 25 Feb 2023 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 2046 | HO Expenses Security Services | Security Services. | 12 | Month | 13000 | 8.33 | 0 | 0 | 12999.95 | C+S GST 18% RCM | 2340 | 15339.95 | 15339.95 | Approved | 0 | 0 | 130 | 25 Feb 2023
GANGA DHAM TOWERS | 1206 | 98336 | 25 Feb 2023 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2277 | Tower Crane A & C Annual maintenance for tower crane & lift | AMC Charges | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 25 Feb 2023
GANGA DHAM TOWERS | 1207 | 98334 | 25 Feb 2023 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2275 | Material Lift A - Material Lift Height Increase 25th to 31st | Erection work | 6.6 | Mtrs | 1200 | 100 | 0 | 0 | 7920 | C+S GST 18% I/P RD | 1425.6 | 9345.6 | 9345.6 | Approved | 0 | 0 | 79 | 25 Feb 2023
GANGA DHAM TOWERS | 1208 | 98333 | 25 Feb 2023 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2276 | Material Lift B - Material Lift Height Increase 25th to 31st | Erection work | 9.9 | Mtrs | 1200 | 100 | 0 | 0 | 11880 | C+S GST 18% I/P RD | 2138.4 | 14018.4 | 14018.4 | Approved | 0 | 0 | 119 | 25 Feb 2023
GANGA DHAM TOWERS | 351 | 98332 | 25 Feb 2023 |  | TECHKNOW EARTHMOVING SERVICES | PURVA ENTERPRISES | EV - 2273 | A Bldg 33th SlabTower Crane Jumping Work | Tower Crane Jumping Charges | 1 | No. | 30000 | 100 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 300 | 25 Feb 2023
GANGA DHAM TOWERS | 1502 | 98331 | 25 Feb 2023 |  | TASLIM NANHE KHAN | TASLIM NANHE KHAN | EV - 2157 | New Site Office Gypsum work | Gypsum Ceiling (L) | 2504.25 | Sq.Ft | 5 | 100 | 313.03 | 0 | 12521.25 | CGST 0% URD I/P | 0 | 12521.25 | 12521.25 | Approved | 0 | 0 | 437 | 25 Feb 2023
GANGA DHAM TOWERS | 1502 | 98331 | 25 Feb 2023 |  | TASLIM NANHE KHAN | TASLIM NANHE KHAN | EV - 2157 | New Site Office Gypsum work | Tikki Dhada (L) | 3121.8 | Sq.Ft | 10 | 100 | 780.45 | 0 | 31218 | CGST 0% URD I/P | 0 | 31218 | 31218 | Approved | 0 | 0 | 437 | 25 Feb 2023
GANGA DHAM TOWERS | 1162 | 98330 | 25 Feb 2023 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 2169 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 25 Feb 2023
GANGA DHAM TOWERS | 1242 | 98311 | 23 Feb 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2261 | EWS STP Excavation Work | Excavation by Bucket | 134.29 | Cu.Mtrs | 325 | 100 | 0 | 0 | 43644.25 | C+S GST 18% I/P RD | 7855.96 | 51500.21 | 51500.21 | Approved | 0 | 0 | 1330 | 23 Feb 2023
GANGA DHAM TOWERS | 1242 | 98311 | 23 Feb 2023 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2261 | EWS STP Excavation Work | Excavation By Needle | 215.33 | Cu.Mtrs | 415 | 100 | 0 | 0 | 89361.95 | C+S GST 18% I/P RD | 16085.16 | 105447.11 | 105447.11 | Approved | 0 | 0 | 1330 | 23 Feb 2023
GANGA DHAM TOWERS | 1006 | 98306 | 23 Feb 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2289 | B 201 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | CGST 0% URD I/P | 0 | 662.58 | 662.58 | Approved | 0 | 0 | 7 | 23 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 401 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 502 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1302 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 501 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1202 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1301 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 701 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1102 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 202 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 102 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1401 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 402 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 802 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1702 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1001 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 602 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 702 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 302 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1002 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 101 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 301 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1402 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 801 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1601 Terrcae Railling | S.S. Railing (M)- BC | 73.6 | R.Ft | 1336 | 100 | 0 | 0 | 98329.6 | C+S GST 18% I/P RD | 17699.32 | 116028.92 | 116028.92 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1101 Terrcae Railling | S.S. Railing (M)- BC | 73.6 | R.Ft | 1336 | 100 | 0 | 0 | 98329.6 | C+S GST 18% I/P RD | 17699.32 | 116028.92 | 116028.92 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1502 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1701 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 201 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 902 Terrcae Railling | S.S. Railing (M)- BC | 22.67 | R.Ft | 1336 | 100 | 0 | 0 | 30287.12 | C+S GST 18% I/P RD | 5451.68 | 35738.8 | 35738.8 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1501 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1602 Terrcae Railling | S.S. Railing (M)- BC | 26.84 | R.Ft | 1336 | 100 | 0 | 0 | 35858.24 | C+S GST 18% I/P RD | 6454.48 | 42312.72 | 42312.72 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 601 Terrcae Railling | S.S. Railing (M)- BC | 73.6 | R.Ft | 1336 | 100 | 0 | 0 | 98329.6 | C+S GST 18% I/P RD | 17699.32 | 116028.92 | 116028.92 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 1201 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 977 | 98304 | 22 Feb 2023 |  | DIVINE ENTERPRISES | HELIOS (Material) | EV - 2253 | B 901 Terrcae Railling | S.S. Railing (M)- BC | 26.25 | R.Ft | 1336 | 100 | 0 | 0 | 35070 | C+S GST 18% I/P RD | 6312.6 | 41382.6 | 41382.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 1101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 1701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1372.5 | Sq.Ft | 20 | 100 | 686.25 | 0 | 27450 | C+S GST 18% I/P RD | 4941 | 32391 | 32391 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 1102 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 2401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 453 | Sq.Ft | 20 | 100 | 226.5 | 0 | 9060 | C+S GST 18% I/P RD | 1630.8 | 10690.8 | 10690.8 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 475.5 | Sq.Ft | 20 | 100 | 237.75 | 0 | 9510 | C+S GST 18% I/P RD | 1711.8 | 11221.8 | 11221.8 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 101 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 505.008 | R.Ft | 20 | 100 | 252.5 | 0 | 10100.16 | C+S GST 18% I/P RD | 1818.02 | 11918.18 | 11918.18 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.35 | R.Ft | 20 | 100 | 84.18 | 0 | 3367 | C+S GST 18% I/P RD | 606.06 | 3973.06 | 3973.06 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 402 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 470.988 | R.Ft | 20 | 100 | 235.49 | 0 | 9419.76 | C+S GST 18% I/P RD | 1695.56 | 11115.32 | 11115.32 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 2301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 1701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168 | R.Ft | 20 | 100 | 84 | 0 | 3360 | C+S GST 18% I/P RD | 604.8 | 3964.8 | 3964.8 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 2401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 631 | 98303 | 22 Feb 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2153 | A 1102 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 1467 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 2301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 1102 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 603 | Sq.Ft | 55 | 100 | 0 | 0 | 33165 | C+S GST 18% I/P RD | 5969.7 | 39134.7 | 39134.7 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 2401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 1102 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 2301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 1701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 224 | R.Ft | 55 | 100 | 0 | 0 | 12320 | C+S GST 18% I/P RD | 2217.6 | 14537.6 | 14537.6 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 2401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 630 | 98302 | 22 Feb 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2155 | A 402 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 209 | R.Ft | 55 | 100 | 0 | 0 | 11495 | C+S GST 18% I/P RD | 2069.1 | 13564.1 | 13564.1 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Velvet Touch Paint ARW | 625 | Sq.Ft | 40 | 100 | 625 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Melamine Polish 1" Patti | 43.98 | R.Ft | 20 | 100 | 21.99 | 0 | 879.6 | C+S GST 18% I/P RD | 158.32 | 1037.92 | 1037.92 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Oil paint - BC | 48.32 | Sq.Ft | 15 | 100 | 18.12 | 0 | 724.8 | C+S GST 18% I/P RD | 130.46 | 855.26 | 855.26 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Melamine Polish 2" Patti | 38.32 | R.Ft | 30 | 100 | 28.74 | 0 | 1149.6 | C+S GST 18% I/P RD | 206.92 | 1356.52 | 1356.52 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Melamine Polish - BC | 65.61 | Sq.Ft | 75 | 100 | 123.02 | 0 | 4920.75 | C+S GST 18% I/P RD | 885.74 | 5806.49 | 5806.49 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1164 | 98301 | 22 Feb 2023 |  | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 2177 | B 1 - 1101 Painting Work | Oil paint - BC | 226 | Sq.Ft | 6 | 100 | 33.9 | 0 | 1356 | C+S GST 18% I/P RD | 244.08 | 1600.08 | 1600.08 | Approved | 0 | 0 | 340 | 22 Feb 2023
GANGA DHAM TOWERS | 1120 | 98300 | 22 Feb 2023 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES |  | Tower C Podium P3 slab incl. ramp area (105 to 111) Built-up | RCC Superstructure (B-up area) | 4379 | Sq.Ft | 210 | 100 | 22989.75 | 0 | 919590 | C+S GST 18% I/P RD | 165526.2 | 1085116.2 | 1085116.2 |  | 0 | 0 | 9196 | 22 Feb 2023
GANGA DHAM TOWERS | 620 | 98299 | 22 Feb 2023 |  | VECTOR SURVEYORS | VECTOR SURVEYORS | EV - 2204 | C Total Station Survey Pt. Marking - | Total Station Point marking. | 100 | No. | 100 | 100 | 0 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 1122 | 98298 | 22 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2292 | Tower C Retaining wall & Footing Waterproofing work | Rate Diff.Membrane Vertical Waterproofing (M) | 1276.6 | Sq.Ft | 10 | 100 | 0 | 0 | 12766 | C+S GST 18% I/P RD | 2297.88 | 15063.88 | 15063.88 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 1122 | 98298 | 22 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2292 | Tower C Retaining wall & Footing Waterproofing work | Membrane Vertical Waterproofing (M) | 1276.6333 | Sq.Ft | 30 | 100 | 0 | 0 | 38299 | C+S GST 18% I/P RD | 6893.82 | 45192.82 | 45192.82 | Approved | 0 | 0 | 0 | 22 Feb 2023
GANGA DHAM TOWERS | 1121 | 98297 | 22 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2291 | Tower C Retaining wall & Footing Waterproofing work | Membrane Vertical Waterproofing (L) | 1276.6667 | Sq.Ft | 12 | 100 | 1532 | 0 | 15320 | C+S GST 18% I/P RD | 2757.6 | 18077.6 | 18077.6 | Approved | 0 | 0 | 192 | 22 Feb 2023
GANGA DHAM TOWERS | 1121 | 98297 | 22 Feb 2023 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 2291 | Tower C Retaining wall & Footing Waterproofing work | Rate Diff.Membrane Vertical Waterproofing (L) | 1276.6667 | Sq.Ft | 3 | 100 | 95.75 | 0 | 3830 | C+S GST 18% I/P RD | 689.4 | 4519.4 | 4519.4 | Approved | 0 | 0 | 192 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 12th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A Terrace Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A P3 Parking Floor Staircase I waist slab side Gypsum plast | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 13th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 9th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 16th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 2nd Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A Ground Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 15th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 6th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 20th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 21st Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 22nd Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 8th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 7th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 18th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 4th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 5th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A P1 Parking Floor Staircase I waist slab side Gypsum plaste | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 10th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 19th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 11th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A Podium Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 3rd Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 1st Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 14th Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A 23rd Floor Staircase I waist slab side Gypsum plaster | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 544 | 98296 | 22 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2082 | A P2 Parking Floor Staircase I waist slab side Gypsum plaste | Gypsum Plaster & scaffolding (L) | 1 | Floor | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 560 | 22 Feb 2023
GANGA DHAM TOWERS | 1344 | 98295 | 22 Feb 2023 |  | PRATHAM ELECTRICALS | PARTH ENTERPRISES | EV - 2200 | A Rising Main From Ground Fl to OHWT (L) | SITC GI Pipe C Class 50mm dia.(L) | 45 | Mtrs | 210 | 100 | 236.25 | 0 | 9450 | CGST 0% URD I/P | 0 | 9450 | 9450 | Approved | 0 | 0 | 236 | 22 Feb 2023
GANGA DHAM TOWERS | 1344 | 98295 | 22 Feb 2023 |  | PRATHAM ELECTRICALS | PARTH ENTERPRISES | EV - 2200 | A Rising Main From Ground Fl to OHWT (L) | SITC GI Pipe C Class 40mm dia.(L) | 90 | Mtrs | 157 | 100 | 353.25 | 0 | 14130 | CGST 0% URD I/P | 0 | 14130 | 14130 | Approved | 0 | 0 | 236 | 22 Feb 2023
GANGA DHAM TOWERS | 1296 | 98277 | 21 Feb 2023 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2005 | Miscellaneous expenses | Marketing Operating Expenses | 6.9114 | Month | 25000 | 8.33 | 0 | 0 | 14393 | C+S GST 0% I/P RD | 0 | 14393 | 14393 | Approved | 0 | 0 | 0 | 21 Feb 2023
GANGA DHAM TOWERS | 978 | 98271 | 21 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2000 | 53rd National Safety Week 2023 | Prize (Gift) | 1 | No. | 4500 | 100 | 0 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 0 | 21 Feb 2023
GANGA DHAM TOWERS | 978 | 98271 | 21 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2000 | 53rd National Safety Week 2023 | Prize (Gift) | 1 | No. | 9500 | 100 | 0 | 0 | 9500 | CGST 0% URD I/P | 0 | 9500 | 9500 | Approved | 0 | 0 | 0 | 21 Feb 2023
GANGA DHAM TOWERS | 978 | 98271 | 21 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2000 | 53rd National Safety Week 2023 | Prize (Gift) | 1 | No. | 11000 | 100 | 0 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 0 | 21 Feb 2023
GANGA DHAM TOWERS | 978 | 98271 | 21 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2000 | 53rd National Safety Week 2023 | Prize (Gift) | 1 | No. | 11000 | 100 | 0 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 0 | 21 Feb 2023
GANGA DHAM TOWERS | 272 | 98270 | 21 Feb 2023 |  | GOURI INFRA | SURESH KUMAR MURALIDHAR | EV - 2027 | A Bldg 35th slab (30th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 169.6053 | Sq.Ft | 190 | 100 | 805.63 | 0 | 32225 | CGST 0% URD I/P | 0 | 32225 | 32225 | Approved | 0 | 0 | 322 | 21 Feb 2023
GANGA DHAM TOWERS | 814 | 98269 | 21 Feb 2023 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 2080 | B 102 Terrace False Ceiling | Painting work (M+L) -BC | 165.23 | Sq.Ft | 35 | 100 | 0 | 0 | 5783.05 | C+S GST 18% I/P RD | 1040.94 | 6823.99 | 6823.99 | Approved | 0 | 0 | 58 | 21 Feb 2023
GANGA DHAM TOWERS | 1120 | 98262 | 20 Feb 2023 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 2029 | Tower C Podium P2 slab Built-up Area (L) | RCC Superstructure (B-up area) | 4379 | Sq.Ft | 195 | 100 | 21347.63 | 0 | 853905 | C+S GST 18% I/P RD | 153702.9 | 1007607.9 | 1007607.9 | Approved | 0 | 0 | 8539 | 20 Feb 2023
GANGA DHAM TOWERS | 814 | 98245 | 18 Feb 2023 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 2081 | B 102 Terrace False Ceiling | Sherawood False Ceiling (M) | 165.23 | Sq.Ft | 140 | 100 | 0 | 0 | 23132.2 | C+S GST 18% I/P RD | 4163.8 | 27296 | 27296 | Approved | 0 | 0 | 0 | 18 Feb 2023
GANGA DHAM TOWERS | 815 | 98244 | 18 Feb 2023 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 2079 | B 102 Terrace False Ceiling | Sherawood False Ceiling (L) | 148.707 | Sq.Ft | 42 | 100 | 156.14 | 0 | 6245.69 | C+S GST 18% I/P RD | 1124.22 | 7369.91 | 7369.91 | Approved | 0 | 0 | 62 | 18 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Safety Banner | 2 | No. | 600 | 100 | 0 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Prize (Gift) | 30 | No. | 250 | 100 | 0 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Miscellaneous Expenses | 1 | No. | 12000 | 100 | 0 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Flag | 1 | No. | 400 | 100 | 0 | 0 | 400 | CGST 0% URD I/P | 0 | 400 | 400 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Safety Badge | 100 | No. | 4 | 100 | 0 | 0 | 400 | CGST 0% URD I/P | 0 | 400 | 400 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 978 | 98241 | 17 Feb 2023 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1971 | 53rd National Safety Week 2023 | Food Expenses | 1190 | No. | 30 | 100 | 0 | 0 | 35700 | CGST 0% URD I/P | 0 | 35700 | 35700 | Approved | 0 | 0 | 0 | 17 Feb 2023
GANGA DHAM TOWERS | 632 | 98235 | 17 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR |  | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 172 | Sq.Ft | 15 | 100 | 64.5 | 0 | 2580 | C+S GST 18% I/P RD | 464.4 | 3044.4 | 3044.4 |  | 0 | 0 | 26 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Granite Kitchen Otta | Granite Kitchen Otta BC | 15.498 | R.Ft | 300 | 100 | 116.24 | 0 | 4649.4 | C+S GST 18% I/P RD | 836.9 | 5486.3 | 5486.3 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.87 | R.Ft | 650 | 100 | 46.64 | 0 | 1865.5 | C+S GST 18% I/P RD | 335.8 | 2201.3 | 2201.3 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 601 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.134 | Sq.Ft | 13 | 100 | 50.09 | 0 | 2003.74 | C+S GST 18% I/P RD | 360.68 | 2364.42 | 2364.42 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 43.06 | Sq.Ft | 17 | 100 | 18.3 | 0 | 732.02 | C+S GST 18% I/P RD | 131.76 | 863.78 | 863.78 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 43 | Sq.Ft | 17 | 100 | 18.28 | 0 | 731 | C+S GST 18% I/P RD | 131.58 | 862.58 | 862.58 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 17 | 100 | 21.25 | 0 | 850 | C+S GST 18% I/P RD | 153 | 1003 | 1003 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 31.0648 | Sq.Ft | 17 | 100 | 13.2 | 0 | 528.1 | C+S GST 18% I/P RD | 95.06 | 623.16 | 623.16 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 20 | Sq.Ft | 17 | 100 | 8.5 | 0 | 340 | C+S GST 18% I/P RD | 61.2 | 401.2 | 401.2 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 17.436 | Sq.Ft | 17 | 100 | 7.41 | 0 | 296.41 | C+S GST 18% I/P RD | 53.36 | 349.77 | 349.77 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | C+S GST 18% I/P RD | 131.26 | 860.44 | 860.44 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Children Toilet | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Tiling Below Wooden Flooring | Ceramic Flooring work | 180 | Sq.Ft | 16 | 100 | 72 | 0 | 2880 | C+S GST 18% I/P RD | 518.4 | 3398.4 | 3398.4 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 18 | 100 | 38.58 | 0 | 1543.05 | C+S GST 18% I/P RD | 277.74 | 1820.79 | 1820.79 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 18 | 100 | 61.77 | 0 | 2470.82 | C+S GST 18% I/P RD | 444.74 | 2915.56 | 2915.56 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 18 | 100 | 50.02 | 0 | 2000.86 | C+S GST 18% I/P RD | 360.16 | 2361.02 | 2361.02 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Children Toilet | Dado BC | 169.587 | Sq.Ft | 18 | 100 | 76.31 | 0 | 3052.57 | C+S GST 18% I/P RD | 549.46 | 3602.03 | 3602.03 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 18 | 100 | 33.55 | 0 | 1341.85 | C+S GST 18% I/P RD | 241.54 | 1583.39 | 1583.39 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 650 | 100 | 99.13 | 0 | 3965 | C+S GST 18% I/P RD | 713.7 | 4678.7 | 4678.7 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 650 | 100 | 99.13 | 0 | 3965 | C+S GST 18% I/P RD | 713.7 | 4678.7 | 4678.7 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.4908 | R.Ft | 650 | 100 | 40.48 | 0 | 1619 | C+S GST 18% I/P RD | 291.42 | 1910.42 | 1910.42 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 402 Kitchen dado | Dado BC | 47.51 | Sq.Ft | 14 | 100 | 16.63 | 0 | 665.14 | C+S GST 18% I/P RD | 119.72 | 784.86 | 784.86 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Children Toilet | Dado BC | 38.448 | Sq.Ft | 20 | 100 | 19.22 | 0 | 768.96 | C+S GST 18% I/P RD | 138.42 | 907.38 | 907.38 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 20 | 100 | 30.5 | 0 | 1220.04 | C+S GST 18% I/P RD | 219.6 | 1439.64 | 1439.64 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 20 | 100 | 36.79 | 0 | 1471.5 | C+S GST 18% I/P RD | 264.88 | 1736.38 | 1736.38 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 537 | 98234 | 17 Feb 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2141 | A 802 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 20 | 100 | 19.33 | 0 | 773.1 | C+S GST 18% I/P RD | 139.16 | 912.26 | 912.26 | Approved | 0 | 0 | 421 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2104 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 145.746 | Sq.Ft | 28 | 100 | 102.02 | 0 | 4080.89 | C+S GST 18% I/P RD | 734.56 | 4815.45 | 4815.45 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 103 Dry Balcony dado | Dado BC | 78.03 | Sq.Ft | 14 | 100 | 27.31 | 0 | 1092.42 | C+S GST 18% I/P RD | 196.64 | 1289.06 | 1289.06 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 103 Staff Toilet dado | L Groove - BCV | 22.203 | R.Ft | 20 | 100 | 11.1 | 0 | 444.06 | C+S GST 18% I/P RD | 79.94 | 524 | 524 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 1604 Staff Toilet dado | L Groove - BCV | 21.933 | R.Ft | 20 | 100 | 10.97 | 0 | 438.66 | C+S GST 18% I/P RD | 78.96 | 517.62 | 517.62 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Powder Toilet dado | L Groove - BCV | 32.238 | R.Ft | 20 | 100 | 16.12 | 0 | 644.76 | C+S GST 18% I/P RD | 116.06 | 760.82 | 760.82 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2104 Staff Toilet dado | L Groove - BCV | 21.933 | R.Ft | 20 | 100 | 10.97 | 0 | 438.66 | C+S GST 18% I/P RD | 78.96 | 517.62 | 517.62 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Parents Toilet dado | L Groove - BCV | 21.996 | R.Ft | 20 | 100 | 11 | 0 | 439.92 | C+S GST 18% I/P RD | 79.18 | 519.1 | 519.1 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 103 Dry Balcony dado | L Groove - BCV | 5.607 | R.Ft | 20 | 100 | 2.8 | 0 | 112.14 | C+S GST 18% I/P RD | 20.18 | 132.32 | 132.32 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | C+S GST 18% I/P RD | 176.26 | 1155.53 | 1155.53 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Parents Toilet dado | Dado BC | 95.436 | Sq.Ft | 28 | 100 | 66.81 | 0 | 2672.21 | C+S GST 18% I/P RD | 481 | 3153.21 | 3153.21 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Parents Toilet dado | Dado BC | 77.931 | Sq.Ft | 28 | 100 | 54.55 | 0 | 2182.07 | C+S GST 18% I/P RD | 392.78 | 2574.85 | 2574.85 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 28 | 100 | 82.54 | 0 | 3301.7 | C+S GST 18% I/P RD | 594.3 | 3896 | 3896 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 28 | 100 | 24.75 | 0 | 990.11 | C+S GST 18% I/P RD | 178.22 | 1168.33 | 1168.33 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2204 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | C+S GST 18% I/P RD | 441.62 | 2895.09 | 2895.09 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 28 | 100 | 53.69 | 0 | 2147.8 | C+S GST 18% I/P RD | 386.6 | 2534.4 | 2534.4 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2203 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 28 | 100 | 36.72 | 0 | 1468.66 | C+S GST 18% I/P RD | 264.36 | 1733.02 | 1733.02 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98233 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2039 | A 2104 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 24 | 100 | 73.1 | 0 | 2923.99 | C+S GST 18% I/P RD | 526.32 | 3450.31 | 3450.31 | Approved | 0 | 0 | 375 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1003 Dry Balcony dado | L Groove - BCV | 5.607 | R.Ft | 20 | 100 | 2.8 | 0 | 112.14 | C+S GST 18% I/P RD | 20.18 | 132.32 | 132.32 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1003 Master Toilet dado | L Groove - BCV | 38.907 | R.Ft | 20 | 100 | 19.45 | 0 | 778.14 | C+S GST 18% I/P RD | 140.06 | 918.2 | 918.2 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1204 Powder Toilet dado | L Groove - BCV | 32.238 | R.Ft | 20 | 100 | 16.12 | 0 | 644.76 | C+S GST 18% I/P RD | 116.06 | 760.82 | 760.82 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1003 Powder Toilet dado | L Groove - BCV | 5.166 | R.Ft | 20 | 100 | 2.58 | 0 | 103.32 | C+S GST 18% I/P RD | 18.6 | 121.92 | 121.92 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1203 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1003 Staff Toilet dado | L Groove - BCV | 22.203 | R.Ft | 20 | 100 | 11.1 | 0 | 444.06 | C+S GST 18% I/P RD | 79.94 | 524 | 524 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1003 Staff Room Vitrified Flooring | Vitrified Skirting BC | 28.044 | R.Ft | 17 | 100 | 11.92 | 0 | 476.75 | C+S GST 18% I/P RD | 85.82 | 562.57 | 562.57 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1303 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 18 | 100 | 69.49 | 0 | 2779.6 | C+S GST 18% I/P RD | 500.32 | 3279.92 | 3279.92 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1403 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 18 | 100 | 69.49 | 0 | 2779.6 | C+S GST 18% I/P RD | 500.32 | 3279.92 | 3279.92 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 1703 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 18 | 100 | 69.49 | 0 | 2779.6 | C+S GST 18% I/P RD | 500.32 | 3279.92 | 3279.92 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 2004 Tiling Below Wooden Flooring | Ceramic Flooring work | 160.812 | Sq.Ft | 21 | 100 | 84.43 | 0 | 3377.05 | C+S GST 18% I/P RD | 607.86 | 3984.91 | 3984.91 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 204 Tiling Below Wooden Flooring | Ceramic Flooring work | 160.812 | Sq.Ft | 13 | 100 | 52.26 | 0 | 2090.56 | C+S GST 18% I/P RD | 376.3 | 2466.86 | 2466.86 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 503 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 13 | 100 | 50.19 | 0 | 2007.49 | C+S GST 18% I/P RD | 361.34 | 2368.83 | 2368.83 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 203 Dry Balcony dado | Dado BC | 78.03 | Sq.Ft | 14 | 100 | 27.31 | 0 | 1092.42 | C+S GST 18% I/P RD | 196.64 | 1289.06 | 1289.06 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 803 Tiling Below Wooden Flooring | Ceramic Flooring work | 154.422 | Sq.Ft | 16 | 100 | 61.77 | 0 | 2470.75 | C+S GST 18% I/P RD | 444.74 | 2915.49 | 2915.49 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 104 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.2908 | R.Ft | 650 | 100 | 37.23 | 0 | 1489 | C+S GST 18% I/P RD | 268.02 | 1757.02 | 1757.02 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 803 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20.01 | R.Ft | 50 | 100 | 25.01 | 0 | 1000.5 | C+S GST 18% I/P RD | 180.1 | 1180.6 | 1180.6 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 104 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.34 | R.Ft | 650 | 100 | 86.78 | 0 | 3471 | C+S GST 18% I/P RD | 624.78 | 4095.78 | 4095.78 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 104 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.3708 | R.Ft | 650 | 100 | 87.28 | 0 | 3491 | C+S GST 18% I/P RD | 628.38 | 4119.38 | 4119.38 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 551 | 98232 | 17 Feb 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2167 | A 104 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.98 | R.Ft | 650 | 100 | 48.43 | 0 | 1937 | C+S GST 18% I/P RD | 348.66 | 2285.66 | 2285.66 | Approved | 0 | 0 | 339 | 17 Feb 2023
GANGA DHAM TOWERS | 1433 | 98215 | 16 Feb 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1967 | RMC Pump Per Month Rental Charges | Pump Hiring for RMC | 1 | Month | 250000 | 100 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 10041 | 5440 | 16 Feb 2023
GANGA DHAM TOWERS | 1433 | 98215 | 16 Feb 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1967 | RMC 150m Pipe Line Rental Charges | Rental Charges. | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 18% I/P RD | 3960 | 25960 | 25960 | Approved | 0 | 10041 | 5440 | 16 Feb 2023
GANGA DHAM TOWERS | 1468 | 98210 | 16 Feb 2023 |  | K B N FABRICATION | K B N FABRICATION | EV - 2028 | B Opening Railing For Safety 27th to 31st Floor | Fabrication work (L) | 416.6667 | Kgs | 12 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 16 Feb 2023
GANGA DHAM TOWERS | 1387 | 98208 | 15 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1978 | D Rainwater Line (L) | Rainwater Line | 18 | Flat | 1200 | 100 | 540 | 0 | 21600 | 0% | 0 | 21600 | 21600 | Approved | 0 | 0 | 1092 | 15 Feb 2023
GANGA DHAM TOWERS | 1387 | 98208 | 15 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1978 | D Duct GI & PVC work (L) | Duct Line | 28.8 | Flat | 1200 | 100 | 864 | 0 | 34560 | 0% | 0 | 34560 | 34560 | Approved | 0 | 0 | 1092 | 15 Feb 2023
GANGA DHAM TOWERS | 1387 | 98208 | 15 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1978 | D Duct GI & PVC work (L) | Duct Line | 19.2 | Flat | 1700 | 100 | 816 | 0 | 32640 | 0% | 0 | 32640 | 32640 | Approved | 0 | 0 | 1092 | 15 Feb 2023
GANGA DHAM TOWERS | 1387 | 98208 | 15 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1978 | D Rainwater Line (L) | Rainwater Line | 12 | Flat | 1700 | 100 | 510 | 0 | 20400 | 0% | 0 | 20400 | 20400 | Approved | 0 | 0 | 1092 | 15 Feb 2023
GANGA DHAM TOWERS | 184 | 98200 | 15 Feb 2023 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 1999 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 1 | No. | 1000000 | 20 | 0 | 0 | 200000 | C+S GST 18% I/P RD | 36000 | 236000 | 236000 | Approved | 0 | 0 | 30000 | 15 Feb 2023
GANGA DHAM TOWERS | 184 | 98200 | 15 Feb 2023 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 1999 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 1 | No. | 1000000 | 10 | 0 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 30000 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156 | R.Ft | 20 | 100 | 78 | 0 | 3120 | C+S GST 18% I/P RD | 561.6 | 3681.6 | 3681.6 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156 | R.Ft | 20 | 100 | 78 | 0 | 3120 | C+S GST 18% I/P RD | 561.6 | 3681.6 | 3681.6 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 504 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156 | R.Ft | 20 | 100 | 78 | 0 | 3120 | C+S GST 18% I/P RD | 561.6 | 3681.6 | 3681.6 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352 | Sq.Ft | 20 | 100 | 176 | 0 | 7040 | C+S GST 18% I/P RD | 1267.2 | 8307.2 | 8307.2 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 444 | Sq.Ft | 20 | 100 | 222 | 0 | 8880 | C+S GST 18% I/P RD | 1598.4 | 10478.4 | 10478.4 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 444 | Sq.Ft | 20 | 100 | 222 | 0 | 8880 | C+S GST 18% I/P RD | 1598.4 | 10478.4 | 10478.4 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 504 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 444 | Sq.Ft | 20 | 100 | 222 | 0 | 8880 | C+S GST 18% I/P RD | 1598.4 | 10478.4 | 10478.4 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352 | Sq.Ft | 20 | 100 | 176 | 0 | 7040 | C+S GST 18% I/P RD | 1267.2 | 8307.2 | 8307.2 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352 | Sq.Ft | 20 | 100 | 176 | 0 | 7040 | C+S GST 18% I/P RD | 1267.2 | 8307.2 | 8307.2 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 352 | Sq.Ft | 20 | 100 | 176 | 0 | 7040 | C+S GST 18% I/P RD | 1267.2 | 8307.2 | 8307.2 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 632 | 98192 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2037 | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 444 | Sq.Ft | 15 | 100 | 166.5 | 0 | 6660 | C+S GST 18% I/P RD | 1198.8 | 7858.8 | 7858.8 | Approved | 0 | 0 | 820 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 504 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 207 | R.Ft | 55 | 100 | 0 | 0 | 11385 | C+S GST 18% I/P RD | 2049.3 | 13434.3 | 13434.3 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 207 | R.Ft | 55 | 100 | 0 | 0 | 11385 | C+S GST 18% I/P RD | 2049.3 | 13434.3 | 13434.3 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 207 | R.Ft | 55 | 100 | 0 | 0 | 11385 | C+S GST 18% I/P RD | 2049.3 | 13434.3 | 13434.3 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 591 | Sq.Ft | 50 | 100 | 0 | 0 | 29550 | C+S GST 18% I/P RD | 5319 | 34869 | 34869 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 123 | Sq.Ft | 50 | 100 | 0 | 0 | 6150 | C+S GST 18% I/P RD | 1107 | 7257 | 7257 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 147.1091 | Sq.Ft | 55 | 100 | 0 | 0 | 8091 | C+S GST 18% I/P RD | 1456.38 | 9547.38 | 9547.38 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 469 | Sq.Ft | 55 | 100 | 0 | 0 | 25795 | C+S GST 18% I/P RD | 4643.1 | 30438.1 | 30438.1 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 469 | Sq.Ft | 55 | 100 | 0 | 0 | 25795 | C+S GST 18% I/P RD | 4643.1 | 30438.1 | 30438.1 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 117.3091 | Sq.Ft | 55 | 100 | 0 | 0 | 6452 | C+S GST 18% I/P RD | 1161.36 | 7613.36 | 7613.36 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 469 | Sq.Ft | 55 | 100 | 0 | 0 | 25795 | C+S GST 18% I/P RD | 4643.1 | 30438.1 | 30438.1 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 504 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 591 | Sq.Ft | 55 | 100 | 0 | 0 | 32505 | C+S GST 18% I/P RD | 5850.9 | 38355.9 | 38355.9 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 629 | 98191 | 15 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2038 | A 704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 591 | Sq.Ft | 55 | 100 | 0 | 0 | 32505 | C+S GST 18% I/P RD | 5850.9 | 38355.9 | 38355.9 | Approved | 0 | 0 | 0 | 15 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 801 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 303 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 602 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 901 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 902 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 804 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 702 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 5% I/P RD | 57.56 | 1208.61 | 1208.61 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 705 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 5% I/P RD | 78.46 | 1647.48 | 1647.48 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 905 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 38 | Sq.Ft | 3.5 | 100 | 0 | 0 | 133 | C+S GST 5% I/P RD | 6.66 | 139.66 | 139.66 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1104 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 604 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 805 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 603 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 605 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 5% I/P RD | 78.46 | 1647.48 | 1647.48 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1102 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 404 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 705 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 704 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 902 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 5% I/P RD | 57.56 | 1208.61 | 1208.61 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 801 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 5% I/P RD | 78.46 | 1647.48 | 1647.48 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1004 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 301 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 702 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 802 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 805 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 5% I/P RD | 78.46 | 1647.48 | 1647.48 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 102 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 403 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 704 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 105 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 803 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 601 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 236 | Sq.Ft | 3.5 | 100 | 0 | 0 | 826 | C+S GST 5% I/P RD | 41.3 | 867.3 | 867.3 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 904 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 202 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 501 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 402 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 5% I/P RD | 57.56 | 1208.61 | 1208.61 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 901 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 339.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1187 | C+S GST 5% I/P RD | 59.36 | 1246.36 | 1246.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 401 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 402 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1002 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 205 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 504 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 305 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 701 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 604 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 302 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 503 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 605 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 804 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 703 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1101 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1005 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1001 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 203 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 204 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 505 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 701 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 5% I/P RD | 78.46 | 1647.48 | 1647.48 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 803 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 201 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 405 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 502 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 62.53 | Sq.Ft | 3.5 | 100 | 0 | 0 | 218.86 | C+S GST 5% I/P RD | 10.94 | 229.8 | 229.8 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 905 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1003 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 903 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 904 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1105 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 602 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 5% I/P RD | 57.56 | 1208.61 | 1208.61 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 104 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 703 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 603 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 802 (Refuge area) Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 465.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1630.13 | C+S GST 5% I/P RD | 81.5 | 1711.63 | 1711.63 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 101 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 38.75 | Sq.Ft | 3.5 | 100 | 0 | 0 | 135.63 | C+S GST 5% I/P RD | 6.78 | 142.41 | 142.41 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 1103 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 103 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 304 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (M) | 31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 108.5 | C+S GST 5% I/P RD | 5.42 | 113.92 | 113.92 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 697 | 98184 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2078 | D 903 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 5% I/P RD | 56.92 | 1195.51 | 1195.51 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | MS Plate (L) | 321.6 | Kgs | 20 | 100 | 160.8 | 0 | 6432 | C+S GST 18% I/P RD | 1157.76 | 7589.76 | 7589.76 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | ISMB 150 (L) | 724.14 | Kgs | 20 | 100 | 362.07 | 0 | 14482.8 | C+S GST 18% I/P RD | 2606.9 | 17089.7 | 17089.7 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | Chemical Fastner fixing (L) | 96 | No. | 80 | 100 | 192 | 0 | 7680 | C+S GST 18% I/P RD | 1382.4 | 9062.4 | 9062.4 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | ISMC 200 (L) | 859.69 | Kgs | 20 | 100 | 429.85 | 0 | 17193.8 | C+S GST 18% I/P RD | 3094.88 | 20288.68 | 20288.68 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | ISMB 200 (L) | 693.93 | Kgs | 20 | 100 | 346.97 | 0 | 13878.6 | C+S GST 18% I/P RD | 2498.14 | 16376.74 | 16376.74 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(L) | 913.5 | Kgs | 20 | 100 | 456.75 | 0 | 18270 | C+S GST 18% I/P RD | 3288.6 | 21558.6 | 21558.6 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | ISMB 125 (L) -BCo | 59.8 | Kgs | 20 | 100 | 29.9 | 0 | 1196 | C+S GST 18% I/P RD | 215.28 | 1411.28 | 1411.28 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 1447 | 98176 | 13 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2013 | Tower A Service Platform Fabrication Work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | 43.52 | Kgs | 20 | 100 | 21.76 | 0 | 870.4 | C+S GST 18% I/P RD | 156.68 | 1027.08 | 1027.08 | Approved | 0 | 0 | 800 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 1st to 2nd Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 10th to 11th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 11th to Terrace Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 2nd to 3rd Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 11th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 5% I/P RD | 39.58 | 831.32 | 831.32 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 7th to 8th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 6th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 5% I/P RD | 39.58 | 831.32 | 831.32 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 8th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 5% I/P RD | 39.58 | 831.32 | 831.32 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 9th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 5% I/P RD | 39.58 | 831.32 | 831.32 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 4th to 5th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 8th to 9th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 9th to 10th Fl. | Gypsum on Ceiling (M) | 118.2438 | Sq.Ft | 3.5 | 100 | 0 | 0 | 413.85 | C+S GST 5% I/P RD | 20.7 | 434.55 | 434.55 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 3rd to 4th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 7th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 5% I/P RD | 39.58 | 831.32 | 831.32 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 5th to 6th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D Fire St.case Ceiling Gyp. Plaster 6th to 7th Fl. | Gypsum on Ceiling (M) | 162 | Sq.Ft | 3.5 | 100 | 0 | 0 | 567 | C+S GST 5% I/P RD | 28.36 | 595.36 | 595.36 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 796 | 98172 | 13 Feb 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2076 | D 12th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 4 | 100 | 0 | 0 | 904.84 | C+S GST 5% I/P RD | 45.24 | 950.08 | 950.08 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1314 | 98170 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2077 | D 1205 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 4 | 100 | 0 | 0 | 1793.16 | C+S GST 5% I/P RD | 89.66 | 1882.82 | 1882.82 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1314 | 98170 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2077 | D 1201 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 4 | 100 | 0 | 0 | 1793.16 | C+S GST 5% I/P RD | 89.66 | 1882.82 | 1882.82 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1314 | 98170 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2077 | D 1203 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 4 | 100 | 0 | 0 | 1301.24 | C+S GST 5% I/P RD | 65.06 | 1366.3 | 1366.3 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1314 | 98170 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2077 | D 1202 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 4 | 100 | 0 | 0 | 1315.48 | C+S GST 5% I/P RD | 65.78 | 1381.26 | 1381.26 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 1314 | 98170 | 13 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2077 | D 1204 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 4 | 100 | 0 | 0 | 1301.24 | C+S GST 5% I/P RD | 65.06 | 1366.3 | 1366.3 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 149 | 98169 | 13 Feb 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1977 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 4000 | No. | 4 | 100 | 0 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 0 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Master Toilet Dado | Dado BC | 156.249 | Sq.Ft | 18 | 100 | 70.31 | 0 | 2812.48 | C+S GST 18% I/P RD | 506.24 | 3318.72 | 3318.72 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Kitchen Dado | Dado BC | 75.717 | Sq.Ft | 18 | 100 | 34.07 | 0 | 1362.91 | C+S GST 18% I/P RD | 245.32 | 1608.23 | 1608.23 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Guest Toilet Dado | Dado BC | 121.365 | Sq.Ft | 18 | 100 | 54.61 | 0 | 2184.57 | C+S GST 18% I/P RD | 393.22 | 2577.79 | 2577.79 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Dry Balcony Dado | Dado BC | 73.242 | Sq.Ft | 18 | 100 | 32.96 | 0 | 1318.36 | C+S GST 18% I/P RD | 237.3 | 1555.66 | 1555.66 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Children Toilet 1 Dado | Dado BC | 146.493 | Sq.Ft | 18 | 100 | 65.92 | 0 | 2636.87 | C+S GST 18% I/P RD | 474.64 | 3111.51 | 3111.51 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Parents Toilet Dado | Dado BC | 162.9 | Sq.Ft | 18 | 100 | 73.31 | 0 | 2932.2 | C+S GST 18% I/P RD | 527.8 | 3460 | 3460 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Dry Balcony Dado | Dado BC | 73.242 | Sq.Ft | 18 | 100 | 32.96 | 0 | 1318.36 | C+S GST 18% I/P RD | 237.3 | 1555.66 | 1555.66 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Powder Toilet Dado | Dado BC | 85.446 | Sq.Ft | 18 | 100 | 38.45 | 0 | 1538.03 | C+S GST 18% I/P RD | 276.84 | 1814.87 | 1814.87 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 StaffToilet Dado | Dado BC | 122.805 | Sq.Ft | 13 | 100 | 39.91 | 0 | 1596.47 | C+S GST 18% I/P RD | 287.36 | 1883.83 | 1883.83 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Powder Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 22 | 100 | 47 | 0 | 1879.81 | C+S GST 18% I/P RD | 338.36 | 2218.17 | 2218.17 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 22 | 100 | 66.75 | 0 | 2670.03 | C+S GST 18% I/P RD | 480.6 | 3150.63 | 3150.63 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 22 | 100 | 80.57 | 0 | 3222.85 | C+S GST 18% I/P RD | 580.12 | 3802.97 | 3802.97 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 22 | 100 | 89.6 | 0 | 3583.8 | C+S GST 18% I/P RD | 645.08 | 4228.88 | 4228.88 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1302 Kitchen Dado | Dado BC | 75.717 | Sq.Ft | 22 | 100 | 41.64 | 0 | 1665.77 | C+S GST 18% I/P RD | 299.84 | 1965.61 | 1965.61 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 StaffToilet Dado - 1 No. | Dado BC | 122.805 | Sq.Ft | 21 | 100 | 64.47 | 0 | 2578.91 | C+S GST 18% I/P RD | 464.2 | 3043.11 | 3043.11 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 22 | 100 | 85.94 | 0 | 3437.48 | C+S GST 18% I/P RD | 618.74 | 4056.22 | 4056.22 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Powder Toilet Dado | Dado BC | 34.893 | Sq.Ft | 15 | 100 | 13.08 | 0 | 523.4 | C+S GST 18% I/P RD | 94.22 | 617.62 | 617.62 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 24 | 100 | 26.77 | 0 | 1070.93 | C+S GST 18% I/P RD | 192.76 | 1263.69 | 1263.69 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Master Toilet Dado | Dado BC | 51.03 | Sq.Ft | 15 | 100 | 19.14 | 0 | 765.45 | C+S GST 18% I/P RD | 137.78 | 903.23 | 903.23 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Children Toilet 1 Dado | Dado BC | 44.622 | Sq.Ft | 15 | 100 | 16.73 | 0 | 669.33 | C+S GST 18% I/P RD | 120.48 | 789.81 | 789.81 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Parents Toilet Dado - 1 No. | Dado BC | 48.654 | Sq.Ft | 24 | 100 | 29.19 | 0 | 1167.7 | C+S GST 18% I/P RD | 210.18 | 1377.88 | 1377.88 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 24 | 100 | 35.6 | 0 | 1424.09 | C+S GST 18% I/P RD | 256.34 | 1680.43 | 1680.43 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Guest Toilet Dado | Dado BC | 59.337 | Sq.Ft | 15 | 100 | 22.25 | 0 | 890.06 | C+S GST 18% I/P RD | 160.22 | 1050.28 | 1050.28 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 24 | 100 | 30.62 | 0 | 1224.72 | C+S GST 18% I/P RD | 220.44 | 1445.16 | 1445.16 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Powder Toilet Dado - 1 No. | Dado BC | 34.893 | Sq.Ft | 24 | 100 | 20.94 | 0 | 837.43 | C+S GST 18% I/P RD | 150.74 | 988.17 | 988.17 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Parents Toilet Dado | Dado BC | 48.654 | Sq.Ft | 15 | 100 | 18.25 | 0 | 729.81 | C+S GST 18% I/P RD | 131.36 | 861.17 | 861.17 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 73.431 | Sq.Ft | 13 | 100 | 23.87 | 0 | 954.6 | C+S GST 18% I/P RD | 171.82 | 1126.42 | 1126.42 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 13 | 100 | 17.47 | 0 | 698.96 | C+S GST 18% I/P RD | 125.82 | 824.78 | 824.78 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 13 | 100 | 6.52 | 0 | 260.68 | C+S GST 18% I/P RD | 46.92 | 307.6 | 307.6 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 13 | 100 | 8.03 | 0 | 321.17 | C+S GST 18% I/P RD | 57.82 | 378.99 | 378.99 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 13 | 100 | 14.7 | 0 | 588.16 | C+S GST 18% I/P RD | 105.86 | 694.02 | 694.02 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 13 | 100 | 14.17 | 0 | 566.75 | C+S GST 18% I/P RD | 102.02 | 668.77 | 668.77 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 13 | 100 | 7.08 | 0 | 283.37 | C+S GST 18% I/P RD | 51 | 334.37 | 334.37 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Children Toilet 1 Vitrified Flooring | Vitrified Flooring -BC | 52.506 | Sq.Ft | 13 | 100 | 17.06 | 0 | 682.58 | C+S GST 18% I/P RD | 122.86 | 805.44 | 805.44 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 13 | 100 | 6.52 | 0 | 260.68 | C+S GST 18% I/P RD | 46.92 | 307.6 | 307.6 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 13 | 100 | 17.44 | 0 | 697.67 | C+S GST 18% I/P RD | 125.58 | 823.25 | 823.25 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 13 | 100 | 17.47 | 0 | 698.96 | C+S GST 18% I/P RD | 125.82 | 824.78 | 824.78 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 13 | 100 | 7.08 | 0 | 283.37 | C+S GST 18% I/P RD | 51 | 334.37 | 334.37 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 13 | 100 | 17.44 | 0 | 697.67 | C+S GST 18% I/P RD | 125.58 | 823.25 | 823.25 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Children Toilet 2 Vitrified Flooring | Vitrified Flooring -BC | 41.175 | Sq.Ft | 13 | 100 | 13.38 | 0 | 535.28 | C+S GST 18% I/P RD | 96.36 | 631.64 | 631.64 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 13 | 100 | 6.52 | 0 | 260.68 | C+S GST 18% I/P RD | 46.92 | 307.6 | 307.6 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 201 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 13 | 100 | 16.59 | 0 | 663.74 | C+S GST 18% I/P RD | 119.48 | 783.22 | 783.22 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 700 | 100 | 103.43 | 0 | 4137 | C+S GST 18% I/P RD | 744.66 | 4881.66 | 4881.66 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 700 | 100 | 53.9 | 0 | 2156 | C+S GST 18% I/P RD | 388.08 | 2544.08 | 2544.08 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 700 | 100 | 102.03 | 0 | 4081 | C+S GST 18% I/P RD | 734.58 | 4815.58 | 4815.58 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Common Toilet Counter Wash Basin - 1 No. | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 700 | 100 | 102.03 | 0 | 4081 | C+S GST 18% I/P RD | 734.58 | 4815.58 | 4815.58 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 700 | 100 | 103.43 | 0 | 4137 | C+S GST 18% I/P RD | 744.66 | 4881.66 | 4881.66 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 700 | 100 | 53.9 | 0 | 2156 | C+S GST 18% I/P RD | 388.08 | 2544.08 | 2544.08 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Window Sill | Italian Marble Sill- BC- | 46.791 | R.Ft | 45 | 100 | 52.64 | 0 | 2105.6 | C+S GST 18% I/P RD | 379 | 2484.6 | 2484.6 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 402 Window Sill- | Italian Marble Sill- BC- | 46.791 | R.Ft | 45 | 100 | 52.64 | 0 | 2105.6 | C+S GST 18% I/P RD | 379 | 2484.6 | 2484.6 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 102 Window Sill- | Italian Marble Sill- BC- | 51.363 | R.Ft | 45 | 100 | 57.78 | 0 | 2311.34 | C+S GST 18% I/P RD | 416.04 | 2727.38 | 2727.38 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Parents Toilet Dado | Dado BC | 48.654 | Sq.Ft | 20 | 100 | 24.33 | 0 | 973.08 | C+S GST 18% I/P RD | 175.16 | 1148.24 | 1148.24 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 StaffToilet Dado | Dado BC | 122.805 | Sq.Ft | 17 | 100 | 52.19 | 0 | 2087.69 | C+S GST 18% I/P RD | 375.78 | 2463.47 | 2463.47 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 20 | 100 | 74.35 | 0 | 2974.14 | C+S GST 18% I/P RD | 535.34 | 3509.48 | 3509.48 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 17 | 100 | 18.05 | 0 | 722.16 | C+S GST 18% I/P RD | 129.98 | 852.14 | 852.14 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 17 | 100 | 22.85 | 0 | 914.02 | C+S GST 18% I/P RD | 164.52 | 1078.54 | 1078.54 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 17 | 100 | 9.26 | 0 | 370.57 | C+S GST 18% I/P RD | 66.7 | 437.27 | 437.27 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 17 | 100 | 8.52 | 0 | 340.88 | C+S GST 18% I/P RD | 61.36 | 402.24 | 402.24 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 17 | 100 | 19.64 | 0 | 785.5 | C+S GST 18% I/P RD | 141.4 | 926.9 | 926.9 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 17 | 100 | 16.34 | 0 | 653.77 | C+S GST 18% I/P RD | 117.68 | 771.45 | 771.45 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 17 | 100 | 22.81 | 0 | 912.34 | C+S GST 18% I/P RD | 164.22 | 1076.56 | 1076.56 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 17 | 100 | 19.23 | 0 | 769.13 | C+S GST 18% I/P RD | 138.44 | 907.57 | 907.57 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 17 | 100 | 23.59 | 0 | 943.7 | C+S GST 18% I/P RD | 169.86 | 1113.56 | 1113.56 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 17 | 100 | 9.26 | 0 | 370.57 | C+S GST 18% I/P RD | 66.7 | 437.27 | 437.27 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 17 | 100 | 22.81 | 0 | 912.34 | C+S GST 18% I/P RD | 164.22 | 1076.56 | 1076.56 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 17 | 100 | 8.52 | 0 | 340.88 | C+S GST 18% I/P RD | 61.36 | 402.24 | 402.24 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 17 | 100 | 18.05 | 0 | 722.16 | C+S GST 18% I/P RD | 129.98 | 852.14 | 852.14 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 17 | 100 | 22.85 | 0 | 914.02 | C+S GST 18% I/P RD | 164.52 | 1078.54 | 1078.54 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 17 | 100 | 19.64 | 0 | 785.5 | C+S GST 18% I/P RD | 141.4 | 926.9 | 926.9 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 17 | 100 | 23.59 | 0 | 943.7 | C+S GST 18% I/P RD | 169.86 | 1113.56 | 1113.56 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 17 | 100 | 16.34 | 0 | 653.77 | C+S GST 18% I/P RD | 117.68 | 771.45 | 771.45 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 17 | 100 | 19.23 | 0 | 769.13 | C+S GST 18% I/P RD | 138.44 | 907.57 | 907.57 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Guest Toilet Dado | Dado BC | 59.337 | Sq.Ft | 20 | 100 | 29.67 | 0 | 1186.74 | C+S GST 18% I/P RD | 213.62 | 1400.36 | 1400.36 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Powder Toilet Dado | Dado BC | 34.893 | Sq.Ft | 20 | 100 | 17.45 | 0 | 697.86 | C+S GST 18% I/P RD | 125.62 | 823.48 | 823.48 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Master Toilet Dado | Dado BC | 51.03 | Sq.Ft | 20 | 100 | 25.52 | 0 | 1020.6 | C+S GST 18% I/P RD | 183.7 | 1204.3 | 1204.3 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Children Toilet 1 Dado | Dado BC | 44.622 | Sq.Ft | 20 | 100 | 22.31 | 0 | 892.44 | C+S GST 18% I/P RD | 160.64 | 1053.08 | 1053.08 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 650 | 100 | 96.04 | 0 | 3841.5 | C+S GST 18% I/P RD | 691.48 | 4532.98 | 4532.98 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 650 | 100 | 77.19 | 0 | 3087.5 | C+S GST 18% I/P RD | 555.76 | 3643.26 | 3643.26 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 650 | 100 | 50.05 | 0 | 2002 | C+S GST 18% I/P RD | 360.36 | 2362.36 | 2362.36 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.91 | R.Ft | 650 | 100 | 96.04 | 0 | 3841.5 | C+S GST 18% I/P RD | 691.48 | 4532.98 | 4532.98 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 650 | 100 | 94.74 | 0 | 3789.5 | C+S GST 18% I/P RD | 682.12 | 4471.62 | 4471.62 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 650 | 100 | 50.05 | 0 | 2002 | C+S GST 18% I/P RD | 360.36 | 2362.36 | 2362.36 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Common Toilet Counter Wash Basin - 1 No. | Italian Marble Counter - Mkt | 4.75 | R.Ft | 650 | 100 | 77.19 | 0 | 3087.5 | C+S GST 18% I/P RD | 555.76 | 3643.26 | 3643.26 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 650 | 100 | 77.19 | 0 | 3087.5 | C+S GST 18% I/P RD | 555.76 | 3643.26 | 3643.26 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Master Toilet Dado | Dado BC | 156.249 | Sq.Ft | 14 | 100 | 54.69 | 0 | 2187.49 | C+S GST 18% I/P RD | 393.74 | 2581.23 | 2581.23 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Guest Toilet Dado | Dado BC | 121.365 | Sq.Ft | 14 | 100 | 42.48 | 0 | 1699.11 | C+S GST 18% I/P RD | 305.84 | 2004.95 | 2004.95 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Parents Toilet Dado | Dado BC | 162.9 | Sq.Ft | 14 | 100 | 57.02 | 0 | 2280.6 | C+S GST 18% I/P RD | 410.5 | 2691.1 | 2691.1 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Children Toilet 1 Dado | Dado BC | 146.493 | Sq.Ft | 14 | 100 | 51.27 | 0 | 2050.9 | C+S GST 18% I/P RD | 369.16 | 2420.06 | 2420.06 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 502 Powder Toilet Dado | Dado BC | 85.446 | Sq.Ft | 14 | 100 | 29.91 | 0 | 1196.24 | C+S GST 18% I/P RD | 215.32 | 1411.56 | 1411.56 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 602 Dry Balcony Dado | Dado BC | 73.242 | Sq.Ft | 14 | 100 | 25.63 | 0 | 1025.39 | C+S GST 18% I/P RD | 184.58 | 1209.97 | 1209.97 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 21 | 100 | 28.18 | 0 | 1127.01 | C+S GST 18% I/P RD | 202.86 | 1329.87 | 1329.87 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 21 | 100 | 28.23 | 0 | 1129.09 | C+S GST 18% I/P RD | 203.24 | 1332.33 | 1332.33 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 21 | 100 | 20.19 | 0 | 807.6 | C+S GST 18% I/P RD | 145.36 | 952.96 | 952.96 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 21 | 100 | 11.44 | 0 | 457.76 | C+S GST 18% I/P RD | 82.4 | 540.16 | 540.16 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1702 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 21 | 100 | 10.53 | 0 | 421.09 | C+S GST 18% I/P RD | 75.8 | 496.89 | 496.89 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 802 Window Sill | Italian Marble Sill- BC- | 46.791 | R.Ft | 50 | 100 | 58.49 | 0 | 2339.55 | C+S GST 18% I/P RD | 421.12 | 2760.67 | 2760.67 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 902 Window Sill | Italian Marble Sill- BC- | 51.363 | R.Ft | 50 | 100 | 64.2 | 0 | 2568.15 | C+S GST 18% I/P RD | 462.26 | 3030.41 | 3030.41 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1002 Window Sill | Italian Marble Sill- BC- | 46.791 | R.Ft | 50 | 100 | 58.49 | 0 | 2339.55 | C+S GST 18% I/P RD | 421.12 | 2760.67 | 2760.67 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1202 Window Sill- | Italian Marble Sill- BC- | 46.791 | R.Ft | 50 | 100 | 58.49 | 0 | 2339.55 | C+S GST 18% I/P RD | 421.12 | 2760.67 | 2760.67 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 702 Window Sill - | Italian Marble Sill- BC- | 51.363 | R.Ft | 50 | 100 | 64.2 | 0 | 2568.15 | C+S GST 18% I/P RD | 462.26 | 3030.41 | 3030.41 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 758 | 98168 | 13 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2143 | B 1102 Window Sill- | Italian Marble Sill- BC- | 51.363 | R.Ft | 50 | 100 | 64.2 | 0 | 2568.15 | C+S GST 18% I/P RD | 462.26 | 3030.41 | 3030.41 | Approved | 0 | 0 | 1716 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 404 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1004 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 26015 | 45 | 96.87 | 0 | 3875 | C+S GST 18% I/P RD | 697.5 | 4572.5 | 4572.5 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 404 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 26015 | 45 | 96.87 | 0 | 3875 | C+S GST 18% I/P RD | 697.5 | 4572.5 | 4572.5 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1004 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 803 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 903 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 23237 | 45 | 86.53 | 0 | 3461 | C+S GST 18% I/P RD | 622.98 | 4083.98 | 4083.98 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 903 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 7.5 | 43.57 | 0 | 1742.78 | C+S GST 18% I/P RD | 313.7 | 2056.48 | 2056.48 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 803 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 23237 | 45 | 86.53 | 0 | 3461 | C+S GST 18% I/P RD | 622.98 | 4083.98 | 4083.98 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1501 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 901 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1501 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 26925 | 45 | 100.26 | 0 | 4010 | C+S GST 18% I/P RD | 721.8 | 4731.8 | 4731.8 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1502 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 26015 | 45 | 96.87 | 0 | 3875 | C+S GST 18% I/P RD | 697.5 | 4572.5 | 4572.5 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1602 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1118 | 98160 | 13 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2058 | A 1602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.331 | No. | 26015 | 45 | 96.87 | 0 | 3875 | C+S GST 18% I/P RD | 697.5 | 4572.5 | 4572.5 | Approved | 0 | 0 | 418 | 13 Feb 2023
GANGA DHAM TOWERS | 1496 | 98154 | 11 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2185 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 1 | No. | 5500 | 100 | 0 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 2520 | 11 Feb 2023
GANGA DHAM TOWERS | 1496 | 98154 | 11 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2185 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 3 | No. | 5500 | 100 | 0 | 0 | 16500 | C+S GST 18% I/P RD | 2970 | 19470 | 19470 | Approved | 0 | 0 | 2520 | 11 Feb 2023
GANGA DHAM TOWERS | 1496 | 98154 | 11 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2185 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 1 | No. | 26000 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 2520 | 11 Feb 2023
GANGA DHAM TOWERS | 1496 | 98154 | 11 Feb 2023 |  | SIDDHIVINAYAK CORPORATION | SIDDHIVINAYAK CORPORATION | EV - 2185 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gandola. | 3 | No. | 26000 | 100 | 0 | 0 | 78000 | C+S GST 18% I/P RD | 14040 | 92040 | 92040 | Approved | 0 | 0 | 2520 | 11 Feb 2023
GANGA DHAM TOWERS | 1446 | 98137 | 10 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2012 | Tower A Service Platform Fabrication Work | ISMB 125 (M) -BCo | 875.16 | Kgs | 64 | 100 | 0 | 0 | 56010.24 | C+S GST 18% I/P RD | 10081.84 | 66092.08 | 66092.08 | Approved | 0 | 0 | 0 | 10 Feb 2023
GANGA DHAM TOWERS | 1446 | 98137 | 10 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2012 | Tower A Service Platform Fabrication Work | ISMB 150 (M) | 2370.89 | Kgs | 64 | 100 | 0 | 0 | 151736.96 | C+S GST 18% I/P RD | 27312.66 | 179049.62 | 179049.62 | Approved | 0 | 0 | 0 | 10 Feb 2023
GANGA DHAM TOWERS | 1446 | 98137 | 10 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2012 | Tower A Service Platform Fabrication Work | ISMB 200 (M) | 2503.42 | Kgs | 64 | 100 | 0 | 0 | 160218.88 | C+S GST 18% I/P RD | 28839.4 | 189058.28 | 189058.28 | Approved | 0 | 0 | 0 | 10 Feb 2023
GANGA DHAM TOWERS | 1446 | 98137 | 10 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2012 | Tower A Service Platform Fabrication Work | ISMC 200 (M) | 3668.51 | Kgs | 64 | 100 | 0 | 0 | 234784.64 | C+S GST 18% I/P RD | 42261.24 | 277045.88 | 277045.88 | Approved | 0 | 0 | 0 | 10 Feb 2023
GANGA DHAM TOWERS | 1446 | 98137 | 10 Feb 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 2012 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(M) | 2360.7 | Kgs | 64 | 100 | 0 | 0 | 151084.8 | C+S GST 18% I/P RD | 27195.26 | 178280.06 | 178280.06 | Approved | 0 | 0 | 0 | 10 Feb 2023
GANGA DHAM TOWERS | 968 | 98136 | 10 Feb 2023 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2146 | Safety Boards / Flex Printing | Safety Posters (Flex Printing) | 7 | No. | 180 | 100 | 0 | 0 | 1260 | C+S GST 18% I/P RD | 226.8 | 1486.8 | 1486.8 | Approved | 0 | 0 | 58 | 10 Feb 2023
GANGA DHAM TOWERS | 968 | 98136 | 10 Feb 2023 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2146 | Safety Boards / Flex Printing | Safety Posters (Flex Printing) | 35 | No. | 130 | 100 | 0 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 58 | 10 Feb 2023
GANGA DHAM TOWERS | 904 | 98132 | 10 Feb 2023 |  | AVCON TECHNICS PVT LTD | RAHUL ENTERPRISES (Prop Laburi) |  | B 701 NOC | Italian Marble Mirror Polish- BCo | 11.001 | Sq.Ft | 45 | 100 | 12.38 | 0 | 495.05 | C+S GST 18% I/P RD | 89.1 | 584.15 | 584.15 |  | 0 | 0 | 5 | 10 Feb 2023
GANGA DHAM TOWERS | 1252 | 98131 | 10 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2166 | B 601 NOC | Italian Marble Mirror Polish- BCo | 82.161 | Sq.Ft | 45 | 100 | 92.43 | 0 | 3697.25 | C+S GST 18% I/P RD | 665.5 | 4362.75 | 4362.75 | Approved | 0 | 0 | 37 | 10 Feb 2023
GANGA DHAM TOWERS | 1146 | 98130 | 10 Feb 2023 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2158 | B 102 NOC | Italian Marble Mirror Polish- BCo | 45.948 | Sq.Ft | 45 | 100 | 51.69 | 0 | 2067.66 | C+S GST 18% I/P RD | 372.18 | 2439.84 | 2439.84 | Approved | 0 | 0 | 21 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 702 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 40 | 100 | 61.68 | 0 | 2467.08 | C+S GST 18% I/P RD | 444.08 | 2911.16 | 2911.16 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 901 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 40 | 100 | 59.08 | 0 | 2363.16 | C+S GST 18% I/P RD | 425.36 | 2788.52 | 2788.52 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 902 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 40 | 100 | 80.83 | 0 | 3233.04 | C+S GST 18% I/P RD | 581.94 | 3814.98 | 3814.98 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 901 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 40 | 100 | 72.9 | 0 | 2916 | C+S GST 18% I/P RD | 524.88 | 3440.88 | 3440.88 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 902 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 40 | 100 | 61.68 | 0 | 2467.08 | C+S GST 18% I/P RD | 444.08 | 2911.16 | 2911.16 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 801 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 40 | 100 | 352.5 | 0 | 14100 | C+S GST 18% I/P RD | 2538 | 16638 | 16638 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 902 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 40 | 100 | 197.87 | 0 | 7914.72 | C+S GST 18% I/P RD | 1424.64 | 9339.36 | 9339.36 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 702 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 40 | 100 | 80.83 | 0 | 3233.04 | C+S GST 18% I/P RD | 581.94 | 3814.98 | 3814.98 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 801 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 40 | 100 | 72.9 | 0 | 2916 | C+S GST 18% I/P RD | 524.88 | 3440.88 | 3440.88 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 801 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 40 | 100 | 94.42 | 0 | 3776.88 | C+S GST 18% I/P RD | 679.84 | 4456.72 | 4456.72 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 701 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 40 | 100 | 94.42 | 0 | 3776.88 | C+S GST 18% I/P RD | 679.84 | 4456.72 | 4456.72 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 801 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 40 | 100 | 59.08 | 0 | 2363.16 | C+S GST 18% I/P RD | 425.36 | 2788.52 | 2788.52 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 901 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 40 | 100 | 94.42 | 0 | 3776.88 | C+S GST 18% I/P RD | 679.84 | 4456.72 | 4456.72 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 701 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 40 | 100 | 72.9 | 0 | 2916 | C+S GST 18% I/P RD | 524.88 | 3440.88 | 3440.88 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 40 | 100 | 197.87 | 0 | 7914.72 | C+S GST 18% I/P RD | 1424.64 | 9339.36 | 9339.36 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 40 | 100 | 352.5 | 0 | 14100 | C+S GST 18% I/P RD | 2538 | 16638 | 16638 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 901 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 40 | 100 | 352.5 | 0 | 14100 | C+S GST 18% I/P RD | 2538 | 16638 | 16638 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 601 Living,Dining,Ent.Lobby | Italian Marble Mirror Polish- BCo | 345.201 | Sq.Ft | 35 | 100 | 302.05 | 0 | 12082.04 | C+S GST 18% I/P RD | 2174.76 | 14256.8 | 14256.8 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 501 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 35 | 100 | 63.79 | 0 | 2551.5 | C+S GST 18% I/P RD | 459.28 | 3010.78 | 3010.78 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 102 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 35 | 100 | 53.97 | 0 | 2158.7 | C+S GST 18% I/P RD | 388.56 | 2547.26 | 2547.26 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 35 | 100 | 173.13 | 0 | 6925.38 | C+S GST 18% I/P RD | 1246.56 | 8171.94 | 8171.94 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 602 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 35 | 100 | 70.72 | 0 | 2828.91 | C+S GST 18% I/P RD | 509.2 | 3338.11 | 3338.11 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 501 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 352.5 | Sq.Ft | 35 | 100 | 308.44 | 0 | 12337.5 | C+S GST 18% I/P RD | 2220.76 | 14558.26 | 14558.26 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 197.868 | Sq.Ft | 35 | 100 | 173.13 | 0 | 6925.38 | C+S GST 18% I/P RD | 1246.56 | 8171.94 | 8171.94 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 501 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 94.422 | Sq.Ft | 35 | 100 | 82.62 | 0 | 3304.77 | C+S GST 18% I/P RD | 594.86 | 3899.63 | 3899.63 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 601 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 96.294 | Sq.Ft | 35 | 100 | 84.26 | 0 | 3370.29 | C+S GST 18% I/P RD | 606.66 | 3976.95 | 3976.95 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 601 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 35 | 100 | 63.79 | 0 | 2551.5 | C+S GST 18% I/P RD | 459.28 | 3010.78 | 3010.78 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 102 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 35 | 100 | 70.72 | 0 | 2828.91 | C+S GST 18% I/P RD | 509.2 | 3338.11 | 3338.11 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 602 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 61.677 | Sq.Ft | 35 | 100 | 53.97 | 0 | 2158.7 | C+S GST 18% I/P RD | 388.56 | 2547.26 | 2547.26 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 501 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 35 | 100 | 51.69 | 0 | 2067.77 | C+S GST 18% I/P RD | 372.2 | 2439.97 | 2439.97 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish.- BCo | 69.066 | R.Ft | 35 | 100 | 60.43 | 0 | 2417.31 | C+S GST 18% I/P RD | 435.12 | 2852.43 | 2852.43 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 812 | 98129 | 10 Feb 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2145 | B 101 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 15.159 | R.Ft | 35 | 100 | 13.26 | 0 | 530.57 | C+S GST 18% I/P RD | 95.5 | 626.07 | 626.07 | Approved | 0 | 0 | 1594 | 10 Feb 2023
GANGA DHAM TOWERS | 1497 | 98116 | 09 Feb 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2060 | Site Expenses | Site Expenses -SO | 0.4176 | Month | 30000 | 100 | 0 | 0 | 12528 | CGST 0% URD I/P | 0 | 12528 | 12528 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 1497 | 98116 | 09 Feb 2023 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2060 | Site Expenses | Site Expenses -SO | 0.135 | Month | 30000 | 100 | 0 | 0 | 4050 | CGST 0% URD I/P | 0 | 4050 | 4050 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1056 | 98115 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1956 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 1055 | 98114 | 09 Feb 2023 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 1955 | DG Annual Maintenance Charges (Month) | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 105 | 09 Feb 2023
GANGA DHAM TOWERS | 804 | 98113 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2035 | B 901 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 960.8 | Sq.Ft | 55 | 100 | 0 | 0 | 52844 | C+S GST 18% I/P RD | 9511.92 | 62355.92 | 62355.92 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 804 | 98113 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2035 | B 801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 960.8 | Sq.Ft | 55 | 100 | 0 | 0 | 52844 | C+S GST 18% I/P RD | 9511.92 | 62355.92 | 62355.92 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 804 | 98113 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2035 | B 801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378.14 | R.Ft | 55 | 100 | 0 | 0 | 20797.7 | C+S GST 18% I/P RD | 3743.58 | 24541.28 | 24541.28 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 804 | 98113 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2035 | B 901 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378.14 | R.Ft | 55 | 100 | 0 | 0 | 20797.7 | C+S GST 18% I/P RD | 3743.58 | 24541.28 | 24541.28 | Approved | 0 | 0 | 0 | 09 Feb 2023
GANGA DHAM TOWERS | 805 | 98112 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2036 | B 801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 720.7 | Sq.Ft | 20 | 100 | 360.35 | 0 | 14414 | C+S GST 18% I/P RD | 2594.52 | 17008.52 | 17008.52 | Approved | 0 | 0 | 402 | 09 Feb 2023
GANGA DHAM TOWERS | 805 | 98112 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2036 | B 901 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 720.7 | Sq.Ft | 20 | 100 | 360.35 | 0 | 14414 | C+S GST 18% I/P RD | 2594.52 | 17008.52 | 17008.52 | Approved | 0 | 0 | 402 | 09 Feb 2023
GANGA DHAM TOWERS | 805 | 98112 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2036 | B 801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 402 | 09 Feb 2023
GANGA DHAM TOWERS | 805 | 98112 | 09 Feb 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2036 | B 901 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 402 | 09 Feb 2023
GANGA DHAM TOWERS | 389 | 98098 | 08 Feb 2023 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1941 | Loading / Unloading Expenses | Unloading of Tile Adhesive | 12.5 | Metric Tonnes | 200 | 100 | 0 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 0 | 08 Feb 2023
GANGA DHAM TOWERS | 1507 | 98082 | 07 Feb 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 1910 | A Bldg - Misc. Tiling work | Tiling work lumpsum BC | 0.5201 | No. | 192272.5 | 100 | 2500.02 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 4000 | 07 Feb 2023
GANGA DHAM TOWERS | 1507 | 98082 | 07 Feb 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 1910 | A Bldg - Misc. Tiling work | Tiling work lumpsum BC | 0.5201 | No. | 192272.5 | 100 | 2500.02 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 4000 | 07 Feb 2023
GANGA DHAM TOWERS | 1507 | 98082 | 07 Feb 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 1910 | A Bldg - Misc. Tiling work | Tiling work lumpsum BC | 0.5201 | No. | 192272.5 | 100 | 2500.02 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 4000 | 07 Feb 2023
GANGA DHAM TOWERS | 1507 | 98082 | 07 Feb 2023 |  | Kishan Enterprises | Kishan Enterprises | EV - 1910 | A Bldg - Misc. Tiling work | Tiling work lumpsum BC | 0.5201 | No. | 192272.5 | 100 | 2500.02 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 4000 | 07 Feb 2023
GANGA DHAM TOWERS | 1313 | 98080 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1987 | D 1203 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 68 | 07 Feb 2023
GANGA DHAM TOWERS | 1313 | 98080 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1987 | D 1204 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 68 | 07 Feb 2023
GANGA DHAM TOWERS | 1313 | 98080 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1987 | D 1205 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 68 | 07 Feb 2023
GANGA DHAM TOWERS | 1313 | 98080 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1987 | D 1202 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 295.983 | Sq.Ft | 4 | 100 | 29.6 | 0 | 1183.93 | CGST 0% URD I/P | 0 | 1183.93 | 1183.93 | Approved | 0 | 0 | 68 | 07 Feb 2023
GANGA DHAM TOWERS | 1313 | 98080 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1987 | D 1201 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 68 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 604 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 704 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 902 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 102 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 504 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 104 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 805 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 704 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 202 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 101 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 904 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 404 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 705 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 605 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 702 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 502 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 705 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 405 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 905 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 305 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 302 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 1004 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 105 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 804 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 605 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 904 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 1105 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 103 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 205 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 601 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 403.461 | Sq.Ft | 4 | 100 | 40.35 | 0 | 1613.84 | CGST 0% URD I/P | 0 | 1613.84 | 1613.84 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 304 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 27.9 | Sq.Ft | 4 | 100 | 2.79 | 0 | 111.6 | CGST 0% URD I/P | 0 | 111.6 | 111.6 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 802 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 804 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 604 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 1104 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 292.779 | Sq.Ft | 4 | 100 | 29.28 | 0 | 1171.12 | CGST 0% URD I/P | 0 | 1171.12 | 1171.12 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 402 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 56.277 | Sq.Ft | 4 | 100 | 5.63 | 0 | 225.11 | CGST 0% URD I/P | 0 | 225.11 | 225.11 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 698 | 98079 | 07 Feb 2023 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1988 | D 505 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 34.875 | Sq.Ft | 4 | 100 | 3.49 | 0 | 139.5 | CGST 0% URD I/P | 0 | 139.5 | 139.5 | Approved | 0 | 0 | 177 | 07 Feb 2023
GANGA DHAM TOWERS | 1296 | 98073 | 06 Feb 2023 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1909 | Miscellaneous expenses | Marketing Operating Expenses | 8.2084 | Month | 25000 | 8.37 | 0 | 0 | 17176 | CGST 0% URD I/P | 0 | 17176 | 17176 | Approved | 0 | 0 | 0 | 06 Feb 2023
GANGA DHAM TOWERS | 724 | 98072 | 06 Feb 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 1986 | A Ground Floor Parking Trimix work | Weld mesh fixing(L) BCo | 2516.35 | Sq.Ft | 1 | 100 | 62.91 | 0 | 2516.35 | CGST 0% URD I/P | 0 | 2516.35 | 2516.35 | Approved | 0 | 0 | 444 | 06 Feb 2023
GANGA DHAM TOWERS | 724 | 98072 | 06 Feb 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 1986 | A Ground Floor Parking Trimix work | Weld mesh fixing(L) BCo | 1922 | Sq.Ft | 1 | 100 | 48.05 | 0 | 1922 | CGST 0% URD I/P | 0 | 1922 | 1922 | Approved | 0 | 0 | 444 | 06 Feb 2023
GANGA DHAM TOWERS | 724 | 98072 | 06 Feb 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 1986 | A Ground Floor Parking Trimix work | Trimix Work - BC | 1922 | Sq.Ft | 9 | 100 | 432.45 | 0 | 17298 | CGST 0% URD I/P | 0 | 17298 | 17298 | Approved | 0 | 0 | 444 | 06 Feb 2023
GANGA DHAM TOWERS | 724 | 98072 | 06 Feb 2023 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 1986 | A Ground Floor Parking Trimix work | Trimix Work - BC | 2516.35 | Sq.Ft | 9 | 100 | 566.18 | 0 | 22647.15 | CGST 0% URD I/P | 0 | 22647.15 | 22647.15 | Approved | 0 | 0 | 444 | 06 Feb 2023
GANGA DHAM TOWERS | 1052 | 98068 | 06 Feb 2023 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1902 | Legal Consultancy - 1 No | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 06 Feb 2023
GANGA DHAM TOWERS | 522 | 98066 | 06 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1979 | B Bldg 2302 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1500 | 100 | 225 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 90 | 06 Feb 2023
GANGA DHAM TOWERS | 1404 | 98065 | 06 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 2014 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 4.2597 | Flat | 3353.52 | 100 | 357.12 | 0 | 14285 | CGST 0% URD I/P | 0 | 14285 | 14285 | Approved | 0 | 0 | 1160 | 06 Feb 2023
GANGA DHAM TOWERS | 1404 | 98065 | 06 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 2014 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 25.44 | Flat | 4000 | 100 | 2544 | 0 | 101760 | CGST 0% URD I/P | 0 | 101760 | 101760 | Approved | 0 | 0 | 1160 | 06 Feb 2023
GANGA DHAM TOWERS | 1406 | 98064 | 06 Feb 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1980 | Core Cutting For Fire Work - 18 to 26 Fl | Core Cutting Work 4" BCE | 70 | No. | 300 | 100 | 0 | 0 | 21000 | CGST 0% URD I/P | 0 | 21000 | 21000 | Approved | 0 | 0 | 210 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 602 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 202 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 402 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1702 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1102 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 2002 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 502 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1802 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1302 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1002 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1402 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 102 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 202 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 704 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 504 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 204 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 504 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1204 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 604 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26015 | 7.5 | 48.78 | 0 | 1951.13 | C+S GST 18% I/P RD | 351.2 | 2302.33 | 2302.33 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 704 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3899.52 | C+S GST 18% I/P RD | 701.92 | 4601.44 | 4601.44 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1201 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1901 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 2001 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1101 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 2401 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 101 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1801 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 201 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1701 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1001 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 2301 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1118 | 98063 | 06 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2190 | A 1301 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 26925 | 7.5 | 50.48 | 0 | 2019.38 | C+S GST 18% I/P RD | 363.48 | 2382.86 | 2382.86 | Approved | 0 | 0 | 886 | 06 Feb 2023
GANGA DHAM TOWERS | 1306 | 98047 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1947 | B Ground Floor Blockwork 5" (99 Level) | 5'' Blockwork Rate Diff. | 400 | Sq.Ft | 2 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 50 | 04 Feb 2023
GANGA DHAM TOWERS | 1306 | 98047 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1947 | B Ground Floor Blockwork 4" (99 Level) | 4'' Blockwork Rate Diff. | 1000 | Sq.Ft | 2 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 50 | 04 Feb 2023
GANGA DHAM TOWERS | 1306 | 98047 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1947 | B P1 Parking Floor Blockwork 4" (102 Level) | 4'' Blockwork Rate Diff. | 184 | Sq.Ft | 2 | 100 | 9.2 | 0 | 368 | CGST 0% URD I/P | 0 | 368 | 368 | Approved | 0 | 0 | 50 | 04 Feb 2023
GANGA DHAM TOWERS | 1306 | 98047 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1947 | B P2 Parking Floor Blockwork 4" (105 Level) | 4'' Blockwork Rate Diff. | 900 | Sq.Ft | 2 | 100 | 45 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 50 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A Ground Floor Blockwork 4" (99 Level) | 4'' Blockwork Rate Diff. | 773.69 | Sq.Ft | 2 | 100 | 38.68 | 0 | 1547.38 | CGST 0% URD I/P | 0 | 1547.38 | 1547.38 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A P2 Parking Floor Blockwork 4" (105 Level) | 4'' Blockwork Rate Diff. | 669.6154 | Sq.Ft | 2 | 100 | 33.48 | 0 | 1339.23 | CGST 0% URD I/P | 0 | 1339.23 | 1339.23 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A P1 Parking Floor Blockwork 4" (102 Level) | 4'' Blockwork Rate Diff. | 495.7654 | Sq.Ft | 2 | 100 | 24.79 | 0 | 991.53 | CGST 0% URD I/P | 0 | 991.53 | 991.53 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A P2 Parking Floor Blockwork 5" (105 Level) | 5'' Blockwork Rate Diff. | 230 | Sq.Ft | 2 | 100 | 11.5 | 0 | 460 | CGST 0% URD I/P | 0 | 460 | 460 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A P1 Parking Floor Blockwork 5" (102 Level) | 5'' Blockwork Rate Diff. | 132.6 | Sq.Ft | 2 | 100 | 6.63 | 0 | 265.2 | CGST 0% URD I/P | 0 | 265.2 | 265.2 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1321 | 98045 | 04 Feb 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1948 | A Ground Floor Blockwork 5" (99 Level) | 5'' Blockwork Rate Diff. | 531.4654 | Sq.Ft | 2 | 100 | 26.57 | 0 | 1062.93 | CGST 0% URD I/P | 0 | 1062.93 | 1062.93 | Approved | 0 | 0 | 57 | 04 Feb 2023
GANGA DHAM TOWERS | 1184 | 98043 | 04 Feb 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1946 | B Grond Floor External Sand Face Plaster | External Plaster- BC | 937.68 | Sq.Ft | 20 | 100 | 468.84 | 0 | 18753.6 | CGST 0% URD I/P | 0 | 18753.6 | 18753.6 | Approved | 0 | 0 | 472 | 04 Feb 2023
GANGA DHAM TOWERS | 1184 | 98043 | 04 Feb 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1946 | B P2 Floor External Sand Face Plaster | External Plaster- BC | 1422.29 | Sq.Ft | 20 | 100 | 711.15 | 0 | 28445.8 | CGST 0% URD I/P | 0 | 28445.8 | 28445.8 | Approved | 0 | 0 | 472 | 04 Feb 2023
GANGA DHAM TOWERS | 1038 | 98041 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2216 | B 702 Flat Door (L) | Quality Inspection (Bedroom Door) | 8 | No. | 2000 | 100 | 400 | 0 | 16000 | C+S GST 18% I/P RD | 2880 | 18880 | 18880 | Approved | 0 | 0 | 160 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 202 Flat Door (L) | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 203 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 304 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 502 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 101 Flat Door (L) | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 201 Flat Door (L) | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 501 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 402 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 301 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 204 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 103 Flat Door (L) | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 504 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 302 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 404 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 401 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 102 Flat Door (L) | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 403 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 303 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 503 Flat Door (L) - 1 No. | Quality Inspection (Main Door) | 1 | No. | 2200 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 303 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 502 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 504 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 403 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 501 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 503 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 301 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 404 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 402 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 304 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 401 Flat Door (L) - 1 No. | Quality Inspection (Safety Door) | 1 | No. | 2300 | 100 | 57.5 | 0 | 2300 | C+S GST 18% I/P RD | 414 | 2714 | 2714 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 303 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 304 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 603 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 803 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 1002 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 101 Flat Door (L) | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 303 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 102 Flat Door (L) | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 301 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 1201 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 6.5825 | No. | 2000 | 100 | 329.13 | 0 | 13165 | C+S GST 18% I/P RD | 2369.7 | 15534.7 | 15534.7 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 503 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 704 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 302 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 1003 Flat Door (L) - 1 No. - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 103 Flat Door (L) | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 701 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 401 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 403 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 404 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 8 | No. | 2000 | 100 | 400 | 0 | 16000 | C+S GST 18% I/P RD | 2880 | 18880 | 18880 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 502 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 702 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 1001 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 504 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 602 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 402 Flat Door (L) - 1 No. | Quality Inspection (Bedroom Door) | 7 | No. | 2000 | 100 | 350 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 404 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 103 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 402 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 203 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 104 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 302 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 502 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 304 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 102 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 403 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 301 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 503 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 401 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 504 Flat Door (L) - 1 No. | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 202 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 201 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1027 | 98040 | 04 Feb 2023 |  | GREENCON INFRATECH SOLUTION | GREENCON INFRATECH SOLUTION | EV - 2217 | A 101 Flat Door (L) | Quality Inspection (Toilet Door) | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 5843 | 04 Feb 2023
GANGA DHAM TOWERS | 1482 | 98039 | 04 Feb 2023 |  | RAHUL SHYAMKUMAR KHANDELWAL | RAHUL SHYAMKUMAR KHANDELWAL | EV - 1901 | Company Secretary | Company Secretary charges | 1 | Month | 20000 | 100 | 0 | 0 | 20000 | CGST 0% URD I/P | 0 | 20000 | 20000 | Approved | 0 | 0 | 2000 | 04 Feb 2023
GANGA DHAM TOWERS | 1383 | 98037 | 04 Feb 2023 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1898 | Professional Consultancy (Finalcial) | Professional Fees | 1 | Month | 116666.666 | 100 | 0 | 0 | 116666.67 | CGST 0% URD I/P | 0 | 116666.67 | 116666.67 | Approved | 0 | 0 | 11667 | 04 Feb 2023
GANGA DHAM TOWERS | 1452 | 98031 | 04 Feb 2023 |  | OMKAR PRADEEP MANE | OMKAR PRADEEP MANE | EV - 1897 | Professional Consultancy | Professional Fees | 1 | Month | 25000 | 100 | 0 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 2500 | 04 Feb 2023
GANGA DHAM TOWERS | 272 | 98022 | 04 Feb 2023 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1989 | A Bldg 35th slab (30th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 6336 | Sq.Ft | 190 | 100 | 30096 | 0 | 1203840 | C+S GST 18% I/P RD | 216691.2 | 1420531.2 | 1420531.2 | Approved | 0 | 0 | 24077 | 04 Feb 2023
GANGA DHAM TOWERS | 493 | 98021 | 04 Feb 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1944 | D Bldg Terrace Floor External Plaster | External Plaster- BC | 2503 | Sq.Ft | 28 | 100 | 1752.1 | 0 | 70084 | CGST 0% URD I/P | 0 | 70084 | 70084 | Approved | 0 | 0 | 701 | 04 Feb 2023
GANGA DHAM TOWERS | 455 | 98020 | 04 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1982 | A Bldg Flat No. 2003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1650 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 138 | 04 Feb 2023
GANGA DHAM TOWERS | 455 | 98020 | 04 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1982 | A Bldg Flat No. 1803 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1400 | 100 | 70 | 0 | 2800 | CGST 0% URD I/P | 0 | 2800 | 2800 | Approved | 0 | 0 | 138 | 04 Feb 2023
GANGA DHAM TOWERS | 455 | 98020 | 04 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1982 | A Bldg Flat No. 1703 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5 | No. | 1400 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 138 | 04 Feb 2023
GANGA DHAM TOWERS | 455 | 98020 | 04 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1982 | A Bldg Flat No. 1303 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1400 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 138 | 04 Feb 2023
GANGA DHAM TOWERS | 455 | 97999 | 03 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN |  | A Bldg Flat No. 503 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 |  | 0 | 0 | 47 | 03 Feb 2023
GANGA DHAM TOWERS | 455 | 97999 | 03 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN |  | A Bldg Flat No. 504 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 |  | 0 | 0 | 47 | 03 Feb 2023
GANGA DHAM TOWERS | 455 | 97999 | 03 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN |  | A Bldg Flat No. 1003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 47 | 03 Feb 2023
GANGA DHAM TOWERS | 455 | 97999 | 03 Feb 2023 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN |  | A Bldg Flat No. 703 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.25 | No. | 1200 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 |  | 0 | 0 | 47 | 03 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg North Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1302.606 | Sq.Ft | 1 | 100 | 32.57 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg South Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 1318.914 | Sq.Ft | 1 | 100 | 32.97 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg East Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 759.699 | Sq.Ft | 1 | 100 | 18.99 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1461 | 97990 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1975 | D Bldg West Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (L) | 544.779 | Sq.Ft | 1 | 100 | 13.62 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 464 | 02 Feb 2023
GANGA DHAM TOWERS | 1407 | 97989 | 02 Feb 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 2019 | EWS STP RCC | RCC Work STP | 39429.3333 | Ltrs | 3.75 | 40 | 1478.6 | 0 | 59144 | CGST 0% URD I/P | 0 | 59144 | 59144 | Approved | 0 | 0 | 828 | 02 Feb 2023
GANGA DHAM TOWERS | 1407 | 97989 | 02 Feb 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 2019 | EWS STP RCC | RCC Work STP | 15771.3333 | Ltrs | 3.75 | 40 | 591.42 | 0 | 23657 | CGST 0% URD I/P | 0 | 23657 | 23657 | Approved | 0 | 0 | 828 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 8th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 9th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 3rd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 1st Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 10th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 7th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg North Side 5th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1302.606 | Sq.Ft | 1 | 100 | 0 | 0 | 1302.61 | C+S GST 18% I/P RD | 234.46 | 1537.07 | 1537.07 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 2nd Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg South Side 11th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 1318.914 | Sq.Ft | 1 | 100 | 0 | 0 | 1318.91 | C+S GST 18% I/P RD | 237.4 | 1556.31 | 1556.31 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 4th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg West Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 544.779 | Sq.Ft | 1 | 100 | 0 | 0 | 544.78 | C+S GST 18% I/P RD | 98.06 | 642.84 | 642.84 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 6th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 1460 | 97988 | 02 Feb 2023 |  | ANIL MAHTO ENTERPRISES | ANIL MAHTO ENTERPRISES | EV - 1976 | D Bldg East Side 12th Flr Semi Acrylic Paint | 1 Coat Primer (Water Base) (M) | 759.699 | Sq.Ft | 1 | 100 | 0 | 0 | 759.7 | C+S GST 18% I/P RD | 136.74 | 896.44 | 896.44 | Approved | 0 | 0 | 0 | 02 Feb 2023
GANGA DHAM TOWERS | 145 | 97976 | 01 Feb 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 2016 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 165 | 01 Feb 2023
GANGA DHAM TOWERS | 145 | 97976 | 01 Feb 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 2016 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 165 | 01 Feb 2023
GANGA DHAM TOWERS | 145 | 97976 | 01 Feb 2023 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 2016 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 165 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 1102 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 18 | 100 | 33.55 | 0 | 1341.85 | C+S GST 18% I/P RD | 241.54 | 1583.39 | 1583.39 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 13 | 100 | 12.88 | 0 | 515.39 | C+S GST 18% I/P RD | 92.78 | 608.17 | 608.17 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Children Toilet Flooring | Vitrified Flooring -BC | 44.172 | Sq.Ft | 13 | 100 | 14.36 | 0 | 574.24 | C+S GST 18% I/P RD | 103.36 | 677.6 | 677.6 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.61 | Sq.Ft | 13 | 100 | 6.7 | 0 | 267.93 | C+S GST 18% I/P RD | 48.22 | 316.15 | 316.15 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 15 | 100 | 13.12 | 0 | 524.61 | C+S GST 18% I/P RD | 94.42 | 619.03 | 619.03 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 15 | 100 | 24.92 | 0 | 996.84 | C+S GST 18% I/P RD | 179.44 | 1176.28 | 1176.28 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 15 | 100 | 23.85 | 0 | 954.18 | C+S GST 18% I/P RD | 171.76 | 1125.94 | 1125.94 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 15 | 100 | 21.98 | 0 | 879.39 | C+S GST 18% I/P RD | 158.3 | 1037.69 | 1037.69 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Staff Toilet dado | Dado BC | 110.214 | Sq.Ft | 13 | 100 | 35.82 | 0 | 1432.78 | C+S GST 18% I/P RD | 257.9 | 1690.68 | 1690.68 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 13 | 100 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.466 | Sq.Ft | 13 | 100 | 15.43 | 0 | 617.06 | C+S GST 18% I/P RD | 111.08 | 728.14 | 728.14 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 35.847 | Sq.Ft | 13 | 100 | 11.65 | 0 | 466.01 | C+S GST 18% I/P RD | 83.88 | 549.89 | 549.89 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.288 | Sq.Ft | 13 | 100 | 14.72 | 0 | 588.74 | C+S GST 18% I/P RD | 105.98 | 694.72 | 694.72 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 1102 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Master Toilet dado | L Groove - BCV | 28.989 | R.Ft | 20 | 100 | 14.49 | 0 | 579.78 | C+S GST 18% I/P RD | 104.36 | 684.14 | 684.14 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Staff Toilet dado | L Groove - BCV | 14.634 | R.Ft | 20 | 100 | 7.32 | 0 | 292.68 | C+S GST 18% I/P RD | 52.68 | 345.36 | 345.36 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Powder Toilet dado | L Groove - BCV | 31.437 | R.Ft | 20 | 100 | 15.72 | 0 | 628.74 | C+S GST 18% I/P RD | 113.18 | 741.92 | 741.92 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Children Toilet dado | L Groove - BCV | 33.804 | R.Ft | 20 | 100 | 16.9 | 0 | 676.08 | C+S GST 18% I/P RD | 121.7 | 797.78 | 797.78 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 1102 Dry Balcony dado | L Groove - BCV | 5.022 | R.Ft | 20 | 100 | 2.51 | 0 | 100.44 | C+S GST 18% I/P RD | 18.08 | 118.52 | 118.52 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 1102 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 2302 Dry Balcony dado | L Groove - BCV | 5.022 | R.Ft | 20 | 100 | 2.51 | 0 | 100.44 | C+S GST 18% I/P RD | 18.08 | 118.52 | 118.52 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 2402 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 2402 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 2402 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | C+S GST 18% I/P RD | 131.26 | 860.44 | 860.44 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 2402 Children Toilet | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Parents Toilet dado | L Groove - BCV | 38.673 | R.Ft | 20 | 100 | 19.34 | 0 | 773.46 | C+S GST 18% I/P RD | 139.22 | 912.68 | 912.68 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 14 | 100 | 40.15 | 0 | 1606 | C+S GST 18% I/P RD | 289.08 | 1895.08 | 1895.08 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 14 | 100 | 42.27 | 0 | 1690.79 | C+S GST 18% I/P RD | 304.34 | 1995.13 | 1995.13 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 14 | 100 | 46.73 | 0 | 1869.08 | C+S GST 18% I/P RD | 336.44 | 2205.52 | 2205.52 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 14 | 100 | 30.67 | 0 | 1226.74 | C+S GST 18% I/P RD | 220.82 | 1447.56 | 1447.56 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 537 | 97975 | 01 Feb 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2011 | A 101 Dry Balcony dado | Dado BC | 71.055 | Sq.Ft | 14 | 100 | 24.87 | 0 | 994.77 | C+S GST 18% I/P RD | 179.06 | 1173.83 | 1173.83 | Approved | 0 | 0 | 238 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 604 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1302 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1802 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 2002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3331 | No. | 26015 | 45 | 97.49 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1801 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 2001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 2301 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 2401 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1301 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 1901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 1118 | 97974 | 01 Feb 2023 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2056 | A 601 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.3333 | No. | 26925 | 45 | 100.96 | 0 | 4038 | C+S GST 18% I/P RD | 726.84 | 4764.84 | 4764.84 | Approved | 0 | 0 | 957 | 01 Feb 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 1001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 601 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 457.5 | Sq.Ft | 20 | 100 | 228.75 | 0 | 9150 | C+S GST 18% I/P RD | 1647 | 10797 | 10797 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 601 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 1001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 631 | 97948 | 28 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1983 | A 1501 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 168.336 | R.Ft | 20 | 100 | 84.17 | 0 | 3366.72 | C+S GST 18% I/P RD | 606 | 3972.72 | 3972.72 | Approved | 0 | 0 | 534 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 402 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 601 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 55.4364 | R.Ft | 55 | 100 | 0 | 0 | 3049 | C+S GST 18% I/P RD | 548.82 | 3597.82 | 3597.82 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 1001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 224.4364 | R.Ft | 55 | 100 | 0 | 0 | 12344 | C+S GST 18% I/P RD | 2221.92 | 14565.92 | 14565.92 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 224 | R.Ft | 55 | 100 | 0 | 0 | 12320 | C+S GST 18% I/P RD | 2217.6 | 14537.6 | 14537.6 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 101 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 561.12 | R.Ft | 55 | 100 | 0 | 0 | 30861.6 | C+S GST 18% I/P RD | 5555.08 | 36416.68 | 36416.68 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 55 | R.Ft | 55 | 100 | 0 | 0 | 3025 | C+S GST 18% I/P RD | 544.5 | 3569.5 | 3569.5 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 1501 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 42 | R.Ft | 55 | 100 | 0 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 1001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 610 | Sq.Ft | 55 | 100 | 0 | 0 | 33550 | C+S GST 18% I/P RD | 6039 | 39589 | 39589 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 601 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 155 | Sq.Ft | 55 | 100 | 0 | 0 | 8525 | C+S GST 18% I/P RD | 1534.5 | 10059.5 | 10059.5 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 1501 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 64 | Sq.Ft | 55 | 100 | 0 | 0 | 3520 | C+S GST 18% I/P RD | 633.6 | 4153.6 | 4153.6 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1525 | Sq.Ft | 55 | 100 | 0 | 0 | 83875 | C+S GST 18% I/P RD | 15097.5 | 98972.5 | 98972.5 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 155 | Sq.Ft | 55 | 100 | 0 | 0 | 8525 | C+S GST 18% I/P RD | 1534.5 | 10059.5 | 10059.5 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 630 | 97947 | 28 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1950 | A 401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 155 | Sq.Ft | 55 | 100 | 0 | 0 | 8525 | C+S GST 18% I/P RD | 1534.5 | 10059.5 | 10059.5 | Approved | 0 | 0 | 0 | 28 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 2000.09 | C+S GST 18% I/P RD | 360.02 | 2360.11 | 2360.11 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | AMC Charges | 1 | No. | 24000 | 8.33 | 0 | 0 | 1999.99 | C+S GST 18% I/P RD | 360 | 2359.99 | 2359.99 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 363 | 97941 | 27 Jan 2023 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2290 | Weigh Bridge AMC Charges & Stamping Charges | Stamping Charges | 1 | No. | 20000 | 100 | 0 | 0 | 20000 | C+S GST 18% I/P RD | 3600 | 23600 | 23600 | Approved | 0 | 0 | 145 | 27 Jan 2023
GANGA DHAM TOWERS | 1420 | 97937 | 27 Jan 2023 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1945 | D Bldg Scaffolding for Ext. Plaster | Lumpsum work- DCW | 0.1582 | No. | 100000 | 100 | 395.5 | 0 | 15820 | CGST 0% URD I/P | 0 | 15820 | 15820 | Approved | 0 | 0 | 158 | 27 Jan 2023
GANGA DHAM TOWERS | 807 | 97934 | 25 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2062 | B-1002 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 484.74 | Sq.Ft | 20 | 100 | 242.37 | 0 | 9694.8 | C+S GST 18% I/P RD | 1745.06 | 11439.86 | 11439.86 | Approved | 0 | 0 | 142 | 25 Jan 2023
GANGA DHAM TOWERS | 807 | 97934 | 25 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 2062 | B-1002 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 222.9 | R.Ft | 20 | 100 | 111.45 | 0 | 4458 | C+S GST 18% I/P RD | 802.44 | 5260.44 | 5260.44 | Approved | 0 | 0 | 142 | 25 Jan 2023
GANGA DHAM TOWERS | 805 | 97933 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1933 | B 701 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 720.6 | Sq.Ft | 20 | 100 | 360.3 | 0 | 14412 | C+S GST 18% I/P RD | 2594.16 | 17006.16 | 17006.16 | Approved | 0 | 0 | 210 | 25 Jan 2023
GANGA DHAM TOWERS | 805 | 97933 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1933 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 45 | Sq.Ft | 20 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 210 | 25 Jan 2023
GANGA DHAM TOWERS | 805 | 97933 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1933 | B 701 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 210 | 25 Jan 2023
GANGA DHAM TOWERS | 806 | 97932 | 25 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1984 | B 702 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1615.8 | Sq.Ft | 55 | 100 | 0 | 0 | 88869 | C+S GST 18% I/P RD | 15996.42 | 104865.42 | 104865.42 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 806 | 97932 | 25 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1984 | B-1002 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 646.32 | Sq.Ft | 55 | 100 | 0 | 0 | 35547.6 | C+S GST 18% I/P RD | 6398.56 | 41946.16 | 41946.16 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 806 | 97932 | 25 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1984 | B-1002 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 222.9 | R.Ft | 55 | 100 | 0 | 0 | 12259.5 | C+S GST 18% I/P RD | 2206.72 | 14466.22 | 14466.22 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 806 | 97932 | 25 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1984 | B 702 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 557.25 | R.Ft | 55 | 100 | 0 | 0 | 30648.75 | C+S GST 18% I/P RD | 5516.78 | 36165.53 | 36165.53 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 804 | 97931 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1932 | B 701 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378.14 | R.Ft | 55 | 100 | 0 | 0 | 20797.7 | C+S GST 18% I/P RD | 3743.58 | 24541.28 | 24541.28 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 804 | 97931 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1932 | B 701 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 960.8 | Sq.Ft | 55 | 100 | 0 | 0 | 52844 | C+S GST 18% I/P RD | 9511.92 | 62355.92 | 62355.92 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 804 | 97931 | 25 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1932 | B 301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 679.6364 | Sq.Ft | 55 | 100 | 0 | 0 | 37380 | C+S GST 18% I/P RD | 6728.4 | 44108.4 | 44108.4 | Approved | 0 | 0 | 0 | 25 Jan 2023
GANGA DHAM TOWERS | 1479 | 97923 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2015 | Civil work | Kerb Stone Fixing | 246 | Sq.Ft | 207 | 100 | 0 | 0 | 50922 | C+S GST 18% I/P RD | 9165.96 | 60087.96 | 60087.96 | Approved | 0 | 0 | 439 | 24 Jan 2023
GANGA DHAM TOWERS | 1479 | 97923 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2015 | Civil work | Removing Curb Stone - Dld | 25.63 | Sq.Ft | 45 | 100 | 0 | 0 | 1153.35 | C+S GST 18% I/P RD | 207.6 | 1360.95 | 1360.95 | Approved | 0 | 0 | 439 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | Back coat Plaster- BRE | 360 | Sq.Ft | 90 | 100 | 810 | 0 | 32400 | C+S GST 18% I/P RD | 5832 | 38232 | 38232 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | 9" Brick Work | 162 | Sq.Ft | 144 | 100 | 583.2 | 0 | 23328 | C+S GST 18% I/P RD | 4199.04 | 27527.04 | 27527.04 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | Paving Block removing- DLd | 50 | Sq.Ft | 28 | 100 | 0 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | Excavation - AIE | 72 | Cu.Ft | 10 | 100 | 0 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | PCC (M+L)-DCW | 183 | Sq.Ft | 85.5 | 100 | 391.16 | 0 | 15646.5 | C+S GST 18% I/P RD | 2816.38 | 18462.88 | 18462.88 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | Granite Cladding - BCo | 246 | Sq.Ft | 612 | 100 | 3763.8 | 0 | 150552 | C+S GST 18% I/P RD | 27099.36 | 177651.36 | 177651.36 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 1478 | 97922 | 24 Jan 2023 |  | R K INTERIOR | R K INTERIOR | EV - 2051 | Civil Work | Murum Filling | 1 | Lumsum | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 2090 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1005 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1104 IPS Waterproofing | IPS W/P | 32 | Sq.Ft | 11 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1105 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 102 IPS Waterproofing | IPS W/P | 99.46 | Sq.Ft | 11 | 100 | 109.41 | 0 | 1094.06 | CGST 0% URD I/P | 0 | 1094.06 | 1094.06 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 902 IPS Waterproofing | IPS W/P | 61 | Sq.Ft | 11 | 100 | 67.1 | 0 | 671 | CGST 0% URD I/P | 0 | 671 | 671 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 605 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 602 IPS Waterproofing | IPS W/P | 61 | Sq.Ft | 11 | 100 | 67.1 | 0 | 671 | CGST 0% URD I/P | 0 | 671 | 671 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 705 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 802 IPS Waterproofing | IPS W/P | 61 | Sq.Ft | 11 | 100 | 67.1 | 0 | 671 | CGST 0% URD I/P | 0 | 671 | 671 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 104 IPS Waterproofing | IPS W/P | 69.67 | Sq.Ft | 11 | 100 | 76.64 | 0 | 766.37 | CGST 0% URD I/P | 0 | 766.37 | 766.37 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1002 IPS Waterproofing | IPS W/P | 61 | Sq.Ft | 11 | 100 | 67.1 | 0 | 671 | CGST 0% URD I/P | 0 | 671 | 671 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 103 IPS Waterproofing | IPS W/P | 69.67 | Sq.Ft | 11 | 100 | 76.64 | 0 | 766.37 | CGST 0% URD I/P | 0 | 766.37 | 766.37 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 805 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 604 IPS Waterproofing | IPS W/P | 32 | Sq.Ft | 11 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 905 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1004 IPS Waterproofing | IPS W/P | 32 | Sq.Ft | 11 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 101 IPS Waterproofing | IPS W/P | 103.9 | Sq.Ft | 11 | 100 | 114.29 | 0 | 1142.9 | CGST 0% URD I/P | 0 | 1142.9 | 1142.9 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1102 IPS Waterproofing | IPS W/P | 61.5455 | Sq.Ft | 11 | 100 | 67.7 | 0 | 677 | CGST 0% URD I/P | 0 | 677 | 677 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 105 IPS Waterproofing | IPS W/P | 103.9 | Sq.Ft | 11 | 100 | 114.29 | 0 | 1142.9 | CGST 0% URD I/P | 0 | 1142.9 | 1142.9 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 804 IPS Waterproofing | IPS W/P | 32 | Sq.Ft | 11 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 904 IPS Waterproofing | IPS W/P | 32 | Sq.Ft | 11 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 301 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 303 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 602 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 603 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 605 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 904 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 804 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 805 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 901 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 902 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 701 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1101 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 204 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 503 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 504 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 302 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 404 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 501 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 304 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1005 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1004 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 604 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 801 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1104 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 201 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 505 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 105 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 502 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 903 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 905 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 103 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 705 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 405 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 104 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 803 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1002 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1102 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 601 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 403 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 305 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 703 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 704 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1003 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 203 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 102 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 202 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 101 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 401 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 702 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 802 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1105 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 205 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1001 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 1103 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 653 | 97913 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 2298 | D 402 Bore Packing | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 787 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1205 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 37 | Sq.Ft | 22 | 100 | 81.4 | 0 | 814 | CGST 0% URD I/P | 0 | 814 | 814 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1205 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 40 | Sq.Ft | 22 | 100 | 88 | 0 | 880 | CGST 0% URD I/P | 0 | 880 | 880 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1203 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 32 | Sq.Ft | 22 | 100 | 70.4 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1204 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 26 | Sq.Ft | 22 | 100 | 57.2 | 0 | 572 | CGST 0% URD I/P | 0 | 572 | 572 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1203 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 26 | Sq.Ft | 22 | 100 | 57.2 | 0 | 572 | CGST 0% URD I/P | 0 | 572 | 572 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1201 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 40 | Sq.Ft | 22 | 100 | 88 | 0 | 880 | CGST 0% URD I/P | 0 | 880 | 880 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1201 Window Box Chemical Waterproofing - | Chemical Waterproofing (M+L).Sq.ft | 37 | Sq.Ft | 22 | 100 | 81.4 | 0 | 814 | CGST 0% URD I/P | 0 | 814 | 814 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1202 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 61 | Sq.Ft | 22 | 100 | 134.2 | 0 | 1342 | CGST 0% URD I/P | 0 | 1342 | 1342 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1204 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 32 | Sq.Ft | 22 | 100 | 70.4 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1202 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 50 | Sq.Ft | 22 | 100 | 110 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1201 IPS Waterproofing | IPS W/P | 103.9 | Sq.Ft | 15 | 100 | 155.85 | 0 | 1558.5 | CGST 0% URD I/P | 0 | 1558.5 | 1558.5 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1204 IPS Waterproofing - 69.67 Sq.Ft | IPS W/P | 69.67 | Sq.Ft | 15 | 100 | 104.51 | 0 | 1045.05 | CGST 0% URD I/P | 0 | 1045.05 | 1045.05 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1202 Window Box IPS Waterproofing | IPS W/P | 50 | Sq.Ft | 15 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1202 IPS Waterproofing | IPS W/P | 99.45 | Sq.Ft | 15 | 100 | 149.18 | 0 | 1491.75 | CGST 0% URD I/P | 0 | 1491.75 | 1491.75 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1205 IPS Waterproofing - 103.9 Sq.Ft | IPS W/P | 103.9 | Sq.Ft | 15 | 100 | 155.85 | 0 | 1558.5 | CGST 0% URD I/P | 0 | 1558.5 | 1558.5 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1320 | 97912 | 24 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1926 | D 1203 IPS Waterproofing - 69.67 Sq.Ft | IPS W/P | 69.6667 | Sq.Ft | 15 | 100 | 104.5 | 0 | 1045 | CGST 0% URD I/P | 0 | 1045 | 1045 | Approved | 0 | 0 | 158 | 24 Jan 2023
GANGA DHAM TOWERS | 1334 | 97911 | 24 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2251 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 148 | Mtrs | 90 | 100 | 333 | 0 | 13320 | C+S GST 18% I/P RD | 2397.6 | 15717.6 | 15717.6 | Approved | 0 | 0 | 253 | 24 Jan 2023
GANGA DHAM TOWERS | 1334 | 97911 | 24 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2251 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 120sqmm-UTI | 45 | Mtrs | 65 | 100 | 73.13 | 0 | 2925 | C+S GST 18% I/P RD | 526.5 | 3451.5 | 3451.5 | Approved | 0 | 0 | 253 | 24 Jan 2023
GANGA DHAM TOWERS | 1334 | 97911 | 24 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2251 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 95sqmm-DCH | 34 | Mtrs | 55 | 100 | 46.75 | 0 | 1870 | C+S GST 18% I/P RD | 336.6 | 2206.6 | 2206.6 | Approved | 0 | 0 | 253 | 24 Jan 2023
GANGA DHAM TOWERS | 1334 | 97911 | 24 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2251 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 240sqmm-UTI | 80 | Mtrs | 90 | 100 | 180 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 253 | 24 Jan 2023
GANGA DHAM TOWERS | 813 | 97910 | 24 Jan 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 1917 | D 1st Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 9 | 24 Jan 2023
GANGA DHAM TOWERS | 813 | 97910 | 24 Jan 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 1917 | D 5th Floor Lobby Ghadai work | Ghadai work- BCP | 230.78 | Sq.Ft | 2 | 100 | 46.16 | 0 | 461.56 | CGST 0% URD I/P | 0 | 461.56 | 461.56 | Approved | 0 | 0 | 9 | 24 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 601 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 904 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 804 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1103 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1003 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 803 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 801 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 902 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1101 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1102 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1005 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 702 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1001 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1105 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 802 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 901 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 703 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 704 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1004 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26.8421 | Sq.Ft | 9.5 | 100 | 25.5 | 0 | 255 | CGST 0% URD I/P | 0 | 255 | 255 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1104 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 603 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26.8421 | Sq.Ft | 9.5 | 100 | 25.5 | 0 | 255 | CGST 0% URD I/P | 0 | 255 | 255 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 903 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 26 | Sq.Ft | 9.5 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 805 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 1002 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 602 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 50 | Sq.Ft | 9.5 | 100 | 47.5 | 0 | 475 | CGST 0% URD I/P | 0 | 475 | 475 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 905 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 770 | 97898 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1918 | D 705 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 37.0526 | Sq.Ft | 9.5 | 100 | 35.2 | 0 | 352 | CGST 0% URD I/P | 0 | 352 | 352 | Approved | 0 | 0 | 91 | 23 Jan 2023
GANGA DHAM TOWERS | 1312 | 97897 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1924 | D 1202 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 2 | 100 | 69.62 | 0 | 696.2 | C+S GST 0% I/P RD | 0 | 696.2 | 696.2 | Approved | 0 | 0 | 39 | 23 Jan 2023
GANGA DHAM TOWERS | 1312 | 97897 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1924 | D 1205 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 2 | 100 | 94.79 | 0 | 947.86 | C+S GST 0% I/P RD | 0 | 947.86 | 947.86 | Approved | 0 | 0 | 39 | 23 Jan 2023
GANGA DHAM TOWERS | 1312 | 97897 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1924 | D 1203 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 2 | 100 | 67.73 | 0 | 677.26 | C+S GST 0% I/P RD | 0 | 677.26 | 677.26 | Approved | 0 | 0 | 39 | 23 Jan 2023
GANGA DHAM TOWERS | 1312 | 97897 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1924 | D 1204 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 2 | 100 | 67.73 | 0 | 677.26 | C+S GST 0% I/P RD | 0 | 677.26 | 677.26 | Approved | 0 | 0 | 39 | 23 Jan 2023
GANGA DHAM TOWERS | 1312 | 97897 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1924 | D 1201 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 2 | 100 | 94.79 | 0 | 947.86 | C+S GST 0% I/P RD | 0 | 947.86 | 947.86 | Approved | 0 | 0 | 39 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1105 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1004 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1003 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1104 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1002 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 1 | 100 | 0 | 0 | 348.1 | CGST 0% URD I/P | 0 | 348.1 | 348.1 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1103 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 705 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1001 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 803 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 804 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 701 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 903 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 901 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 503 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 504 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 902 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 1 | 100 | 0 | 0 | 348.1 | CGST 0% URD I/P | 0 | 348.1 | 348.1 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1101 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1102 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 1 | 100 | 0 | 0 | 348.1 | CGST 0% URD I/P | 0 | 348.1 | 348.1 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 801 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 704 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1105 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 805 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 905 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 103 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 702 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 1 | 100 | 0 | 0 | 348.1 | CGST 0% URD I/P | 0 | 348.1 | 348.1 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 104 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 703 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 604 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 603 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1004 Internal Ghadai work | Ghadai work- BCP | 338.63 | Sq.Ft | 1 | 100 | 0 | 0 | 338.63 | CGST 0% URD I/P | 0 | 338.63 | 338.63 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 802 Internal Ghadai work | Ghadai work- BCP | 348.1 | Sq.Ft | 1 | 100 | 0 | 0 | 348.1 | CGST 0% URD I/P | 0 | 348.1 | 348.1 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1005 Internal Ghadai work | Ghadai work- BCP | 473.93 | Sq.Ft | 1 | 100 | 0 | 0 | 473.93 | CGST 0% URD I/P | 0 | 473.93 | 473.93 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 103 Floor Chemical Waterproofing | Chemical Waterproofing (L) | 69.67 | Sq.Ft | 4 | 100 | 27.87 | 0 | 278.68 | CGST 0% URD I/P | 0 | 278.68 | 278.68 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1002 Chemical Waterproofing | Chemical Waterproofing (L) | 61 | Sq.Ft | 4 | 100 | 24.4 | 0 | 244 | CGST 0% URD I/P | 0 | 244 | 244 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 705 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 804 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 904 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 101 Chemical Waterproofing | Chemical Waterproofing (L) | 103.9 | Sq.Ft | 4 | 100 | 41.56 | 0 | 415.6 | CGST 0% URD I/P | 0 | 415.6 | 415.6 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1005 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1102 Chemical Waterproofing | Chemical Waterproofing (L) | 61 | Sq.Ft | 4 | 100 | 24.4 | 0 | 244 | CGST 0% URD I/P | 0 | 244 | 244 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 104 Floor Chemical Waterproofing | Chemical Waterproofing (L) | 69.67 | Sq.Ft | 4 | 100 | 27.87 | 0 | 278.68 | CGST 0% URD I/P | 0 | 278.68 | 278.68 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 602 Chemical Waterproofing | Chemical Waterproofing (L) | 61 | Sq.Ft | 4 | 100 | 24.4 | 0 | 244 | CGST 0% URD I/P | 0 | 244 | 244 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 802 Chemical Waterproofing | Chemical Waterproofing (L) | 61 | Sq.Ft | 4 | 100 | 24.4 | 0 | 244 | CGST 0% URD I/P | 0 | 244 | 244 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 102 Floor Chemical Waterproofing | Chemical Waterproofing (L) | 99.46 | Sq.Ft | 4 | 100 | 39.78 | 0 | 397.84 | CGST 0% URD I/P | 0 | 397.84 | 397.84 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1104 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 704 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 105 Floor Chemical Waterproofing | Chemical Waterproofing (L) | 103.9 | Sq.Ft | 4 | 100 | 41.56 | 0 | 415.6 | CGST 0% URD I/P | 0 | 415.6 | 415.6 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 605 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 905 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 805 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 902 Chemical Waterproofing | Chemical Waterproofing (L) | 61 | Sq.Ft | 4 | 100 | 24.4 | 0 | 244 | CGST 0% URD I/P | 0 | 244 | 244 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 604 Chemical Waterproofing | Chemical Waterproofing (L) | 32 | Sq.Ft | 4 | 100 | 12.8 | 0 | 128 | CGST 0% URD I/P | 0 | 128 | 128 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 905 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1002 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1102 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1105 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 703 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1104 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 803 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 102 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 604 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 805 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 804 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 704 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 903 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1005 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 104 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 602 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 605 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 101 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 702 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1003 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1004 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 802 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 904 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 603 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 1103 Bore Packing | Perma Eazee Coat W/P (M+L) | 4 | No. | 70 | 100 | 28 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 105 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 902 Bore Packing | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 103 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 653 | 97896 | 23 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1919 | D 705 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 234 | 23 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Dry Balcony dado | L Groove - BCV | 3.834 | R.Ft | 20 | 100 | 1.92 | 0 | 76.68 | C+S GST 18% I/P RD | 13.8 | 90.48 | 90.48 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Parents Toilet dado | L Groove - BCV | 21.996 | R.Ft | 20 | 100 | 11 | 0 | 439.92 | C+S GST 18% I/P RD | 79.18 | 519.1 | 519.1 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Master Toilet dado | L Groove - BCV | 38.61 | R.Ft | 20 | 100 | 19.31 | 0 | 772.2 | C+S GST 18% I/P RD | 139 | 911.2 | 911.2 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Children Toilet Dado | L Groove - BCV | 38.7 | R.Ft | 20 | 100 | 19.35 | 0 | 774 | C+S GST 18% I/P RD | 139.32 | 913.32 | 913.32 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Powder Toilet dado | L Groove - BCV | 32.238 | R.Ft | 20 | 100 | 16.12 | 0 | 644.76 | C+S GST 18% I/P RD | 116.06 | 760.82 | 760.82 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 103 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 13 | 100 | 39.6 | 0 | 1583.83 | C+S GST 18% I/P RD | 285.08 | 1868.91 | 1868.91 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 103 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 13 | 100 | 7.32 | 0 | 292.85 | C+S GST 18% I/P RD | 52.72 | 345.57 | 345.57 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.11 | Sq.Ft | 24 | 100 | 25.87 | 0 | 1034.64 | C+S GST 18% I/P RD | 186.24 | 1220.88 | 1220.88 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 2104 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 41.265 | Sq.Ft | 24 | 100 | 24.76 | 0 | 990.36 | C+S GST 18% I/P RD | 178.26 | 1168.62 | 1168.62 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 103 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 13 | 100 | 12.2 | 0 | 488.01 | C+S GST 18% I/P RD | 87.84 | 575.85 | 575.85 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 551 | 97881 | 21 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1931 | A 103 Terrace Vitrified Flooring | Vitrified Flooring -BC | 118.863 | Sq.Ft | 15 | 100 | 44.57 | 0 | 1782.95 | C+S GST 18% I/P RD | 320.94 | 2103.89 | 2103.89 | Approved | 0 | 0 | 98 | 21 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1101 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 303 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 304 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 805 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1104 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 602 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 602 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 504 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 804 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 702 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 702 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 105 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 503 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 802 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 802 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 401 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 403 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 505 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 605 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1002 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 705 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 202 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 202 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 502 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 502 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1105 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 501 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 501 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 102 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 102 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 301 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 402 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 402 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 404 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 201 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 101 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 604 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 103 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 904 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1004 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 204 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 905 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1005 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1102 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1102 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 104 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 1002 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 305 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 203 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 205 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 902 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 902 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 704 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 302 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D 302 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1101 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1005 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D605 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D804 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D904 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D701 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1001 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1105 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1104 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D104 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D805 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D803 Chemical Grouting | Chemical Grouting.- BC | 247 | Sq.Ft | 1 | 100 | 24.7 | 0 | 247 | CGST 0% URD I/P | 0 | 247 | 247 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D901 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D1004 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D705 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D801 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D905 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 653 | 97880 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1922 | D704 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 225 | 20 Jan 2023
GANGA DHAM TOWERS | 699 | 97878 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1927 | D Bldg Lift Pit Waterproofing (L) | Chemical W/P - Bco | 396.38 | Sq.Ft | 19 | 100 | 753.12 | 0 | 7531.22 | CGST 0% URD I/P | 0 | 7531.22 | 7531.22 | Approved | 0 | 0 | 107 | 20 Jan 2023
GANGA DHAM TOWERS | 699 | 97878 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1927 | D Bldg Lift Pit Waterproofing (L) | IPS W/P BC | 289.01 | Sq.Ft | 11 | 100 | 317.91 | 0 | 3179.11 | CGST 0% URD I/P | 0 | 3179.11 | 3179.11 | Approved | 0 | 0 | 107 | 20 Jan 2023
GANGA DHAM TOWERS | 1312 | 97877 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1925 | D1201 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 2 | 100 | 96.38 | 0 | 963.8 | C+S GST 0% I/P RD | 0 | 963.8 | 963.8 | Approved | 0 | 0 | 26 | 20 Jan 2023
GANGA DHAM TOWERS | 1312 | 97877 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1925 | D1205 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 2 | 100 | 96.38 | 0 | 963.8 | C+S GST 0% I/P RD | 0 | 963.8 | 963.8 | Approved | 0 | 0 | 26 | 20 Jan 2023
GANGA DHAM TOWERS | 1312 | 97877 | 20 Jan 2023 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1925 | D1204 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 2 | 100 | 69.55 | 0 | 695.52 | C+S GST 0% I/P RD | 0 | 695.52 | 695.52 | Approved | 0 | 0 | 26 | 20 Jan 2023
GANGA DHAM TOWERS | 1377 | 97874 | 20 Jan 2023 |  | GREEN PLANET SOLUTION | GREEN PLANET SOLUTION | EV - 1831 | A Garbage Chute Collection System | Garbage Chute (Dry/Wet) | 1 | No. | 900000 | 10 | 0 | 0 | 90000 | C+S GST 12% I/P RD | 10800 | 100800 | 100800 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 1377 | 97874 | 20 Jan 2023 |  | GREEN PLANET SOLUTION | GREEN PLANET SOLUTION | EV - 1831 | A Garbage Chute Collection System | Garbage Chute (Dry/Wet) | 1 | No. | 900000 | 40 | 0 | 0 | 360000 | C+S GST 12% I/P RD | 43200 | 403200 | 403200 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 1118 | 97871 | 20 Jan 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1915 | A 2904 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236 | C+S GST 18% I/P RD | 2922.48 | 19158.48 | 19158.48 | Approved | 0 | 0 | 638 | 20 Jan 2023
GANGA DHAM TOWERS | 1118 | 97871 | 20 Jan 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1915 | A 2902 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236 | C+S GST 18% I/P RD | 2922.48 | 19158.48 | 19158.48 | Approved | 0 | 0 | 638 | 20 Jan 2023
GANGA DHAM TOWERS | 1118 | 97871 | 20 Jan 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1915 | A 2901 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 47964 | 35 | 419.69 | 0 | 16787 | C+S GST 18% I/P RD | 3021.66 | 19808.66 | 19808.66 | Approved | 0 | 0 | 638 | 20 Jan 2023
GANGA DHAM TOWERS | 1118 | 97871 | 20 Jan 2023 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1915 | A 2903 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 41490 | 35 | 363.04 | 0 | 14521.5 | C+S GST 18% I/P RD | 2613.88 | 17135.38 | 17135.38 | Approved | 0 | 0 | 638 | 20 Jan 2023
GANGA DHAM TOWERS | 1382 | 97870 | 20 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1913 | A P3 Comm & Guest Toilet Plumbing Work | Toilet Plumbing work | 1 | No. | 6000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 240 | 20 Jan 2023
GANGA DHAM TOWERS | 1382 | 97870 | 20 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1913 | A GF Comm & Guest Toilet Plumbing Work | Toilet Plumbing work | 1 | No. | 6000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 240 | 20 Jan 2023
GANGA DHAM TOWERS | 1382 | 97870 | 20 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1913 | A P1 Comm & Guest Toilet Plumbing Work | Toilet Plumbing work | 1 | No. | 6000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 240 | 20 Jan 2023
GANGA DHAM TOWERS | 1382 | 97870 | 20 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1913 | A P2 Comm & Guest Toilet Plumbing Work | Toilet Plumbing work | 1 | No. | 6000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 240 | 20 Jan 2023
GANGA DHAM TOWERS | 804 | 97869 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1936 | B 301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 281.1636 | Sq.Ft | 55 | 100 | 0 | 0 | 15464 | C+S GST 18% I/P RD | 2783.52 | 18247.52 | 18247.52 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 804 | 97869 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1936 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 281.1636 | Sq.Ft | 55 | 100 | 0 | 0 | 15464 | C+S GST 18% I/P RD | 2783.52 | 18247.52 | 18247.52 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 804 | 97869 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1936 | B 301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378.1273 | R.Ft | 55 | 100 | 0 | 0 | 20797 | C+S GST 18% I/P RD | 3743.46 | 24540.46 | 24540.46 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 804 | 97869 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1936 | B 101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 378 | R.Ft | 55 | 100 | 0 | 0 | 20790 | C+S GST 18% I/P RD | 3742.2 | 24532.2 | 24532.2 | Approved | 0 | 0 | 0 | 20 Jan 2023
GANGA DHAM TOWERS | 805 | 97868 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1935 | B 301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 720.6 | Sq.Ft | 20 | 100 | 360.3 | 0 | 14412 | C+S GST 18% I/P RD | 2594.16 | 17006.16 | 17006.16 | Approved | 0 | 0 | 402 | 20 Jan 2023
GANGA DHAM TOWERS | 805 | 97868 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1935 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 720.6 | Sq.Ft | 20 | 100 | 360.3 | 0 | 14412 | C+S GST 18% I/P RD | 2594.16 | 17006.16 | 17006.16 | Approved | 0 | 0 | 402 | 20 Jan 2023
GANGA DHAM TOWERS | 805 | 97868 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1935 | B 301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 402 | 20 Jan 2023
GANGA DHAM TOWERS | 805 | 97868 | 20 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1935 | B 101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 283.605 | R.Ft | 20 | 100 | 141.8 | 0 | 5672.1 | C+S GST 18% I/P RD | 1020.98 | 6693.08 | 6693.08 | Approved | 0 | 0 | 402 | 20 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Soil Analysis Test- SOS | 16 | No. | 1500 | 25 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Air Test SOS | 16 | No. | 1500 | 25 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | NOise Test Day SOS | 32 | No. | 125 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Effluent Sample | 4 | No. | 1000 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Effluent Sample | 4 | No. | 1000 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Stack Monitoring Report SOS | 8 | No. | 900 | 25 | 0 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Water Testing report - SOS | 8 | No. | 1000 | 25 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 799 | 97858 | 19 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1767 | Test Report ( 2020-21) - | Noise Test Night SOS | 32 | No. | 175 | 25 | 0 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 202 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 95sqmm-DCH | 15 | Mtrs | 55 | 100 | 20.63 | 0 | 825 | C+S GST 18% I/P RD | 148.5 | 973.5 | 973.5 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 120sqmm X 3.5 core cable (M+L) | 10 | No. | 900 | 100 | 225 | 0 | 9000 | C+S GST 18% I/P RD | 1620 | 10620 | 10620 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Change Over Panel Fixing - UTI | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Change Over Panel Fixing - UTI | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Panel Fixing (L) | 5 | No. | 1500 | 100 | 187.5 | 0 | 7500 | C+S GST 18% I/P RD | 1350 | 8850 | 8850 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Panel Fixing (L) | 3 | No. | 1500 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 120sqmm-UTI | 46 | Mtrs | 65 | 100 | 74.75 | 0 | 2990 | C+S GST 18% I/P RD | 538.2 | 3528.2 | 3528.2 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 120sqmm-UTI | 80 | Mtrs | 65 | 100 | 130 | 0 | 5200 | C+S GST 18% I/P RD | 936 | 6136 | 6136 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 95sqmm X 3.5 core cable (M+L) | 3 | No. | 900 | 100 | 67.5 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 95sqmm X 3.5 core cable (M+L) | 3 | No. | 900 | 100 | 0 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 300sqmm X 3.5 core cable (M+L) | 8 | No. | 1700 | 100 | 340 | 0 | 13600 | C+S GST 18% I/P RD | 2448 | 16048 | 16048 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 57 | Mtrs | 90 | 100 | 128.25 | 0 | 5130 | C+S GST 18% I/P RD | 923.4 | 6053.4 | 6053.4 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 240sqmm X 3.5 core cable (M+L) | 15 | No. | 1700 | 100 | 637.5 | 0 | 25500 | C+S GST 18% I/P RD | 4590 | 30090 | 30090 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 1334 | 97854 | 19 Jan 2023 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 2022 | A,B,D Meter Room to Substation LT Cable | End Termination 150sqmm X 3.5 core cable (M+L) | 3 | No. | 900 | 100 | 67.5 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 903 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1404 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1502 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1302 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 504 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 601 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 901 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 502 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1003 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1303 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1701 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 603 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 604 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1001 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1703 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 101 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 103 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1704 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1402 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 403 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 903 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 204 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 404 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1102 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1101 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1103 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1504 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 203 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1002 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1301 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 701 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 804 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1401 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1004 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 503 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1604 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 303 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 602 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 904 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1601 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1602 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1503 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 902 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 301 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 801 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1501 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1702 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 202 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 104 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 102 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 401 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1104 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1202 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 402 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 803 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 304 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 702 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1203 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1603 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1204 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1403 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1201 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 302 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 703 Terrace Railling | S.S. Railing (M)- BC | 25.49 | R.Ft | 1336 | 100 | 0 | 0 | 34054.64 | C+S GST 18% I/P RD | 6129.84 | 40184.48 | 40184.48 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 704 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 802 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 201 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 501 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 967 | 97853 | 19 Jan 2023 |  | HELIOS (Material) | HELIOS (Material) | EV - 2254 | A 1304 Terrace Railling | S.S. Railing (M)- BC | 22.51 | R.Ft | 1336 | 100 | 0 | 0 | 30073.36 | C+S GST 18% I/P RD | 5413.2 | 35486.56 | 35486.56 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 551 | 97852 | 19 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 2104 Dry Balcony dado | Dado BC | 80.361 | Sq.Ft | 28 | 100 | 56.25 | 0 | 2250.11 | C+S GST 18% I/P RD | 405.02 | 2655.13 | 2655.13 |  | 0 | 0 | 77 | 19 Jan 2023
GANGA DHAM TOWERS | 551 | 97852 | 19 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 2104 Parents Toilet dado | Dado BC | 77.931 | Sq.Ft | 28 | 100 | 54.55 | 0 | 2182.07 | C+S GST 18% I/P RD | 392.78 | 2574.85 | 2574.85 |  | 0 | 0 | 77 | 19 Jan 2023
GANGA DHAM TOWERS | 551 | 97852 | 19 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 2104 Parents Toilet dado | Dado BC | 95.436 | Sq.Ft | 28 | 100 | 66.81 | 0 | 2672.21 | C+S GST 18% I/P RD | 481 | 3153.21 | 3153.21 |  | 0 | 0 | 77 | 19 Jan 2023
GANGA DHAM TOWERS | 551 | 97852 | 19 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 103 Powder Toilet dado | L Groove - BCV | 5.166 | R.Ft | 20 | 100 | 2.58 | 0 | 103.32 | C+S GST 18% I/P RD | 18.6 | 121.92 | 121.92 |  | 0 | 0 | 77 | 19 Jan 2023
GANGA DHAM TOWERS | 551 | 97852 | 19 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 103 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 |  | 0 | 0 | 77 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 29.98 | R.Ft | 60 | 100 | 44.97 | 0 | 1798.8 | C+S GST 18% I/P RD | 323.78 | 2122.58 | 2122.58 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Staff Toilet dado | L Groove - BCV | 14.607 | R.Ft | 20 | 100 | 7.3 | 0 | 292.14 | C+S GST 18% I/P RD | 52.58 | 344.72 | 344.72 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | C+S GST 18% I/P RD | 131.26 | 860.44 | 860.44 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Children Toilet | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 537 | 97851 | 19 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Dry Balcony dado | L Groove - BCV | 5.022 | R.Ft | 20 | 100 | 2.51 | 0 | 100.44 | C+S GST 18% I/P RD | 18.08 | 118.52 | 118.52 |  | 0 | 0 | 46 | 19 Jan 2023
GANGA DHAM TOWERS | 149 | 97850 | 19 Jan 2023 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1861 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3966 | No. | 4 | 100 | 0 | 0 | 15864 | CGST 0% URD I/P | 0 | 15864 | 15864 | Approved | 0 | 0 | 0 | 19 Jan 2023
GANGA DHAM TOWERS | 1428 | 97847 | 19 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1981 | Sales office Plumbing Maintenance Work | Plumber. | 4 | Day | 800 | 100 | 80 | 0 | 3200 | CGST 0% URD I/P | 0 | 3200 | 3200 | Approved | 0 | 0 | 32 | 19 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 147.1 | Sq.Ft | 20 | 100 | 73.55 | 0 | 2942 | C+S GST 18% I/P RD | 529.56 | 3471.56 | 3471.56 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 295 | Sq.Ft | 20 | 100 | 147.5 | 0 | 5900 | C+S GST 18% I/P RD | 1062 | 6962 | 6962 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 117.25 | Sq.Ft | 20 | 100 | 58.63 | 0 | 2345 | C+S GST 18% I/P RD | 422.1 | 2767.1 | 2767.1 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 234 | Sq.Ft | 20 | 100 | 117 | 0 | 4680 | C+S GST 18% I/P RD | 842.4 | 5522.4 | 5522.4 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 381.25 | Sq.Ft | 20 | 100 | 190.63 | 0 | 7625 | C+S GST 18% I/P RD | 1372.5 | 8997.5 | 8997.5 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 156 | R.Ft | 20 | 100 | 78 | 0 | 3120 | C+S GST 18% I/P RD | 561.6 | 3681.6 | 3681.6 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 632 | 97843 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1934 | A 303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 140 | R.Ft | 20 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 322 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 117.3273 | Sq.Ft | 55 | 100 | 0 | 0 | 6453 | C+S GST 18% I/P RD | 1161.54 | 7614.54 | 7614.54 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 117.3273 | Sq.Ft | 55 | 100 | 0 | 0 | 6453 | C+S GST 18% I/P RD | 1161.54 | 7614.54 | 7614.54 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 147.1273 | Sq.Ft | 55 | 100 | 0 | 0 | 8092 | C+S GST 18% I/P RD | 1456.56 | 9548.56 | 9548.56 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 208 | R.Ft | 55 | 100 | 0 | 0 | 11440 | C+S GST 18% I/P RD | 2059.2 | 13499.2 | 13499.2 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 629 | 97842 | 18 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1937 | A 303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 186 | R.Ft | 55 | 100 | 0 | 0 | 10230 | C+S GST 18% I/P RD | 1841.4 | 12071.4 | 12071.4 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 103 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 14 | 100 | 41.27 | 0 | 1650.85 | C+S GST 18% I/P RD | 297.16 | 1948.01 | 1948.01 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 103 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 14 | 100 | 26.85 | 0 | 1073.9 | C+S GST 18% I/P RD | 193.3 | 1267.2 | 1267.2 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 2104 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 24 | 100 | 26.16 | 0 | 1046.3 | C+S GST 18% I/P RD | 188.34 | 1234.64 | 1234.64 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 2104 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | C+S GST 18% I/P RD | 93.86 | 615.28 | 615.28 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 103 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 15 | 100 | 19.67 | 0 | 786.78 | C+S GST 18% I/P RD | 141.62 | 928.4 | 928.4 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 551 | 97841 | 18 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1930 | A 103 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 15 | 100 | 13.26 | 0 | 530.42 | C+S GST 18% I/P RD | 95.48 | 625.9 | 625.9 | Approved | 0 | 0 | 56 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 173.5818 | Sq.Ft | 55 | 100 | 0 | 0 | 9547 | C+S GST 18% I/P RD | 1718.46 | 11265.46 | 11265.46 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 402 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 173.5818 | Sq.Ft | 55 | 100 | 0 | 0 | 9547 | C+S GST 18% I/P RD | 1718.46 | 11265.46 | 11265.46 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 902 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 173.5818 | Sq.Ft | 55 | 100 | 0 | 0 | 9547 | C+S GST 18% I/P RD | 1718.46 | 11265.46 | 11265.46 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 902 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 222.8909 | R.Ft | 55 | 100 | 0 | 0 | 12259 | C+S GST 18% I/P RD | 2206.62 | 14465.62 | 14465.62 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 402 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 222.8909 | R.Ft | 55 | 100 | 0 | 0 | 12259 | C+S GST 18% I/P RD | 2206.62 | 14465.62 | 14465.62 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 806 | 97840 | 18 Jan 2023 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1949 | B 102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 222.8909 | R.Ft | 55 | 100 | 0 | 0 | 12259 | C+S GST 18% I/P RD | 2206.62 | 14465.62 | 14465.62 | Approved | 0 | 0 | 0 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 484.74 | Sq.Ft | 20 | 100 | 242.37 | 0 | 9694.8 | C+S GST 18% I/P RD | 1745.06 | 11439.86 | 11439.86 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 902 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 484.74 | Sq.Ft | 20 | 100 | 242.37 | 0 | 9694.8 | C+S GST 18% I/P RD | 1745.06 | 11439.86 | 11439.86 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 402 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 484.74 | Sq.Ft | 20 | 100 | 242.37 | 0 | 9694.8 | C+S GST 18% I/P RD | 1745.06 | 11439.86 | 11439.86 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 402 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 167.175 | R.Ft | 20 | 100 | 83.59 | 0 | 3343.5 | C+S GST 18% I/P RD | 601.84 | 3945.34 | 3945.34 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 902 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 167.175 | R.Ft | 20 | 100 | 83.59 | 0 | 3343.5 | C+S GST 18% I/P RD | 601.84 | 3945.34 | 3945.34 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 807 | 97839 | 18 Jan 2023 |  | J K INTERIOR | J K INTERIOR | EV - 1985 | B 102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 167.175 | R.Ft | 20 | 100 | 83.59 | 0 | 3343.5 | C+S GST 18% I/P RD | 601.84 | 3945.34 | 3945.34 | Approved | 0 | 0 | 391 | 18 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | M.S. Door fixing-Dld. | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | M.S. Box Pipe 40x40 (L) | 56.76 | Kgs | 12 | 100 | 17.03 | 0 | 681.12 | CGST 0% URD I/P | 0 | 681.12 | 681.12 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | M.S. Box Pipe 40x40 (L) | 33.11 | Kgs | 12 | 100 | 9.93 | 0 | 397.32 | CGST 0% URD I/P | 0 | 397.32 | 397.32 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | Meta colour Sheet Fixing BC | 312 | Sq.Ft | 5 | 100 | 39 | 0 | 1560 | CGST 0% URD I/P | 0 | 1560 | 1560 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | Meta colour Sheet Fixing BC | 232 | Sq.Ft | 5 | 100 | 29 | 0 | 1160 | CGST 0% URD I/P | 0 | 1160 | 1160 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | MS Framing. (L) | 59.34 | Kgs | 12 | 100 | 17.8 | 0 | 712.08 | CGST 0% URD I/P | 0 | 712.08 | 712.08 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1362 | 97830 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1827 | Shuttering Oil Store Room Fabrication | M.S. Door fixing-Dld. | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 61 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | A Tower 108 Lvl Store Fabrication | MS Door (L) | 3 | No. | 800 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | B Tower 108 Lvl Store Fabrication | MS Door (L) | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | A Tower 108 Lvl Store Fabrication | Fabrication Work (L) | 175.37 | Kgs | 12 | 100 | 52.61 | 0 | 2104.44 | CGST 0% URD I/P | 0 | 2104.44 | 2104.44 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | B Tower 108 Lvl Store Fabrication | Fabrication Work (L) | 74.04 | Kgs | 12 | 100 | 22.21 | 0 | 888.48 | CGST 0% URD I/P | 0 | 888.48 | 888.48 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | New Labour camp toilet compound fabrication | Fabrication Work (L) | 108.47 | Kgs | 12 | 100 | 32.54 | 0 | 1301.64 | CGST 0% URD I/P | 0 | 1301.64 | 1301.64 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | New labour Camp Canopy cover Fabrication | Fabrication Work (L) | 34.64 | Kgs | 12 | 100 | 10.39 | 0 | 415.68 | CGST 0% URD I/P | 0 | 415.68 | 415.68 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | B Tower 108 Lvl Store Fabrication | Meta colour Sheet Fixing BC | 258 | Sq.Ft | 5 | 100 | 32.25 | 0 | 1290 | CGST 0% URD I/P | 0 | 1290 | 1290 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | New labour Camp Canopy cover Fabrication | Meta colour Sheet Fixing BC | 160 | Sq.Ft | 5 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | Broken Compound wall covering in Fabrication | Meta colour Sheet Fixing BC | 160 | Sq.Ft | 5 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | New Labour camp toilet compound fabrication | Meta colour Sheet Fixing BC | 1505 | Sq.Ft | 5 | 100 | 188.13 | 0 | 7525 | CGST 0% URD I/P | 0 | 7525 | 7525 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | A Tower 108 Lvl Store Fabrication | Meta colour Sheet Fixing BC | 1059.5 | Sq.Ft | 5 | 100 | 132.44 | 0 | 5297.5 | CGST 0% URD I/P | 0 | 5297.5 | 5297.5 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | RMU Staircase & Platform making | Fabrication Work (L) | 394.42 | Kgs | 12 | 100 | 118.33 | 0 | 4733.04 | CGST 0% URD I/P | 0 | 4733.04 | 4733.04 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 1275 | 97829 | 17 Jan 2023 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1828 | Broken Compound wall covering in Fabrication | Fabrication Work (L) | 18.19 | Kgs | 12 | 100 | 5.46 | 0 | 218.28 | CGST 0% URD I/P | 0 | 218.28 | 218.28 | Approved | 0 | 0 | 286 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97828 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2074 | D 901 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 108.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 381 | C+S GST 5% I/P RD | 19.06 | 400.06 | 400.06 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 103 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 402 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 102 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2003 Chemical & IPS Waterproofing | IPS W/P | 46 | Sq.Ft | 11 | 100 | 50.6 | 0 | 506 | CGST 0% URD I/P | 0 | 506 | 506 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2204 Chemical & IPS Waterproofing | IPS W/P | 21.9091 | Sq.Ft | 11 | 100 | 24.1 | 0 | 241 | CGST 0% URD I/P | 0 | 241 | 241 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2103 Chemical & IPS Waterproofing | IPS W/P | 46 | Sq.Ft | 11 | 100 | 50.6 | 0 | 506 | CGST 0% URD I/P | 0 | 506 | 506 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 203 Chemical & IPS Waterproofing | IPS W/P | 46 | Sq.Ft | 11 | 100 | 50.6 | 0 | 506 | CGST 0% URD I/P | 0 | 506 | 506 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 103 Chemical & IPS Waterproofing | IPS W/P | 46 | Sq.Ft | 11 | 100 | 50.6 | 0 | 506 | CGST 0% URD I/P | 0 | 506 | 506 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Chemical & IPS Waterproofing | IPS W/P | 169 | Sq.Ft | 11 | 100 | 185.9 | 0 | 1859 | CGST 0% URD I/P | 0 | 1859 | 1859 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2003 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 46 | Sq.Ft | 19 | 100 | 87.4 | 0 | 874 | CGST 0% URD I/P | 0 | 874 | 874 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 169 | Sq.Ft | 19 | 100 | 321.1 | 0 | 3211 | CGST 0% URD I/P | 0 | 3211 | 3211 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2204 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 21.8947 | Sq.Ft | 19 | 100 | 41.6 | 0 | 416 | CGST 0% URD I/P | 0 | 416 | 416 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 46 | Sq.Ft | 19 | 100 | 87.4 | 0 | 874 | CGST 0% URD I/P | 0 | 874 | 874 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 203 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 46 | Sq.Ft | 19 | 100 | 87.4 | 0 | 874 | CGST 0% URD I/P | 0 | 874 | 874 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 46 | Sq.Ft | 19 | 100 | 87.4 | 0 | 874 | CGST 0% URD I/P | 0 | 874 | 874 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6.4667 | No. | 150 | 100 | 97 | 0 | 970.01 | CGST 0% URD I/P | 0 | 970.01 | 970.01 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 103 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 20 | No. | 70 | 100 | 140 | 0 | 1400 | CGST 0% URD I/P | 0 | 1400 | 1400 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 401 | 97821 | 17 Jan 2023 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1860 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 1 | No. | 70 | 100 | 7 | 0 | 70 | CGST 0% URD I/P | 0 | 70 | 70 | Approved | 0 | 0 | 269 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1001 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1568 | C+S GST 5% I/P RD | 78.4 | 1646.4 | 1646.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1103 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 324.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1137 | C+S GST 5% I/P RD | 56.86 | 1193.86 | 1193.86 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1105 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1568 | C+S GST 5% I/P RD | 78.4 | 1646.4 | 1646.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1004 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 324.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1137 | C+S GST 5% I/P RD | 56.86 | 1193.86 | 1193.86 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1101 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1568 | C+S GST 5% I/P RD | 78.4 | 1646.4 | 1646.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1104 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 324.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1137 | C+S GST 5% I/P RD | 56.86 | 1193.86 | 1193.86 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1005 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1568 | C+S GST 5% I/P RD | 78.4 | 1646.4 | 1646.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1102 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1148 | C+S GST 5% I/P RD | 57.4 | 1205.4 | 1205.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1003 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 324.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1137 | C+S GST 5% I/P RD | 56.86 | 1193.86 | 1193.86 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 697 | 97819 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2075 | D 1002 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1148 | C+S GST 5% I/P RD | 57.4 | 1205.4 | 1205.4 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 711 | 97818 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2070 | A 25th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2163 | C+S GST 5% I/P RD | 108.16 | 2271.16 | 2271.16 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 711 | 97818 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2070 | A 26th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2163 | C+S GST 5% I/P RD | 108.16 | 2271.16 | 2271.16 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 711 | 97818 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2070 | A 1st Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2163 | C+S GST 5% I/P RD | 108.16 | 2271.16 | 2271.16 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 543 | 97817 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR | LAXMI STRUCTURES & FIXTURES LLP | EV - 2072 | A 1st Floor Lobby Gypsum | Gypsum on Wall (M) | 1102.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3860 | C+S GST 5% I/P RD | 193 | 4053 | 4053 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 543 | 97817 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR | LAXMI STRUCTURES & FIXTURES LLP | EV - 2072 | A 26thFloor Lobby Gypsum | Gypsum on Wall (M) | 327.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1145 | C+S GST 5% I/P RD | 57.26 | 1202.26 | 1202.26 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 543 | 97817 | 17 Jan 2023 |  | A K INTERIOR CONTRACTOR | LAXMI STRUCTURES & FIXTURES LLP | EV - 2072 | A 25th Floor Lobby Gypsum | Gypsum on Wall (M) | 798 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2793 | C+S GST 5% I/P RD | 139.66 | 2932.66 | 2932.66 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 392 | 97816 | 17 Jan 2023 |  | J K INTERIOR | LAXMI STRUCTURES & FIXTURES LLP | EV - 2069 | A Bldg Flat No. 101 Gypsum Plaster | Gypsum on Wall (M) | 3414 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11949 | C+S GST 5% I/P RD | 597.46 | 12546.46 | 12546.46 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 796 | 97815 | 17 Jan 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2073 | D 10th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791 | C+S GST 5% I/P RD | 39.56 | 830.56 | 830.56 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 710 | 97814 | 17 Jan 2023 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 2071 | A 13th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.7143 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337 | C+S GST 5% I/P RD | 116.86 | 2453.86 | 2453.86 | Approved | 0 | 0 | 0 | 17 Jan 2023
GANGA DHAM TOWERS | 813 | 97812 | 17 Jan 2023 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 1858 | D Top Terrace Brickbat W/P | Brickbat W/P BCo | 2925.87 | Sq.Ft | 24 | 100 | 7022.09 | 0 | 70220.88 | CGST 0% URD I/P | 0 | 70220.88 | 70220.88 | Approved | 0 | 0 | 702 | 17 Jan 2023
GANGA DHAM TOWERS | 1455 | 97811 | 17 Jan 2023 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 1863 | D Bldg OHWT Internal W/P | Chemical Waterproofing (M+L).Sq.ft | 1205.53 | Sq.Ft | 22 | 100 | 2652.17 | 0 | 26521.66 | CGST 0% URD I/P | 0 | 26521.66 | 26521.66 | Approved | 0 | 0 | 518 | 17 Jan 2023
GANGA DHAM TOWERS | 1455 | 97811 | 17 Jan 2023 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 1863 | D Bldg OHWT Internal W/P | Pressure Grouting (M+L) | 45 | No. | 160 | 100 | 720 | 0 | 7200 | CGST 0% URD I/P | 0 | 7200 | 7200 | Approved | 0 | 0 | 518 | 17 Jan 2023
GANGA DHAM TOWERS | 1455 | 97811 | 17 Jan 2023 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 1863 | D Bldg OHWT Internal W/P | Ghotai Plaster - DPo | 816.02 | Sq.Ft | 15 | 100 | 1224.03 | 0 | 12240.3 | CGST 0% URD I/P | 0 | 12240.3 | 12240.3 | Approved | 0 | 0 | 518 | 17 Jan 2023
GANGA DHAM TOWERS | 1455 | 97811 | 17 Jan 2023 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 1863 | D Bldg OHWT Internal W/P | Screeding work- UST | 389.51 | Sq.Ft | 15 | 100 | 584.27 | 0 | 5842.65 | CGST 0% URD I/P | 0 | 5842.65 | 5842.65 | Approved | 0 | 0 | 518 | 17 Jan 2023
GANGA DHAM TOWERS | 799 | 97806 | 16 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1752 | Test Report ( 2020-21) - | Stack Monitoring Report SOS | 8 | No. | 900 | 25 | 0 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 122 | 16 Jan 2023
GANGA DHAM TOWERS | 799 | 97806 | 16 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1752 | Test Report ( 2020-21) - | NOise Test Day SOS | 32 | No. | 125 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 122 | 16 Jan 2023
GANGA DHAM TOWERS | 799 | 97806 | 16 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1752 | Test Report ( 2020-21) - | Air Test SOS | 16 | No. | 1500 | 25 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 122 | 16 Jan 2023
GANGA DHAM TOWERS | 799 | 97806 | 16 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1752 | Test Report ( 2020-21) - | Noise Test Night SOS | 32 | No. | 175 | 25 | 0 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 122 | 16 Jan 2023
GANGA DHAM TOWERS | 799 | 97806 | 16 Jan 2023 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 1752 | Test Report ( 2020-21) - | Water Testing report - SOS | 8 | No. | 1000 | 25 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 122 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Curtain Point | 12 | No. | 200 | 35 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Curtain Point | 16 | No. | 200 | 35 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Exhaust Fan Point | 6 | No. | 200 | 35 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Exhaust Fan Point | 7 | No. | 200 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 63 | No. | 200 | 35 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 81 | No. | 200 | 35 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Secondary Light Points (Looping) | 60 | No. | 67 | 35 | 35.18 | 0 | 1407 | C+S GST 18% I/P RD | 253.26 | 1660.26 | 1660.26 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Secondary Light Points (Looping) | 37.9957 | No. | 67 | 35 | 22.27 | 0 | 891 | C+S GST 18% I/P RD | 160.38 | 1051.38 | 1051.38 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Data Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | 6 AMP Plug point (Dependent) | 22.9851 | No. | 67 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | 6 AMP Plug point (Dependent) | 40 | No. | 67 | 35 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B 30th Floor 3002 | 15 Amp Point for Inverter Point | 14 | No. | 220 | 35 | 26.95 | 0 | 1078 | C+S GST 18% I/P RD | 194.04 | 1272.04 | 1272.04 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B 30th Floor 3001 | 15 Amp Point for Inverter Point | 17 | No. | 220 | 35 | 32.73 | 0 | 1309 | C+S GST 18% I/P RD | 235.62 | 1544.62 | 1544.62 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Conduit Piping work- BC | 167.2727 | R.Ft | 2.75 | 100 | 11.5 | 0 | 460 | C+S GST 18% I/P RD | 82.8 | 542.8 | 542.8 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Conduit Piping work- BC | 226.1818 | R.Ft | 2.75 | 100 | 15.55 | 0 | 622 | C+S GST 18% I/P RD | 111.96 | 733.96 | 733.96 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | 6 AMP Plug point (Independent) | 58 | No. | 200 | 35 | 101.5 | 0 | 4060 | C+S GST 18% I/P RD | 730.8 | 4790.8 | 4790.8 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | 6 AMP Plug point (Independent) | 38 | No. | 200 | 35 | 66.5 | 0 | 2660 | C+S GST 18% I/P RD | 478.8 | 3138.8 | 3138.8 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3001 Internal Electrical work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 399 | 97803 | 16 Jan 2023 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1914 | B Bldg Flat No. 3002 Internal Electrical work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 695 | 16 Jan 2023
GANGA DHAM TOWERS | 971 | 97802 | 16 Jan 2023 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1912 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 10 | No. | 300 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 168 | 16 Jan 2023
GANGA DHAM TOWERS | 971 | 97802 | 16 Jan 2023 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1912 | B-Bldg Core cutting work for AC & Fire fighting | Core Cutting Work 5" BCE | 4 | No. | 300 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 168 | 16 Jan 2023
GANGA DHAM TOWERS | 971 | 97802 | 16 Jan 2023 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1912 | B-Bldg Core cutting work for AC & Fire fighting | Core Cutting Work 3" BCE | 42 | No. | 300 | 100 | 315 | 0 | 12600 | CGST 0% URD I/P | 0 | 12600 | 12600 | Approved | 0 | 0 | 168 | 16 Jan 2023
GANGA DHAM TOWERS | 641 | 97801 | 16 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 2142 | A 904 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 250 | Sq.Ft | 40 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 100 | 16 Jan 2023
GANGA DHAM TOWERS | 551 | 97800 | 16 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2140 | A 904 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 161.94 | Sq.Ft | 20 | 100 | 80.97 | 0 | 3238.8 | C+S GST 18% I/P RD | 582.98 | 3821.78 | 3821.78 | Approved | 0 | 0 | 69 | 16 Jan 2023
GANGA DHAM TOWERS | 551 | 97800 | 16 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2140 | A 904 Tiling Below Wooden Flooring | Ceramic Flooring work | 177 | Sq.Ft | 16 | 100 | 70.8 | 0 | 2832 | C+S GST 18% I/P RD | 509.76 | 3341.76 | 3341.76 | Approved | 0 | 0 | 69 | 16 Jan 2023
GANGA DHAM TOWERS | 551 | 97800 | 16 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2140 | A 904 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 45.85 | Sq.Ft | 17 | 100 | 19.49 | 0 | 779.45 | C+S GST 18% I/P RD | 140.3 | 919.75 | 919.75 | Approved | 0 | 0 | 69 | 16 Jan 2023
GANGA DHAM TOWERS | 983 | 97799 | 16 Jan 2023 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1876 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 98 | No. | 210 | 100 | 514.5 | 0 | 20580 | CGST 0% URD I/P | 0 | 20580 | 20580 | Approved | 0 | 0 | 206 | 16 Jan 2023
GANGA DHAM TOWERS | 927 | 97796 | 14 Jan 2023 |  | VENKAT RATHOD | JAY GANESH ENTERPRISES | EV - 1771 | A 22nd Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 14 Jan 2023
GANGA DHAM TOWERS | 1261 | 97795 | 14 Jan 2023 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 1772 | A 2101 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 164 | Sq.Ft | 55 | 100 | 225.5 | 0 | 9020 | C+S GST 0% I/P RD | 0 | 9020 | 9020 | Approved | 0 | 0 | 90 | 14 Jan 2023
GANGA DHAM TOWERS | 493 | 97794 | 14 Jan 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1770 | D Build.Parking Floor External Plaster | External Plaster- BC | 1623.7 | Sq.Ft | 20 | 100 | 811.85 | 0 | 32474 | CGST 0% URD I/P | 0 | 32474 | 32474 | Approved | 0 | 0 | 325 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 15 | 100 | 19.67 | 0 | 786.78 | C+S GST 18% I/P RD | 141.62 | 928.4 | 928.4 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 15 | 100 | 22.52 | 0 | 900.72 | C+S GST 18% I/P RD | 162.12 | 1062.84 | 1062.84 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 15 | 100 | 22.52 | 0 | 900.72 | C+S GST 18% I/P RD | 162.12 | 1062.84 | 1062.84 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 15 | 100 | 13.26 | 0 | 530.42 | C+S GST 18% I/P RD | 95.48 | 625.9 | 625.9 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Children Toilet dado | L Groove - BCV | 38.763 | R.Ft | 20 | 100 | 19.38 | 0 | 775.26 | C+S GST 18% I/P RD | 139.54 | 914.8 | 914.8 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Powder Toilet dado | L Groove - BCV | 5 | R.Ft | 20 | 100 | 2.5 | 0 | 100 | C+S GST 18% I/P RD | 18 | 118 | 118 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Master Toilet dado | L Groove - BCV | 38.907 | R.Ft | 20 | 100 | 19.45 | 0 | 778.14 | C+S GST 18% I/P RD | 140.06 | 918.2 | 918.2 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 2403 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 180.288 | Sq.Ft | 60 | 100 | 270.43 | 0 | 10817.28 | C+S GST 18% I/P RD | 1947.12 | 12764.4 | 12764.4 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 2403 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 129.672 | Sq.Ft | 60 | 100 | 194.51 | 0 | 7780.32 | C+S GST 18% I/P RD | 1400.46 | 9180.78 | 9180.78 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 2403 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 439.191 | Sq.Ft | 60 | 100 | 658.79 | 0 | 26351.46 | C+S GST 18% I/P RD | 4743.26 | 31094.72 | 31094.72 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 13 | 100 | 39.6 | 0 | 1583.83 | C+S GST 18% I/P RD | 285.08 | 1868.91 | 1868.91 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 13 | 100 | 7.32 | 0 | 292.85 | C+S GST 18% I/P RD | 52.72 | 345.57 | 345.57 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.401 | Sq.Ft | 13 | 100 | 7.28 | 0 | 291.21 | C+S GST 18% I/P RD | 52.42 | 343.63 | 343.63 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 13 | 100 | 14.86 | 0 | 594.48 | C+S GST 18% I/P RD | 107 | 701.48 | 701.48 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 13 | 100 | 12.2 | 0 | 488.01 | C+S GST 18% I/P RD | 87.84 | 575.85 | 575.85 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 13 | 100 | 14.86 | 0 | 594.48 | C+S GST 18% I/P RD | 107 | 701.48 | 701.48 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 14 | 100 | 45.74 | 0 | 1829.77 | C+S GST 18% I/P RD | 329.36 | 2159.13 | 2159.13 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 14 | 100 | 26.85 | 0 | 1073.9 | C+S GST 18% I/P RD | 193.3 | 1267.2 | 1267.2 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 14 | 100 | 41.27 | 0 | 1650.85 | C+S GST 18% I/P RD | 297.16 | 1948.01 | 1948.01 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 14 | 100 | 45.74 | 0 | 1829.77 | C+S GST 18% I/P RD | 329.36 | 2159.13 | 2159.13 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 551 | 97793 | 14 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1848 | A 203 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 103.896 | Sq.Ft | 15 | 100 | 38.96 | 0 | 1558.44 | C+S GST 18% I/P RD | 280.52 | 1838.96 | 1838.96 | Approved | 0 | 0 | 620 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Children Toilet | L Groove - BCV | 29 | R.Ft | 20 | 100 | 14.5 | 0 | 580 | C+S GST 18% I/P RD | 104.4 | 684.4 | 684.4 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | C+S GST 18% I/P RD | 131.26 | 860.44 | 860.44 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Dry Balcony dado | L Groove - BCV | 5 | R.Ft | 20 | 100 | 2.5 | 0 | 100 | C+S GST 18% I/P RD | 18 | 118 | 118 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Master Toilet dado | Dado BC | 100 | Sq.Ft | 14 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Powder Toilet dado | Dado BC | 80 | Sq.Ft | 14 | 100 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 14 | 100 | 48.04 | 0 | 1921.75 | C+S GST 18% I/P RD | 345.92 | 2267.67 | 2267.67 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Master Toilet dado | Dado BC | 60 | Sq.Ft | 15 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 15 | 100 | 27.59 | 0 | 1103.63 | C+S GST 18% I/P RD | 198.66 | 1302.29 | 1302.29 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Children Toilet | Dado BC | 38.448 | Sq.Ft | 15 | 100 | 14.42 | 0 | 576.72 | C+S GST 18% I/P RD | 103.8 | 680.52 | 680.52 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 13 | 100 | 17.47 | 0 | 698.96 | C+S GST 18% I/P RD | 125.82 | 824.78 | 824.78 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 13 | 100 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 13 | 100 | 12.6 | 0 | 503.8 | C+S GST 18% I/P RD | 90.68 | 594.48 | 594.48 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.14 | Sq.Ft | 13 | 100 | 7.85 | 0 | 313.82 | C+S GST 18% I/P RD | 56.48 | 370.3 | 370.3 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 13 | 100 | 14.48 | 0 | 579.27 | C+S GST 18% I/P RD | 104.26 | 683.53 | 683.53 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 13 | 100 | 17.47 | 0 | 698.96 | C+S GST 18% I/P RD | 125.82 | 824.78 | 824.78 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 13 | 100 | 13.2 | 0 | 528.02 | C+S GST 18% I/P RD | 95.04 | 623.06 | 623.06 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Powder Toilet dado | Dado BC | 36 | Sq.Ft | 15 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 402 Dry Balcony dado | Dado BC | 82.83 | Sq.Ft | 14 | 100 | 28.99 | 0 | 1159.62 | C+S GST 18% I/P RD | 208.74 | 1368.36 | 1368.36 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 14 | 100 | 26.09 | 0 | 1043.66 | C+S GST 18% I/P RD | 187.86 | 1231.52 | 1231.52 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 537 | 97792 | 14 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1850 | A 102 Children Toilet | Dado BC | 169.587 | Sq.Ft | 14 | 100 | 59.36 | 0 | 2374.22 | C+S GST 18% I/P RD | 427.36 | 2801.58 | 2801.58 | Approved | 0 | 0 | 185 | 14 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1104 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1102 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1105 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1101 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1103 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 202 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 201 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 504 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 701 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 703 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 403 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 803 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 604 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1002 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 605 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 603 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 905 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 203 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 702 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 903 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 404 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 301 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 503 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 801 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 505 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1003 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 601 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 705 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 901 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 204 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 304 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 501 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 805 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 401 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 303 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 602 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1001 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 902 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1005 GI Folding Door | Galv. Folding Door - Shutter (M) | 62 | Sq.Ft | 180 | 100 | 0 | 0 | 11160 | C+S GST 18% I/P RD | 2008.8 | 13168.8 | 13168.8 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 402 GI Folding Door | Galv. Folding Door - Shutter (M) | 56.83 | Sq.Ft | 180 | 100 | 0 | 0 | 10229.4 | C+S GST 18% I/P RD | 1841.3 | 12070.7 | 12070.7 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1203 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1205 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1204 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1202 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 704 | 97783 | 13 Jan 2023 |  | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1812 | D 1201 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 1001 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 203 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 801 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 401 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 701 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 903 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 504 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 602 GI Folding Door | Galv. Folding Door Fixing | 39.781 | Sq.Ft | 30 | 100 | 29.84 | 0 | 1193.43 | C+S GST 18% I/P RD | 214.82 | 1408.25 | 1408.25 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 602 GI Folding Door | Galv. Folding Door Fixing | 17.049 | Sq.Ft | 30 | 100 | 12.79 | 0 | 511.47 | C+S GST 18% I/P RD | 92.06 | 603.53 | 603.53 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 402 GI Folding Door | Galv. Folding Door Fixing | 39.2127 | Sq.Ft | 30 | 100 | 29.41 | 0 | 1176.38 | C+S GST 18% I/P RD | 211.74 | 1388.12 | 1388.12 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 705 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 902 GI Folding Door | Galv. Folding Door Fixing | 56.83 | Sq.Ft | 30 | 100 | 42.62 | 0 | 1704.9 | C+S GST 18% I/P RD | 306.88 | 2011.78 | 2011.78 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 601 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 601 GI Folding Door | Galv. Folding Door Fixing | 18.6 | Sq.Ft | 30 | 100 | 13.95 | 0 | 558 | C+S GST 18% I/P RD | 100.44 | 658.44 | 658.44 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 201 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 603 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 303 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 803 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 204 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 703 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 905 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 503 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 501 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 403 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 404 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 505 GI Folding Door | Galv. Folding Door Fixing | 39 | Sq.Ft | 30 | 100 | 29.25 | 0 | 1170 | C+S GST 18% I/P RD | 210.6 | 1380.6 | 1380.6 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 805 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 1002 GI Folding Door | Galv. Folding Door Fixing | 56.83 | Sq.Ft | 30 | 100 | 42.62 | 0 | 1704.9 | C+S GST 18% I/P RD | 306.88 | 2011.78 | 2011.78 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 202 GI Folding Door | Galv. Folding Door Fixing | 39.2127 | Sq.Ft | 30 | 100 | 29.41 | 0 | 1176.38 | C+S GST 18% I/P RD | 211.74 | 1388.12 | 1388.12 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 304 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 1003 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 1005 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 605 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 505 GI Folding Door | Galv. Folding Door Fixing | 4.34 | Sq.Ft | 30 | 100 | 3.26 | 0 | 130.2 | C+S GST 18% I/P RD | 23.44 | 153.64 | 153.64 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 702 GI Folding Door | Galv. Folding Door Fixing | 56.83 | Sq.Ft | 30 | 100 | 42.62 | 0 | 1704.9 | C+S GST 18% I/P RD | 306.88 | 2011.78 | 2011.78 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 901 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 604 GI Folding Door | Galv. Folding Door Fixing | 62 | Sq.Ft | 30 | 100 | 46.5 | 0 | 1860 | C+S GST 18% I/P RD | 334.8 | 2194.8 | 2194.8 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 705 | 97782 | 13 Jan 2023 |  | SAI ENGINEERING WORKS | SAI ENGINEERING WORKS | EV - 1811 | D 301 GI Folding Door | Galv. Folding Door Fixing | 43.4 | Sq.Ft | 30 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 | Approved | 0 | 0 | 1117 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1603 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1403 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 2103 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 2103 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 503 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 503 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1403 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1803 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1703 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1103 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1303 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1303 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1903 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1903 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1803 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 6.6667 | R.Ft | 30 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1503 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 43.3333 | R.Ft | 30 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 1406 | 97781 | 13 Jan 2023 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1862 | A 1503 Groove Making In RCC Wall Kitchen | Groove Making.-BC | 66.6667 | R.Ft | 30 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 280 | 13 Jan 2023
GANGA DHAM TOWERS | 540 | 97777 | 13 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) |  | A 204 NOC | Italian Marble Mirror Polish- BCo | 53.583 | Sq.Ft | 45 | 100 | 60.28 | 0 | 2411.24 | C+S GST 18% I/P RD | 434.02 | 2845.26 | 2845.26 |  | 0 | 0 | 24 | 13 Jan 2023
GANGA DHAM TOWERS | 537 | 97776 | 13 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1847 | A 402 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 45 | 100 | 147.57 | 0 | 5902.79 | C+S GST 18% I/P RD | 1062.5 | 6965.29 | 6965.29 | Approved | 0 | 0 | 131 | 13 Jan 2023
GANGA DHAM TOWERS | 537 | 97776 | 13 Jan 2023 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1847 | A 1301 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 55 | 100 | 180.36 | 0 | 7214.52 | C+S GST 18% I/P RD | 1298.62 | 8513.14 | 8513.14 | Approved | 0 | 0 | 131 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 204 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 35 | 100 | 35.14 | 0 | 1405.43 | C+S GST 18% I/P RD | 252.98 | 1658.41 | 1658.41 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 602 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.843 | Sq.Ft | 35 | 100 | 150.36 | 0 | 6014.51 | C+S GST 18% I/P RD | 1082.62 | 7097.13 | 7097.13 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 603 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 60.096 | Sq.Ft | 35 | 100 | 52.58 | 0 | 2103.36 | C+S GST 18% I/P RD | 378.6 | 2481.96 | 2481.96 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 202 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 35 | 100 | 35.14 | 0 | 1405.43 | C+S GST 18% I/P RD | 252.98 | 1658.41 | 1658.41 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 504 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 35 | 100 | 35.14 | 0 | 1405.43 | C+S GST 18% I/P RD | 252.98 | 1658.41 | 1658.41 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 503 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 43.224 | Sq.Ft | 35 | 100 | 37.82 | 0 | 1512.84 | C+S GST 18% I/P RD | 272.32 | 1785.16 | 1785.16 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 504 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 177.267 | Sq.Ft | 35 | 100 | 155.11 | 0 | 6204.35 | C+S GST 18% I/P RD | 1116.78 | 7321.13 | 7321.13 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 603 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 43.224 | Sq.Ft | 35 | 100 | 37.82 | 0 | 1512.84 | C+S GST 18% I/P RD | 272.32 | 1785.16 | 1785.16 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 202 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.843 | Sq.Ft | 35 | 100 | 150.36 | 0 | 6014.51 | C+S GST 18% I/P RD | 1082.62 | 7097.13 | 7097.13 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 603 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 146.397 | Sq.Ft | 35 | 100 | 128.1 | 0 | 5123.9 | C+S GST 18% I/P RD | 922.3 | 6046.2 | 6046.2 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 202 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.195 | Sq.Ft | 35 | 100 | 55.3 | 0 | 2211.83 | C+S GST 18% I/P RD | 398.12 | 2609.95 | 2609.95 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 202 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 54.735 | Sq.Ft | 35 | 100 | 47.89 | 0 | 1915.73 | C+S GST 18% I/P RD | 344.84 | 2260.57 | 2260.57 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 204 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.132 | Sq.Ft | 35 | 100 | 55.24 | 0 | 2209.62 | C+S GST 18% I/P RD | 397.74 | 2607.36 | 2607.36 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 503 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 60.096 | Sq.Ft | 35 | 100 | 52.58 | 0 | 2103.36 | C+S GST 18% I/P RD | 378.6 | 2481.96 | 2481.96 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 602 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 54.735 | Sq.Ft | 35 | 100 | 47.89 | 0 | 1915.73 | C+S GST 18% I/P RD | 344.84 | 2260.57 | 2260.57 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 504 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 45.597 | Sq.Ft | 35 | 100 | 39.9 | 0 | 1595.9 | C+S GST 18% I/P RD | 287.26 | 1883.16 | 1883.16 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 602 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 35 | 100 | 35.14 | 0 | 1405.43 | C+S GST 18% I/P RD | 252.98 | 1658.41 | 1658.41 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 204 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 177.267 | Sq.Ft | 35 | 100 | 155.11 | 0 | 6204.35 | C+S GST 18% I/P RD | 1116.78 | 7321.13 | 7321.13 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 504 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.132 | Sq.Ft | 35 | 100 | 55.24 | 0 | 2209.62 | C+S GST 18% I/P RD | 397.74 | 2607.36 | 2607.36 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 503 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 146.397 | Sq.Ft | 35 | 100 | 128.1 | 0 | 5123.9 | C+S GST 18% I/P RD | 922.3 | 6046.2 | 6046.2 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 602 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.195 | Sq.Ft | 35 | 100 | 55.3 | 0 | 2211.83 | C+S GST 18% I/P RD | 398.12 | 2609.95 | 2609.95 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 641 | 97775 | 13 Jan 2023 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1849 | A 204 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 45.597 | Sq.Ft | 35 | 100 | 39.9 | 0 | 1595.9 | C+S GST 18% I/P RD | 287.26 | 1883.16 | 1883.16 | Approved | 0 | 0 | 1268 | 13 Jan 2023
GANGA DHAM TOWERS | 491 | 97774 | 13 Jan 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1769 | D Build.Parking Floor Blockwork 5" | Blockwork 5" - BC - | 950 | Sq.Ft | 13 | 100 | 308.75 | 0 | 12350 | CGST 0% URD I/P | 0 | 12350 | 12350 | Approved | 0 | 0 | 150 | 13 Jan 2023
GANGA DHAM TOWERS | 491 | 97774 | 13 Jan 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1769 | D Build.Parking Floor Blockwork 8" | Blockwork 8" - BC | 174 | Sq.Ft | 15 | 100 | 65.25 | 0 | 2610 | CGST 0% URD I/P | 0 | 2610 | 2610 | Approved | 0 | 0 | 150 | 13 Jan 2023
GANGA DHAM TOWERS | 493 | 97772 | 13 Jan 2023 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1826 | D Bldg Duct External Plaster | External Plaster- BC | 858 | Sq.Ft | 28 | 100 | 600.6 | 0 | 24024 | CGST 0% URD I/P | 0 | 24024 | 24024 | Approved | 0 | 0 | 240 | 13 Jan 2023
GANGA DHAM TOWERS | 983 | 97771 | 13 Jan 2023 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1877 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 200 | No. | 210 | 100 | 1050 | 0 | 42000 | CGST 0% URD I/P | 0 | 42000 | 42000 | Approved | 0 | 0 | 420 | 13 Jan 2023
GANGA DHAM TOWERS | 413 | 97764 | 12 Jan 2023 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1814 | Sales office Garden Maintenance | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 225 | 12 Jan 2023
GANGA DHAM TOWERS | 774 | 97760 | 12 Jan 2023 |  | MUKESH CONSTRUCTIONS | JAI SAIRAM CONSTRUCTION | EV - 1878 | B Parking Floor 1 Trimix work | Weld mesh fixing(L) BCo | 4047.715 | Sq.Ft | 1 | 100 | 101.19 | 0 | 4047.72 | C+S GST 18% I/P RD | 728.58 | 4776.3 | 4776.3 | Approved | 0 | 0 | 405 | 12 Jan 2023
GANGA DHAM TOWERS | 774 | 97760 | 12 Jan 2023 |  | MUKESH CONSTRUCTIONS | JAI SAIRAM CONSTRUCTION | EV - 1878 | B Parking Floor 1 Trimix work | Trimix Work - BC | 4047.715 | Sq.Ft | 9 | 100 | 910.74 | 0 | 36429.44 | C+S GST 18% I/P RD | 6557.3 | 42986.74 | 42986.74 | Approved | 0 | 0 | 405 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Master Toilet dado | L Groove - BCV | 38.907 | R.Ft | 20 | 100 | 19.45 | 0 | 778.14 | C+S GST 18% I/P RD | 140.06 | 918.2 | 918.2 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Children Toilet dado | L Groove - BCV | 38.763 | R.Ft | 20 | 100 | 19.38 | 0 | 775.26 | C+S GST 18% I/P RD | 139.54 | 914.8 | 914.8 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Powder Toilet dado | L Groove - BCV | 5.166 | R.Ft | 20 | 100 | 2.58 | 0 | 103.32 | C+S GST 18% I/P RD | 18.6 | 121.92 | 121.92 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.869 | R.Ft | 800 | 100 | 97.38 | 0 | 3895.2 | C+S GST 18% I/P RD | 701.14 | 4596.34 | 4596.34 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.968 | R.Ft | 800 | 100 | 99.36 | 0 | 3974.4 | C+S GST 18% I/P RD | 715.4 | 4689.8 | 4689.8 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.545 | R.Ft | 800 | 100 | 90.9 | 0 | 3636 | C+S GST 18% I/P RD | 654.48 | 4290.48 | 4290.48 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | C+S GST 18% I/P RD | 307.46 | 2015.52 | 2015.52 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Children Toilet Dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | C+S GST 18% I/P RD | 671.88 | 4404.5 | 4404.5 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 28 | 100 | 36.72 | 0 | 1468.66 | C+S GST 18% I/P RD | 264.36 | 1733.02 | 1733.02 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | C+S GST 18% I/P RD | 176.26 | 1155.53 | 1155.53 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Children Toilet Dado | Dado BC | 61.713 | Sq.Ft | 28 | 100 | 43.2 | 0 | 1727.96 | C+S GST 18% I/P RD | 311.04 | 2039 | 2039 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 28 | 100 | 53.69 | 0 | 2147.8 | C+S GST 18% I/P RD | 386.6 | 2534.4 | 2534.4 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | C+S GST 18% I/P RD | 441.62 | 2895.09 | 2895.09 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 28 | 100 | 82.54 | 0 | 3301.7 | C+S GST 18% I/P RD | 594.3 | 3896 | 3896 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 28 | 100 | 91.49 | 0 | 3659.54 | C+S GST 18% I/P RD | 658.72 | 4318.26 | 4318.26 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 28 | 100 | 24.75 | 0 | 990.11 | C+S GST 18% I/P RD | 178.22 | 1168.33 | 1168.33 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 28 | 100 | 42.03 | 0 | 1681.34 | C+S GST 18% I/P RD | 302.64 | 1983.98 | 1983.98 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Master Toilet dado | Dado BC | 133.308 | Sq.Ft | 28 | 100 | 93.32 | 0 | 3732.62 | C+S GST 18% I/P RD | 671.88 | 4404.5 | 4404.5 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.494 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1115.86 | C+S GST 18% I/P RD | 200.86 | 1316.72 | 1316.72 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 24 | 100 | 13.52 | 0 | 540.65 | C+S GST 18% I/P RD | 97.32 | 637.97 | 637.97 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 24 | 100 | 27.44 | 0 | 1097.5 | C+S GST 18% I/P RD | 197.56 | 1295.06 | 1295.06 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 24 | 100 | 22.52 | 0 | 900.94 | C+S GST 18% I/P RD | 162.16 | 1063.1 | 1063.1 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2104 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.503 | Sq.Ft | 24 | 100 | 27.9 | 0 | 1116.07 | C+S GST 18% I/P RD | 200.9 | 1316.97 | 1316.97 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 551 | 97754 | 12 Jan 2023 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1868 | A 2103 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20.01 | R.Ft | 60 | 100 | 30.02 | 0 | 1200.6 | C+S GST 18% I/P RD | 216.1 | 1416.7 | 1416.7 | Approved | 0 | 0 | 537 | 12 Jan 2023
GANGA DHAM TOWERS | 473 | 97752 | 11 Jan 2023 |  | ARYA CONSULTANCY | ARYA CONSULTANCY | EV - 1736 | Electricity Infrastructure | Highrise Perm UTI | 1 | No. | 70000 | 100 | 0 | 0 | 70000 | C+S GST 18% I/P RD | 12600 | 82600 | 82600 | Approved | 0 | 0 | 26326 | 11 Jan 2023
GANGA DHAM TOWERS | 473 | 97752 | 11 Jan 2023 |  | ARYA CONSULTANCY | ARYA CONSULTANCY | EV - 1736 | Electricity Infrastructure | Highrise Perm UTI | 1 | No. | 70000 | 100 | 0 | 0 | 70000 | C+S GST 18% I/P RD | 12600 | 82600 | 82600 | Approved | 0 | 0 | 26326 | 11 Jan 2023
GANGA DHAM TOWERS | 473 | 97752 | 11 Jan 2023 |  | ARYA CONSULTANCY | ARYA CONSULTANCY | EV - 1736 | Electricity Infrastructure | Elect Meters UTI | 172.9993 | No. | 1500 | 47.5 | 0 | 0 | 123262 | C+S GST 18% I/P RD | 22187.16 | 145449.16 | 145449.16 | Approved | 0 | 0 | 26326 | 11 Jan 2023
GANGA DHAM TOWERS | 537 | 97744 | 11 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1869 | A 1201 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 95 | 11 Jan 2023
GANGA DHAM TOWERS | 537 | 97744 | 11 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1869 | A 1201 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 700 | 100 | 87.89 | 0 | 3515.4 | C+S GST 18% I/P RD | 632.78 | 4148.18 | 4148.18 | Approved | 0 | 0 | 95 | 11 Jan 2023
GANGA DHAM TOWERS | 537 | 97744 | 11 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1869 | A 1201 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.123 | R.Ft | 700 | 100 | 54.65 | 0 | 2186.1 | C+S GST 18% I/P RD | 393.5 | 2579.6 | 2579.6 | Approved | 0 | 0 | 95 | 11 Jan 2023
GANGA DHAM TOWERS | 537 | 97744 | 11 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1869 | A 1201 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 95 | 11 Jan 2023
GANGA DHAM TOWERS | 537 | 97744 | 11 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1869 | A 1602 Dry Balcony dado | L Groove - BCV | 5.022 | R.Ft | 20 | 100 | 2.51 | 0 | 100.44 | C+S GST 18% I/P RD | 18.08 | 118.52 | 118.52 | Approved | 0 | 0 | 95 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1102 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 704 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 902 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1002 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 904 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1104 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 604 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 702 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 901 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 802 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 602 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 804 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 103 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 601 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 504 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 801 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 402 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1001 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 303 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 701 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 403 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1004 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 637 | 97743 | 11 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1834 | A 1101 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 575 | 11 Jan 2023
GANGA DHAM TOWERS | 1231 | 97711 | 10 Jan 2023 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2337 | B 1901 NOC | Lumpsum work- DCW | 1 | No. | 100000 | 100 | 2500 | 0 | 100000 | C+S GST 18% I/P RD | 18000 | 118000 | 118000 | Approved | 0 | 0 | 2000 | 10 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 404 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 901 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 801 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 804 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1101 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1102 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1104 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 902 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 402 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 103 Terrace False Ceiling | Painting work (M+L) -BC | 118.863 | Sq.Ft | 35 | 100 | 0 | 0 | 4160.21 | C+S GST 18% I/P RD | 748.84 | 4909.05 | 4909.05 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 904 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 303 Terrace False Ceiling | Painting work (M+L) -BC | 118.863 | Sq.Ft | 35 | 100 | 0 | 0 | 4160.21 | C+S GST 18% I/P RD | 748.84 | 4909.05 | 4909.05 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1004 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 704 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 802 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1002 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 636 | 97707 | 09 Jan 2023 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1825 | A 1001 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 701 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 902 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 704 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 904 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1001 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 402 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 802 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 404 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 602 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 604 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1004 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 303 Terrace False Ceiling | Sherawood False Ceiling (L) | 118.863 | Sq.Ft | 42 | 100 | 124.81 | 0 | 4992.25 | C+S GST 18% I/P RD | 898.6 | 5890.85 | 5890.85 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 804 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 801 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 901 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1102 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1104 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 601 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 702 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 103 Terrace False Ceiling | Sherawood False Ceiling (L) | 118.863 | Sq.Ft | 42 | 100 | 124.81 | 0 | 4992.25 | C+S GST 18% I/P RD | 898.6 | 5890.85 | 5890.85 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1002 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 637 | 97706 | 09 Jan 2023 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1835 | A 1101 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 1369 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 183 | Sq.Ft | 161.5 | 100 | 0 | 0 | 29554.5 | C+S GST 18% I/P RD | 5319.82 | 34874.32 | 34874.32 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 58 | Sq.Ft | 161.5 | 100 | 0 | 0 | 9367 | C+S GST 18% I/P RD | 1686.06 | 11053.06 | 11053.06 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 274 | Sq.Ft | 181.3 | 100 | 0 | 0 | 49676.2 | C+S GST 18% I/P RD | 8941.72 | 58617.92 | 58617.92 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 300.81 | Sq.Ft | 161.5 | 100 | 0 | 0 | 48580.82 | C+S GST 18% I/P RD | 8744.54 | 57325.36 | 57325.36 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 401 | Sq.Ft | 161.5 | 100 | 0 | 0 | 64761.5 | C+S GST 18% I/P RD | 11657.08 | 76418.58 | 76418.58 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 333 | Sq.Ft | 152 | 100 | 0 | 0 | 50616 | C+S GST 18% I/P RD | 9110.88 | 59726.88 | 59726.88 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 27th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 259 | Sq.Ft | 171 | 100 | 0 | 0 | 44289 | C+S GST 18% I/P RD | 7972.02 | 52261.02 | 52261.02 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 148 | Sq.Ft | 152 | 100 | 0 | 0 | 22496 | C+S GST 18% I/P RD | 4049.28 | 26545.28 | 26545.28 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 64 | Sq.Ft | 152 | 100 | 0 | 0 | 9728 | C+S GST 18% I/P RD | 1751.04 | 11479.04 | 11479.04 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 259 | Sq.Ft | 171 | 100 | 0 | 0 | 44289 | C+S GST 18% I/P RD | 7972.02 | 52261.02 | 52261.02 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 272 | 97705 | 09 Jan 2023 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1870 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 269 | Sq.Ft | 171 | 100 | 0 | 0 | 45999 | C+S GST 18% I/P RD | 8279.82 | 54278.82 | 54278.82 | Approved | 0 | 0 | 8387 | 09 Jan 2023
GANGA DHAM TOWERS | 178 | 97693 | 07 Jan 2023 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2055 | Sales office Garden Maintenance | Garden work. | 58.0012 | Day | 407.25 | 100 | 0 | 0 | 23621 | C+S GST 18% I/P RD | 4251.78 | 27872.78 | 27872.78 | Approved | 0 | 0 | 236 | 07 Jan 2023
GANGA DHAM TOWERS | 1407 | 97692 | 07 Jan 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 1804 | EWS STP RCC | RCC Work STP | 23658 | Ltrs | 3.75 | 40 | 887.18 | 0 | 35487 | CGST 0% URD I/P | 0 | 35487 | 35487 | Approved | 0 | 0 | 651 | 07 Jan 2023
GANGA DHAM TOWERS | 1407 | 97692 | 07 Jan 2023 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 1804 | EWS STP RCC | RCC Work STP | 39429.3333 | Ltrs | 3.75 | 20 | 739.3 | 0 | 29572 | CGST 0% URD I/P | 0 | 29572 | 29572 | Approved | 0 | 0 | 651 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | ISMB 150 (M) | 1556.7818 | Kgs | 64 | 100 | 0 | 0 | 99634.04 | C+S GST 18% I/P RD | 17934.12 | 117568.16 | 117568.16 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | ISMB 125 (M) -BCo | 396.37 | Kgs | 64 | 100 | 0 | 0 | 25367.68 | C+S GST 18% I/P RD | 4566.18 | 29933.86 | 29933.86 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | ISMB 200 (M) | 780.542 | Kgs | 64 | 100 | 0 | 0 | 49954.69 | C+S GST 18% I/P RD | 8991.84 | 58946.53 | 58946.53 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | ISMC 200 (M) | 1901.5724 | Kgs | 64 | 100 | 0 | 0 | 121700.63 | C+S GST 18% I/P RD | 21906.12 | 143606.75 | 143606.75 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | M.S. Angle 75x75x6 (M)- Kgs - Kgs | 292.64 | Kgs | 64 | 100 | 0 | 0 | 18728.96 | C+S GST 18% I/P RD | 3371.22 | 22100.18 | 22100.18 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(M) | 1438.63 | Kgs | 64 | 100 | 0 | 0 | 92072.32 | C+S GST 18% I/P RD | 16573.02 | 108645.34 | 108645.34 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1446 | 97691 | 07 Jan 2023 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1718 | Tower A Service Platform Fabrication Work | ISMB 250 (M) | 667.67 | Kgs | 64 | 100 | 0 | 0 | 42730.88 | C+S GST 18% I/P RD | 7691.56 | 50422.44 | 50422.44 | Approved | 0 | 0 | 0 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 7th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 8th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D Parking Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 10th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | C+S GST 0% I/P RD | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 12th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | C+S GST 0% I/P RD | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 9th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 2nd Floor Lift Opening BBM/Plaste | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 6th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 1st Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 4th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 5th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 3rd Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 1306 | 97690 | 07 Jan 2023 |  | JAY GANESH ENTERPRISES | VYANKAT SAI CONSTRUCTION | EV - 2053 | D 11th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 5000 | 100 | 25 | 0 | 1000 | C+S GST 0% I/P RD | 0 | 1000 | 1000 | Approved | 0 | 0 | 130 | 07 Jan 2023
GANGA DHAM TOWERS | 371 | 97681 | 07 Jan 2023 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 2052 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | Schedule & Quality | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | CGST 0% URD I/P | 0 | 8547.88 | 8547.88 | Approved | 0 | 0 | 320 | 07 Jan 2023
GANGA DHAM TOWERS | 371 | 97681 | 07 Jan 2023 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 2052 | EWS Bldg RCC 9th Slab Built-up Area (L) | Schedule & Quality | 543.2 | Sq.Ft | 2.5 | 100 | 33.95 | 0 | 1358 | CGST 0% URD I/P | 0 | 1358 | 1358 | Approved | 0 | 0 | 320 | 07 Jan 2023
GANGA DHAM TOWERS | 371 | 97681 | 07 Jan 2023 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 2052 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | Schedule & Quality | 2000 | Sq.Ft | 2.5 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 320 | 07 Jan 2023
GANGA DHAM TOWERS | 371 | 97681 | 07 Jan 2023 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 2052 | EWS Bldg RCC 10th Slab Built-up Area (L) | Schedule & Quality | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | CGST 0% URD I/P | 0 | 8547.88 | 8547.88 | Approved | 0 | 0 | 320 | 07 Jan 2023
GANGA DHAM TOWERS | 371 | 97681 | 07 Jan 2023 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 2052 | EWS Bldg RCC 11th Slab Built-up Area (L) | Schedule & Quality | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | CGST 0% URD I/P | 0 | 8547.88 | 8547.88 | Approved | 0 | 0 | 320 | 07 Jan 2023
GANGA DHAM TOWERS | 1433 | 97675 | 06 Jan 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1776 | RMC Pump Per Month Rental Charges | Pump Hiring for RMC | 1 | Month | 250000 | 100 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 0 | 0 | 06 Jan 2023
GANGA DHAM TOWERS | 1433 | 97673 | 06 Jan 2023 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1773 | RMC 150m Pipe Line Rental Charges | Rental Charges. | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 18% I/P RD | 3960 | 25960 | 25960 | Approved | 0 | 0 | 440 | 06 Jan 2023
GANGA DHAM TOWERS | 537 | 97659 | 06 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 28 | 100 | 52.18 | 0 | 2087.32 | C+S GST 18% I/P RD | 375.72 | 2463.04 | 2463.04 |  | 0 | 0 | 30 | 06 Jan 2023
GANGA DHAM TOWERS | 537 | 97659 | 06 Jan 2023 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2102 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 24 | 100 | 23.25 | 0 | 930.1 | C+S GST 18% I/P RD | 167.42 | 1097.52 | 1097.52 |  | 0 | 0 | 30 | 06 Jan 2023
GANGA DHAM TOWERS | 1173 | 97658 | 06 Jan 2023 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2021 | Tower A& B Parking 3 Fire Fighting | M.S. Work (M)- BCLF | 587.7975 | Kgs | 79 | 100 | 0 | 0 | 46436 | C+S GST 18% I/P RD | 8358.48 | 54794.48 | 54794.48 | Approved | 0 | 0 | 0 | 06 Jan 2023
GANGA DHAM TOWERS | 1173 | 97658 | 06 Jan 2023 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2021 | Tower A& B Parking 3 Fire Fighting | Butterfly Valve 150mm -(M) | 2 | No. | 3585 | 100 | 0 | 0 | 7170 | C+S GST 18% I/P RD | 1290.6 | 8460.6 | 8460.6 | Approved | 0 | 0 | 0 | 06 Jan 2023
GANGA DHAM TOWERS | 1171 | 97657 | 06 Jan 2023 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2020 | Towerr A& B Parking 1 Fire Fighting | Butterfly Valve 150mm -(M) | 2 | No. | 3585 | 100 | 0 | 0 | 7170 | C+S GST 18% I/P RD | 1290.6 | 8460.6 | 8460.6 | Approved | 0 | 0 | 0 | 06 Jan 2023
GANGA DHAM TOWERS | 1171 | 97657 | 06 Jan 2023 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2020 | Towerr A& B Parking 1 Fire Fighting | M.S. Work (M)- BCLF | 546.4051 | Kgs | 79 | 100 | 0 | 0 | 43166 | C+S GST 18% I/P RD | 7769.88 | 50935.88 | 50935.88 | Approved | 0 | 0 | 0 | 06 Jan 2023
GANGA DHAM TOWERS | 940 | 97656 | 06 Jan 2023 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1805 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 06 Jan 2023
GANGA DHAM TOWERS | 1360 | 97655 | 06 Jan 2023 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1803 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 06 Jan 2023
GANGA DHAM TOWERS | 1052 | 97642 | 05 Jan 2023 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1686 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.37 | 0 | 0 | 30132 | CGST 0% URD I/P | 0 | 30132 | 30132 | Approved | 0 | 0 | 3013 | 05 Jan 2023
GANGA DHAM TOWERS | 1482 | 97641 | 05 Jan 2023 |  | RAHUL SHYAMKUMAR KHANDELWAL | RAHUL SHYAMKUMAR KHANDELWAL | EV - 1685 | Company Secretary | Company Secretary charges | 1 | Month | 20000 | 100 | 0 | 0 | 20000 | CGST 0% URD I/P | 0 | 20000 | 20000 | Approved | 0 | 0 | 2000 | 05 Jan 2023
GANGA DHAM TOWERS | 1383 | 97640 | 05 Jan 2023 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1684 | Professional Consultancy (Finalcial) | Professional Fees | 1 | Month | 116666.666 | 100 | 0 | 0 | 116666 | CGST 0% URD I/P | 0 | 116666 | 116666 | Approved | 0 | 0 | 11667 | 05 Jan 2023
GANGA DHAM TOWERS | 1452 | 97639 | 05 Jan 2023 |  | OMKAR PRADEEP MANE | OMKAR PRADEEP MANE | EV - 1683 | Professional Consultancy | Professional Fees | 1 | Month | 25000 | 100 | 0 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 2500 | 05 Jan 2023
GANGA DHAM TOWERS | 1340 | 97636 | 05 Jan 2023 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1690 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 26001.14 | C+S GST 18% RCM | 4680.2 | 30681.34 | 30681.34 | Approved | 0 | 0 | 260 | 05 Jan 2023
GANGA DHAM TOWERS | 1162 | 97595 | 03 Jan 2023 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1714 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 03 Jan 2023
GANGA DHAM TOWERS | 1135 | 97576 | 02 Jan 2023 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1787 | Bund Gardern M.S. Staircase making | Fabrication work-lumpsum | 1 | No. | 39000 | 100 | 0 | 0 | 39000 | CGST 0% URD I/P | 0 | 39000 | 39000 | Approved | 0 | 0 | 390 | 02 Jan 2023
GANGA DHAM TOWERS | 1495 | 97575 | 31 Dec 2022 |  | IFFCO TOKIO GENERAL INSURANCE Co.Ltd | IFFCO TOKIO GENERAL INSURANCE Co.Ltd | EV - 1676 | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | 1 | No. | 128075 | 100 | 0 | 0 | 128075 | C+S GST 18% I/P RD | 23053.5 | 151128.5 | 151128.5 | Approved | 0 | 0 | 0 | 31 Dec 2022
GANGA DHAM TOWERS | 389 | 97572 | 31 Dec 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1680 | Loading / Unloading Expenses | Unloading of tiles. | 11.5385 | Metric Tonnes | 260 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 31 Dec 2022
GANGA DHAM TOWERS | 389 | 97572 | 31 Dec 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1680 | Loading / Unloading Expenses | Unloading of Tile Adhesive-SO | 14000 | Kgs | 0.2 | 100 | 0 | 0 | 2800 | CGST 0% URD I/P | 0 | 2800 | 2800 | Approved | 0 | 0 | 0 | 31 Dec 2022
GANGA DHAM TOWERS | 1388 | 97558 | 30 Dec 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 1768 | Tower C Podium P1 -PT Slab Work | Post Tensioning Work -BC | 4.1465 | Metric Tonnes | 154000 | 37.5 | 0 | 0 | 239460 | C+S GST 18% I/P RD | 43102.8 | 282562.8 | 282562.8 | Approved | 0 | 0 | 0 | 30 Dec 2022
GANGA DHAM TOWERS | 1388 | 97558 | 30 Dec 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 1768 | Tower C Podium P1 -PT Slab Work | Post Tensioning Work -BC | 11.77 | Metric Tonnes | 154000 | 10 | 0 | 0 | 181258 | C+S GST 18% I/P RD | 32626.44 | 213884.44 | 213884.44 | Approved | 0 | 0 | 0 | 30 Dec 2022
GANGA DHAM TOWERS | 1366 | 97556 | 30 Dec 2022 |  | PARTH ENTERPRISES | MAHALAXMI FABRICATORS | EV - 1738 | Tower C Safety work | Barricating Work (L) - SO | 549.5 | Kgs | 12 | 100 | 164.85 | 0 | 6594 | C+S GST 18% I/P RD | 1186.92 | 7780.92 | 7780.92 | Approved | 0 | 0 | 66 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Living Terrace Vitrfied Flooring | Vitrified Skirting BC | 36.513 | R.Ft | 15 | 100 | 13.69 | 0 | 547.7 | C+S GST 18% I/P RD | 98.58 | 646.28 | 646.28 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Parents Toilet Dado | Dado BC | 162.9 | Sq.Ft | 18 | 100 | 73.31 | 0 | 2932.2 | C+S GST 18% I/P RD | 527.8 | 3460 | 3460 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Guest Toilet Dado | Dado BC | 121.365 | Sq.Ft | 18 | 100 | 54.61 | 0 | 2184.57 | C+S GST 18% I/P RD | 393.22 | 2577.79 | 2577.79 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Powder Toilet Dado | Dado BC | 85.446 | Sq.Ft | 18 | 100 | 38.45 | 0 | 1538.03 | C+S GST 18% I/P RD | 276.84 | 1814.87 | 1814.87 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Kitchen Dado | Dado BC | 42.624 | Sq.Ft | 18 | 100 | 19.18 | 0 | 767.23 | C+S GST 18% I/P RD | 138.1 | 905.33 | 905.33 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Children Toilet 1 Dado | Dado BC | 146.493 | Sq.Ft | 18 | 100 | 65.92 | 0 | 2636.87 | C+S GST 18% I/P RD | 474.64 | 3111.51 | 3111.51 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Master Toilet Dado | Dado BC | 156.249 | Sq.Ft | 18 | 100 | 70.31 | 0 | 2812.48 | C+S GST 18% I/P RD | 506.24 | 3318.72 | 3318.72 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Master Toilet Dado | Dado BC | 85.446 | Sq.Ft | 15 | 100 | 32.04 | 0 | 1281.69 | C+S GST 18% I/P RD | 230.7 | 1512.39 | 1512.39 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Children Toilet 1 Dado | Dado BC | 36.252 | Sq.Ft | 15 | 100 | 13.59 | 0 | 543.78 | C+S GST 18% I/P RD | 97.88 | 641.66 | 641.66 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Parents Toilet Dado | Dado BC | 68.121 | Sq.Ft | 15 | 100 | 25.55 | 0 | 1021.82 | C+S GST 18% I/P RD | 183.92 | 1205.74 | 1205.74 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Powder Toilet Dado | Dado BC | 34.893 | Sq.Ft | 15 | 100 | 13.08 | 0 | 523.4 | C+S GST 18% I/P RD | 94.22 | 617.62 | 617.62 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Powder Toilet Dado | Dado BC | 35.604 | Sq.Ft | 15 | 100 | 13.35 | 0 | 534.06 | C+S GST 18% I/P RD | 96.14 | 630.2 | 630.2 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Children Toilet 1 Dado | Dado BC | 44.622 | Sq.Ft | 15 | 100 | 16.73 | 0 | 669.33 | C+S GST 18% I/P RD | 120.48 | 789.81 | 789.81 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Master Toilet Dado | Dado BC | 51.03 | Sq.Ft | 15 | 100 | 19.14 | 0 | 765.45 | C+S GST 18% I/P RD | 137.78 | 903.23 | 903.23 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 StaffToilet Dado - | Dado BC | 122.805 | Sq.Ft | 13 | 100 | 39.91 | 0 | 1596.47 | C+S GST 18% I/P RD | 287.36 | 1883.83 | 1883.83 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Children Toilet 1 Dado | Dado BC | 146.493 | Sq.Ft | 14 | 100 | 51.27 | 0 | 2050.9 | C+S GST 18% I/P RD | 369.16 | 2420.06 | 2420.06 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Powder Toilet Dado | Dado BC | 85.446 | Sq.Ft | 14 | 100 | 29.91 | 0 | 1196.24 | C+S GST 18% I/P RD | 215.32 | 1411.56 | 1411.56 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Dry Balcony Dado | Dado BC | 73.242 | Sq.Ft | 14 | 100 | 25.63 | 0 | 1025.39 | C+S GST 18% I/P RD | 184.58 | 1209.97 | 1209.97 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Parents Toilet Dado | Dado BC | 162.9 | Sq.Ft | 14 | 100 | 57.02 | 0 | 2280.6 | C+S GST 18% I/P RD | 410.5 | 2691.1 | 2691.1 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Parents Toilet Dado | Dado BC | 162.9 | Sq.Ft | 14 | 100 | 57.02 | 0 | 2280.6 | C+S GST 18% I/P RD | 410.5 | 2691.1 | 2691.1 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Children Toilet 2 Dado | Dado BC | 153.162 | Sq.Ft | 14 | 100 | 53.61 | 0 | 2144.27 | C+S GST 18% I/P RD | 385.96 | 2530.23 | 2530.23 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Powder Toilet Dado | Dado BC | 85.446 | Sq.Ft | 14 | 100 | 29.91 | 0 | 1196.24 | C+S GST 18% I/P RD | 215.32 | 1411.56 | 1411.56 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Parents Toilet Dado | Dado BC | 132.867 | Sq.Ft | 14 | 100 | 46.5 | 0 | 1860.14 | C+S GST 18% I/P RD | 334.82 | 2194.96 | 2194.96 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Children Toilet 1 Dado | Dado BC | 146.493 | Sq.Ft | 14 | 100 | 51.27 | 0 | 2050.9 | C+S GST 18% I/P RD | 369.16 | 2420.06 | 2420.06 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Guest Toilet Dado | Dado BC | 121.365 | Sq.Ft | 14 | 100 | 42.48 | 0 | 1699.11 | C+S GST 18% I/P RD | 305.84 | 2004.95 | 2004.95 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Children Toilet 1 Dado | Dado BC | 171.693 | Sq.Ft | 14 | 100 | 60.09 | 0 | 2403.7 | C+S GST 18% I/P RD | 432.66 | 2836.36 | 2836.36 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Powder Toilet Dado | Dado BC | 96.129 | Sq.Ft | 14 | 100 | 33.65 | 0 | 1345.81 | C+S GST 18% I/P RD | 242.24 | 1588.05 | 1588.05 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Master Toilet Dado | Dado BC | 156.249 | Sq.Ft | 14 | 100 | 54.69 | 0 | 2187.49 | C+S GST 18% I/P RD | 393.74 | 2581.23 | 2581.23 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Master Toilet Dado | Dado BC | 125.838 | Sq.Ft | 14 | 100 | 44.04 | 0 | 1761.73 | C+S GST 18% I/P RD | 317.12 | 2078.85 | 2078.85 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Master Toilet Dado | Dado BC | 156.249 | Sq.Ft | 14 | 100 | 54.69 | 0 | 2187.49 | C+S GST 18% I/P RD | 393.74 | 2581.23 | 2581.23 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Guest Toilet Dado | Dado BC | 168.732 | Sq.Ft | 14 | 100 | 59.06 | 0 | 2362.25 | C+S GST 18% I/P RD | 425.2 | 2787.45 | 2787.45 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 402 Kitchen Dado | Dado BC | 75.717 | Sq.Ft | 14 | 100 | 26.5 | 0 | 1060.04 | C+S GST 18% I/P RD | 190.8 | 1250.84 | 1250.84 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 13 | 100 | 13.81 | 0 | 552.24 | C+S GST 18% I/P RD | 99.4 | 651.64 | 651.64 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 13 | 100 | 18.04 | 0 | 721.66 | C+S GST 18% I/P RD | 129.9 | 851.56 | 851.56 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 StaffToilet Dado | Dado BC | 122.805 | Sq.Ft | 17 | 100 | 52.19 | 0 | 2087.69 | C+S GST 18% I/P RD | 375.78 | 2463.47 | 2463.47 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 700 | 100 | 48.51 | 0 | 1940.4 | C+S GST 18% I/P RD | 349.28 | 2289.68 | 2289.68 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 700 | 100 | 86.63 | 0 | 3465 | C+S GST 18% I/P RD | 623.7 | 4088.7 | 4088.7 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 700 | 100 | 99.7 | 0 | 3987.9 | C+S GST 18% I/P RD | 717.82 | 4705.72 | 4705.72 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 4.572 | R.Ft | 700 | 100 | 80.01 | 0 | 3200.4 | C+S GST 18% I/P RD | 576.08 | 3776.48 | 3776.48 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Master Toilet Counter Wash Basin - 1 No. | Italian Marble Counter - Mkt | 14.049 | R.Ft | 700 | 100 | 245.86 | 0 | 9834.3 | C+S GST 18% I/P RD | 1770.18 | 11604.48 | 11604.48 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Guest Toilet Dado | Dado BC | 59.337 | Sq.Ft | 20 | 100 | 29.67 | 0 | 1186.74 | C+S GST 18% I/P RD | 213.62 | 1400.36 | 1400.36 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Granite Kitchen otta - 1 No. | Granite Kitchen Otta BC | 13.581 | R.Ft | 350 | 100 | 118.83 | 0 | 4753.35 | C+S GST 18% I/P RD | 855.6 | 5608.95 | 5608.95 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Children Toilet 2 Dado | Dado BC | 24.174 | Sq.Ft | 15 | 100 | 9.07 | 0 | 362.61 | C+S GST 18% I/P RD | 65.26 | 427.87 | 427.87 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 602 Parents Toilet Dado | Dado BC | 48.654 | Sq.Ft | 15 | 100 | 18.25 | 0 | 729.81 | C+S GST 18% I/P RD | 131.36 | 861.17 | 861.17 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 Guest Toilet Dado | Dado BC | 35.604 | Sq.Ft | 15 | 100 | 13.35 | 0 | 534.06 | C+S GST 18% I/P RD | 96.14 | 630.2 | 630.2 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Parents Toilet Dado | Dado BC | 48.654 | Sq.Ft | 15 | 100 | 18.25 | 0 | 729.81 | C+S GST 18% I/P RD | 131.36 | 861.17 | 861.17 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Powder Toilet Dado | Dado BC | 34.893 | Sq.Ft | 15 | 100 | 13.08 | 0 | 523.4 | C+S GST 18% I/P RD | 94.22 | 617.62 | 617.62 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Master Toilet Dado | Dado BC | 51.03 | Sq.Ft | 15 | 100 | 19.14 | 0 | 765.45 | C+S GST 18% I/P RD | 137.78 | 903.23 | 903.23 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Children Toilet 1 Dado | Dado BC | 44.622 | Sq.Ft | 15 | 100 | 16.73 | 0 | 669.33 | C+S GST 18% I/P RD | 120.48 | 789.81 | 789.81 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Guest Toilet Dado | Dado BC | 59.337 | Sq.Ft | 15 | 100 | 22.25 | 0 | 890.06 | C+S GST 18% I/P RD | 160.22 | 1050.28 | 1050.28 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Kitchen Dado | Dado BC | 75.717 | Sq.Ft | 14 | 100 | 26.5 | 0 | 1060.04 | C+S GST 18% I/P RD | 190.8 | 1250.84 | 1250.84 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 201 StaffToilet Dado | Dado BC | 122.706 | Sq.Ft | 13 | 100 | 39.88 | 0 | 1595.18 | C+S GST 18% I/P RD | 287.14 | 1882.32 | 1882.32 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 StaffToilet Dado | Dado BC | 122.805 | Sq.Ft | 13 | 100 | 39.91 | 0 | 1596.47 | C+S GST 18% I/P RD | 287.36 | 1883.83 | 1883.83 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Kitchen Dado - 1 No. | Dado BC | 47.36 | Sq.Ft | 22 | 100 | 26.05 | 0 | 1041.92 | C+S GST 18% I/P RD | 187.54 | 1229.46 | 1229.46 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Common Toilet Counter Wash Basin - | Italian Marble Counter - Mkt | 4.275 | R.Ft | 650 | 100 | 69.47 | 0 | 2778.75 | C+S GST 18% I/P RD | 500.18 | 3278.93 | 3278.93 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 650 | 100 | 45.05 | 0 | 1801.8 | C+S GST 18% I/P RD | 324.32 | 2126.12 | 2126.12 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.275 | R.Ft | 650 | 100 | 69.47 | 0 | 2778.75 | C+S GST 18% I/P RD | 500.18 | 3278.93 | 3278.93 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.319 | R.Ft | 650 | 100 | 86.43 | 0 | 3457.35 | C+S GST 18% I/P RD | 622.32 | 4079.67 | 4079.67 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.247 | R.Ft | 650 | 100 | 85.26 | 0 | 3410.55 | C+S GST 18% I/P RD | 613.9 | 4024.45 | 4024.45 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Master Toilet Dado | Dado BC | 51.03 | Sq.Ft | 20 | 100 | 25.52 | 0 | 1020.6 | C+S GST 18% I/P RD | 183.7 | 1204.3 | 1204.3 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Children Toilet 1 Dado | Dado BC | 44.622 | Sq.Ft | 20 | 100 | 22.31 | 0 | 892.44 | C+S GST 18% I/P RD | 160.64 | 1053.08 | 1053.08 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Parents Toilet Dado | Dado BC | 48.654 | Sq.Ft | 20 | 100 | 24.33 | 0 | 973.08 | C+S GST 18% I/P RD | 175.16 | 1148.24 | 1148.24 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 702 Powder Toilet Dado | Dado BC | 34.893 | Sq.Ft | 20 | 100 | 17.45 | 0 | 697.86 | C+S GST 18% I/P RD | 125.62 | 823.48 | 823.48 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1101 Granite kitchen otta - | Granite Kitchen Otta BC | 13.581 | R.Ft | 325 | 100 | 110.35 | 0 | 4413.83 | C+S GST 18% I/P RD | 794.48 | 5208.31 | 5208.31 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 750 | 100 | 106.82 | 0 | 4272.75 | C+S GST 18% I/P RD | 769.1 | 5041.85 | 5041.85 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 750 | 100 | 92.81 | 0 | 3712.5 | C+S GST 18% I/P RD | 668.26 | 4380.76 | 4380.76 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 14.049 | R.Ft | 750 | 100 | 263.42 | 0 | 10536.75 | C+S GST 18% I/P RD | 1896.62 | 12433.37 | 12433.37 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 1601 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 750 | 100 | 51.98 | 0 | 2079 | C+S GST 18% I/P RD | 374.22 | 2453.22 | 2453.22 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 758 | 97549 | 30 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1715 | B 102 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 15 | 100 | 55.77 | 0 | 2230.61 | C+S GST 18% I/P RD | 401.5 | 2632.11 | 2632.11 | Approved | 0 | 0 | 1387 | 30 Dec 2022
GANGA DHAM TOWERS | 272 | 97548 | 30 Dec 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2048 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 115.4605 | Sq.Ft | 152 | 100 | 0 | 0 | 17550 | C+S GST 18% I/P RD | 3159 | 20709 | 20709 | Approved | 0 | 0 | 176 | 30 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1205 Dado | Dado Fixing | 285.02 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4985 | CGST 0% URD I/P | 0 | 4985 | 4985 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1201 Dado - 366.02 Sq.Ft | Dado Fixing | 283.9909 | Sq.Ft | 17.49 | 100 | 124.18 | 0 | 4967 | CGST 0% URD I/P | 0 | 4967 | 4967 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1202 Ceramic Flooring - 103.01 Sq.Ft | Ceramic Flooring work | 65.122 | Sq.Ft | 16.56 | 100 | 26.96 | 0 | 1078.42 | CGST 0% URD I/P | 0 | 1078.42 | 1078.42 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1203 Ceramic Flooring | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1205 Ceramic Flooring | Ceramic Flooring work | 40.688 | Sq.Ft | 16.56 | 100 | 16.84 | 0 | 673.79 | CGST 0% URD I/P | 0 | 673.79 | 673.79 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1201 Ceramic Flooring - 103.9 Sq.Ft | Ceramic Flooring work | 40.688 | Sq.Ft | 16.56 | 100 | 16.84 | 0 | 673.79 | CGST 0% URD I/P | 0 | 673.79 | 673.79 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1203 Ceramic Flooring | Ceramic Flooring work | 25.182 | Sq.Ft | 16.48 | 100 | 10.37 | 0 | 415 | CGST 0% URD I/P | 0 | 415 | 415 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1205 Ceramic Flooring | Ceramic Flooring work | 63.212 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.73 | CGST 0% URD I/P | 0 | 1041.73 | 1041.73 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1202 Ceramic Flooring - 103.01 Sq.Ft | Ceramic Flooring work | 27.1238 | Sq.Ft | 16.48 | 100 | 11.18 | 0 | 447 | CGST 0% URD I/P | 0 | 447 | 447 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1204 Ceramic Flooring | Ceramic Flooring work | 25.182 | Sq.Ft | 16.48 | 100 | 10.37 | 0 | 415 | CGST 0% URD I/P | 0 | 415 | 415 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1201 Ceramic Flooring - 103.9 Sq.Ft | Ceramic Flooring work | 63.212 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.73 | CGST 0% URD I/P | 0 | 1041.73 | 1041.73 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1201 Vitrified Flooring - 479.11 Sq.Ft | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1203 Vitrified Flooring | Vitrified Flooring work | 344.56 | Sq.Ft | 17.49 | 100 | 150.66 | 0 | 6026.35 | CGST 0% URD I/P | 0 | 6026.35 | 6026.35 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1205 Vitrified Flooring - | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 505 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 603 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 903 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 904 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1004 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 101 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 402 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 403 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 604 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1004 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 204 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 301 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 901 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 905 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 102 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 104 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1005 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 103 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 504 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 901 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 902 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 602 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 703 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 704 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 203 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 502 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 205 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 403 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 804 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 904 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1003 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 402 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 703 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 305 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 405 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 105 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 404 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 905 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1002 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 701 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 301 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 304 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 802 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1001 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1003 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 501 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 603 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 105 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 701 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 303 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 405 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 202 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 501 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 605 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 804 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 505 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 903 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 203 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 204 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 602 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 902 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 101 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 305 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 503 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 702 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 401 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 404 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 801 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1005 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 401 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 102 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 304 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 704 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 104 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 705 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 205 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 302 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 502 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 604 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 605 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 803 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 303 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 504 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 803 Window Sill | Granite Cutting & fixing (L) | 9.02 | R.Ft | 35 | 100 | 7.89 | 0 | 315.7 | CGST 0% URD I/P | 0 | 315.7 | 315.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 805 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1002 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 705 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 201 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 801 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 1001 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 302 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 702 Window Sill | Granite Cutting & fixing (L) | 10.82 | R.Ft | 35 | 100 | 9.47 | 0 | 378.7 | CGST 0% URD I/P | 0 | 378.7 | 378.7 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 201 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 503 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 202 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 601 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 805 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 601 Window Sill | Granite Cutting & fixing (L) | 14.76 | R.Ft | 35 | 100 | 12.92 | 0 | 516.6 | CGST 0% URD I/P | 0 | 516.6 | 516.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 798 | 97542 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2267 | D 103 Umbra Patti | Granite Cutting & fixing (L) | 8.36 | R.Ft | 35 | 100 | 7.32 | 0 | 292.6 | CGST 0% URD I/P | 0 | 292.6 | 292.6 | Approved | 0 | 0 | 738 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1003 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 17.49 | 100 | 150.7 | 0 | 6028.1 | CGST 0% URD I/P | 0 | 6028.1 | 6028.1 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 701 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1101 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1003 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 801 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1001 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1103 Ceramic Flooring (L) | Ceramic Flooring work | 20.9579 | Sq.Ft | 16.56 | 100 | 8.68 | 0 | 347.06 | CGST 0% URD I/P | 0 | 347.06 | 347.06 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 905 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 204 Vitrified Flooring (L) | Vitrified Flooring work | 51.6154 | Sq.Ft | 13 | 100 | 16.78 | 0 | 671 | CGST 0% URD I/P | 0 | 671 | 671 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 202 Vitrified Flooring (L) | Vitrified Flooring work | 52 | Sq.Ft | 13 | 100 | 16.9 | 0 | 676 | CGST 0% URD I/P | 0 | 676 | 676 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 205 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 104 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 402 Vitrified Flooring (L) | Vitrified Flooring work | 52 | Sq.Ft | 13 | 100 | 16.9 | 0 | 676 | CGST 0% URD I/P | 0 | 676 | 676 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 605 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 13 | 100 | 155.71 | 0 | 6228.43 | CGST 0% URD I/P | 0 | 6228.43 | 6228.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 903 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 20.49 | 100 | 49.85 | 0 | 1994.09 | CGST 0% URD I/P | 0 | 1994.09 | 1994.09 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 905 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1101 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1003 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1103 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1005 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 901 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1003 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 20.49 | 100 | 49.85 | 0 | 1994.09 | CGST 0% URD I/P | 0 | 1994.09 | 1994.09 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 702 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 20.49 | 100 | 52.19 | 0 | 2087.52 | CGST 0% URD I/P | 0 | 2087.52 | 2087.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 701 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1001 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1002 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 20.49 | 100 | 52.19 | 0 | 2087.52 | CGST 0% URD I/P | 0 | 2087.52 | 2087.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 703 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 20.49 | 100 | 49.85 | 0 | 1994.09 | CGST 0% URD I/P | 0 | 1994.09 | 1994.09 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 901 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 705 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 803 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 804 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 705 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 703 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 17.49 | 100 | 150.7 | 0 | 6028.1 | CGST 0% URD I/P | 0 | 6028.1 | 6028.1 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 903 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 17.49 | 100 | 150.7 | 0 | 6028.1 | CGST 0% URD I/P | 0 | 6028.1 | 6028.1 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 103 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 405 Dado (L) | Dado Fixing | 309 | Sq.Ft | 13 | 100 | 100.43 | 0 | 4017 | CGST 0% URD I/P | 0 | 4017 | 4017 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 501 Dado (L) | Dado Fixing | 198 | Sq.Ft | 13 | 100 | 64.35 | 0 | 2574 | CGST 0% URD I/P | 0 | 2574 | 2574 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 101 Dado (L) | Dado Fixing | 307 | Sq.Ft | 13 | 100 | 99.78 | 0 | 3991 | CGST 0% URD I/P | 0 | 3991 | 3991 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 404 Dado (L) | Dado Fixing | 185 | Sq.Ft | 13 | 100 | 60.13 | 0 | 2405 | CGST 0% URD I/P | 0 | 2405 | 2405 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 503 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 401 Dado (L) | Dado Fixing | 306 | Sq.Ft | 13 | 100 | 99.45 | 0 | 3978 | CGST 0% URD I/P | 0 | 3978 | 3978 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 504 Dado (L) | Dado Fixing | 100 | Sq.Ft | 13 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 304 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 303 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 402 Dado (L) | Dado Fixing | 172 | Sq.Ft | 13 | 100 | 55.9 | 0 | 2236 | CGST 0% URD I/P | 0 | 2236 | 2236 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 403 Dado (L) | Dado Fixing | 185 | Sq.Ft | 13 | 100 | 60.13 | 0 | 2405 | CGST 0% URD I/P | 0 | 2405 | 2405 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 202 Dado (L) | Dado Fixing | 46 | Sq.Ft | 13 | 100 | 14.95 | 0 | 598 | CGST 0% URD I/P | 0 | 598 | 598 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 302 Dado (L) | Dado Fixing | 236 | Sq.Ft | 13 | 100 | 76.7 | 0 | 3068 | CGST 0% URD I/P | 0 | 3068 | 3068 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 104 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 502 Dado (L) | Dado Fixing | 172 | Sq.Ft | 13 | 100 | 55.9 | 0 | 2236 | CGST 0% URD I/P | 0 | 2236 | 2236 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 201 Dado (L) | Dado Fixing | 36 | Sq.Ft | 13 | 100 | 11.7 | 0 | 468 | CGST 0% URD I/P | 0 | 468 | 468 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 203 Dado (L) | Dado Fixing | 58 | Sq.Ft | 13 | 100 | 18.85 | 0 | 754 | CGST 0% URD I/P | 0 | 754 | 754 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1101 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1101 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 902 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 16.48 | 100 | 15.61 | 0 | 624.43 | CGST 0% URD I/P | 0 | 624.43 | 624.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 705 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1002 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 16.48 | 100 | 15.61 | 0 | 624.43 | CGST 0% URD I/P | 0 | 624.43 | 624.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 905 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 704 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1102 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 16.48 | 100 | 15.61 | 0 | 624.43 | CGST 0% URD I/P | 0 | 624.43 | 624.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 903 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 801 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 803 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 901 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 701 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 703 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 16.48 | 100 | 15.27 | 0 | 610.75 | CGST 0% URD I/P | 0 | 610.75 | 610.75 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 702 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 16.48 | 100 | 15.61 | 0 | 624.43 | CGST 0% URD I/P | 0 | 624.43 | 624.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1001 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 16.48 | 100 | 26.04 | 0 | 1041.7 | CGST 0% URD I/P | 0 | 1041.7 | 1041.7 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 803 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 17.49 | 100 | 150.7 | 0 | 6028.1 | CGST 0% URD I/P | 0 | 6028.1 | 6028.1 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 904 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 401 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 602 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 404 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 405 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 805 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 901 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 803 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 20.49 | 100 | 49.85 | 0 | 1994.09 | CGST 0% URD I/P | 0 | 1994.09 | 1994.09 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 905 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1102 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 16.56 | 100 | 26.96 | 0 | 1078.39 | CGST 0% URD I/P | 0 | 1078.39 | 1078.39 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 903 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1104 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 305 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 602 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 12 | 100 | 11.37 | 0 | 454.68 | CGST 0% URD I/P | 0 | 454.68 | 454.68 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 303 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 405 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 403 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 601 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 402 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 104 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 605 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 105 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 201 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 504 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 105 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 401 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 402 Ceramic Flooring (L) | Ceramic Flooring work | 27.0833 | Sq.Ft | 12 | 100 | 8.12 | 0 | 325 | CGST 0% URD I/P | 0 | 325 | 325 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 503 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 501 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 503 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 502 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 101 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 303 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 602 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 104 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 401 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 302 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 12 | 100 | 11.37 | 0 | 454.68 | CGST 0% URD I/P | 0 | 454.68 | 454.68 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 405 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 203 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 502 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 12 | 100 | 11.37 | 0 | 454.68 | CGST 0% URD I/P | 0 | 454.68 | 454.68 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 201 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 203 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 504 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 103 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 403 Ceramic Flooring (L) | Ceramic Flooring work | 25.1667 | Sq.Ft | 12 | 100 | 7.55 | 0 | 302 | CGST 0% URD I/P | 0 | 302 | 302 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 603 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1004 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1002 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 16.56 | 100 | 26.96 | 0 | 1078.39 | CGST 0% URD I/P | 0 | 1078.39 | 1078.39 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 703 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 16.56 | 100 | 13.59 | 0 | 543.66 | CGST 0% URD I/P | 0 | 543.66 | 543.66 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1005 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1105 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 805 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 801 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 203 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 302 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 502 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 303 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 504 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 505 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 605 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 101 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 102 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 402 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 305 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 503 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 301 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 601 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 604 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 205 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 204 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 603 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 501 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 202 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 16 | 100 | 40.75 | 0 | 1630.08 | CGST 0% URD I/P | 0 | 1630.08 | 1630.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 201 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 103 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 104 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 403 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 105 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 16 | 100 | 57.53 | 0 | 2301.28 | CGST 0% URD I/P | 0 | 2301.28 | 2301.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 304 Vitrified Skirting (L) | Vitrified Skirting work | 97.32 | R.Ft | 16 | 100 | 38.93 | 0 | 1557.12 | CGST 0% URD I/P | 0 | 1557.12 | 1557.12 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 705 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 601 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 13 | 100 | 155.71 | 0 | 6228.43 | CGST 0% URD I/P | 0 | 6228.43 | 6228.43 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 105 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 201 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 203 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 101 Vitrified Flooring (L) | Vitrified Flooring work | 72.0769 | Sq.Ft | 13 | 100 | 23.42 | 0 | 937 | CGST 0% URD I/P | 0 | 937 | 937 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 404 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 501 Vitrified Flooring (L) | Vitrified Flooring work | 95 | Sq.Ft | 13 | 100 | 30.88 | 0 | 1235 | CGST 0% URD I/P | 0 | 1235 | 1235 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 502 Vitrified Flooring (L) | Vitrified Flooring work | 52 | Sq.Ft | 13 | 100 | 16.9 | 0 | 676 | CGST 0% URD I/P | 0 | 676 | 676 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 305 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 403 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 302 Vitrified Flooring (L) | Vitrified Flooring work | 52 | Sq.Ft | 13 | 100 | 16.9 | 0 | 676 | CGST 0% URD I/P | 0 | 676 | 676 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 405 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 401 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 602 Vitrified Flooring (L) | Vitrified Flooring work | 348.54 | Sq.Ft | 13 | 100 | 113.28 | 0 | 4531.02 | CGST 0% URD I/P | 0 | 4531.02 | 4531.02 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 505 Vitrified Flooring (L) | Vitrified Flooring work | 95 | Sq.Ft | 13 | 100 | 30.88 | 0 | 1235 | CGST 0% URD I/P | 0 | 1235 | 1235 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 301 Vitrified Flooring (L) | Vitrified Flooring work | 71.8462 | Sq.Ft | 13 | 100 | 23.35 | 0 | 934 | CGST 0% URD I/P | 0 | 934 | 934 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 303 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 304 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 103 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 102 Vitrified Flooring (L) | Vitrified Flooring work | 52 | Sq.Ft | 13 | 100 | 16.9 | 0 | 676 | CGST 0% URD I/P | 0 | 676 | 676 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 905 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1001 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 801 Vitrified Skirting (L) | Vitrified Skirting work | 143.83 | R.Ft | 20.49 | 100 | 73.68 | 0 | 2947.08 | CGST 0% URD I/P | 0 | 2947.08 | 2947.08 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 902 Vitrified Skirting (L) | Vitrified Skirting work | 101.88 | R.Ft | 20.49 | 100 | 52.19 | 0 | 2087.52 | CGST 0% URD I/P | 0 | 2087.52 | 2087.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1001 Vitrified Flooring (L) | Vitrified Flooring work | 479.11 | Sq.Ft | 17.49 | 100 | 209.49 | 0 | 8379.63 | CGST 0% URD I/P | 0 | 8379.63 | 8379.63 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 701 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 16.56 | 100 | 16.85 | 0 | 673.83 | CGST 0% URD I/P | 0 | 673.83 | 673.83 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 702 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 16.56 | 100 | 26.96 | 0 | 1078.39 | CGST 0% URD I/P | 0 | 1078.39 | 1078.39 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 304 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 102 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 604 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 404 Ceramic Flooring (L) | Ceramic Flooring work | 25.1667 | Sq.Ft | 12 | 100 | 7.55 | 0 | 302 | CGST 0% URD I/P | 0 | 302 | 302 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 205 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 202 Ceramic Flooring (L) | Ceramic Flooring work | 37.89 | Sq.Ft | 12 | 100 | 11.37 | 0 | 454.68 | CGST 0% URD I/P | 0 | 454.68 | 454.68 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 204 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 103 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 404 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 202 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 505 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 304 Ceramic Flooring (L) | Ceramic Flooring work | 37.06 | Sq.Ft | 12 | 100 | 11.12 | 0 | 444.72 | CGST 0% URD I/P | 0 | 444.72 | 444.72 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 605 Ceramic Flooring (L) | Ceramic Flooring work | 63.21 | Sq.Ft | 12 | 100 | 18.96 | 0 | 758.52 | CGST 0% URD I/P | 0 | 758.52 | 758.52 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 601 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 301 Ceramic Flooring (L) | Ceramic Flooring work | 40.69 | Sq.Ft | 12 | 100 | 12.21 | 0 | 488.28 | CGST 0% URD I/P | 0 | 488.28 | 488.28 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 302 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 12 | 100 | 19.54 | 0 | 781.44 | CGST 0% URD I/P | 0 | 781.44 | 781.44 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 603 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 604 Ceramic Flooring (L) | Ceramic Flooring work | 32.83 | Sq.Ft | 12 | 100 | 9.85 | 0 | 393.96 | CGST 0% URD I/P | 0 | 393.96 | 393.96 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 902 Ceramic Flooring (L) | Ceramic Flooring work | 65.12 | Sq.Ft | 16.56 | 100 | 26.96 | 0 | 1078.39 | CGST 0% URD I/P | 0 | 1078.39 | 1078.39 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 792 | 97541 | 29 Dec 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1774 | D 1103 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 17.49 | 100 | 150.7 | 0 | 6028.1 | CGST 0% URD I/P | 0 | 6028.1 | 6028.1 | Approved | 0 | 0 | 3886 | 29 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2001 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 301 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 901 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2401 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 301 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1901 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 302 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2401 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 302 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1801 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2001 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2001 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1901 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 302 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1801 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2301 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 401 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 401 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1802 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2401 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 301 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1102 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1102 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1802 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1901 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 901 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1102 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2301 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 901 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1801 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 2301 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 401 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 603 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 603 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 1802 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 359 | 97537 | 28 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 2059 | A 603 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 90 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 1802 Electrical Work (L) - 1 No. | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 2202 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 2002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 1102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26015 | 40 | 234.14 | 0 | 9365.4 | C+S GST 18% I/P RD | 1685.78 | 11051.18 | 11051.18 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 2001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 1901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 1801 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 901 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 2301 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1118 | 97536 | 28 Dec 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2057 | A 2401 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.9 | No. | 26925 | 40 | 242.33 | 0 | 9693 | C+S GST 18% I/P RD | 1744.74 | 11437.74 | 11437.74 | Approved | 0 | 0 | 907 | 28 Dec 2022
GANGA DHAM TOWERS | 1208 | 97535 | 28 Dec 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 1695 | Tower Crane B-Bldg Annual Maintenance charges of lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 28 Dec 2022
GANGA DHAM TOWERS | 1207 | 97534 | 28 Dec 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 1694 | Tower Crane A & C Annual maintenance for tower crane & lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 28 Dec 2022
GANGA DHAM TOWERS | 641 | 97533 | 28 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1730 | A 2402 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 29.98 | R.Ft | 60 | 100 | 44.97 | 0 | 1798.8 | C+S GST 18% I/P RD | 323.78 | 2122.58 | 2122.58 | Approved | 0 | 0 | 18 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2302 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 800 | 100 | 45.72 | 0 | 1828.8 | C+S GST 18% I/P RD | 329.18 | 2157.98 | 2157.98 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 800 | 100 | 45.72 | 0 | 1828.8 | C+S GST 18% I/P RD | 329.18 | 2157.98 | 2157.98 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2302 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 800 | 100 | 51.66 | 0 | 2066.4 | C+S GST 18% I/P RD | 371.96 | 2438.36 | 2438.36 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.679 | R.Ft | 800 | 100 | 113.58 | 0 | 4543.2 | C+S GST 18% I/P RD | 817.78 | 5360.98 | 5360.98 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 800 | 100 | 51.66 | 0 | 2066.4 | C+S GST 18% I/P RD | 371.96 | 2438.36 | 2438.36 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 800 | 100 | 51.66 | 0 | 2066.4 | C+S GST 18% I/P RD | 371.96 | 2438.36 | 2438.36 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 800 | 100 | 45.72 | 0 | 1828.8 | C+S GST 18% I/P RD | 329.18 | 2157.98 | 2157.98 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2302 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.679 | R.Ft | 800 | 100 | 113.58 | 0 | 4543.2 | C+S GST 18% I/P RD | 817.78 | 5360.98 | 5360.98 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2302 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 53.964 | R.Ft | 60 | 100 | 80.95 | 0 | 3237.84 | C+S GST 18% I/P RD | 582.82 | 3820.66 | 3820.66 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 29.98 | R.Ft | 60 | 100 | 44.97 | 0 | 1798.8 | C+S GST 18% I/P RD | 323.78 | 2122.58 | 2122.58 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 1602 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 22 | 100 | 41 | 0 | 1640.03 | C+S GST 18% I/P RD | 295.2 | 1935.23 | 1935.23 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Staff Toilet dado | Dado BC | 116.262 | Sq.Ft | 24 | 100 | 69.76 | 0 | 2790.29 | C+S GST 18% I/P RD | 502.26 | 3292.55 | 3292.55 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Staff Toilet dado | Dado BC | 116.262 | Sq.Ft | 24 | 100 | 69.76 | 0 | 2790.29 | C+S GST 18% I/P RD | 502.26 | 3292.55 | 3292.55 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 1602 Dry Balcony Vitrified Flooring. | Vitrified Flooring -BC | 38.754 | Sq.Ft | 21 | 100 | 20.35 | 0 | 813.83 | C+S GST 18% I/P RD | 146.48 | 960.31 | 960.31 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 24 | 100 | 24.37 | 0 | 974.81 | C+S GST 18% I/P RD | 175.46 | 1150.27 | 1150.27 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | C+S GST 18% I/P RD | 93.86 | 615.28 | 615.28 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 24 | 100 | 26.74 | 0 | 1069.42 | C+S GST 18% I/P RD | 192.5 | 1261.92 | 1261.92 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Children Toilet | Dado BC | 38.448 | Sq.Ft | 28 | 100 | 26.91 | 0 | 1076.54 | C+S GST 18% I/P RD | 193.78 | 1270.32 | 1270.32 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Children Toilet | Dado BC | 38.448 | Sq.Ft | 28 | 100 | 26.91 | 0 | 1076.54 | C+S GST 18% I/P RD | 193.78 | 1270.32 | 1270.32 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 28 | 100 | 27.06 | 0 | 1082.34 | C+S GST 18% I/P RD | 194.82 | 1277.16 | 1277.16 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 28 | 100 | 60.01 | 0 | 2400.3 | C+S GST 18% I/P RD | 432.06 | 2832.36 | 2832.36 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 28 | 100 | 77.81 | 0 | 3112.45 | C+S GST 18% I/P RD | 560.24 | 3672.69 | 3672.69 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Children Toilet | Dado BC | 169.587 | Sq.Ft | 28 | 100 | 118.71 | 0 | 4748.44 | C+S GST 18% I/P RD | 854.72 | 5603.16 | 5603.16 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2402 Children Toilet | Dado BC | 169.587 | Sq.Ft | 28 | 100 | 118.71 | 0 | 4748.44 | C+S GST 18% I/P RD | 854.72 | 5603.16 | 5603.16 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | C+S GST 18% I/P RD | 307.46 | 2015.52 | 2015.52 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 28 | 100 | 96.09 | 0 | 3843.5 | C+S GST 18% I/P RD | 691.84 | 4535.34 | 4535.34 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 2102 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 28 | 100 | 51.5 | 0 | 2060.1 | C+S GST 18% I/P RD | 370.82 | 2430.92 | 2430.92 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 702 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 700 | 100 | 45.2 | 0 | 1808.1 | C+S GST 18% I/P RD | 325.46 | 2133.56 | 2133.56 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 702 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.571 | R.Ft | 700 | 100 | 97.49 | 0 | 3899.7 | C+S GST 18% I/P RD | 701.94 | 4601.64 | 4601.64 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 1102 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 700 | 100 | 45.2 | 0 | 1808.1 | C+S GST 18% I/P RD | 325.46 | 2133.56 | 2133.56 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 537 | 97532 | 28 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1731 | A 1102 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 700 | 100 | 40.01 | 0 | 1600.2 | C+S GST 18% I/P RD | 288.04 | 1888.24 | 1888.24 | Approved | 0 | 0 | 762 | 28 Dec 2022
GANGA DHAM TOWERS | 209 | 97529 | 27 Dec 2022 |  | UNIQUE ENTERPRISES | A K INTERIOR CONTRACTOR | EV - 2199 | A Bldg 4th RCC Slab (P3 Floor) Built-up Area (L) | Hacking Work | 1845.46 | Sq.Ft | 5 | 100 | 230.68 | 0 | 9227.3 | C+S GST 18% I/P RD | 1660.92 | 10888.22 | 10888.22 | Approved | 0 | 0 | 92 | 27 Dec 2022
GANGA DHAM TOWERS | 652 | 97518 | 27 Dec 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1846 | A P3 Podium Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 5450.8 | Sq.Ft | 4 | 100 | 545.08 | 0 | 21803.2 | C+S GST 18% I/P RD | 3924.58 | 25727.78 | 25727.78 | Approved | 0 | 0 | 280 | 27 Dec 2022
GANGA DHAM TOWERS | 652 | 97518 | 27 Dec 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1846 | A GF Podium Column Plaster | Gypsum Plaster (L) | 433.13 | Sq.Ft | 4 | 100 | 43.31 | 0 | 1732.52 | C+S GST 18% I/P RD | 311.86 | 2044.38 | 2044.38 | Approved | 0 | 0 | 280 | 27 Dec 2022
GANGA DHAM TOWERS | 652 | 97518 | 27 Dec 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1846 | A GF Podium Drop Panel Plaster | Gypsum Plaster (L) | 267.6 | Sq.Ft | 4 | 100 | 26.76 | 0 | 1070.4 | C+S GST 18% I/P RD | 192.68 | 1263.08 | 1263.08 | Approved | 0 | 0 | 280 | 27 Dec 2022
GANGA DHAM TOWERS | 652 | 97518 | 27 Dec 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1846 | A GF Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 459 | R.Ft | 7.5 | 100 | 86.06 | 0 | 3442.5 | C+S GST 18% I/P RD | 619.66 | 4062.16 | 4062.16 | Approved | 0 | 0 | 280 | 27 Dec 2022
GANGA DHAM TOWERS | 604 | 97517 | 27 Dec 2022 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1732 | A Sprinkler System | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | 440 | No. | 205 | 100 | 2255 | 0 | 90200 | C+S GST 18% I/P RD | 16236 | 106436 | 106436 | Approved | 0 | 0 | 1804 | 27 Dec 2022
GANGA DHAM TOWERS | 1464 | 97516 | 27 Dec 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1693 | A Opening Railing For Safety 26th To 31st Floor | Plumbing Nails (M+L) | 9.8 | Kgs | 12 | 100 | 2.94 | 0 | 117.6 | C+S GST 18% I/P RD | 21.16 | 138.76 | 138.76 | Approved | 0 | 0 | 124 | 27 Dec 2022
GANGA DHAM TOWERS | 1464 | 97516 | 27 Dec 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1693 | A Opening Railing For Safety 26th To 31st Floor | Fabrication work (L) | 897 | Kgs | 12 | 100 | 269.1 | 0 | 10764 | C+S GST 18% I/P RD | 1937.52 | 12701.52 | 12701.52 | Approved | 0 | 0 | 124 | 27 Dec 2022
GANGA DHAM TOWERS | 1464 | 97516 | 27 Dec 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1693 | A Opening Railing For Safety 26th To 31st Floor | Hold Fast Patti- DSP | 305 | No. | 5 | 100 | 38.13 | 0 | 1525 | C+S GST 18% I/P RD | 274.5 | 1799.5 | 1799.5 | Approved | 0 | 0 | 124 | 27 Dec 2022
GANGA DHAM TOWERS | 1482 | 97515 | 26 Dec 2022 |  | RAHUL SHYAMKUMAR KHANDELWAL | RAHUL SHYAMKUMAR KHANDELWAL | EV - 1620 | Company Secretary | Company Secretary charges | 0.4334 | Month | 20000 | 100 | 0 | 0 | 8667 | CGST 0% URD I/P | 0 | 8667 | 8667 | Approved | 0 | 0 | 867 | 26 Dec 2022
GANGA DHAM TOWERS | 1361 | 97509 | 26 Dec 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES |  | A Lift Opening Door Making 1st to 31st Floor | M.S. Work (L)- SO | 322.5333 | Kgs | 15 | 100 | 120.95 | 0 | 4838 | CGST 0% URD I/P | 0 | 4838 | 4838 |  | 0 | 0 | 48 | 26 Dec 2022
GANGA DHAM TOWERS | 713 | 97505 | 24 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1728 | A P2 Parking Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 259.84 | Sq.Ft | 3.5 | 100 | 0 | 0 | 909.44 | C+S GST 5% I/P RD | 45.48 | 954.92 | 954.92 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 713 | 97505 | 24 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1728 | A P3 Parking Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 259.84 | Sq.Ft | 3.5 | 100 | 0 | 0 | 909.44 | C+S GST 5% I/P RD | 45.48 | 954.92 | 954.92 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 716 | 97504 | 24 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1727 | B P1 Parking Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 198.6 | Sq.Ft | 3.5 | 100 | 0 | 0 | 695.1 | C+S GST 5% I/P RD | 34.76 | 729.86 | 729.86 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 712 | 97503 | 24 Dec 2022 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1726 | A P3 Parking Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 309.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1083.15 | C+S GST 5% I/P RD | 54.16 | 1137.31 | 1137.31 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 648 | 97502 | 24 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1725 | A P2 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 8412 | Sq.Ft | 3.5 | 100 | 0 | 0 | 29442 | C+S GST 5% I/P RD | 1472.1 | 30914.1 | 30914.1 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 695 | 97501 | 24 Dec 2022 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1724 | B P3 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 3048.7881 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10670.76 | C+S GST 5% I/P RD | 533.54 | 11204.3 | 11204.3 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 695 | 97501 | 24 Dec 2022 |  | J K INTERIOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1724 | B P3 Parking Staircase & Lobby Plaster | Gypsum Plaster (M) | 1473.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 5156 | C+S GST 5% I/P RD | 257.8 | 5413.8 | 5413.8 | Approved | 0 | 0 | 0 | 24 Dec 2022
GANGA DHAM TOWERS | 372 | 97499 | 24 Dec 2022 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 2047 | B Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 100 | Sq.Ft | 155 | 100 | 0 | 0 | 15500 | C+S GST 18% I/P RD | 2790 | 18290 | 18290 | Approved | 0 | 0 | 289 | 24 Dec 2022
GANGA DHAM TOWERS | 372 | 97499 | 24 Dec 2022 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 2047 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 83.625 | Sq.Ft | 160 | 100 | 0 | 0 | 13380 | C+S GST 18% I/P RD | 2408.4 | 15788.4 | 15788.4 | Approved | 0 | 0 | 289 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 1st Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 14th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 15th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 18th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 4th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 12th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 6th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 23rd Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 24th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 13th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 22nd Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 16th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 20th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 5th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 8th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 9th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 11th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 19th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 10th Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 21st Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 7th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 2nd Floor Texture Painting | Scaffolding/Gondola work | 88.5714 | Sq.Ft | 3.5 | 100 | 7.75 | 0 | 310 | C+S GST 18% I/P RD | 55.8 | 365.8 | 365.8 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 17th Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 3rd Floor Texture Painting | Scaffolding/Gondola work | 160.2857 | Sq.Ft | 3.5 | 100 | 14.02 | 0 | 561 | C+S GST 18% I/P RD | 100.98 | 661.98 | 661.98 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 6th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 7th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 9th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 1st Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 17th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 16th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 24th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 2nd Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 4th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 22nd Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 19th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 18th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 8th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 23rd Floor Texture Painting | Texture Paint (L) | 16.4138 | Sq.Ft | 7.25 | 100 | 2.98 | 0 | 119 | C+S GST 18% I/P RD | 21.42 | 140.42 | 140.42 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 23rd Floor Texture Painting | Texture Paint (L) | 143.8621 | Sq.Ft | 7.25 | 100 | 26.08 | 0 | 1043 | C+S GST 18% I/P RD | 187.74 | 1230.74 | 1230.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 14th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 15th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 11th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 13th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 5th Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 3rd Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 21st Floor Texture Painting | Texture Paint (L) | 160.4138 | Sq.Ft | 7.25 | 100 | 29.08 | 0 | 1163 | C+S GST 18% I/P RD | 209.34 | 1372.34 | 1372.34 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 10th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 12th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1199 | 97498 | 24 Dec 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1784 | B Westside 20th Floor Texture Painting | Texture Paint (L) | 88.6897 | Sq.Ft | 7.25 | 100 | 16.08 | 0 | 643 | C+S GST 18% I/P RD | 115.74 | 758.74 | 758.74 | Approved | 0 | 0 | 326 | 24 Dec 2022
GANGA DHAM TOWERS | 1481 | 97493 | 23 Dec 2022 |  | ICICI LOMBARD GIC LTD | ICICI LOMBARD GIC LTD | EV - 1584 | Vehicle Insurance Renewal | Insurance Renewal | 1 | No. | 26128 | 100 | 0 | 0 | 26128 | C+S GST 18% I/P RD | 4703.04 | 30831.04 | 30831.04 | Approved | 0 | 0 | 0 | 23 Dec 2022
GANGA DHAM TOWERS | 1228 | 97483 | 22 Dec 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1875 | Site Expenses | Site Expenses -SO | 0.3165 | Month | 30000 | 100 | 0 | 0 | 9495 | CGST 0% URD I/P | 0 | 9495 | 9495 | Approved | 0 | 0 | 0 | 22 Dec 2022
GANGA DHAM TOWERS | 1446 | 97482 | 22 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1582 | Tower A Service Platform Fabrication Work | MS Plate (M) | 2149 | Kgs | 75 | 100 | 0 | 0 | 161175 | C+S GST 18% I/P RD | 29011.5 | 190186.5 | 190186.5 | Approved | 0 | 0 | 0 | 22 Dec 2022
GANGA DHAM TOWERS | 493 | 97474 | 21 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2017 | D Bldg Terrace Floor External Plaster | External Plaster- BC | 2801 | Sq.Ft | 28 | 100 | 1960.7 | 0 | 78428 | CGST 0% URD I/P | 0 | 78428 | 78428 | Approved | 0 | 0 | 784 | 21 Dec 2022
GANGA DHAM TOWERS | 1228 | 97473 | 21 Dec 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 1673 | R & D Purpose | R & D Purpose | 0.1536 | No. | 100000 | 100 | 0 | 0 | 15360 | C+S GST 18% I/P RD | 2764.8 | 18124.8 | 18124.8 | Approved | 0 | 0 | 307 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 502 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 900 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 602 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 5 | No. | 900 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 601 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 5 | No. | 900 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 102 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 900 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 201 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1050 | 100 | 183.75 | 0 | 7350 | CGST 0% URD I/P | 0 | 7350 | 7350 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 702 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1100 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 522 | 97472 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1717 | B Bldg 1102 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1100 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 404 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 201 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 201 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 17 | No. | 70 | 100 | 119 | 0 | 1190 | CGST 0% URD I/P | 0 | 1190 | 1190 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 25 | No. | 70 | 100 | 175 | 0 | 1750 | CGST 0% URD I/P | 0 | 1750 | 1750 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 25 | No. | 70 | 100 | 175 | 0 | 1750 | CGST 0% URD I/P | 0 | 1750 | 1750 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 201 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 2402 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 502 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 303 | Sq.Ft | 19 | 100 | 575.7 | 0 | 5757 | CGST 0% URD I/P | 0 | 5757 | 5757 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 388 | Sq.Ft | 19 | 100 | 737.2 | 0 | 7372 | CGST 0% URD I/P | 0 | 7372 | 7372 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 498 | 97471 | 21 Dec 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1716 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 332 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1902 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1402 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2002 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1802 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1502 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2202 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2102 Terrace False Ceiling | Sherawood False Ceiling (M) | 19.5786 | Sq.Ft | 140 | 100 | 0 | 0 | 2741 | C+S GST 18% I/P RD | 493.38 | 3234.38 | 3234.38 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1602 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1502 Terrace False Ceiling | Painting work (M+L) -BC | 148 | Sq.Ft | 35 | 100 | 0 | 0 | 5180 | C+S GST 18% I/P RD | 932.4 | 6112.4 | 6112.4 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2202 Terrace False Ceiling | Painting work (M+L) -BC | 187 | Sq.Ft | 35 | 100 | 0 | 0 | 6545 | C+S GST 18% I/P RD | 1178.1 | 7723.1 | 7723.1 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2102 Terrace False Ceiling | Painting work (M+L) -BC | 148 | Sq.Ft | 35 | 100 | 0 | 0 | 5180 | C+S GST 18% I/P RD | 932.4 | 6112.4 | 6112.4 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1902 Terrace False Ceiling | Painting work (M+L) -BC | 148 | Sq.Ft | 35 | 100 | 0 | 0 | 5180 | C+S GST 18% I/P RD | 932.4 | 6112.4 | 6112.4 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1402 Terrace False Ceiling | Painting work (M+L) -BC | 187 | Sq.Ft | 35 | 100 | 0 | 0 | 6545 | C+S GST 18% I/P RD | 1178.1 | 7723.1 | 7723.1 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1602 Terrace False Ceiling | Painting work (M+L) -BC | 187 | Sq.Ft | 35 | 100 | 0 | 0 | 6545 | C+S GST 18% I/P RD | 1178.1 | 7723.1 | 7723.1 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-2002 Terrace False Ceiling | Painting work (M+L) -BC | 187 | Sq.Ft | 35 | 100 | 0 | 0 | 6545 | C+S GST 18% I/P RD | 1178.1 | 7723.1 | 7723.1 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 814 | 97470 | 21 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1656 | B-1802 Terrace False Ceiling | Painting work (M+L) -BC | 187 | Sq.Ft | 35 | 100 | 0 | 0 | 6545 | C+S GST 18% I/P RD | 1178.1 | 7723.1 | 7723.1 | Approved | 0 | 0 | 0 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2202 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1602 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1902 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2002 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1802 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2102 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1502 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1402 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2202 Terrace False Ceiling | Sherawood False Ceiling (L) | 187 | Sq.Ft | 42 | 100 | 196.35 | 0 | 7854 | C+S GST 18% I/P RD | 1413.72 | 9267.72 | 9267.72 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2102 Terrace False Ceiling | Sherawood False Ceiling (L) | 148 | Sq.Ft | 42 | 100 | 155.4 | 0 | 6216 | C+S GST 18% I/P RD | 1118.88 | 7334.88 | 7334.88 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1802 Terrace False Ceiling | Sherawood False Ceiling (L) | 187 | Sq.Ft | 42 | 100 | 196.35 | 0 | 7854 | C+S GST 18% I/P RD | 1413.72 | 9267.72 | 9267.72 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1602 Terrace False Ceiling | Sherawood False Ceiling (L) | 187 | Sq.Ft | 42 | 100 | 196.35 | 0 | 7854 | C+S GST 18% I/P RD | 1413.72 | 9267.72 | 9267.72 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1502 Terrace False Ceiling | Sherawood False Ceiling (L) | 148 | Sq.Ft | 42 | 100 | 155.4 | 0 | 6216 | C+S GST 18% I/P RD | 1118.88 | 7334.88 | 7334.88 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-2002 Terrace False Ceiling | Sherawood False Ceiling (L) | 187 | Sq.Ft | 42 | 100 | 196.35 | 0 | 7854 | C+S GST 18% I/P RD | 1413.72 | 9267.72 | 9267.72 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1902 Terrace False Ceiling | Sherawood False Ceiling (L) | 148 | Sq.Ft | 42 | 100 | 155.4 | 0 | 6216 | C+S GST 18% I/P RD | 1118.88 | 7334.88 | 7334.88 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 815 | 97469 | 21 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1657 | B-1402 Terrace False Ceiling | Sherawood False Ceiling (L) | 187 | Sq.Ft | 42 | 100 | 196.35 | 0 | 7854 | C+S GST 18% I/P RD | 1413.72 | 9267.72 | 9267.72 | Approved | 0 | 0 | 779 | 21 Dec 2022
GANGA DHAM TOWERS | 647 | 97453 | 20 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | Kishan Enterprises | EV - 1729 | A 1001 NOC | Italian Marble Mirror Polish- BCo | 45.288 | Sq.Ft | 45 | 100 | 50.95 | 0 | 2037.96 | C+S GST 18% I/P RD | 366.84 | 2404.8 | 2404.8 | Approved | 0 | 0 | 20 | 20 Dec 2022
GANGA DHAM TOWERS | 540 | 97452 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1632 | A 201 NOC | Italian Marble Mirror Polish- BCo | 53.697 | Sq.Ft | 45 | 100 | 60.41 | 0 | 2416.37 | C+S GST 18% I/P RD | 434.94 | 2851.31 | 2851.31 | Approved | 0 | 0 | 47 | 20 Dec 2022
GANGA DHAM TOWERS | 540 | 97452 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1632 | A 701 NOC | Italian Marble Mirror Polish- BCo | 50.961 | Sq.Ft | 45 | 100 | 57.33 | 0 | 2293.25 | C+S GST 18% I/P RD | 412.78 | 2706.03 | 2706.03 | Approved | 0 | 0 | 47 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 601 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 35 | 100 | 59.9 | 0 | 2396.1 | C+S GST 18% I/P RD | 431.3 | 2827.4 | 2827.4 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 601 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 35 | 100 | 55.38 | 0 | 2215.19 | C+S GST 18% I/P RD | 398.74 | 2613.93 | 2613.93 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 201 Living,Dining,Passa. Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 35 | 100 | 150.33 | 0 | 6013.35 | C+S GST 18% I/P RD | 1082.4 | 7095.75 | 7095.75 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 201 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 35 | 100 | 59.9 | 0 | 2396.1 | C+S GST 18% I/P RD | 431.3 | 2827.4 | 2827.4 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 201 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 35 | 100 | 35.14 | 0 | 1405.43 | C+S GST 18% I/P RD | 252.98 | 1658.41 | 1658.41 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 201 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 35 | 100 | 55.38 | 0 | 2215.19 | C+S GST 18% I/P RD | 398.74 | 2613.93 | 2613.93 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 601 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 35 | 100 | 150.33 | 0 | 6013.35 | C+S GST 18% I/P RD | 1082.4 | 7095.75 | 7095.75 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 1001 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 40 | 100 | 68.46 | 0 | 2738.4 | C+S GST 18% I/P RD | 492.92 | 3231.32 | 3231.32 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 1001 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 40 | 100 | 63.29 | 0 | 2531.64 | C+S GST 18% I/P RD | 455.7 | 2987.34 | 2987.34 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 701 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 63.291 | Sq.Ft | 40 | 100 | 63.29 | 0 | 2531.64 | C+S GST 18% I/P RD | 455.7 | 2987.34 | 2987.34 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 701 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 40 | 100 | 40.16 | 0 | 1606.2 | C+S GST 18% I/P RD | 289.12 | 1895.32 | 1895.32 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 701 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 68.46 | Sq.Ft | 40 | 100 | 68.46 | 0 | 2738.4 | C+S GST 18% I/P RD | 492.92 | 3231.32 | 3231.32 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 701 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 40 | 100 | 171.81 | 0 | 6872.4 | C+S GST 18% I/P RD | 1237.04 | 8109.44 | 8109.44 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 1001 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 40.155 | Sq.Ft | 40 | 100 | 40.16 | 0 | 1606.2 | C+S GST 18% I/P RD | 289.12 | 1895.32 | 1895.32 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 641 | 97451 | 20 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1628 | A 1001 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 171.81 | Sq.Ft | 40 | 100 | 171.81 | 0 | 6872.4 | C+S GST 18% I/P RD | 1237.04 | 8109.44 | 8109.44 | Approved | 0 | 0 | 502 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 345.3143 | Sq.Ft | 35 | 100 | 302.15 | 0 | 12086 | C+S GST 18% I/P RD | 2175.48 | 14261.48 | 14261.48 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 402 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 61.0571 | Sq.Ft | 35 | 100 | 53.42 | 0 | 2137 | C+S GST 18% I/P RD | 384.66 | 2521.66 | 2521.66 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 345.3143 | Sq.Ft | 35 | 100 | 302.15 | 0 | 12086 | C+S GST 18% I/P RD | 2175.48 | 14261.48 | 14261.48 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 401 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.0571 | Sq.Ft | 35 | 100 | 51.67 | 0 | 2067 | C+S GST 18% I/P RD | 372.06 | 2439.06 | 2439.06 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 101 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 91.5429 | Sq.Ft | 35 | 100 | 80.1 | 0 | 3204 | C+S GST 18% I/P RD | 576.72 | 3780.72 | 3780.72 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 101 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9 | Sq.Ft | 35 | 100 | 63.79 | 0 | 2551.5 | C+S GST 18% I/P RD | 459.28 | 3010.78 | 3010.78 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 402 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 80.826 | Sq.Ft | 35 | 100 | 70.72 | 0 | 2828.91 | C+S GST 18% I/P RD | 509.2 | 3338.11 | 3338.11 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 401 Master Bed,Dreeser Marble Flooring | Italian Marble Mirror Polish- BCo | 91.5429 | Sq.Ft | 35 | 100 | 80.1 | 0 | 3204 | C+S GST 18% I/P RD | 576.72 | 3780.72 | 3780.72 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 401 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 72.9143 | Sq.Ft | 35 | 100 | 63.8 | 0 | 2552 | C+S GST 18% I/P RD | 459.36 | 3011.36 | 3011.36 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 402 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Mirror Polish- BCo | 193.2857 | Sq.Ft | 35 | 100 | 169.12 | 0 | 6765 | C+S GST 18% I/P RD | 1217.7 | 7982.7 | 7982.7 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 812 | 97450 | 20 Dec 2022 |  | R K INTERIOR | RAHUL ENTERPRISES (Prop Laburi) | EV - 1719 | B 101 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 59.079 | Sq.Ft | 35 | 100 | 51.69 | 0 | 2067.77 | C+S GST 18% I/P RD | 372.2 | 2439.97 | 2439.97 | Approved | 0 | 0 | 515 | 20 Dec 2022
GANGA DHAM TOWERS | 1256 | 97449 | 20 Dec 2022 |  | SADAF CONSTRUCTION | AVCON TECHNICS PVT LTD | EV - 2271 | B 1601 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 95.7714 | Sq.Ft | 140 | 100 | 335.2 | 0 | 13408 | C+S GST 18% I/P RD | 2413.44 | 15821.44 | 15821.44 | Approved | 0 | 0 | 536 | 20 Dec 2022
GANGA DHAM TOWERS | 1256 | 97449 | 20 Dec 2022 |  | SADAF CONSTRUCTION | AVCON TECHNICS PVT LTD | EV - 2271 | B 1901 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 95.7714 | Sq.Ft | 140 | 100 | 335.2 | 0 | 13408 | C+S GST 18% I/P RD | 2413.44 | 15821.44 | 15821.44 | Approved | 0 | 0 | 536 | 20 Dec 2022
GANGA DHAM TOWERS | 272 | 97448 | 20 Dec 2022 |  | GOURI INFRA | AVCON TECHNICS PVT LTD | EV - 2272 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.7143 | Sq.Ft | 133 | 100 | 0 | 0 | 6080 | C+S GST 18% I/P RD | 1094.4 | 7174.4 | 7174.4 | Approved | 0 | 0 | 122 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 702 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 700 | 100 | 40.01 | 0 | 1600.2 | C+S GST 18% I/P RD | 288.04 | 1888.24 | 1888.24 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 801 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.123 | R.Ft | 700 | 100 | 54.65 | 0 | 2186.1 | C+S GST 18% I/P RD | 393.5 | 2579.6 | 2579.6 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 702 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.679 | R.Ft | 700 | 100 | 99.38 | 0 | 3975.3 | C+S GST 18% I/P RD | 715.56 | 4690.86 | 4690.86 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 701 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.354 | R.Ft | 17 | 100 | 6.53 | 0 | 261.02 | C+S GST 18% I/P RD | 46.98 | 308 | 308 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 1102 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.642 | R.Ft | 17 | 100 | 6.65 | 0 | 265.91 | C+S GST 18% I/P RD | 47.86 | 313.77 | 313.77 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2201 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 11 | R.Ft | 60 | 100 | 16.5 | 0 | 660 | C+S GST 18% I/P RD | 118.8 | 778.8 | 778.8 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2401 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 10 | R.Ft | 60 | 100 | 15 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2402 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.642 | R.Ft | 24 | 100 | 9.39 | 0 | 375.41 | C+S GST 18% I/P RD | 67.58 | 442.99 | 442.99 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 537 | 97447 | 20 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises |  | A 2402 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 |  | 0 | 0 | 112 | 20 Dec 2022
GANGA DHAM TOWERS | 505 | 97434 | 19 Dec 2022 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA | EV - 1864 | A 26th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 640.6587 | Sq.Ft | 2 | 100 | 128.13 | 0 | 1281.32 | CGST 0% URD I/P | 0 | 1281.32 | 1281.32 | Approved | 0 | 0 | 13 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 267 | Sq.Ft | 19 | 100 | 507.3 | 0 | 5073 | CGST 0% URD I/P | 0 | 5073 | 5073 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 24 | Sq.Ft | 19 | 100 | 45.6 | 0 | 456 | CGST 0% URD I/P | 0 | 456 | 456 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2404 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 267 | Sq.Ft | 19 | 100 | 507.3 | 0 | 5073 | CGST 0% URD I/P | 0 | 5073 | 5073 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 4.6533 | No. | 150 | 100 | 69.8 | 0 | 698 | CGST 0% URD I/P | 0 | 698 | 698 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 0.35 | No. | 150 | 100 | 5.25 | 0 | 52.5 | CGST 0% URD I/P | 0 | 52.5 | 52.5 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 0.49 | No. | 150 | 100 | 7.35 | 0 | 73.5 | CGST 0% URD I/P | 0 | 73.5 | 73.5 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Chemical & IPS Waterproofing | IPS W/P | 267 | Sq.Ft | 11 | 100 | 293.7 | 0 | 2937 | CGST 0% URD I/P | 0 | 2937 | 2937 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2402 Chemical & IPS Waterproofing | IPS W/P | 24 | Sq.Ft | 11 | 100 | 26.4 | 0 | 264 | CGST 0% URD I/P | 0 | 264 | 264 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2404 Chemical & IPS Waterproofing | IPS W/P | 267 | Sq.Ft | 11 | 100 | 293.7 | 0 | 2937 | CGST 0% URD I/P | 0 | 2937 | 2937 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 1301 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 902 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 1102 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 904 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 17 | No. | 70 | 100 | 119 | 0 | 1190 | CGST 0% URD I/P | 0 | 1190 | 1190 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 401 | 97433 | 19 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1859 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 22 | No. | 70 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 468 | 19 Dec 2022
GANGA DHAM TOWERS | 1452 | 97419 | 17 Dec 2022 |  | OMKAR PRADEEP MANE | OMKAR PRADEEP MANE | EV - 1528 | Professional Consultancy | Professional Fees | 1 | Month | 25000 | 100 | 0 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 2500 | 17 Dec 2022
GANGA DHAM TOWERS | 355 | 97418 | 17 Dec 2022 |  | SHREE GURUDATTA ENTERPRISES | PUNDLIK P MAHAJAN | EV - 2347 | B Bldg 27th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 0 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 1102 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 17 | 100 | 16.47 | 0 | 658.82 | C+S GST 18% I/P RD | 118.58 | 777.4 | 777.4 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 1102 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 17 | 100 | 17.26 | 0 | 690.49 | C+S GST 18% I/P RD | 124.28 | 814.77 | 814.77 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 2402 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 24 | 100 | 23.25 | 0 | 930.1 | C+S GST 18% I/P RD | 167.42 | 1097.52 | 1097.52 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 2402 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 24 | 100 | 24.37 | 0 | 974.81 | C+S GST 18% I/P RD | 175.46 | 1150.27 | 1150.27 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 801 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 2402 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 28 | 100 | 96.09 | 0 | 3843.5 | C+S GST 18% I/P RD | 691.84 | 4535.34 | 4535.34 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 537 | 97417 | 17 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1630 | A 2402 Dry Balcony dado | Dado BC | 74.547 | Sq.Ft | 28 | 100 | 52.18 | 0 | 2087.32 | C+S GST 18% I/P RD | 375.72 | 2463.04 | 2463.04 | Approved | 0 | 0 | 110 | 17 Dec 2022
GANGA DHAM TOWERS | 983 | 97415 | 16 Dec 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1603 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 262 | No. | 210 | 100 | 1375.5 | 0 | 55020 | CGST 0% URD I/P | 0 | 55020 | 55020 | Approved | 0 | 0 | 550 | 16 Dec 2022
GANGA DHAM TOWERS | 1386 | 97412 | 16 Dec 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1622 | D 901 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 102 | 16 Dec 2022
GANGA DHAM TOWERS | 1386 | 97412 | 16 Dec 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1622 | D 905 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 102 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 302 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 505 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 305 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 501 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 205 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 401 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 405 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.77 | Per Flat | 4500 | 100 | 86.63 | 0 | 3465 | CGST 0% URD I/P | 0 | 3465 | 3465 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 204 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.4301 | Per Flat | 3060 | 100 | 32.9 | 0 | 1316 | CGST 0% URD I/P | 0 | 1316 | 1316 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 402 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 403 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 404 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 304 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 793 | 97411 | 16 Dec 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1604 | D 204 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.0044 | Per Flat | 3060 | 100 | 0.34 | 0 | 13.46 | CGST 0% URD I/P | 0 | 13.46 | 13.46 | Approved | 0 | 0 | 298 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(L) | 28.81 | Kgs | 20 | 100 | 14.41 | 0 | 576.2 | C+S GST 18% I/P RD | 103.72 | 679.92 | 679.92 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | ISMC 200 (L) | 128.02 | Kgs | 20 | 100 | 64.01 | 0 | 2560.4 | C+S GST 18% I/P RD | 460.88 | 3021.28 | 3021.28 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | Chemical Fastner fixing (L) | 18 | No. | 80 | 100 | 36 | 0 | 1440 | C+S GST 18% I/P RD | 259.2 | 1699.2 | 1699.2 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | MS Plate (L) | 60.3 | Kgs | 20 | 100 | 30.15 | 0 | 1206 | C+S GST 18% I/P RD | 217.08 | 1423.08 | 1423.08 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | 16.59 | Kgs | 20 | 100 | 8.3 | 0 | 331.8 | C+S GST 18% I/P RD | 59.72 | 391.52 | 391.52 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1447 | 97410 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1580 | Tower A Service Platform Fabrication Work | MS Chequred Plate (L) - Kgs | 104.37 | Kgs | 20 | 100 | 52.19 | 0 | 2087.4 | C+S GST 18% I/P RD | 375.74 | 2463.14 | 2463.14 | Approved | 0 | 0 | 82 | 16 Dec 2022
GANGA DHAM TOWERS | 1446 | 97409 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1581 | Tower A Service Platform Fabrication Work | MS Chequred Plate (M) - Kgs | 104.37 | Kgs | 75 | 100 | 0 | 0 | 7827.75 | C+S GST 18% I/P RD | 1409 | 9236.75 | 9236.75 | Approved | 0 | 0 | 0 | 16 Dec 2022
GANGA DHAM TOWERS | 1446 | 97409 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1581 | Tower A Service Platform Fabrication Work | MS Angle 50 x 50 x 6mm(M) | 28.81 | Kgs | 64 | 100 | 0 | 0 | 1843.84 | C+S GST 18% I/P RD | 331.9 | 2175.74 | 2175.74 | Approved | 0 | 0 | 0 | 16 Dec 2022
GANGA DHAM TOWERS | 1446 | 97409 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1581 | Tower A Service Platform Fabrication Work | ISMC 200 (M) | 128.02 | Kgs | 64 | 100 | 0 | 0 | 8193.28 | C+S GST 18% I/P RD | 1474.8 | 9668.08 | 9668.08 | Approved | 0 | 0 | 0 | 16 Dec 2022
GANGA DHAM TOWERS | 1446 | 97409 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1581 | Tower A Service Platform Fabrication Work | MS Plate (M) | 60.3 | Kgs | 75 | 100 | 0 | 0 | 4522.5 | C+S GST 18% I/P RD | 814.06 | 5336.56 | 5336.56 | Approved | 0 | 0 | 0 | 16 Dec 2022
GANGA DHAM TOWERS | 1446 | 97409 | 16 Dec 2022 |  | PRESSMET ENTERPRISES | PRESSMET ENTERPRISES | EV - 1581 | Tower A Service Platform Fabrication Work | M.S. Angle 75x75x6 (M)- Kgs - Kgs | 16.59 | Kgs | 64 | 100 | 0 | 0 | 1061.76 | C+S GST 18% I/P RD | 191.12 | 1252.88 | 1252.88 | Approved | 0 | 0 | 0 | 16 Dec 2022
GANGA DHAM TOWERS | 971 | 97408 | 16 Dec 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1602 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 21 | No. | 300 | 100 | 0 | 0 | 6300 | CGST 0% URD I/P | 0 | 6300 | 6300 | Approved | 0 | 0 | 120 | 16 Dec 2022
GANGA DHAM TOWERS | 971 | 97408 | 16 Dec 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1602 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 27 | No. | 210 | 100 | 141.75 | 0 | 5670 | CGST 0% URD I/P | 0 | 5670 | 5670 | Approved | 0 | 0 | 120 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 17 | 100 | 18.94 | 0 | 757.5 | C+S GST 18% I/P RD | 136.36 | 893.86 | 893.86 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 17 | 100 | 16.67 | 0 | 666.93 | C+S GST 18% I/P RD | 120.04 | 786.97 | 786.97 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 20 | 100 | 30.5 | 0 | 1220.04 | C+S GST 18% I/P RD | 219.6 | 1439.64 | 1439.64 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 20 | 100 | 19.33 | 0 | 773.1 | C+S GST 18% I/P RD | 139.16 | 912.26 | 912.26 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 24 | 100 | 26.74 | 0 | 1069.42 | C+S GST 18% I/P RD | 192.5 | 1261.92 | 1261.92 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 18 | 100 | 38.58 | 0 | 1543.05 | C+S GST 18% I/P RD | 277.74 | 1820.79 | 1820.79 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1102 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 18 | 100 | 50.02 | 0 | 2000.86 | C+S GST 18% I/P RD | 360.16 | 2361.02 | 2361.02 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 28 | 100 | 77.81 | 0 | 3112.45 | C+S GST 18% I/P RD | 560.24 | 3672.69 | 3672.69 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | C+S GST 18% I/P RD | 307.46 | 2015.52 | 2015.52 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 28 | 100 | 60.01 | 0 | 2400.3 | C+S GST 18% I/P RD | 432.06 | 2832.36 | 2832.36 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 537 | 97407 | 16 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 2402 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 28 | 100 | 27.06 | 0 | 1082.34 | C+S GST 18% I/P RD | 194.82 | 1277.16 | 1277.16 | Approved | 0 | 0 | 173 | 16 Dec 2022
GANGA DHAM TOWERS | 1406 | 97406 | 16 Dec 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1614 | Core Cutting For AC Conduting- 18 to 26 Fl | Core Cutting Work 3" BCE | 66 | No. | 300 | 100 | 0 | 0 | 19800 | CGST 0% URD I/P | 0 | 19800 | 19800 | Approved | 0 | 0 | 198 | 16 Dec 2022
GANGA DHAM TOWERS | 1343 | 97402 | 15 Dec 2022 |  | HARISH CHANDRA JADHAV ELECTRICALS | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1560 | D Lift Electrical work | Lift Electrical work-BC | 0.8333 | No. | 12000 | 100 | 249.99 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 100 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 80mm dia.(M+L) | 48 | Mtrs | 1400 | 100 | 1680 | 0 | 67200 | C+S GST 18% I/P RD | 12096 | 79296 | 79296 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 40mm dia.(M+L) | 321.6 | Mtrs | 760 | 100 | 6110.4 | 0 | 244416 | C+S GST 18% I/P RD | 43994.88 | 288410.88 | 288410.88 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 25mm dia.(M+L) | 916.8 | Mtrs | 510 | 100 | 11689.2 | 0 | 467568 | C+S GST 18% I/P RD | 84162.24 | 551730.24 | 551730.24 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 150mm dia.(M+L) | 206.4 | Mtrs | 2750 | 100 | 14190 | 0 | 567600 | C+S GST 18% I/P RD | 102168 | 669768 | 669768 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 32mm dia.(M+L) | 484.8 | Mtrs | 660 | 100 | 7999.2 | 0 | 319968 | C+S GST 18% I/P RD | 57594.24 | 377562.24 | 377562.24 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 50mm dia.(M+L) | 48 | Mtrs | 970 | 100 | 1164 | 0 | 46560 | C+S GST 18% I/P RD | 8380.8 | 54940.8 | 54940.8 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1231 | 97401 | 15 Dec 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1666 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 65mm dia.(M+L) | 48 | Mtrs | 1170 | 100 | 1404 | 0 | 56160 | C+S GST 18% I/P RD | 10108.8 | 66268.8 | 66268.8 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 8th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 2nd Floor Lift Opening BBM/Plaste | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 11th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 10th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 1st Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 6th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 12th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 4th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 5th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D Parking Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 9th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 7th Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 1306 | 97400 | 15 Dec 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1572 | D 3rd Floor Lift Opening BBM/Plaster | Blockwork/ Plaster-BC | 0.3098 | No. | 5000 | 100 | 38.73 | 0 | 1549 | C+S GST 0% I/P RD | 0 | 1549 | 1549 | Approved | 0 | 0 | 201 | 15 Dec 2022
GANGA DHAM TOWERS | 806 | 97398 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1652 | B 402 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 472.7273 | Sq.Ft | 55 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 806 | 97398 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1652 | B 902 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 472.7273 | Sq.Ft | 55 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 806 | 97398 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1652 | B 102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 472.7273 | Sq.Ft | 55 | 100 | 0 | 0 | 26000 | C+S GST 18% I/P RD | 4680 | 30680 | 30680 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 630 | 97397 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1653 | A 701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 630 | 97397 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1653 | A 201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 630 | 97397 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1653 | A 502 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 630 | 97397 | 15 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1653 | A 602 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 15 Dec 2022
GANGA DHAM TOWERS | 537 | 97396 | 15 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1627 | A 801 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 700 | 100 | 87.89 | 0 | 3515.4 | C+S GST 18% I/P RD | 632.78 | 4148.18 | 4148.18 | Approved | 0 | 0 | 107 | 15 Dec 2022
GANGA DHAM TOWERS | 537 | 97396 | 15 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1627 | A 801 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 107 | 15 Dec 2022
GANGA DHAM TOWERS | 272 | 97395 | 15 Dec 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1871 | A Bldg 35th slab (30th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1826 | Sq.Ft | 190 | 100 | 8673.5 | 0 | 346940 | C+S GST 18% I/P RD | 62449.2 | 409389.2 | 409389.2 | Approved | 0 | 0 | 6939 | 15 Dec 2022
GANGA DHAM TOWERS | 372 | 97394 | 15 Dec 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1872 | B Bldg 35th Slab ( 30th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 5740 | Sq.Ft | 190 | 100 | 27265 | 0 | 1090600 | C+S GST 18% I/P RD | 196308 | 1286908 | 1286908 | Approved | 0 | 0 | 21812 | 15 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 50 | 100 | 96.68 | 0 | 3867.3 | C+S GST 18% I/P RD | 696.12 | 4563.42 | 4563.42 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2401 Window Sill - 1 No. | Italian Marble Sill- BC- | 77.346 | R.Ft | 60 | 100 | 116.02 | 0 | 4640.76 | C+S GST 18% I/P RD | 835.34 | 5476.1 | 5476.1 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Window Sill Refuge Flat - | Italian Marble Sill- BC- | 62.163 | R.Ft | 50 | 100 | 77.7 | 0 | 3108.15 | C+S GST 18% I/P RD | 559.46 | 3667.61 | 3667.61 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2101 Window Sill - 1 No. | Italian Marble Sill- BC- | 62.163 | R.Ft | 60 | 100 | 93.24 | 0 | 3729.78 | C+S GST 18% I/P RD | 671.36 | 4401.14 | 4401.14 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 801 Window Sill - | Italian Marble Sill- BC- | 77.346 | R.Ft | 50 | 100 | 96.68 | 0 | 3867.3 | C+S GST 18% I/P RD | 696.12 | 4563.42 | 4563.42 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 901 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 50 | 100 | 96.68 | 0 | 3867.3 | C+S GST 18% I/P RD | 696.12 | 4563.42 | 4563.42 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 71.115 | R.Ft | 50 | 100 | 88.89 | 0 | 3555.75 | C+S GST 18% I/P RD | 640.04 | 4195.79 | 4195.79 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 34.6 | R.Ft | 50 | 100 | 43.25 | 0 | 1730 | C+S GST 18% I/P RD | 311.4 | 2041.4 | 2041.4 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Living,Dining,Ent.Lobby | Italian Marble Champher & Polish | 172.3725 | R.Ft | 50 | 100 | 215.47 | 0 | 8618.63 | C+S GST 18% I/P RD | 1551.36 | 10169.99 | 10169.99 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 34.6 | R.Ft | 50 | 100 | 43.25 | 0 | 1730 | C+S GST 18% I/P RD | 311.4 | 2041.4 | 2041.4 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 26.74 | R.Ft | 50 | 100 | 33.43 | 0 | 1337 | C+S GST 18% I/P RD | 240.66 | 1577.66 | 1577.66 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 71.12 | R.Ft | 50 | 100 | 88.9 | 0 | 3556 | C+S GST 18% I/P RD | 640.08 | 4196.08 | 4196.08 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Living,Dining,Ent.Lobby | Italian marble Skirting - BCo | 172.38 | R.Ft | 50 | 100 | 215.48 | 0 | 8619 | C+S GST 18% I/P RD | 1551.42 | 10170.42 | 10170.42 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.06 | R.Ft | 55 | 100 | 94.96 | 0 | 3798.3 | C+S GST 18% I/P RD | 683.7 | 4482 | 4482 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 174.9525 | R.Ft | 55 | 100 | 240.56 | 0 | 9622.39 | C+S GST 18% I/P RD | 1732.04 | 11354.43 | 11354.43 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.9 | R.Ft | 55 | 100 | 71.36 | 0 | 2854.5 | C+S GST 18% I/P RD | 513.82 | 3368.32 | 3368.32 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 40.11 | R.Ft | 55 | 100 | 55.15 | 0 | 2206.05 | C+S GST 18% I/P RD | 397.08 | 2603.13 | 2603.13 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 54.1333 | R.Ft | 60 | 100 | 81.2 | 0 | 3248 | C+S GST 18% I/P RD | 584.64 | 3832.64 | 3832.64 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 96.2167 | R.Ft | 60 | 100 | 144.33 | 0 | 5773 | C+S GST 18% I/P RD | 1039.14 | 6812.14 | 6812.14 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 42.8175 | R.Ft | 60 | 100 | 64.23 | 0 | 2569.05 | C+S GST 18% I/P RD | 462.42 | 3031.47 | 3031.47 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.615 | R.Ft | 50 | 100 | 43.27 | 0 | 1730.75 | C+S GST 18% I/P RD | 311.54 | 2042.29 | 2042.29 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 46.015 | R.Ft | 50 | 100 | 57.52 | 0 | 2300.75 | C+S GST 18% I/P RD | 414.14 | 2714.89 | 2714.89 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 116.64 | R.Ft | 50 | 100 | 145.8 | 0 | 5832 | C+S GST 18% I/P RD | 1049.76 | 6881.76 | 6881.76 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1101 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 50 | 100 | 64.9 | 0 | 2596.13 | C+S GST 18% I/P RD | 467.3 | 3063.43 | 3063.43 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1801 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 55 | 100 | 106.35 | 0 | 4254.03 | C+S GST 18% I/P RD | 765.72 | 5019.75 | 5019.75 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B1601 Window Sill - 1 No. | Italian Marble Sill- BC- | 62.163 | R.Ft | 55 | 100 | 85.47 | 0 | 3418.97 | C+S GST 18% I/P RD | 615.42 | 4034.39 | 4034.39 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1301 Window Sill- | Italian Marble Sill- BC- | 77.346 | R.Ft | 55 | 100 | 106.35 | 0 | 4254.03 | C+S GST 18% I/P RD | 765.72 | 5019.75 | 5019.75 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1401 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 55 | 100 | 106.35 | 0 | 4254.03 | C+S GST 18% I/P RD | 765.72 | 5019.75 | 5019.75 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701Window Sill - | Italian Marble Sill- BC- | 77.346 | R.Ft | 55 | 100 | 106.35 | 0 | 4254.03 | C+S GST 18% I/P RD | 765.72 | 5019.75 | 5019.75 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.0225 | R.Ft | 55 | 100 | 94.91 | 0 | 3796.24 | C+S GST 18% I/P RD | 683.32 | 4479.56 | 4479.56 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 174.9455 | R.Ft | 55 | 100 | 240.55 | 0 | 9622 | C+S GST 18% I/P RD | 1731.96 | 11353.96 | 11353.96 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 55 | 100 | 71.39 | 0 | 2855.74 | C+S GST 18% I/P RD | 514.04 | 3369.78 | 3369.78 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1701 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 40.1091 | R.Ft | 55 | 100 | 55.15 | 0 | 2206 | C+S GST 18% I/P RD | 397.08 | 2603.08 | 2603.08 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 42.8175 | R.Ft | 60 | 100 | 64.23 | 0 | 2569.05 | C+S GST 18% I/P RD | 462.42 | 3031.47 | 3031.47 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 54.135 | R.Ft | 60 | 100 | 81.2 | 0 | 3248.1 | C+S GST 18% I/P RD | 584.66 | 3832.76 | 3832.76 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 2002 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 96.2175 | R.Ft | 60 | 100 | 144.33 | 0 | 5773.05 | C+S GST 18% I/P RD | 1039.14 | 6812.19 | 6812.19 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 4.572 | R.Ft | 700 | 100 | 80.01 | 0 | 3200.4 | C+S GST 18% I/P RD | 576.08 | 3776.48 | 3776.48 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 700 | 100 | 99.7 | 0 | 3987.9 | C+S GST 18% I/P RD | 717.82 | 4705.72 | 4705.72 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 700 | 100 | 99.7 | 0 | 3987.9 | C+S GST 18% I/P RD | 717.82 | 4705.72 | 4705.72 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 700 | 100 | 48.51 | 0 | 1940.4 | C+S GST 18% I/P RD | 349.28 | 2289.68 | 2289.68 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 71.1556 | R.Ft | 45 | 100 | 80.05 | 0 | 3202 | C+S GST 18% I/P RD | 576.36 | 3778.36 | 3778.36 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Living,Dining,Ent.Lobby | Italian marble Skirting - BCo | 172.3778 | R.Ft | 45 | 100 | 193.93 | 0 | 7757 | C+S GST 18% I/P RD | 1396.26 | 9153.26 | 9153.26 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 45 | 100 | 58.41 | 0 | 2336.51 | C+S GST 18% I/P RD | 420.58 | 2757.09 | 2757.09 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 71.115 | R.Ft | 45 | 100 | 80 | 0 | 3200.18 | C+S GST 18% I/P RD | 576.04 | 3776.22 | 3776.22 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Living,Dining,Ent.Lobby | Italian Marble Champher & Polish | 172.3725 | R.Ft | 45 | 100 | 193.92 | 0 | 7756.76 | C+S GST 18% I/P RD | 1396.22 | 9152.98 | 9152.98 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.9 | R.Ft | 45 | 100 | 58.39 | 0 | 2335.5 | C+S GST 18% I/P RD | 420.4 | 2755.9 | 2755.9 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 26.74 | R.Ft | 50 | 100 | 33.43 | 0 | 1337 | C+S GST 18% I/P RD | 240.66 | 1577.66 | 1577.66 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 116.635 | R.Ft | 50 | 100 | 145.79 | 0 | 5831.75 | C+S GST 18% I/P RD | 1049.72 | 6881.47 | 6881.47 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 46.04 | R.Ft | 50 | 100 | 57.55 | 0 | 2302 | C+S GST 18% I/P RD | 414.36 | 2716.36 | 2716.36 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B101 Window Sil | Italian Marble Sill- BC- | 77.346 | R.Ft | 45 | 100 | 87.01 | 0 | 3480.57 | C+S GST 18% I/P RD | 626.5 | 4107.07 | 4107.07 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 601 Window Sill Refuge Flat - 1 No. | Italian Marble Sill- BC- | 62.163 | R.Ft | 45 | 100 | 69.93 | 0 | 2797.34 | C+S GST 18% I/P RD | 503.52 | 3300.86 | 3300.86 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 501 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 45 | 100 | 87.01 | 0 | 3480.57 | C+S GST 18% I/P RD | 626.5 | 4107.07 | 4107.07 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 401 Window Sill | Italian Marble Sill- BC- | 77.346 | R.Ft | 45 | 100 | 87.01 | 0 | 3480.57 | C+S GST 18% I/P RD | 626.5 | 4107.07 | 4107.07 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 700 | 100 | 86.63 | 0 | 3465 | C+S GST 18% I/P RD | 623.7 | 4088.7 | 4088.7 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 758 | 97385 | 14 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1573 | B 1001 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.375 | R.Ft | 700 | 100 | 59.06 | 0 | 2362.5 | C+S GST 18% I/P RD | 425.26 | 2787.76 | 2787.76 | Approved | 0 | 0 | 2135 | 14 Dec 2022
GANGA DHAM TOWERS | 1275 | 97380 | 14 Dec 2022 |  | PARTH ENTERPRISES | K B N FABRICATION | EV - 1563 | B Bldg Safety Jali Work | M.S. Jali- DPo | 1354 | Sq.Ft | 11 | 100 | 372.35 | 0 | 14894 | C+S GST 0% I/P RD | 0 | 14894 | 14894 | Approved | 0 | 0 | 149 | 14 Dec 2022
GANGA DHAM TOWERS | 1274 | 97379 | 14 Dec 2022 |  | PARTH ENTERPRISES | MAHALAXMI FABRICATORS | EV - 1692 | A Safety Jali Fabrication Work | M.S. Jali- DPo | 485 | Sq.Ft | 11 | 100 | 133.38 | 0 | 5335 | C+S GST 18% I/P RD | 960.3 | 6295.3 | 6295.3 | Approved | 0 | 0 | 53 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 1101 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 4.72 | R.Ft | 50 | 100 | 5.9 | 0 | 236 | C+S GST 18% I/P RD | 42.48 | 278.48 | 278.48 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 901 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 1101 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 901 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.123 | R.Ft | 700 | 100 | 54.65 | 0 | 2186.1 | C+S GST 18% I/P RD | 393.5 | 2579.6 | 2579.6 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 901 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 700 | 100 | 46.46 | 0 | 1858.5 | C+S GST 18% I/P RD | 334.54 | 2193.04 | 2193.04 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 901 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 700 | 100 | 87.89 | 0 | 3515.4 | C+S GST 18% I/P RD | 632.78 | 4148.18 | 4148.18 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 537 | 97378 | 14 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1643 | A 201 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 116 | 14 Dec 2022
GANGA DHAM TOWERS | 371 | 97377 | 14 Dec 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1562 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | Hacking Work | 1048 | Sq.Ft | 2.5 | 100 | 65.5 | 0 | 2620 | CGST 0% URD I/P | 0 | 2620 | 2620 | Approved | 0 | 0 | 26 | 14 Dec 2022
GANGA DHAM TOWERS | 493 | 97376 | 14 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2018 | D Bldg Upper Terrace Floor External Plaster | External Plaster- BC | 2497.3929 | Sq.Ft | 28 | 100 | 1748.18 | 0 | 69927 | CGST 0% URD I/P | 0 | 69927 | 69927 | Approved | 0 | 0 | 699 | 14 Dec 2022
GANGA DHAM TOWERS | 804 | 97375 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1558 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 725 | Sq.Ft | 55 | 100 | 0 | 0 | 39875 | C+S GST 18% I/P RD | 7177.5 | 47052.5 | 47052.5 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 804 | 97375 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1558 | B 201 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 725 | Sq.Ft | 55 | 100 | 0 | 0 | 39875 | C+S GST 18% I/P RD | 7177.5 | 47052.5 | 47052.5 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 352 | Sq.Ft | 55 | 100 | 0 | 0 | 19360 | C+S GST 18% I/P RD | 3484.8 | 22844.8 | 22844.8 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 444 | Sq.Ft | 55 | 100 | 0 | 0 | 24420 | C+S GST 18% I/P RD | 4395.6 | 28815.6 | 28815.6 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 352 | Sq.Ft | 55 | 100 | 0 | 0 | 19360 | C+S GST 18% I/P RD | 3484.8 | 22844.8 | 22844.8 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 352 | Sq.Ft | 55 | 100 | 0 | 0 | 19360 | C+S GST 18% I/P RD | 3484.8 | 22844.8 | 22844.8 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 444 | Sq.Ft | 55 | 100 | 0 | 0 | 24420 | C+S GST 18% I/P RD | 4395.6 | 28815.6 | 28815.6 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 629 | 97374 | 14 Dec 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1550 | A 104 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 444 | Sq.Ft | 55 | 100 | 0 | 0 | 24420 | C+S GST 18% I/P RD | 4395.6 | 28815.6 | 28815.6 | Approved | 0 | 0 | 0 | 14 Dec 2022
GANGA DHAM TOWERS | 1120 | 97373 | 14 Dec 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1623 | Tower C Podium P1 slab Built-up Area (L) | RCC Superstructure (B-up area) | 4379 | Sq.Ft | 180 | 100 | 19705.5 | 0 | 788220 | C+S GST 18% I/P RD | 141879.6 | 930099.6 | 930099.6 | Approved | 0 | 0 | 7882 | 14 Dec 2022
GANGA DHAM TOWERS | 389 | 97368 | 13 Dec 2022 |  | SAGARSINGH BINDUSINGH TAK | PUNDLIK P MAHAJAN | EV - 1498 | Loading / Unloading Expenses | Unloading of Tile Adhesive | 9 | Metric Tonnes | 200 | 100 | 0 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 0 | 13 Dec 2022
GANGA DHAM TOWERS | 1296 | 97366 | 13 Dec 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1542 | Miscellaneous expenses | Marketing Operating Expenses | 8.2723 | Month | 25000 | 8.33 | 0 | 0 | 17227 | C+S GST 0% I/P RD | 0 | 17227 | 17227 | Approved | 0 | 0 | 0 | 13 Dec 2022
GANGA DHAM TOWERS | 630 | 97353 | 12 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1500 | A 401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 169 | R.Ft | 55 | 100 | 0 | 0 | 9295 | C+S GST 18% I/P RD | 1673.1 | 10968.1 | 10968.1 | Approved | 0 | 0 | 0 | 12 Dec 2022
GANGA DHAM TOWERS | 630 | 97353 | 12 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1500 | A 601 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 169 | R.Ft | 55 | 100 | 0 | 0 | 9295 | C+S GST 18% I/P RD | 1673.1 | 10968.1 | 10968.1 | Approved | 0 | 0 | 0 | 12 Dec 2022
GANGA DHAM TOWERS | 630 | 97353 | 12 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1500 | A 601 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 12 Dec 2022
GANGA DHAM TOWERS | 630 | 97353 | 12 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1500 | A 401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 454.5455 | Sq.Ft | 55 | 100 | 0 | 0 | 25000 | C+S GST 18% I/P RD | 4500 | 29500 | 29500 | Approved | 0 | 0 | 0 | 12 Dec 2022
GANGA DHAM TOWERS | 1337 | 97349 | 12 Dec 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1611 | HO Expensess (L) | Printer Repairing- | 11.85 | Month | 8000 | 8.33 | 0 | 0 | 7900 | C+S GST 18% I/P RD | 1422 | 9322 | 9322 | Approved | 0 | 0 | 79 | 12 Dec 2022
GANGA DHAM TOWERS | 1337 | 97348 | 12 Dec 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1612 | HO Expensess (L) | Printer Repairing- | 11.9995 | Month | 8000 | 8.33 | 0 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 80 | 12 Dec 2022
GANGA DHAM TOWERS | 1337 | 97347 | 12 Dec 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1613 | HO Expensess (L) | Printer Repairing- | 11.925 | Month | 8000 | 8.33 | 0 | 0 | 7950 | C+S GST 18% I/P RD | 1431 | 9381 | 9381 | Approved | 0 | 0 | 80 | 12 Dec 2022
GANGA DHAM TOWERS | 1338 | 97346 | 12 Dec 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1605 | HO Expensess (L) | Toner refilling | 11.9965 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 12 Dec 2022
GANGA DHAM TOWERS | 1338 | 97345 | 12 Dec 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1598 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 12 Dec 2022
GANGA DHAM TOWERS | 1338 | 97344 | 12 Dec 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1599 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 12 Dec 2022
GANGA DHAM TOWERS | 413 | 97340 | 12 Dec 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1637 | Sales office Garden Maintenance | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 12 Dec 2022
GANGA DHAM TOWERS | 178 | 97339 | 12 Dec 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1672 | Sales office Garden Maintenance | Garden work. | 58.995 | Day | 420.83 | 100 | 0 | 0 | 24826.87 | C+S GST 18% I/P RD | 4468.84 | 29295.71 | 29295.71 | Approved | 0 | 0 | 248 | 12 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 601 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 301 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 701 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 102 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 302 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 702 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 101 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 501 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 401 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 203 Terrace False Ceiling | Painting work (M+L) -BC | 118.863 | Sq.Ft | 35 | 100 | 0 | 0 | 4160.21 | C+S GST 18% I/P RD | 748.84 | 4909.05 | 4909.05 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 502 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 504 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 602 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 104 Terrace False Ceiling | Painting work (M+L) -BC | 140.472 | Sq.Ft | 35 | 100 | 0 | 0 | 4916.52 | C+S GST 18% I/P RD | 884.98 | 5801.5 | 5801.5 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 201 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 604 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 636 | 97318 | 10 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 2054 | A 202 Terrace False Ceiling | Painting work (M+L) -BC | 159.849 | Sq.Ft | 35 | 100 | 0 | 0 | 5594.72 | C+S GST 18% I/P RD | 1007.04 | 6601.76 | 6601.76 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 630 | 97317 | 10 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1504 | A 1501 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 545.4545 | Sq.Ft | 55 | 100 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 630 | 97317 | 10 Dec 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1504 | A 1501 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 181.8182 | R.Ft | 55 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 0 | 10 Dec 2022
GANGA DHAM TOWERS | 631 | 97316 | 10 Dec 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1502 | A 1501 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 545.45 | Sq.Ft | 20 | 100 | 272.73 | 0 | 10909 | C+S GST 18% I/P RD | 1963.62 | 12872.62 | 12872.62 | Approved | 0 | 0 | 109 | 10 Dec 2022
GANGA DHAM TOWERS | 1407 | 97311 | 09 Dec 2022 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 1596 | EWS STP RCC | RCC Work STP | 39429.5 | Ltrs | 3.75 | 40 | 1478.61 | 0 | 59144.25 | CGST 0% URD I/P | 0 | 59144.25 | 59144.25 | Approved | 0 | 0 | 1479 | 09 Dec 2022
GANGA DHAM TOWERS | 1407 | 97311 | 09 Dec 2022 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 1596 | EWS STP RCC | RCC Work STP | 39429.5 | Ltrs | 3.75 | 40 | 1478.61 | 0 | 59144.25 | CGST 0% URD I/P | 0 | 59144.25 | 59144.25 | Approved | 0 | 0 | 1479 | 09 Dec 2022
GANGA DHAM TOWERS | 1407 | 97311 | 09 Dec 2022 |  | VYANKAT SAI CONSTRUCTION | VYANKAT SAI CONSTRUCTION | EV - 1596 | EWS STP RCC | RCC Work STP | 39429.5 | Ltrs | 3.75 | 20 | 739.3 | 0 | 29572.13 | CGST 0% URD I/P | 0 | 29572.13 | 29572.13 | Approved | 0 | 0 | 1479 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 2201 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 800 | 100 | 53.1 | 0 | 2124 | C+S GST 18% I/P RD | 382.32 | 2506.32 | 2506.32 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 2201 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 800 | 100 | 100.44 | 0 | 4017.6 | C+S GST 18% I/P RD | 723.16 | 4740.76 | 4740.76 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.354 | R.Ft | 21 | 100 | 8.06 | 0 | 322.43 | C+S GST 18% I/P RD | 58.04 | 380.47 | 380.47 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1302 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.642 | R.Ft | 21 | 100 | 8.21 | 0 | 328.48 | C+S GST 18% I/P RD | 59.12 | 387.6 | 387.6 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 105.786 | R.Ft | 55 | 100 | 145.46 | 0 | 5818.23 | C+S GST 18% I/P RD | 1047.28 | 6865.51 | 6865.51 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 28.422 | R.Ft | 55 | 100 | 39.08 | 0 | 1563.21 | C+S GST 18% I/P RD | 281.38 | 1844.59 | 1844.59 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 56.106 | R.Ft | 55 | 100 | 77.15 | 0 | 3085.83 | C+S GST 18% I/P RD | 555.44 | 3641.27 | 3641.27 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Master Bed Marble Flooring | Italian marble Skirting - BCo | 59.058 | R.Ft | 55 | 100 | 81.2 | 0 | 3248.19 | C+S GST 18% I/P RD | 584.68 | 3832.87 | 3832.87 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1701 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 750 | 100 | 49.78 | 0 | 1991.25 | C+S GST 18% I/P RD | 358.42 | 2349.67 | 2349.67 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 537 | 97308 | 09 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1602 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 21 | 100 | 11.41 | 0 | 456.25 | C+S GST 18% I/P RD | 82.12 | 538.37 | 538.37 | Approved | 0 | 0 | 230 | 09 Dec 2022
GANGA DHAM TOWERS | 389 | 97290 | 08 Dec 2022 |  | SAGARSINGH BINDUSINGH TAK | PUNDLIK P MAHAJAN | EV - 1488 | Loading / Unloading Expenses | Unloading of Tile Adhesive | 6.5 | Metric Tonnes | 200 | 100 | 0 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 0 | 08 Dec 2022
GANGA DHAM TOWERS | 1052 | 97286 | 08 Dec 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1547 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 08 Dec 2022
GANGA DHAM TOWERS | 1383 | 97283 | 08 Dec 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1543 | Professional Consultancy (Finalcial) | Professional Fees | 0.9495 | Month | 116666.666 | 100 | 0 | 0 | 110770 | CGST 0% URD I/P | 0 | 110770 | 110770 | Approved | 0 | 0 | 11077 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 27th Floor 2701 | 15 Amp Point for Inverter Point | 17 | No. | 220 | 35 | 32.73 | 0 | 1309 | C+S GST 18% I/P RD | 235.62 | 1544.62 | 1544.62 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 27th Floor 2702 | 15 Amp Point for Inverter Point | 14 | No. | 220 | 35 | 26.95 | 0 | 1078 | C+S GST 18% I/P RD | 194.04 | 1272.04 | 1272.04 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | 6 AMP Plug point (Dependent) | 23 | No. | 67 | 35 | 13.48 | 0 | 539.35 | C+S GST 18% I/P RD | 97.08 | 636.43 | 636.43 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | 6 AMP Plug point (Dependent) | 23 | No. | 67 | 35 | 13.48 | 0 | 539.35 | C+S GST 18% I/P RD | 97.08 | 636.43 | 636.43 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | 6 AMP Plug point (Dependent) | 40 | No. | 67 | 35 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | 6 AMP Plug point (Dependent) | 23 | No. | 67 | 35 | 13.48 | 0 | 539.35 | C+S GST 18% I/P RD | 97.08 | 636.43 | 636.43 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | 6 AMP Plug point (Dependent) | 40 | No. | 67 | 35 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Conduit Piping work- BC | 226.32 | R.Ft | 2.75 | 100 | 15.56 | 0 | 622.38 | C+S GST 18% I/P RD | 112.02 | 734.4 | 734.4 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Conduit Piping work- BC | 226.32 | R.Ft | 2.75 | 100 | 15.56 | 0 | 622.38 | C+S GST 18% I/P RD | 112.02 | 734.4 | 734.4 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Conduit Piping work- BC | 167.28 | R.Ft | 2.75 | 100 | 11.5 | 0 | 460.02 | C+S GST 18% I/P RD | 82.8 | 542.82 | 542.82 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Conduit Piping work- BC | 167.28 | R.Ft | 2.75 | 100 | 11.5 | 0 | 460.02 | C+S GST 18% I/P RD | 82.8 | 542.82 | 542.82 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Conduit Piping work- BC | 226.32 | R.Ft | 2.75 | 100 | 15.56 | 0 | 622.38 | C+S GST 18% I/P RD | 112.02 | 734.4 | 734.4 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | 6 AMP Plug point (Independent) | 58 | No. | 200 | 35 | 101.5 | 0 | 4060 | C+S GST 18% I/P RD | 730.8 | 4790.8 | 4790.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | 6 AMP Plug point (Independent) | 38 | No. | 200 | 35 | 66.5 | 0 | 2660 | C+S GST 18% I/P RD | 478.8 | 3138.8 | 3138.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | 6 AMP Plug point (Independent) | 58 | No. | 200 | 35 | 101.5 | 0 | 4060 | C+S GST 18% I/P RD | 730.8 | 4790.8 | 4790.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | 6 AMP Plug point (Independent) | 38 | No. | 200 | 35 | 66.5 | 0 | 2660 | C+S GST 18% I/P RD | 478.8 | 3138.8 | 3138.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | 6 AMP Plug point (Independent) | 38 | No. | 200 | 35 | 66.5 | 0 | 2660 | C+S GST 18% I/P RD | 478.8 | 3138.8 | 3138.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | 6 AMP Plug point (Independent) | 58 | No. | 200 | 35 | 101.5 | 0 | 4060 | C+S GST 18% I/P RD | 730.8 | 4790.8 | 4790.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Secondary Light Points (Looping) | 38 | No. | 67 | 35 | 22.28 | 0 | 891.1 | C+S GST 18% I/P RD | 160.4 | 1051.5 | 1051.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Secondary Light Points (Looping) | 60 | No. | 67 | 35 | 35.18 | 0 | 1407 | C+S GST 18% I/P RD | 253.26 | 1660.26 | 1660.26 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Secondary Light Points (Looping) | 38 | No. | 67 | 35 | 22.28 | 0 | 891.1 | C+S GST 18% I/P RD | 160.4 | 1051.5 | 1051.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Secondary Light Points (Looping) | 38 | No. | 67 | 35 | 22.28 | 0 | 891.1 | C+S GST 18% I/P RD | 160.4 | 1051.5 | 1051.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Secondary Light Points (Looping) | 60 | No. | 67 | 35 | 35.18 | 0 | 1407 | C+S GST 18% I/P RD | 253.26 | 1660.26 | 1660.26 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Secondary Light Points (Looping) | 60 | No. | 67 | 35 | 35.18 | 0 | 1407 | C+S GST 18% I/P RD | 253.26 | 1660.26 | 1660.26 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Power Point (2.5 & 1.5 Sqmm) | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Conduit Piping work- BC | 167.28 | R.Ft | 2.75 | 100 | 11.5 | 0 | 460.02 | C+S GST 18% I/P RD | 82.8 | 542.82 | 542.82 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Exhaust Fan Point | 6 | No. | 200 | 35 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Exhaust Fan Point | 6 | No. | 200 | 35 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Exhaust Fan Point | 7 | No. | 200 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Exhaust Fan Point | 6 | No. | 200 | 35 | 10.5 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Exhaust Fan Point | 7 | No. | 200 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Exhaust Fan Point | 7 | No. | 200 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Curtain Point | 12 | No. | 200 | 35 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Curtain Point | 16 | No. | 200 | 35 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Curtain Point | 16 | No. | 200 | 35 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Curtain Point | 12 | No. | 200 | 35 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Curtain Point | 16 | No. | 200 | 35 | 28 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Curtain Point | 12 | No. | 200 | 35 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 28th Floor 2802 | 15 Amp Point for Inverter Point | 14 | No. | 220 | 35 | 26.95 | 0 | 1078 | C+S GST 18% I/P RD | 194.04 | 1272.04 | 1272.04 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | 6 AMP Plug point (Dependent) | 40 | No. | 67 | 35 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 28th Floor 2801 | 15 Amp Point for Inverter Point | 17 | No. | 220 | 35 | 32.73 | 0 | 1309 | C+S GST 18% I/P RD | 235.62 | 1544.62 | 1544.62 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 29th Floor 2901 | 15 Amp Point for Inverter Point | 17 | No. | 220 | 35 | 32.73 | 0 | 1309 | C+S GST 18% I/P RD | 235.62 | 1544.62 | 1544.62 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B 29th Floor 2902 | 15 Amp Point for Inverter Point | 14 | No. | 220 | 35 | 26.95 | 0 | 1078 | C+S GST 18% I/P RD | 194.04 | 1272.04 | 1272.04 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Data Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Data Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Data Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Wi-Fi Point | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | TV/Tel DB Fixing | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2901 Internal Electrical work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2701 Internal Electrical work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2801 Internal Electrical work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2802 Internal Electrical work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2702 Internal Electrical work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 399 | 97282 | 08 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1663 | B Bldg Flat No. 2902 Internal Electrical work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1480 | 08 Dec 2022
GANGA DHAM TOWERS | 149 | 97281 | 08 Dec 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1559 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3986 | No. | 4 | 100 | 0 | 0 | 15944 | CGST 0% URD I/P | 0 | 15944 | 15944 | Approved | 0 | 0 | 0 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2803 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2802 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2703 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2704 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2702 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2701 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2804 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 359 | 97280 | 08 Dec 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1565 | A Bldg Flat No.-2801 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 2306 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 22 | 100 | 63.09 | 0 | 2523.71 | CGST 0% URD I/P | 0 | 2523.71 | 2523.71 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Staff Toilet dado | Dado BC | 110.214 | Sq.Ft | 21 | 100 | 57.86 | 0 | 2314.49 | CGST 0% URD I/P | 0 | 2314.49 | 2314.49 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 17 | 100 | 18.94 | 0 | 757.5 | CGST 0% URD I/P | 0 | 757.5 | 757.5 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 17 | 100 | 9.23 | 0 | 369.34 | CGST 0% URD I/P | 0 | 369.34 | 369.34 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 17 | 100 | 22.85 | 0 | 914.02 | CGST 0% URD I/P | 0 | 914.02 | 914.02 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 17 | 100 | 22.85 | 0 | 914.02 | CGST 0% URD I/P | 0 | 914.02 | 914.02 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 17 | 100 | 16.67 | 0 | 666.93 | CGST 0% URD I/P | 0 | 666.93 | 666.93 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | CGST 0% URD I/P | 0 | 729.18 | 729.18 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Children Toilet | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | CGST 0% URD I/P | 0 | 584.46 | 584.46 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Staff Toilet dado | L Groove - BCV | 14.607 | R.Ft | 20 | 100 | 7.3 | 0 | 292.14 | CGST 0% URD I/P | 0 | 292.14 | 292.14 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Dry Balcony dado | L Groove - BCV | 5.022 | R.Ft | 20 | 100 | 2.51 | 0 | 100.44 | CGST 0% URD I/P | 0 | 100.44 | 100.44 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | CGST 0% URD I/P | 0 | 497.7 | 497.7 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | CGST 0% URD I/P | 0 | 584.46 | 584.46 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Parents Toilet dado | L Groove - BCV | 36.5245 | R.Ft | 20 | 100 | 18.26 | 0 | 730.49 | CGST 0% URD I/P | 0 | 730.49 | 730.49 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Staff Toilet dado | L Groove - BCV | 13.821 | R.Ft | 20 | 100 | 6.91 | 0 | 276.42 | CGST 0% URD I/P | 0 | 276.42 | 276.42 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | CGST 0% URD I/P | 0 | 79.74 | 79.74 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Children Toilet dado | L Groove - BCV | 33.804 | R.Ft | 20 | 100 | 16.9 | 0 | 676.08 | CGST 0% URD I/P | 0 | 676.08 | 676.08 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Powder Toilet dado | L Groove - BCV | 29.6905 | R.Ft | 20 | 100 | 14.85 | 0 | 593.81 | CGST 0% URD I/P | 0 | 593.81 | 593.81 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Master Toilet dado | L Groove - BCV | 28.989 | R.Ft | 20 | 100 | 14.49 | 0 | 579.78 | CGST 0% URD I/P | 0 | 579.78 | 579.78 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 21 | 100 | 20.6 | 0 | 823.85 | CGST 0% URD I/P | 0 | 823.85 | 823.85 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 35.847 | Sq.Ft | 21 | 100 | 18.82 | 0 | 752.79 | CGST 0% URD I/P | 0 | 752.79 | 752.79 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Children Toilet Flooring | Vitrified Flooring -BC | 44.172 | Sq.Ft | 21 | 100 | 23.19 | 0 | 927.61 | CGST 0% URD I/P | 0 | 927.61 | 927.61 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.288 | Sq.Ft | 21 | 100 | 23.78 | 0 | 951.05 | CGST 0% URD I/P | 0 | 951.05 | 951.05 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.466 | Sq.Ft | 21 | 100 | 24.92 | 0 | 996.79 | CGST 0% URD I/P | 0 | 996.79 | 996.79 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.61 | Sq.Ft | 21 | 100 | 10.82 | 0 | 432.81 | CGST 0% URD I/P | 0 | 432.81 | 432.81 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Dry Balcony dado | Dado BC | 71.055 | Sq.Ft | 22 | 100 | 39.08 | 0 | 1563.21 | CGST 0% URD I/P | 0 | 1563.21 | 1563.21 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 22 | 100 | 73.43 | 0 | 2937.13 | CGST 0% URD I/P | 0 | 2937.13 | 2937.13 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 22 | 100 | 48.19 | 0 | 1927.73 | CGST 0% URD I/P | 0 | 1927.73 | 1927.73 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 22 | 100 | 66.42 | 0 | 2656.96 | CGST 0% URD I/P | 0 | 2656.96 | 2656.96 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Staff Toilet dado | Dado BC | 116.262 | Sq.Ft | 17 | 100 | 49.41 | 0 | 1976.45 | CGST 0% URD I/P | 0 | 1976.45 | 1976.45 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 24 | 100 | 20.98 | 0 | 839.38 | CGST 0% URD I/P | 0 | 839.38 | 839.38 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 24 | 100 | 35.18 | 0 | 1407.02 | CGST 0% URD I/P | 0 | 1407.02 | 1407.02 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 24 | 100 | 39.87 | 0 | 1594.94 | CGST 0% URD I/P | 0 | 1594.94 | 1594.94 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 1301 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 24 | 100 | 38.17 | 0 | 1526.69 | CGST 0% URD I/P | 0 | 1526.69 | 1526.69 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Master Toilet dado | Dado BC | 60 | Sq.Ft | 20 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 20 | 100 | 19.33 | 0 | 773.1 | CGST 0% URD I/P | 0 | 773.1 | 773.1 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 20 | 100 | 36.79 | 0 | 1471.5 | CGST 0% URD I/P | 0 | 1471.5 | 1471.5 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Children Toilet | Dado BC | 38.448 | Sq.Ft | 20 | 100 | 19.22 | 0 | 768.96 | CGST 0% URD I/P | 0 | 768.96 | 768.96 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 18 | 100 | 50.02 | 0 | 2000.86 | CGST 0% URD I/P | 0 | 2000.86 | 2000.86 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Children Toilet | Dado BC | 169.587 | Sq.Ft | 18 | 100 | 76.31 | 0 | 3052.57 | CGST 0% URD I/P | 0 | 3052.57 | 3052.57 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 18 | 100 | 61.77 | 0 | 2470.82 | CGST 0% URD I/P | 0 | 2470.82 | 2470.82 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Dry Balcony dado | Dado BC | 82.83 | Sq.Ft | 18 | 100 | 37.27 | 0 | 1490.94 | CGST 0% URD I/P | 0 | 1490.94 | 1490.94 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97278 | 08 Dec 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1577 | A 902 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 18 | 100 | 38.58 | 0 | 1543.05 | CGST 0% URD I/P | 0 | 1543.05 | 1543.05 | Approved | 0 | 0 | 503 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2001 Kitchen Vitrified Flooring | Vitrified Skirting BC | 40.446 | R.Ft | 28 | 100 | 28.31 | 0 | 1132.49 | C+S GST 18% I/P RD | 203.84 | 1336.33 | 1336.33 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2001 Staff Toilet dado | Dado BC | 110.214 | Sq.Ft | 24 | 100 | 66.13 | 0 | 2645.14 | C+S GST 18% I/P RD | 476.12 | 3121.26 | 3121.26 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2001 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.61 | Sq.Ft | 24 | 100 | 12.37 | 0 | 494.64 | C+S GST 18% I/P RD | 89.04 | 583.68 | 583.68 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1201 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 51.597 | R.Ft | 50 | 100 | 64.5 | 0 | 2579.85 | C+S GST 18% I/P RD | 464.38 | 3044.23 | 3044.23 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 101 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 51.597 | R.Ft | 45 | 100 | 58.05 | 0 | 2321.87 | C+S GST 18% I/P RD | 417.94 | 2739.81 | 2739.81 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2001 Kitchen dado | L Groove - BCV | 13.878 | R.Ft | 20 | 100 | 6.94 | 0 | 277.56 | C+S GST 18% I/P RD | 49.96 | 327.52 | 327.52 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1601 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2201 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.123 | R.Ft | 800 | 100 | 62.46 | 0 | 2498.4 | C+S GST 18% I/P RD | 449.72 | 2948.12 | 2948.12 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 2201 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 800 | 100 | 53.1 | 0 | 2124 | C+S GST 18% I/P RD | 382.32 | 2506.32 | 2506.32 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1302 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 53.964 | R.Ft | 55 | 100 | 74.2 | 0 | 2968.02 | C+S GST 18% I/P RD | 534.24 | 3502.26 | 3502.26 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1701 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 51.597 | R.Ft | 55 | 100 | 70.95 | 0 | 2837.84 | C+S GST 18% I/P RD | 510.82 | 3348.66 | 3348.66 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1601 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 51.597 | R.Ft | 55 | 100 | 70.95 | 0 | 2837.84 | C+S GST 18% I/P RD | 510.82 | 3348.66 | 3348.66 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1602 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 53.964 | R.Ft | 55 | 100 | 74.2 | 0 | 2968.02 | C+S GST 18% I/P RD | 534.24 | 3502.26 | 3502.26 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 537 | 97277 | 08 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1579 | A 1601 Dry Balcony dado | Dado BC | 71.055 | Sq.Ft | 22 | 100 | 39.08 | 0 | 1563.21 | C+S GST 18% I/P RD | 281.38 | 1844.59 | 1844.59 | Approved | 0 | 0 | 273 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 2001 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 28.665 | R.Ft | 60 | 100 | 43 | 0 | 1719.9 | C+S GST 18% I/P RD | 309.58 | 2029.48 | 2029.48 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 2401 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 28.665 | R.Ft | 60 | 100 | 43 | 0 | 1719.9 | C+S GST 18% I/P RD | 309.58 | 2029.48 | 2029.48 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 2201 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 28.665 | R.Ft | 60 | 100 | 43 | 0 | 1719.9 | C+S GST 18% I/P RD | 309.58 | 2029.48 | 2029.48 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 101 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 17.199 | R.Ft | 45 | 100 | 19.35 | 0 | 773.96 | C+S GST 18% I/P RD | 139.32 | 913.28 | 913.28 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 1601 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 45.864 | R.Ft | 55 | 100 | 63.06 | 0 | 2522.52 | C+S GST 18% I/P RD | 454.06 | 2976.58 | 2976.58 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 1602 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 17.988 | R.Ft | 55 | 100 | 24.73 | 0 | 989.34 | C+S GST 18% I/P RD | 178.08 | 1167.42 | 1167.42 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 1302 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 29.98 | R.Ft | 55 | 100 | 41.22 | 0 | 1648.9 | C+S GST 18% I/P RD | 296.8 | 1945.7 | 1945.7 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 1701 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 28.665 | R.Ft | 55 | 100 | 39.41 | 0 | 1576.58 | C+S GST 18% I/P RD | 283.78 | 1860.36 | 1860.36 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 641 | 97276 | 08 Dec 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1641 | A 1201 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 28.665 | R.Ft | 50 | 100 | 35.83 | 0 | 1433.25 | C+S GST 18% I/P RD | 257.98 | 1691.23 | 1691.23 | Approved | 0 | 0 | 141 | 08 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.401 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.403 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.501 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.504 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.505 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.502 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.402 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.503 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.405 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 15 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 15 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 6 AMP Plug point (Independent) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 15 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | 6 AMP Plug point (Independent) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 15 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.404 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Gyser Point BC | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Exhaust Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 15 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 15 | 6.75 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Bell Point BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 15 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Wall Light Point | 6 | No. | 200 | 15 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 15 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 15 | 1.51 | 0 | 60.3 | C+S GST 18% I/P RD | 10.86 | 71.16 | 71.16 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.201 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.204 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1103 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.202 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.105 Electrical Work | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1104 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.303 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1201 Electrical Work | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.304 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1101 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.102 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1202 Electrical Work | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.302 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1105 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.203 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.101 Electrical Work | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.305 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 15 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1203 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.103 Electrical Work | Fan Point | 3 | No. | 200 | 15 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1204 Electrical Work | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1205 Electrical Work | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.104 Electrical Work | Telephone Point | 3 | No. | 220 | 15 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.205 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.301 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 15 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 452 | 97261 | 07 Dec 2022 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1658 | D Bldg Flat No.1102 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 586 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 1101 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 901 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 805 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 1001 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 1005 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 801 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 701 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 698 | 97258 | 07 Dec 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1538 | D 905 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 358 | Sq.Ft | 4 | 100 | 35.8 | 0 | 1432 | CGST 0% URD I/P | 0 | 1432 | 1432 | Approved | 0 | 0 | 115 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Ceiling Gyp. Plaster 10th to 11th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Ceiling Gyp. Plaster 11th to Terrace Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Ceiling Gyp. Plaster 9th to 10th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Ceiling Gyp. Plaster 9th to 10th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Ceiling Gyp. Plaster 8th to 9th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Ceiling Gyp. Plaster 10th to 11th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Ceiling Gyp. Plaster 11th to Terrace Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | CGST 0% URD I/P | 0 | 648 | 648 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Wall Gyp. Plaster 9th to 10th Fl. | Tikki Dhada (L) | 418 | Sq.Ft | 9 | 100 | 94.05 | 0 | 3762 | CGST 0% URD I/P | 0 | 3762 | 3762 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Wall Gyp. Plaster 10th to 11th Fl. | Tikki Dhada (L) | 404 | Sq.Ft | 9 | 100 | 90.9 | 0 | 3636 | CGST 0% URD I/P | 0 | 3636 | 3636 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Wall Gyp. Plaster 9th to 10th Fl. | Tikki Dhada (L) | 404 | Sq.Ft | 9 | 100 | 90.9 | 0 | 3636 | CGST 0% URD I/P | 0 | 3636 | 3636 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Fire St.case Wall Gyp. Plaster 11th to Terrace Fl. | Tikki Dhada (L) | 404 | Sq.Ft | 9 | 100 | 90.9 | 0 | 3636 | CGST 0% URD I/P | 0 | 3636 | 3636 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 797 | 97257 | 07 Dec 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1595 | D Main St.case Wall Gyp. Plaster 10th to 11th Fl. | Tikki Dhada (L) | 418 | Sq.Ft | 9 | 100 | 94.05 | 0 | 3762 | CGST 0% URD I/P | 0 | 3762 | 3762 | Approved | 0 | 0 | 230 | 07 Dec 2022
GANGA DHAM TOWERS | 551 | 97256 | 07 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises |  | A 2304 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | C+S GST 18% I/P RD | 93.86 | 615.28 | 615.28 |  | 0 | 0 | 5 | 07 Dec 2022
GANGA DHAM TOWERS | 537 | 97255 | 07 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1578 | A 2401 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 24 | 100 | 23.79 | 0 | 951.48 | C+S GST 18% I/P RD | 171.26 | 1122.74 | 1122.74 | Approved | 0 | 0 | 22 | 07 Dec 2022
GANGA DHAM TOWERS | 537 | 97255 | 07 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1578 | A 2001 Kitchen dado | Dado BC | 32.976 | Sq.Ft | 28 | 100 | 23.08 | 0 | 923.33 | C+S GST 18% I/P RD | 166.2 | 1089.53 | 1089.53 | Approved | 0 | 0 | 22 | 07 Dec 2022
GANGA DHAM TOWERS | 537 | 97255 | 07 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1578 | A 2401 Staff Room Vitrified Flooring | Vitrified Skirting BC | 15.354 | R.Ft | 24 | 100 | 9.21 | 0 | 368.5 | C+S GST 18% I/P RD | 66.34 | 434.84 | 434.84 | Approved | 0 | 0 | 22 | 07 Dec 2022
GANGA DHAM TOWERS | 1133 | 97246 | 06 Dec 2022 |  | BASSAPPA CHAVAN | NAMANNA RATHOD | EV - 2348 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 18 | No. | 800 | 100 | 0 | 0 | 14400 | CGST 0% URD I/P | 0 | 14400 | 14400 | Approved | 0 | 0 | 144 | 06 Dec 2022
GANGA DHAM TOWERS | 1162 | 97245 | 06 Dec 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1590 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2302 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 54.1333 | R.Ft | 60 | 100 | 81.2 | 0 | 3248 | C+S GST 18% I/P RD | 584.64 | 3832.64 | 3832.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2302 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 42.8167 | R.Ft | 60 | 100 | 64.23 | 0 | 2569 | C+S GST 18% I/P RD | 462.42 | 3031.42 | 3031.42 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2202 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 94.5833 | R.Ft | 60 | 100 | 141.87 | 0 | 5675 | C+S GST 18% I/P RD | 1021.5 | 6696.5 | 6696.5 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2101 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 48.4667 | R.Ft | 60 | 100 | 72.7 | 0 | 2908 | C+S GST 18% I/P RD | 523.44 | 3431.44 | 3431.44 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2202 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 42.8167 | R.Ft | 60 | 100 | 64.23 | 0 | 2569 | C+S GST 18% I/P RD | 462.42 | 3031.42 | 3031.42 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2401 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 37.8833 | R.Ft | 60 | 100 | 56.82 | 0 | 2273 | C+S GST 18% I/P RD | 409.14 | 2682.14 | 2682.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2101 Living,Dining,Ent.Lobby | Italian Marble Champher & Polish | 149 | R.Ft | 60 | 100 | 223.5 | 0 | 8940 | C+S GST 18% I/P RD | 1609.2 | 10549.2 | 10549.2 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2101 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 55.6167 | R.Ft | 60 | 100 | 83.43 | 0 | 3337 | C+S GST 18% I/P RD | 600.66 | 3937.66 | 3937.66 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2302 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 94.5833 | R.Ft | 60 | 100 | 141.87 | 0 | 5675 | C+S GST 18% I/P RD | 1021.5 | 6696.5 | 6696.5 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.2833 | R.Ft | 60 | 100 | 132.42 | 0 | 5297 | C+S GST 18% I/P RD | 953.46 | 6250.46 | 6250.46 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2102 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 39.9667 | R.Ft | 60 | 100 | 59.95 | 0 | 2398 | C+S GST 18% I/P RD | 431.64 | 2829.64 | 2829.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2102 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.5167 | R.Ft | 60 | 100 | 75.78 | 0 | 3031 | C+S GST 18% I/P RD | 545.58 | 3576.58 | 3576.58 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2401 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.0167 | R.Ft | 60 | 100 | 103.53 | 0 | 4141 | C+S GST 18% I/P RD | 745.38 | 4886.38 | 4886.38 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 172.6667 | R.Ft | 60 | 100 | 259 | 0 | 10360 | C+S GST 18% I/P RD | 1864.8 | 12224.8 | 12224.8 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2401 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.9167 | R.Ft | 60 | 100 | 77.88 | 0 | 3115 | C+S GST 18% I/P RD | 560.7 | 3675.7 | 3675.7 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 2202 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 54.1333 | R.Ft | 60 | 100 | 81.2 | 0 | 3248 | C+S GST 18% I/P RD | 584.64 | 3832.64 | 3832.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1502 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 57.4364 | R.Ft | 55 | 100 | 78.98 | 0 | 3159 | C+S GST 18% I/P RD | 568.62 | 3727.62 | 3727.62 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1702 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 39.9636 | R.Ft | 55 | 100 | 54.95 | 0 | 2198 | C+S GST 18% I/P RD | 395.64 | 2593.64 | 2593.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1801 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 184.1636 | R.Ft | 55 | 100 | 253.22 | 0 | 10129 | C+S GST 18% I/P RD | 1823.22 | 11952.22 | 11952.22 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1801 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 40.4182 | R.Ft | 55 | 100 | 55.58 | 0 | 2223 | C+S GST 18% I/P RD | 400.14 | 2623.14 | 2623.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1801 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 73.6182 | R.Ft | 55 | 100 | 101.23 | 0 | 4049 | C+S GST 18% I/P RD | 728.82 | 4777.82 | 4777.82 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1602 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 57.4364 | R.Ft | 55 | 100 | 78.98 | 0 | 3159 | C+S GST 18% I/P RD | 568.62 | 3727.62 | 3727.62 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1602 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 45.6727 | R.Ft | 55 | 100 | 62.8 | 0 | 2512 | C+S GST 18% I/P RD | 452.16 | 2964.16 | 2964.16 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1902 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.5273 | R.Ft | 55 | 100 | 69.48 | 0 | 2779 | C+S GST 18% I/P RD | 500.22 | 3279.22 | 3279.22 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1902 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 39.9636 | R.Ft | 55 | 100 | 54.95 | 0 | 2198 | C+S GST 18% I/P RD | 395.64 | 2593.64 | 2593.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 184.1636 | R.Ft | 55 | 100 | 253.22 | 0 | 10129 | C+S GST 18% I/P RD | 1823.22 | 11952.22 | 11952.22 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1601 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.9273 | R.Ft | 55 | 100 | 71.4 | 0 | 2856 | C+S GST 18% I/P RD | 514.08 | 3370.08 | 3370.08 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.2727 | R.Ft | 55 | 100 | 121.37 | 0 | 4855 | C+S GST 18% I/P RD | 873.9 | 5728.9 | 5728.9 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1502 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 100.8909 | R.Ft | 55 | 100 | 138.72 | 0 | 5549 | C+S GST 18% I/P RD | 998.82 | 6547.82 | 6547.82 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1502 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 45.6727 | R.Ft | 55 | 100 | 62.8 | 0 | 2512 | C+S GST 18% I/P RD | 452.16 | 2964.16 | 2964.16 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1902 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.2727 | R.Ft | 55 | 100 | 121.37 | 0 | 4855 | C+S GST 18% I/P RD | 873.9 | 5728.9 | 5728.9 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1401 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 55.3818 | R.Ft | 55 | 100 | 76.15 | 0 | 3046 | C+S GST 18% I/P RD | 548.28 | 3594.28 | 3594.28 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1702 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.5273 | R.Ft | 55 | 100 | 69.48 | 0 | 2779 | C+S GST 18% I/P RD | 500.22 | 3279.22 | 3279.22 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 94.6 | R.Ft | 45 | 100 | 106.43 | 0 | 4257 | C+S GST 18% I/P RD | 766.26 | 5023.26 | 5023.26 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 102 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 39.9556 | R.Ft | 45 | 100 | 44.95 | 0 | 1798 | C+S GST 18% I/P RD | 323.64 | 2121.64 | 2121.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 702 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 54.1333 | R.Ft | 45 | 100 | 60.9 | 0 | 2436 | C+S GST 18% I/P RD | 438.48 | 2874.48 | 2874.48 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 702 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 42.8222 | R.Ft | 45 | 100 | 48.17 | 0 | 1927 | C+S GST 18% I/P RD | 346.86 | 2273.86 | 2273.86 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 181.1778 | R.Ft | 45 | 100 | 203.83 | 0 | 8153 | C+S GST 18% I/P RD | 1467.54 | 9620.54 | 9620.54 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 401 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 37.8889 | R.Ft | 45 | 100 | 42.63 | 0 | 1705 | C+S GST 18% I/P RD | 306.9 | 2011.9 | 2011.9 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 172.6667 | R.Ft | 45 | 100 | 194.25 | 0 | 7770 | C+S GST 18% I/P RD | 1398.6 | 9168.6 | 9168.6 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 161.1556 | R.Ft | 45 | 100 | 181.3 | 0 | 7252 | C+S GST 18% I/P RD | 1305.36 | 8557.36 | 8557.36 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.2889 | R.Ft | 45 | 100 | 99.33 | 0 | 3973 | C+S GST 18% I/P RD | 715.14 | 4688.14 | 4688.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 401 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.0222 | R.Ft | 45 | 100 | 77.65 | 0 | 3106 | C+S GST 18% I/P RD | 559.08 | 3665.08 | 3665.08 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 402 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 94.6 | R.Ft | 45 | 100 | 106.43 | 0 | 4257 | C+S GST 18% I/P RD | 766.26 | 5023.26 | 5023.26 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 701 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 35.3778 | R.Ft | 45 | 100 | 39.8 | 0 | 1592 | C+S GST 18% I/P RD | 286.56 | 1878.56 | 1878.56 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 602 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.5111 | R.Ft | 45 | 100 | 56.82 | 0 | 2273 | C+S GST 18% I/P RD | 409.14 | 2682.14 | 2682.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 70 | R.Ft | 45 | 100 | 78.75 | 0 | 3150 | C+S GST 18% I/P RD | 567 | 3717 | 3717 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 402 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 54.1333 | R.Ft | 45 | 100 | 60.9 | 0 | 2436 | C+S GST 18% I/P RD | 438.48 | 2874.48 | 2874.48 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 602 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 39.9556 | R.Ft | 45 | 100 | 44.95 | 0 | 1798 | C+S GST 18% I/P RD | 323.64 | 2121.64 | 2121.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 101 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 55.3778 | R.Ft | 45 | 100 | 62.3 | 0 | 2492 | C+S GST 18% I/P RD | 448.56 | 2940.56 | 2940.56 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 402 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 42.8222 | R.Ft | 45 | 100 | 48.17 | 0 | 1927 | C+S GST 18% I/P RD | 346.86 | 2273.86 | 2273.86 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 101 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 40.4222 | R.Ft | 45 | 100 | 45.47 | 0 | 1819 | C+S GST 18% I/P RD | 327.42 | 2146.42 | 2146.42 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 101 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 73.6222 | R.Ft | 45 | 100 | 82.82 | 0 | 3313 | C+S GST 18% I/P RD | 596.34 | 3909.34 | 3909.34 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 701 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 64.4222 | R.Ft | 45 | 100 | 72.47 | 0 | 2899 | C+S GST 18% I/P RD | 521.82 | 3420.82 | 3420.82 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 401 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.9111 | R.Ft | 45 | 100 | 58.4 | 0 | 2336 | C+S GST 18% I/P RD | 420.48 | 2756.48 | 2756.48 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 102 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.5111 | R.Ft | 45 | 100 | 56.82 | 0 | 2273 | C+S GST 18% I/P RD | 409.14 | 2682.14 | 2682.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1801 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 55.3818 | R.Ft | 55 | 100 | 76.15 | 0 | 3046 | C+S GST 18% I/P RD | 548.28 | 3594.28 | 3594.28 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1401 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 73.6182 | R.Ft | 55 | 100 | 101.23 | 0 | 4049 | C+S GST 18% I/P RD | 728.82 | 4777.82 | 4777.82 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1401 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 40.4182 | R.Ft | 55 | 100 | 55.58 | 0 | 2223 | C+S GST 18% I/P RD | 400.14 | 2623.14 | 2623.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1601 Living,Dining,Ent.Lobby | Italian Marble Champher & Polish | 159.6545 | R.Ft | 55 | 100 | 219.52 | 0 | 8781 | C+S GST 18% I/P RD | 1580.58 | 10361.58 | 10361.58 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1601 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.5091 | R.Ft | 55 | 100 | 95.58 | 0 | 3823 | C+S GST 18% I/P RD | 688.14 | 4511.14 | 4511.14 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 100.8909 | R.Ft | 55 | 100 | 138.72 | 0 | 5549 | C+S GST 18% I/P RD | 998.82 | 6547.82 | 6547.82 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1301 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 55.38 | R.Ft | 50 | 100 | 69.23 | 0 | 2769 | C+S GST 18% I/P RD | 498.42 | 3267.42 | 3267.42 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 801 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.92 | R.Ft | 50 | 100 | 64.9 | 0 | 2596 | C+S GST 18% I/P RD | 467.28 | 3063.28 | 3063.28 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1002 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.52 | R.Ft | 50 | 100 | 63.15 | 0 | 2526 | C+S GST 18% I/P RD | 454.68 | 2980.68 | 2980.68 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 902 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 45.68 | R.Ft | 50 | 100 | 57.1 | 0 | 2284 | C+S GST 18% I/P RD | 411.12 | 2695.12 | 2695.12 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1202 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 58.22 | R.Ft | 50 | 100 | 72.78 | 0 | 2911 | C+S GST 18% I/P RD | 523.98 | 3434.98 | 3434.98 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 801 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 172.66 | R.Ft | 50 | 100 | 215.83 | 0 | 8633 | C+S GST 18% I/P RD | 1553.94 | 10186.94 | 10186.94 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1302 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.52 | R.Ft | 50 | 100 | 63.15 | 0 | 2526 | C+S GST 18% I/P RD | 454.68 | 2980.68 | 2980.68 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.28 | R.Ft | 50 | 100 | 110.35 | 0 | 4414 | C+S GST 18% I/P RD | 794.52 | 5208.52 | 5208.52 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1102 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 50.52 | R.Ft | 50 | 100 | 63.15 | 0 | 2526 | C+S GST 18% I/P RD | 454.68 | 2980.68 | 2980.68 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 801 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 37.9 | R.Ft | 50 | 100 | 47.38 | 0 | 1895 | C+S GST 18% I/P RD | 341.1 | 2236.1 | 2236.1 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 801 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.02 | R.Ft | 50 | 100 | 86.28 | 0 | 3451 | C+S GST 18% I/P RD | 621.18 | 4072.18 | 4072.18 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1102 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 39.96 | R.Ft | 50 | 100 | 49.95 | 0 | 1998 | C+S GST 18% I/P RD | 359.64 | 2357.64 | 2357.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1301 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 40.42 | R.Ft | 50 | 100 | 50.53 | 0 | 2021 | C+S GST 18% I/P RD | 363.78 | 2384.78 | 2384.78 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 902 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 100.9 | R.Ft | 50 | 100 | 126.13 | 0 | 5045 | C+S GST 18% I/P RD | 908.1 | 5953.1 | 5953.1 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 901 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 37.9 | R.Ft | 50 | 100 | 47.38 | 0 | 1895 | C+S GST 18% I/P RD | 341.1 | 2236.1 | 2236.1 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 901 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 172.66 | R.Ft | 50 | 100 | 215.83 | 0 | 8633 | C+S GST 18% I/P RD | 1553.94 | 10186.94 | 10186.94 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1302 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.28 | R.Ft | 50 | 100 | 110.35 | 0 | 4414 | C+S GST 18% I/P RD | 794.52 | 5208.52 | 5208.52 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1302 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 39.96 | R.Ft | 50 | 100 | 49.95 | 0 | 1998 | C+S GST 18% I/P RD | 359.64 | 2357.64 | 2357.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1202 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 86.7 | R.Ft | 50 | 100 | 108.38 | 0 | 4335 | C+S GST 18% I/P RD | 780.3 | 5115.3 | 5115.3 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1202 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 38.54 | R.Ft | 50 | 100 | 48.18 | 0 | 1927 | C+S GST 18% I/P RD | 346.86 | 2273.86 | 2273.86 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 901 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 51.92 | R.Ft | 50 | 100 | 64.9 | 0 | 2596 | C+S GST 18% I/P RD | 467.28 | 3063.28 | 3063.28 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 902 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 57.74 | R.Ft | 50 | 100 | 72.18 | 0 | 2887 | C+S GST 18% I/P RD | 519.66 | 3406.66 | 3406.66 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1301 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 73.62 | R.Ft | 50 | 100 | 92.03 | 0 | 3681 | C+S GST 18% I/P RD | 662.58 | 4343.58 | 4343.58 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1301 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 184.18 | R.Ft | 50 | 100 | 230.23 | 0 | 9209 | C+S GST 18% I/P RD | 1657.62 | 10866.62 | 10866.62 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 901 Master Bed,Dreeser Marble Flooring | Italian Marble Champher & Polish | 69.02 | R.Ft | 50 | 100 | 86.28 | 0 | 3451 | C+S GST 18% I/P RD | 621.18 | 4072.18 | 4072.18 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1002 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Champher & Polish | 88.28 | R.Ft | 50 | 100 | 110.35 | 0 | 4414 | C+S GST 18% I/P RD | 794.52 | 5208.52 | 5208.52 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 758 | 97244 | 06 Dec 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1557 | B 1002 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 39.96 | R.Ft | 50 | 100 | 49.95 | 0 | 1998 | C+S GST 18% I/P RD | 359.64 | 2357.64 | 2357.64 | Approved | 0 | 0 | 3372 | 06 Dec 2022
GANGA DHAM TOWERS | 1433 | 97241 | 05 Dec 2022 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1555 | RMC Pump Per Month Rental Charges | Pump Hiring for RMC | 1 | Month | 250000 | 100 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 1169 | 97240 | 05 Dec 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1533 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 150mm dia.(M) | 232 | Mtrs | 2090 | 100 | 0 | 0 | 484880 | C+S GST 18% I/P RD | 87278.4 | 572158.4 | 572158.4 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 1169 | 97240 | 05 Dec 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1533 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 150mm dia.(M) | 230 | Mtrs | 2090 | 100 | 0 | 0 | 480700 | C+S GST 18% I/P RD | 86526 | 567226 | 567226 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Dry Balcony dado | L Groove - BCV | 4 | R.Ft | 20 | 100 | 2 | 0 | 80 | CGST 0% URD I/P | 0 | 80 | 80 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 904 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 579.56 | Sq.Ft | 50 | 100 | 724.45 | 0 | 28978 | CGST 0% URD I/P | 0 | 28978 | 28978 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 904 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 132 | Sq.Ft | 50 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 904 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 50 | 100 | 189.99 | 0 | 7599.5 | CGST 0% URD I/P | 0 | 7599.5 | 7599.5 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Staff Toilet dado | Dado BC | 115.0645 | Sq.Ft | 13 | 100 | 37.4 | 0 | 1495.84 | CGST 0% URD I/P | 0 | 1495.84 | 1495.84 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Children Toilet Dado | L Groove - BCV | 38.7 | R.Ft | 20 | 100 | 19.35 | 0 | 774 | CGST 0% URD I/P | 0 | 774 | 774 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Staff Toilet dado | L Groove - BCV | 18 | R.Ft | 20 | 100 | 9 | 0 | 360 | CGST 0% URD I/P | 0 | 360 | 360 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Master Toilet dado | L Groove - BCV | 38.61 | R.Ft | 20 | 100 | 19.31 | 0 | 772.2 | CGST 0% URD I/P | 0 | 772.2 | 772.2 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Parents Toilet dado | L Groove - BCV | 21.996 | R.Ft | 20 | 100 | 11 | 0 | 439.92 | CGST 0% URD I/P | 0 | 439.92 | 439.92 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Powder Toilet dado | L Groove - BCV | 31 | R.Ft | 20 | 100 | 15.5 | 0 | 620 | CGST 0% URD I/P | 0 | 620 | 620 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Children Toilet Dado | Dado BC | 67 | Sq.Ft | 15 | 100 | 25.13 | 0 | 1005 | CGST 0% URD I/P | 0 | 1005 | 1005 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Powder Toilet dado | Dado BC | 38.86 | Sq.Ft | 15 | 100 | 14.57 | 0 | 582.9 | CGST 0% URD I/P | 0 | 582.9 | 582.9 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Parents Toilet dado | Dado BC | 75 | Sq.Ft | 15 | 100 | 28.13 | 0 | 1125 | CGST 0% URD I/P | 0 | 1125 | 1125 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 15 | 100 | 25.42 | 0 | 1016.7 | CGST 0% URD I/P | 0 | 1016.7 | 1016.7 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 904 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210 | Sq.Ft | 50 | 100 | 262.5 | 0 | 10500 | CGST 0% URD I/P | 0 | 10500 | 10500 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | CGST 0% URD I/P | 0 | 546 | 546 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 13 | 100 | 13 | 0 | 520 | CGST 0% URD I/P | 0 | 520 | 520 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22 | Sq.Ft | 13 | 100 | 7.15 | 0 | 286 | CGST 0% URD I/P | 0 | 286 | 286 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 49 | Sq.Ft | 13 | 100 | 15.93 | 0 | 637 | CGST 0% URD I/P | 0 | 637 | 637 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 13 | 100 | 13 | 0 | 520 | CGST 0% URD I/P | 0 | 520 | 520 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 49 | Sq.Ft | 13 | 100 | 15.93 | 0 | 637 | CGST 0% URD I/P | 0 | 637 | 637 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Parents Toilet dado | Dado BC | 106.04 | Sq.Ft | 14 | 100 | 37.11 | 0 | 1484.56 | CGST 0% URD I/P | 0 | 1484.56 | 1484.56 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Dry Balcony dado | Dado BC | 80.361 | Sq.Ft | 14 | 100 | 28.13 | 0 | 1125.05 | CGST 0% URD I/P | 0 | 1125.05 | 1125.05 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Children Toilet Dado | Dado BC | 148.12 | Sq.Ft | 14 | 100 | 51.84 | 0 | 2073.68 | CGST 0% URD I/P | 0 | 2073.68 | 2073.68 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Powder Toilet dado | Dado BC | 82 | Sq.Ft | 14 | 100 | 28.7 | 0 | 1148 | CGST 0% URD I/P | 0 | 1148 | 1148 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 551 | 97237 | 05 Dec 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1549 | A 104 Master Toilet dado | Dado BC | 148.12 | Sq.Ft | 14 | 100 | 51.84 | 0 | 2073.68 | CGST 0% URD I/P | 0 | 2073.68 | 2073.68 | Approved | 0 | 0 | 735 | 05 Dec 2022
GANGA DHAM TOWERS | 272 | 97236 | 05 Dec 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1675 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 156.0372 | Sq.Ft | 161.5 | 100 | 0 | 0 | 25200 | C+S GST 18% I/P RD | 4536 | 29736 | 29736 | Approved | 0 | 0 | 252 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 14th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 18th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 4th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 2nd floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 20th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 6th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 3rd floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 11th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 19th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 10th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 12th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 21st floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 16th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 17th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside1st floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 3rd floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 39.4483 | Sq.Ft | 7.25 | 100 | 7.15 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 13th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 7th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside1st floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 15th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 8th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 23rd floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 5th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 9th floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 844 | 97235 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1532 | A Northside 22nd floor External Texture Painting | Scaffolding/Gondola work | 39.4286 | Sq.Ft | 3.5 | 100 | 3.45 | 0 | 138 | C+S GST 18% I/P RD | 24.84 | 162.84 | 162.84 | Approved | 0 | 0 | 98 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside1st floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97234 | 05 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1535 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 39.4483 | Sq.Ft | 7.25 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 704 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1001 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1203 Terrace False Ceiling | Sherawood False Ceiling (M) | 81.3415 | Sq.Ft | 140 | 100 | 0 | 0 | 11387.81 | C+S GST 18% I/P RD | 2049.8 | 13437.61 | 13437.61 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1204 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 101 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 102 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 703 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 404 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1003 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1202 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 403 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 401 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 104 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 201 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 301 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 304 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1103 Terrace False Ceiling | Sherawood False Ceiling (M) | 5.07 | Sq.Ft | 140 | 100 | 0 | 0 | 709.8 | C+S GST 18% I/P RD | 127.76 | 837.56 | 837.56 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1502 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 402 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 302 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1004 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1404 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1201 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 202 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 203 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1402 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 103 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 701 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1104 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1401 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1403 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1602 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 303 Terrace False Ceiling | Sherawood False Ceiling (M) | 132.07 | Sq.Ft | 140 | 100 | 0 | 0 | 18489.8 | C+S GST 18% I/P RD | 3328.16 | 21817.96 | 21817.96 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1101 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 1102 Terrace False Ceiling | Sherawood False Ceiling (M) | 156.08 | Sq.Ft | 140 | 100 | 0 | 0 | 21851.2 | C+S GST 18% I/P RD | 3933.22 | 25784.42 | 25784.42 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 636 | 97233 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 1671 | A 204 Terrace False Ceiling | Sherawood False Ceiling (M) | 177.61 | Sq.Ft | 140 | 100 | 0 | 0 | 24865.4 | C+S GST 18% I/P RD | 4475.78 | 29341.18 | 29341.18 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 702 Terrace False Ceiling | Painting work (M+L) -BC | 165.23 | Sq.Ft | 35 | 100 | 0 | 0 | 5783.05 | C+S GST 18% I/P RD | 1040.94 | 6823.99 | 6823.99 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 802 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 202 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 302 Terrace False Ceiling | Painting work (M+L) -BC | 165.23 | Sq.Ft | 35 | 100 | 0 | 0 | 5783.05 | C+S GST 18% I/P RD | 1040.94 | 6823.99 | 6823.99 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B-1202 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B-1002 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 502 Terrace False Ceiling | Painting work (M+L) -BC | 165.23 | Sq.Ft | 35 | 100 | 0 | 0 | 5783.05 | C+S GST 18% I/P RD | 1040.94 | 6823.99 | 6823.99 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 602 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 902 Terrace False Ceiling | Painting work (M+L) -BC | 165.23 | Sq.Ft | 35 | 100 | 0 | 0 | 5783.05 | C+S GST 18% I/P RD | 1040.94 | 6823.99 | 6823.99 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 402 Terrace False Ceiling | Painting work (M+L) -BC | 208.07 | Sq.Ft | 35 | 100 | 0 | 0 | 7282.45 | C+S GST 18% I/P RD | 1310.84 | 8593.29 | 8593.29 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 302 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 202 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 402 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 802 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 502 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B-1002 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B-1202 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 902 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 602 Terrace False Ceiling | Sherawood False Ceiling (M) | 62.421 | Sq.Ft | 140 | 100 | 0 | 0 | 8738.94 | C+S GST 18% I/P RD | 1573 | 10311.94 | 10311.94 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 814 | 97232 | 05 Dec 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1523 | B 702 Terrace False Ceiling | Sherawood False Ceiling (M) | 49.569 | Sq.Ft | 140 | 100 | 0 | 0 | 6939.66 | C+S GST 18% I/P RD | 1249.14 | 8188.8 | 8188.8 | Approved | 0 | 0 | 0 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 602 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 902 Terrace False Ceiling | Sherawood False Ceiling (L) | 148.707 | Sq.Ft | 42 | 100 | 156.14 | 0 | 6245.69 | C+S GST 18% I/P RD | 1124.22 | 7369.91 | 7369.91 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 702 Terrace False Ceiling | Sherawood False Ceiling (L) | 148.707 | Sq.Ft | 42 | 100 | 156.14 | 0 | 6245.69 | C+S GST 18% I/P RD | 1124.22 | 7369.91 | 7369.91 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 402 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 302 Terrace False Ceiling | Sherawood False Ceiling (L) | 148.707 | Sq.Ft | 42 | 100 | 156.14 | 0 | 6245.69 | C+S GST 18% I/P RD | 1124.22 | 7369.91 | 7369.91 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 202 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B-1202 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B-1002 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 502 Terrace False Ceiling | Sherawood False Ceiling (L) | 148.707 | Sq.Ft | 42 | 100 | 156.14 | 0 | 6245.69 | C+S GST 18% I/P RD | 1124.22 | 7369.91 | 7369.91 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 802 Terrace False Ceiling | Sherawood False Ceiling (L) | 187.263 | Sq.Ft | 42 | 100 | 196.63 | 0 | 7865.05 | C+S GST 18% I/P RD | 1415.7 | 9280.75 | 9280.75 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 202 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 902 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 702 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B-1002 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 602 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 502 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 802 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 402 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B 302 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 815 | 97231 | 05 Dec 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1506 | B-1202 Terrace False Ceiling | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 972 | 05 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 9th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 7th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 23rd floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 8th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 2nd floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 1st floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 19th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 15th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 22nd floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 5th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 4th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 3rd floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 17th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 18th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 20th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 21st floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 11th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 12th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 6th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 13th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 14th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 16th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 845 | 97223 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1529 | A Westside 10th floor External Texture Painting | Texture Paint (M) | 294.6207 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 0 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 21st floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 1st floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 18th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 19th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 16th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 22nd floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 2nd floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 4th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 12th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 6th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 8th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 13th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 17th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 5th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 9th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 10th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 3rd floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 20th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 11th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 15th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 7th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 14th floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 23rd floor External Texture Painting | Texture Paint (L) | 294.6207 | Sq.Ft | 7.25 | 100 | 53.4 | 0 | 2136 | C+S GST 18% I/P RD | 384.48 | 2520.48 | 2520.48 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 5th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 6th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 21st floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 10th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 19th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 3rd floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 20th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 4th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 12th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 22nd floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 23rd floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 11th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 14th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 7th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 2nd floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 9th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 18th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 8th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 17th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 1st floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 13th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 15th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 844 | 97222 | 03 Dec 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1534 | A Westside 16th floor External Texture Painting | Scaffolding/Gondola work | 294.5714 | Sq.Ft | 3.5 | 100 | 25.77 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 728 | 03 Dec 2022
GANGA DHAM TOWERS | 372 | 97221 | 03 Dec 2022 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 1476 | B Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 110.3226 | Sq.Ft | 155 | 100 | 0 | 0 | 17100 | C+S GST 18% I/P RD | 3078 | 20178 | 20178 | Approved | 0 | 0 | 171 | 03 Dec 2022
GANGA DHAM TOWERS | 1360 | 97216 | 03 Dec 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1607 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 03 Dec 2022
GANGA DHAM TOWERS | 940 | 97215 | 03 Dec 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1606 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 03 Dec 2022
GANGA DHAM TOWERS | 1340 | 97214 | 03 Dec 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1674 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2702 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 63 | No. | 200 | 35 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2901 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 81 | No. | 200 | 35 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2802 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 63 | No. | 200 | 35 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2801 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 81 | No. | 200 | 35 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2701 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 81 | No. | 200 | 35 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 399 | 97212 | 03 Dec 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1664 | B Bldg Flat No. 2902 Internal Electrical work | Primary Light Pt. (Controlled by Sw. Board) | 63 | No. | 200 | 35 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 605 | 03 Dec 2022
GANGA DHAM TOWERS | 491 | 97204 | 02 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1594 | D Build.Terrace Floor Blockwork 5" | Blockwork 5" - BC - | 1715 | Sq.Ft | 13 | 100 | 557.38 | 0 | 22295 | CGST 0% URD I/P | 0 | 22295 | 22295 | Approved | 0 | 0 | 223 | 02 Dec 2022
GANGA DHAM TOWERS | 371 | 97203 | 02 Dec 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1759 | EWS Bldg RCC 9th Slab Built-up Area (L) | Schedule & Quality | 1962.8 | Sq.Ft | 2.5 | 100 | 122.68 | 0 | 4907 | CGST 0% URD I/P | 0 | 4907 | 4907 | Approved | 0 | 0 | 166 | 02 Dec 2022
GANGA DHAM TOWERS | 371 | 97203 | 02 Dec 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1759 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | Hacking Work | 951.2 | Sq.Ft | 2.5 | 100 | 59.45 | 0 | 2378 | CGST 0% URD I/P | 0 | 2378 | 2378 | Approved | 0 | 0 | 166 | 02 Dec 2022
GANGA DHAM TOWERS | 371 | 97203 | 02 Dec 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1759 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | Hacking Work | 1688 | Sq.Ft | 2.5 | 100 | 105.5 | 0 | 4220 | CGST 0% URD I/P | 0 | 4220 | 4220 | Approved | 0 | 0 | 166 | 02 Dec 2022
GANGA DHAM TOWERS | 371 | 97203 | 02 Dec 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1759 | EWS Bldg RCC 8th Slab Built-up Area (L) | Schedule & Quality | 2037.2 | Sq.Ft | 2.5 | 100 | 127.33 | 0 | 5093 | CGST 0% URD I/P | 0 | 5093 | 5093 | Approved | 0 | 0 | 166 | 02 Dec 2022
GANGA DHAM TOWERS | 493 | 97202 | 02 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1522 | D Bldg Terrace Floor External Plaster | External Plaster- BC | 1394 | Sq.Ft | 28 | 100 | 975.8 | 0 | 39032 | CGST 0% URD I/P | 0 | 39032 | 39032 | Approved | 0 | 0 | 1507 | 02 Dec 2022
GANGA DHAM TOWERS | 493 | 97202 | 02 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1522 | D Bldg North Side External Plaster | External Plaster- BC | 2954 | Sq.Ft | 28 | 100 | 2067.8 | 0 | 82712 | CGST 0% URD I/P | 0 | 82712 | 82712 | Approved | 0 | 0 | 1507 | 02 Dec 2022
GANGA DHAM TOWERS | 493 | 97202 | 02 Dec 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1522 | D Bldg External Plaster North Side | External Plaster- BC | 1033 | Sq.Ft | 28 | 100 | 723.1 | 0 | 28924 | CGST 0% URD I/P | 0 | 28924 | 28924 | Approved | 0 | 0 | 1507 | 02 Dec 2022
GANGA DHAM TOWERS | 1287 | 97201 | 02 Dec 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 1505 | B 102 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 281.9636 | Sq.Ft | 55 | 100 | 387.7 | 0 | 15508 | C+S GST 0% I/P RD | 0 | 15508 | 15508 | Approved | 0 | 0 | 155 | 02 Dec 2022
GANGA DHAM TOWERS | 395 | 97191 | 02 Dec 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1515 | A Gypsum Plaster A - Tikki Dhada Plaster Rate Diff | Tikki Dhada Rate Diff (L) | 801 | Sq.Ft | 1 | 100 | 20.03 | 0 | 801 | C+S GST 18% I/P RD | 144.18 | 945.18 | 945.18 | Approved | 0 | 0 | 8 | 02 Dec 2022
GANGA DHAM TOWERS | 537 | 97190 | 02 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1508 | A 2001 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 47 | R.Ft | 60 | 100 | 70.5 | 0 | 2820 | C+S GST 18% I/P RD | 507.6 | 3327.6 | 3327.6 | Approved | 0 | 0 | 85 | 02 Dec 2022
GANGA DHAM TOWERS | 537 | 97190 | 02 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1508 | A 2401 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 47 | R.Ft | 60 | 100 | 70.5 | 0 | 2820 | C+S GST 18% I/P RD | 507.6 | 3327.6 | 3327.6 | Approved | 0 | 0 | 85 | 02 Dec 2022
GANGA DHAM TOWERS | 537 | 97190 | 02 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1508 | A 2201 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 47 | R.Ft | 60 | 100 | 70.5 | 0 | 2820 | C+S GST 18% I/P RD | 507.6 | 3327.6 | 3327.6 | Approved | 0 | 0 | 85 | 02 Dec 2022
GANGA DHAM TOWERS | 1173 | 97189 | 02 Dec 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1530 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 150mm dia.(M) | 138 | Mtrs | 2090 | 100 | 0 | 0 | 288420 | C+S GST 18% I/P RD | 51915.6 | 340335.6 | 340335.6 | Approved | 0 | 0 | 0 | 02 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.288 | Sq.Ft | 24 | 100 | 27.17 | 0 | 1086.91 | C+S GST 18% I/P RD | 195.64 | 1282.55 | 1282.55 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.466 | Sq.Ft | 24 | 100 | 28.48 | 0 | 1139.18 | C+S GST 18% I/P RD | 205.06 | 1344.24 | 1344.24 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Children Toilet Flooring | Vitrified Flooring -BC | 44.172 | Sq.Ft | 24 | 100 | 26.5 | 0 | 1060.13 | C+S GST 18% I/P RD | 190.82 | 1250.95 | 1250.95 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 28 | 100 | 44.53 | 0 | 1781.14 | C+S GST 18% I/P RD | 320.6 | 2101.74 | 2101.74 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 28 | 100 | 84.54 | 0 | 3381.59 | C+S GST 18% I/P RD | 608.68 | 3990.27 | 3990.27 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Dry Balcony dado | Dado BC | 71.055 | Sq.Ft | 28 | 100 | 49.74 | 0 | 1989.54 | C+S GST 18% I/P RD | 358.12 | 2347.66 | 2347.66 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 28 | 100 | 93.45 | 0 | 3738.17 | C+S GST 18% I/P RD | 672.88 | 4411.05 | 4411.05 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | C+S GST 18% I/P RD | 176.26 | 1155.53 | 1155.53 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 28 | 100 | 80.3 | 0 | 3211.99 | C+S GST 18% I/P RD | 578.16 | 3790.15 | 3790.15 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 28 | 100 | 46.52 | 0 | 1860.77 | C+S GST 18% I/P RD | 334.94 | 2195.71 | 2195.71 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | C+S GST 18% I/P RD | 441.62 | 2895.09 | 2895.09 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 28 | 100 | 41.04 | 0 | 1641.53 | C+S GST 18% I/P RD | 295.48 | 1937.01 | 1937.01 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Parents Toilet dado | L Groove - BCV | 35 | R.Ft | 20 | 100 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Children Toilet dado | L Groove - BCV | 33.804 | R.Ft | 20 | 100 | 16.9 | 0 | 676.08 | C+S GST 18% I/P RD | 121.7 | 797.78 | 797.78 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Children Toilet dado | L Groove - BCV | 33.804 | R.Ft | 20 | 100 | 16.9 | 0 | 676.08 | C+S GST 18% I/P RD | 121.7 | 797.78 | 797.78 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Powder Toilet dado | L Groove - BCV | 27.9 | R.Ft | 20 | 100 | 13.95 | 0 | 558 | C+S GST 18% I/P RD | 100.44 | 658.44 | 658.44 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Powder Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Master Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Staff Toilet dado | L Groove - BCV | 14.634 | R.Ft | 20 | 100 | 7.32 | 0 | 292.68 | C+S GST 18% I/P RD | 52.68 | 345.36 | 345.36 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Staff Toilet dado | L Groove - BCV | 15 | R.Ft | 20 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Parents Toilet dado | L Groove - BCV | 35 | R.Ft | 20 | 100 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2401 Powder Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Parents Toilet dado | L Groove - BCV | 35 | R.Ft | 20 | 100 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Children Toilet dado | L Groove - BCV | 32 | R.Ft | 20 | 100 | 16 | 0 | 640 | C+S GST 18% I/P RD | 115.2 | 755.2 | 755.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Dry Balcony dado | L Groove - BCV | 3.987 | R.Ft | 20 | 100 | 1.99 | 0 | 79.74 | C+S GST 18% I/P RD | 14.36 | 94.1 | 94.1 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2201 Master Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Staff Toilet dado | L Groove - BCV | 14.634 | R.Ft | 20 | 100 | 7.32 | 0 | 292.68 | C+S GST 18% I/P RD | 52.68 | 345.36 | 345.36 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 537 | 97173 | 01 Dec 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1509 | A 2001 Master Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 337 | 01 Dec 2022
GANGA DHAM TOWERS | 395 | 97167 | 30 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1514 | A Bldg Flat No. 603 Gypsum Plaster | Gypsum on Wall (L) | 161.75 | Sq.Ft | 4 | 100 | 16.18 | 0 | 647 | C+S GST 18% I/P RD | 116.46 | 763.46 | 763.46 | Approved | 0 | 0 | 32 | 30 Nov 2022
GANGA DHAM TOWERS | 395 | 97167 | 30 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1514 | A Bldg Flat No. 704 Gypsum Plaster | Gypsum on Wall (L) | 238 | Sq.Ft | 4 | 100 | 23.8 | 0 | 952 | C+S GST 18% I/P RD | 171.36 | 1123.36 | 1123.36 | Approved | 0 | 0 | 32 | 30 Nov 2022
GANGA DHAM TOWERS | 395 | 97167 | 30 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1514 | A Bldg Flat No. 404 Gypsum Plaster | Gypsum on Wall (L) | 238 | Sq.Ft | 4 | 100 | 23.8 | 0 | 952 | C+S GST 18% I/P RD | 171.36 | 1123.36 | 1123.36 | Approved | 0 | 0 | 32 | 30 Nov 2022
GANGA DHAM TOWERS | 395 | 97167 | 30 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1514 | A Bldg Flat No. 403 Gypsum Plaster | Gypsum on Wall (L) | 161.75 | Sq.Ft | 4 | 100 | 16.18 | 0 | 647 | C+S GST 18% I/P RD | 116.46 | 763.46 | 763.46 | Approved | 0 | 0 | 32 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Parents Toilet dado | Dado BC | 58 | Sq.Ft | 28 | 100 | 40.6 | 0 | 1624 | C+S GST 18% I/P RD | 292.32 | 1916.32 | 1916.32 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Master Toilet dado | Dado BC | 114 | Sq.Ft | 28 | 100 | 79.8 | 0 | 3192 | C+S GST 18% I/P RD | 574.56 | 3766.56 | 3766.56 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 28 | 100 | 46.52 | 0 | 1860.77 | C+S GST 18% I/P RD | 334.94 | 2195.71 | 2195.71 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Dry Balcony dado | Dado BC | 71 | Sq.Ft | 28 | 100 | 49.7 | 0 | 1988 | C+S GST 18% I/P RD | 357.84 | 2345.84 | 2345.84 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Parents Toilet dado | Dado BC | 133 | Sq.Ft | 28 | 100 | 93.1 | 0 | 3724 | C+S GST 18% I/P RD | 670.32 | 4394.32 | 4394.32 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45 | Sq.Ft | 24 | 100 | 27 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 35 | Sq.Ft | 24 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Children Toilet Flooring | Vitrified Flooring -BC | 44 | Sq.Ft | 24 | 100 | 26.4 | 0 | 1056 | C+S GST 18% I/P RD | 190.08 | 1246.08 | 1246.08 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46 | Sq.Ft | 24 | 100 | 27.6 | 0 | 1104 | C+S GST 18% I/P RD | 198.72 | 1302.72 | 1302.72 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 24 | 100 | 23.79 | 0 | 951.48 | C+S GST 18% I/P RD | 171.26 | 1122.74 | 1122.74 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 537 | 97166 | 30 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1510 | A 2201 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.7083 | Sq.Ft | 24 | 100 | 23.22 | 0 | 929 | C+S GST 18% I/P RD | 167.22 | 1096.22 | 1096.22 | Approved | 0 | 0 | 183 | 30 Nov 2022
GANGA DHAM TOWERS | 227 | 97165 | 29 Nov 2022 |  | MAHALAXMI ENTERPRISES | AVCON TECHNICS PVT LTD | EV - 1654 | A Bldg Tie Beams - 4th To 5th Slab Rebaring Work | Rebarring work 16mm dia- BRE | 75.3846 | No. | 130 | 100 | 245 | 0 | 9800 | C+S GST 18% I/P RD | 1764 | 11564 | 11564 | Approved | 0 | 0 | 196 | 29 Nov 2022
GANGA DHAM TOWERS | 389 | 97163 | 29 Nov 2022 |  | SAGARSINGH BINDUSINGH TAK | PUNDLIK P MAHAJAN | EV - 1432 | Loading / Unloading Expenses | Unloading of tiles. | 34 | Metric Tonnes | 260 | 100 | 0 | 0 | 8840 | CGST 0% URD I/P | 0 | 8840 | 8840 | Approved | 0 | 0 | 0 | 29 Nov 2022
GANGA DHAM TOWERS | 395 | 97161 | 29 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1516 | A 704 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | Tikki Dhada Rate Diff (L) | 238 | Sq.Ft | 5 | 100 | 29.75 | 0 | 1190 | C+S GST 18% I/P RD | 214.2 | 1404.2 | 1404.2 | Approved | 0 | 0 | 40 | 29 Nov 2022
GANGA DHAM TOWERS | 395 | 97161 | 29 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1516 | A 603 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | Tikki Dhada Rate Diff (L) | 161.8 | Sq.Ft | 5 | 100 | 20.23 | 0 | 809 | C+S GST 18% I/P RD | 145.62 | 954.62 | 954.62 | Approved | 0 | 0 | 40 | 29 Nov 2022
GANGA DHAM TOWERS | 395 | 97161 | 29 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1516 | A 403 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada - 1 | Tikki Dhada Rate Diff (L) | 161.8 | Sq.Ft | 5 | 100 | 20.23 | 0 | 809 | C+S GST 18% I/P RD | 145.62 | 954.62 | 954.62 | Approved | 0 | 0 | 40 | 29 Nov 2022
GANGA DHAM TOWERS | 395 | 97161 | 29 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1516 | A 604 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | Tikki Dhada Rate Diff (L) | 239 | Sq.Ft | 5 | 100 | 29.88 | 0 | 1195 | C+S GST 18% I/P RD | 215.1 | 1410.1 | 1410.1 | Approved | 0 | 0 | 40 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Powder Toilet dado | Dado BC | 84.1429 | Sq.Ft | 28 | 100 | 58.9 | 0 | 2356 | C+S GST 18% I/P RD | 424.08 | 2780.08 | 2780.08 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Powder Toilet dado | Dado BC | 34.9643 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979 | C+S GST 18% I/P RD | 176.22 | 1155.22 | 1155.22 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Parents Toilet dado | Dado BC | 133 | Sq.Ft | 28 | 100 | 93.1 | 0 | 3724 | C+S GST 18% I/P RD | 670.32 | 4394.32 | 4394.32 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Children Toilet dado | Dado BC | 120 | Sq.Ft | 28 | 100 | 84 | 0 | 3360 | C+S GST 18% I/P RD | 604.8 | 3964.8 | 3964.8 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 28 | 100 | 46.52 | 0 | 1860.77 | C+S GST 18% I/P RD | 334.94 | 2195.71 | 2195.71 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Parents Toilet dado | Dado BC | 58.5 | Sq.Ft | 28 | 100 | 40.95 | 0 | 1638 | C+S GST 18% I/P RD | 294.84 | 1932.84 | 1932.84 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Children Toilet dado | Dado BC | 63.6071 | Sq.Ft | 28 | 100 | 44.52 | 0 | 1781 | C+S GST 18% I/P RD | 320.58 | 2101.58 | 2101.58 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Dry Balcony dado | Dado BC | 70.2143 | Sq.Ft | 28 | 100 | 49.15 | 0 | 1966 | C+S GST 18% I/P RD | 353.88 | 2319.88 | 2319.88 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Master Toilet dado | Dado BC | 114.2857 | Sq.Ft | 28 | 100 | 80 | 0 | 3200 | C+S GST 18% I/P RD | 576 | 3776 | 3776 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45 | Sq.Ft | 24 | 100 | 27 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Children Toilet Flooring | Vitrified Flooring -BC | 44.0833 | Sq.Ft | 24 | 100 | 26.45 | 0 | 1058 | C+S GST 18% I/P RD | 190.44 | 1248.44 | 1248.44 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.7083 | Sq.Ft | 24 | 100 | 23.22 | 0 | 929 | C+S GST 18% I/P RD | 167.22 | 1096.22 | 1096.22 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 19.7917 | Sq.Ft | 24 | 100 | 11.88 | 0 | 475 | C+S GST 18% I/P RD | 85.5 | 560.5 | 560.5 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.7917 | Sq.Ft | 24 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 36 | Sq.Ft | 24 | 100 | 21.6 | 0 | 864 | C+S GST 18% I/P RD | 155.52 | 1019.52 | 1019.52 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 537 | 97159 | 29 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1511 | A 2401 Staff Toilet dado | Dado BC | 109.7917 | Sq.Ft | 24 | 100 | 65.88 | 0 | 2635 | C+S GST 18% I/P RD | 474.3 | 3109.3 | 3109.3 | Approved | 0 | 0 | 290 | 29 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 301 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.45 | No. | 1000 | 100 | 36.25 | 0 | 1450 | CGST 0% URD I/P | 0 | 1450 | 1450 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 302 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.45 | No. | 1000 | 100 | 36.25 | 0 | 1450 | CGST 0% URD I/P | 0 | 1450 | 1450 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 502 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.45 | No. | 1000 | 100 | 36.25 | 0 | 1450 | CGST 0% URD I/P | 0 | 1450 | 1450 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 902 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.75 | No. | 1200 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 802 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.6667 | No. | 1200 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 455 | 97155 | 28 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1571 | A Bldg Flat No. 2102 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.7497 | No. | 1650 | 100 | 154.68 | 0 | 6187.01 | CGST 0% URD I/P | 0 | 6187.01 | 6187.01 | Approved | 0 | 0 | 146 | 28 Nov 2022
GANGA DHAM TOWERS | 1274 | 97134 | 26 Nov 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1587 | B-Bldg Safety Net | MS Pipe Fixing -SOSB | 60 | No. | 50 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 30 | 26 Nov 2022
GANGA DHAM TOWERS | 1361 | 97133 | 26 Nov 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1588 | A-Bldg Safety Net | MS Pipe Fixing -SOSB | 80 | No. | 50 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 26 Nov 2022
GANGA DHAM TOWERS | 355 | 97132 | 26 Nov 2022 |  | SHREE GURUDATTA ENTERPRISES | SAROJ KUMAR PRADHAN | EV - 1591 | B Bldg 26th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 2001 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.7497 | No. | 1650 | 100 | 113.43 | 0 | 4537.01 | CGST 0% URD I/P | 0 | 4537.01 | 4537.01 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1901 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.0479 | No. | 1650 | 100 | 43.23 | 0 | 1729 | CGST 0% URD I/P | 0 | 1729 | 1729 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1102 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.75 | No. | 1200 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 0.625 | No. | 1200 | 100 | 18.75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1202 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.75 | No. | 1200 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1201 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1200 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1101 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1200 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1801 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.75 | No. | 1400 | 100 | 61.25 | 0 | 2450 | CGST 0% URD I/P | 0 | 2450 | 2450 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1802 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.965 | No. | 1400 | 100 | 68.78 | 0 | 2751 | CGST 0% URD I/P | 0 | 2751 | 2751 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1301 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4.0714 | No. | 1400 | 100 | 142.5 | 0 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5700 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1402 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.3929 | No. | 1400 | 100 | 83.75 | 0 | 3350 | CGST 0% URD I/P | 0 | 3350 | 3350 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1302 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.4 | No. | 1400 | 100 | 84 | 0 | 3360 | CGST 0% URD I/P | 0 | 3360 | 3360 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 455 | 97131 | 26 Nov 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1593 | A Bldg Flat No. 1502 Internal Plumbing PPR-C | Int Flat PPRC Work. | 0.75 | No. | 1400 | 100 | 26.25 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 371 | 26 Nov 2022
GANGA DHAM TOWERS | 291 | 97112 | 25 Nov 2022 |  | SHREE GURUDATTA ENTERPRISES | SAROJ KUMAR PRADHAN | EV - 1554 | A Bldg 28th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 3000 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 50 | 25 Nov 2022
GANGA DHAM TOWERS | 291 | 97112 | 25 Nov 2022 |  | SHREE GURUDATTA ENTERPRISES | SAROJ KUMAR PRADHAN | EV - 1554 | A Bldg 28th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing Rate Diff. | 1 | Slab | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 50 | 25 Nov 2022
GANGA DHAM TOWERS | 355 | 97111 | 25 Nov 2022 |  | SHREE GURUDATTA ENTERPRISES | SAROJ KUMAR PRADHAN | EV - 1537 | B Bldg 28th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 25 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 25mm dia-(L) | 93.2 | Mtrs | 110 | 100 | 256.3 | 0 | 10252 | C+S GST 18% I/P RD | 1845.36 | 12097.36 | 12097.36 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(L) | 39.503 | Mtrs | 165 | 100 | 162.95 | 0 | 6518 | C+S GST 18% I/P RD | 1173.24 | 7691.24 | 7691.24 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 80mm dia.(L) | 4.9 | Mtrs | 270 | 100 | 33.08 | 0 | 1323 | C+S GST 18% I/P RD | 238.14 | 1561.14 | 1561.14 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 50mm dia.(L) | 2.9 | Mtrs | 200 | 100 | 14.5 | 0 | 580 | C+S GST 18% I/P RD | 104.4 | 684.4 | 684.4 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 65mm dia.(L) | 20.2 | Mtrs | 225 | 100 | 0 | 0 | 4545 | C+S GST 18% I/P RD | 818.1 | 5363.1 | 5363.1 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1170 | 97108 | 24 Nov 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1531 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 32mm dia.(L) | 19.75 | Mtrs | 140 | 100 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 520 | 24 Nov 2022
GANGA DHAM TOWERS | 1296 | 97104 | 23 Nov 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1585 | Miscellaneous expenses | Marketing Operating Expenses | 8.74 | Month | 25000 | 8.33 | 0 | 0 | 18201 | CGST 0% URD I/P | 0 | 18201 | 18201 | Approved | 0 | 0 | 182 | 23 Nov 2022
GANGA DHAM TOWERS | 1228 | 97092 | 22 Nov 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1445 | Site Expenses | Site Expenses -SO | 0.3436 | Month | 30000 | 100 | 0 | 0 | 10307 | CGST 0% URD I/P | 0 | 10307 | 10307 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1901 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-2301 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1801 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 701 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1401 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1501 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1601 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1301 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1001 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 201 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 401 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1201 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1701 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-2001 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 601 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-2201 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 901 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 501 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-2101 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 301 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B-1101 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 801 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 815 | 97091 | 22 Nov 2022 |  | S R INFRA PROJECTS | A K INTERIOR CONTRACTOR | EV - 1434 | B 101 Terrace False Ceiling | Sherawood False Ceiling (L) | 173.2143 | Sq.Ft | 42 | 100 | 181.88 | 0 | 7275 | C+S GST 18% I/P RD | 1309.5 | 8584.5 | 8584.5 | Approved | 0 | 0 | 1673 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2001 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 801 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1001 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1901 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 701 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1401 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1601 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1701 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 501 Terrace False Ceiling | Sherawood False Ceiling (M) | 192.46 | Sq.Ft | 140 | 100 | 0 | 0 | 26944.4 | C+S GST 18% I/P RD | 4850 | 31794.4 | 31794.4 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 901 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1301 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2101 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 201 Terrace False Ceiling | Sherawood False Ceiling (M) | 192.46 | Sq.Ft | 140 | 100 | 0 | 0 | 26944.4 | C+S GST 18% I/P RD | 4850 | 31794.4 | 31794.4 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 301 Terrace False Ceiling | Sherawood False Ceiling (M) | 192.46 | Sq.Ft | 140 | 100 | 0 | 0 | 26944.4 | C+S GST 18% I/P RD | 4850 | 31794.4 | 31794.4 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1801 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1501 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1101 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 401 Terrace False Ceiling | Sherawood False Ceiling (M) | 192.46 | Sq.Ft | 140 | 100 | 0 | 0 | 26944.4 | C+S GST 18% I/P RD | 4850 | 31794.4 | 31794.4 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1201 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2301 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2201 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 101 Terrace False Ceiling | Sherawood False Ceiling (M) | 192.4571 | Sq.Ft | 140 | 100 | 0 | 0 | 26944 | C+S GST 18% I/P RD | 4849.92 | 31793.92 | 31793.92 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 601 Terrace False Ceiling | Sherawood False Ceiling (M) | 57.7286 | Sq.Ft | 140 | 100 | 0 | 0 | 8082 | C+S GST 18% I/P RD | 1454.76 | 9536.76 | 9536.76 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 401 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2001 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 901 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2301 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1201 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2201 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 601 Terrace False Ceiling | Painting work (M+L) -BC | 192.4571 | Sq.Ft | 35 | 100 | 0 | 0 | 6736 | C+S GST 18% I/P RD | 1212.48 | 7948.48 | 7948.48 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 701 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 501 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1301 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-2101 Terrace False Ceiling | Painting work (M+L) -BC | 192.4571 | Sq.Ft | 35 | 100 | 0 | 0 | 6736 | C+S GST 18% I/P RD | 1212.48 | 7948.48 | 7948.48 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1901 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 801 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1601 Terrace False Ceiling | Painting work (M+L) -BC | 192.4571 | Sq.Ft | 35 | 100 | 0 | 0 | 6736 | C+S GST 18% I/P RD | 1212.48 | 7948.48 | 7948.48 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1701 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1501 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 201 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 301 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1801 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1001 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1401 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B-1101 Terrace False Ceiling | Painting work (M+L) -BC | 192.4571 | Sq.Ft | 35 | 100 | 0 | 0 | 6736 | C+S GST 18% I/P RD | 1212.48 | 7948.48 | 7948.48 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 814 | 97090 | 22 Nov 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1446 | B 101 Terrace False Ceiling | Painting work (M+L) -BC | 192.46 | Sq.Ft | 35 | 100 | 0 | 0 | 6736.1 | C+S GST 18% I/P RD | 1212.5 | 7948.6 | 7948.6 | Approved | 0 | 0 | 0 | 22 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1801 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 750 | 100 | 55.31 | 0 | 2212.5 | C+S GST 18% I/P RD | 398.26 | 2610.76 | 2610.76 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1801 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 750 | 100 | 64.5 | 0 | 2580 | C+S GST 18% I/P RD | 464.4 | 3044.4 | 3044.4 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1801 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 750 | 100 | 102 | 0 | 4080 | C+S GST 18% I/P RD | 734.4 | 4814.4 | 4814.4 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1601 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 750 | 100 | 46.13 | 0 | 1845 | C+S GST 18% I/P RD | 332.1 | 2177.1 | 2177.1 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1601 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 750 | 100 | 64.5 | 0 | 2580 | C+S GST 18% I/P RD | 464.4 | 3044.4 | 3044.4 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 101 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 650 | 100 | 55.9 | 0 | 2236 | C+S GST 18% I/P RD | 402.48 | 2638.48 | 2638.48 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 101 Parents Toilet Counter wash Basi | Italian Marble Counter - Mkt | 5.44 | R.Ft | 650 | 100 | 88.4 | 0 | 3536 | C+S GST 18% I/P RD | 636.48 | 4172.48 | 4172.48 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 101 Children Toilet Counter wash Basi | Italian Marble Counter - Mkt | 2.95 | R.Ft | 650 | 100 | 47.94 | 0 | 1917.5 | C+S GST 18% I/P RD | 345.16 | 2262.66 | 2262.66 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 101 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 650 | 100 | 39.98 | 0 | 1599 | C+S GST 18% I/P RD | 287.82 | 1886.82 | 1886.82 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2001 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 800 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2001 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 800 | 100 | 49.2 | 0 | 1968 | C+S GST 18% I/P RD | 354.24 | 2322.24 | 2322.24 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1601 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 750 | 100 | 102 | 0 | 4080 | C+S GST 18% I/P RD | 734.4 | 4814.4 | 4814.4 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1801 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 750 | 100 | 46.13 | 0 | 1845 | C+S GST 18% I/P RD | 332.1 | 2177.1 | 2177.1 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2401 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 800 | 100 | 59 | 0 | 2360 | C+S GST 18% I/P RD | 424.8 | 2784.8 | 2784.8 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2401 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 800 | 100 | 108.8 | 0 | 4352 | C+S GST 18% I/P RD | 783.36 | 5135.36 | 5135.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2001 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 800 | 100 | 59 | 0 | 2360 | C+S GST 18% I/P RD | 424.8 | 2784.8 | 2784.8 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2001 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 800 | 100 | 108.8 | 0 | 4352 | C+S GST 18% I/P RD | 783.36 | 5135.36 | 5135.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1901 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 800 | 100 | 108.8 | 0 | 4352 | C+S GST 18% I/P RD | 783.36 | 5135.36 | 5135.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1901 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 800 | 100 | 59 | 0 | 2360 | C+S GST 18% I/P RD | 424.8 | 2784.8 | 2784.8 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2401 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 800 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1901 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 800 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 1901 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 800 | 100 | 49.2 | 0 | 1968 | C+S GST 18% I/P RD | 354.24 | 2322.24 | 2322.24 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 537 | 97084 | 21 Nov 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1467 | A 2401 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 800 | 100 | 49.2 | 0 | 1968 | C+S GST 18% I/P RD | 354.24 | 2322.24 | 2322.24 | Approved | 0 | 0 | 628 | 21 Nov 2022
GANGA DHAM TOWERS | 395 | 97083 | 21 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1512 | B Internal plaster -Tikki Dhada Plaster Rate Diff | Tikki Dhada Rate Diff (L) | 569 | Sq.Ft | 1 | 100 | 14.23 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 6 | 21 Nov 2022
GANGA DHAM TOWERS | 272 | 97082 | 19 Nov 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1437 | A Bldg 34th slab (29th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1826.4 | Sq.Ft | 190 | 100 | 8675.4 | 0 | 347016 | C+S GST 18% I/P RD | 62462.88 | 409478.88 | 409478.88 | Approved | 0 | 0 | 6940 | 19 Nov 2022
GANGA DHAM TOWERS | 372 | 97081 | 19 Nov 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1519 | B Bldg - Fire Check Slab - Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1425.154 | Sq.Ft | 170 | 100 | 6056.9 | 0 | 242276.18 | C+S GST 18% I/P RD | 43609.72 | 285885.9 | 285885.9 | Approved | 0 | 0 | 4846 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Webbing Sling | 4 | No. | 150 | 100 | 0 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | PM Lift Height Extension | 2 | No. | 1500 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | PM Lift Height Extension | 2 | No. | 1500 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Wire Rope Sling | 2 | No. | 200 | 100 | 0 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Material Lifting Bucket | 2 | No. | 450 | 100 | 0 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Concrete Bucket | 1 | No. | 350 | 100 | 0 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | PM Lift (Tower Crane) | 2 | No. | 1700 | 100 | 0 | 0 | 3400 | C+S GST 18% I/P RD | 612 | 4012 | 4012 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Lift Drop test PM | 2 | No. | 1500 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 1437 | 97078 | 19 Nov 2022 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1667 | PM Lift AMC in A & B Tower | Dee Shackle Testing | 4 | No. | 150 | 100 | 0 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 0 | 153 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 901 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 701 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 1401 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 301 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 101 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 401 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 1601 Gypsum Plaster (Refuge Flat) | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 1301 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 801 Gypsum Plaster | Gypsum on Wall (L) | 63.25 | Sq.Ft | 4 | 100 | 6.33 | 0 | 253 | C+S GST 18% I/P RD | 45.54 | 298.54 | 298.54 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 801 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 401 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 701 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 901 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 101 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 301 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 1601 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 1401 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 495 | 97077 | 19 Nov 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1513 | B 5 Bhk 1301 Dry Balcony Tikki Dhada | Tikki Dhada rate diff. (L) | 63.2 | Sq.Ft | 5 | 100 | 7.9 | 0 | 316 | C+S GST 18% I/P RD | 56.88 | 372.88 | 372.88 | Approved | 0 | 0 | 51 | 19 Nov 2022
GANGA DHAM TOWERS | 372 | 97069 | 18 Nov 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1521 | B Bldg. 34th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 5740 | Sq.Ft | 190 | 100 | 27265 | 0 | 1090600 | C+S GST 18% I/P RD | 196308 | 1286908 | 1286908 | Approved | 0 | 0 | 21812 | 18 Nov 2022
GANGA DHAM TOWERS | 272 | 97068 | 18 Nov 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1520 | A Bldg 34th slab (29th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1826.4 | Sq.Ft | 190 | 100 | 8675.4 | 0 | 347016 | C+S GST 18% I/P RD | 62462.88 | 409478.88 | 409478.88 | Approved | 0 | 0 | 8453 | 18 Nov 2022
GANGA DHAM TOWERS | 272 | 97068 | 18 Nov 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1520 | A Bldg Fire Check slab- Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 445 | Sq.Ft | 170 | 100 | 1891.25 | 0 | 75650 | C+S GST 18% I/P RD | 13617 | 89267 | 89267 | Approved | 0 | 0 | 8453 | 18 Nov 2022
GANGA DHAM TOWERS | 272 | 97067 | 18 Nov 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1436 | A Bldg 34th slab (29th Floor) Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 4509.6 | Sq.Ft | 190 | 100 | 21420.6 | 0 | 856824 | C+S GST 18% I/P RD | 154228.32 | 1011052.32 | 1011052.32 | Approved | 0 | 0 | 17136 | 18 Nov 2022
GANGA DHAM TOWERS | 493 | 97065 | 18 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1413 | D Bldg East Side External Plaster | External Plaster- BC | 844 | Sq.Ft | 28 | 100 | 590.8 | 0 | 23632 | CGST 0% URD I/P | 0 | 23632 | 23632 | Approved | 0 | 0 | 2246 | 18 Nov 2022
GANGA DHAM TOWERS | 493 | 97065 | 18 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1413 | D Bldg East Side External Plaster | External Plaster- BC | 2489 | Sq.Ft | 28 | 100 | 1742.3 | 0 | 69692 | CGST 0% URD I/P | 0 | 69692 | 69692 | Approved | 0 | 0 | 2246 | 18 Nov 2022
GANGA DHAM TOWERS | 493 | 97065 | 18 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1413 | D Bldg Duct External Plaster | External Plaster- BC | 3154.3929 | Sq.Ft | 28 | 100 | 2208.08 | 0 | 88323 | CGST 0% URD I/P | 0 | 88323 | 88323 | Approved | 0 | 0 | 2246 | 18 Nov 2022
GANGA DHAM TOWERS | 493 | 97065 | 18 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1413 | D Bldg East Side External Plaster | External Plaster- BC | 844 | Sq.Ft | 28 | 100 | 590.8 | 0 | 23632 | CGST 0% URD I/P | 0 | 23632 | 23632 | Approved | 0 | 0 | 2246 | 18 Nov 2022
GANGA DHAM TOWERS | 493 | 97065 | 18 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1413 | D Bldg South Side External Plaster | External Plaster- BC | 551 | Sq.Ft | 35 | 100 | 482.13 | 0 | 19285 | CGST 0% URD I/P | 0 | 19285 | 19285 | Approved | 0 | 0 | 2246 | 18 Nov 2022
GANGA DHAM TOWERS | 1314 | 97064 | 18 Nov 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1482 | D 1203 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.9 | Sq.Ft | 9.5 | 100 | 0 | 0 | 7532.55 | C+S GST 5% I/P RD | 376.62 | 7909.17 | 7909.17 | Approved | 0 | 0 | 0 | 18 Nov 2022
GANGA DHAM TOWERS | 1314 | 97064 | 18 Nov 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1482 | D 1204 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.9 | Sq.Ft | 9.5 | 100 | 0 | 0 | 7532.55 | C+S GST 5% I/P RD | 376.62 | 7909.17 | 7909.17 | Approved | 0 | 0 | 0 | 18 Nov 2022
GANGA DHAM TOWERS | 1314 | 97064 | 18 Nov 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1482 | D 1201 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145.0526 | Sq.Ft | 9.5 | 100 | 0 | 0 | 10878 | C+S GST 5% I/P RD | 543.9 | 11421.9 | 11421.9 | Approved | 0 | 0 | 0 | 18 Nov 2022
GANGA DHAM TOWERS | 1314 | 97064 | 18 Nov 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1482 | D 1202 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 979.1579 | Sq.Ft | 9.5 | 100 | 0 | 0 | 9302 | C+S GST 5% I/P RD | 465.1 | 9767.1 | 9767.1 | Approved | 0 | 0 | 0 | 18 Nov 2022
GANGA DHAM TOWERS | 1314 | 97064 | 18 Nov 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | LAXMI STRUCTURES & FIXTURES LLP | EV - 1482 | D 1205 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 801.0526 | Sq.Ft | 9.5 | 100 | 0 | 0 | 7610 | C+S GST 5% I/P RD | 380.5 | 7990.5 | 7990.5 | Approved | 0 | 0 | 0 | 18 Nov 2022
GANGA DHAM TOWERS | 1251 | 97063 | 18 Nov 2022 |  | Kishan Enterprises | RAHUL ENTERPRISES (Prop Laburi) | EV - 1576 | B 202 NOC | Italian Marble Cutting & Shifting | 770 | Sq.Ft | 25 | 100 | 0 | 0 | 19250 | C+S GST 18% I/P RD | 3465 | 22715 | 22715 | Approved | 0 | 0 | 193 | 18 Nov 2022
GANGA DHAM TOWERS | 1436 | 97060 | 17 Nov 2022 |  | KISANARAM SUTAR | KISANARAM SUTAR | EV - 1553 | S5-1101 Carpentry work | Carpentary work lumpsum-BCo | 1 | No. | 80000 | 100 | 2000 | 0 | 80000 | CGST 0% URD I/P | 0 | 80000 | 80000 | Approved | 0 | 0 | 800 | 17 Nov 2022
GANGA DHAM TOWERS | 272 | 97059 | 17 Nov 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1438 | A Bldg Fire Check slab- Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1596 | Sq.Ft | 170 | 100 | 6783 | 0 | 271320 | C+S GST 18% I/P RD | 48837.6 | 320157.6 | 320157.6 | Approved | 0 | 0 | 5426 | 17 Nov 2022
GANGA DHAM TOWERS | 1420 | 97053 | 16 Nov 2022 |  | JAY GANESH ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 1435 | D Bldg Scaffolding for Ext. Plaster | Lumpsum work- DCW | 0.4396 | No. | 100000 | 100 | 1099 | 0 | 43965 | CGST 0% URD I/P | 0 | 43965 | 43965 | Approved | 0 | 0 | 440 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 104 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 201 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 202 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 301 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 203 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 102 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 502 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 501 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 302 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 101 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97052 | 16 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1447 | A 401 Terrace Scaffolding | Scaffolding Work - BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 275 | 16 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 203 Terrace False Ceiling | Sherawood False Ceiling (L) | 118.863 | Sq.Ft | 42 | 100 | 124.81 | 0 | 4992.25 | C+S GST 18% I/P RD | 898.6 | 5890.85 | 5890.85 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 502 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 501 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 201 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 301 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 101 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 202 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 104 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 401 Terrace False Ceiling | Sherawood False Ceiling (L) | 159.849 | Sq.Ft | 42 | 100 | 167.84 | 0 | 6713.66 | C+S GST 18% I/P RD | 1208.46 | 7922.12 | 7922.12 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 302 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 637 | 97044 | 15 Nov 2022 |  | S R INFRA PROJECTS | S R INFRA PROJECTS | EV - 1448 | A 102 Terrace False Ceiling | Sherawood False Ceiling (L) | 140.472 | Sq.Ft | 42 | 100 | 147.5 | 0 | 5899.82 | C+S GST 18% I/P RD | 1061.96 | 6961.78 | 6961.78 | Approved | 0 | 0 | 664 | 15 Nov 2022
GANGA DHAM TOWERS | 1118 | 97037 | 14 Nov 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1556 | A 2802 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236.15 | C+S GST 18% I/P RD | 2922.5 | 19158.65 | 19158.65 | Approved | 0 | 0 | 1276 | 14 Nov 2022
GANGA DHAM TOWERS | 1118 | 97037 | 14 Nov 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1556 | A 2804 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236.15 | C+S GST 18% I/P RD | 2922.5 | 19158.65 | 19158.65 | Approved | 0 | 0 | 1276 | 14 Nov 2022
GANGA DHAM TOWERS | 1118 | 97037 | 14 Nov 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1556 | A 2803 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 41490 | 35 | 363.04 | 0 | 14521.5 | C+S GST 18% I/P RD | 2613.88 | 17135.38 | 17135.38 | Approved | 0 | 0 | 1276 | 14 Nov 2022
GANGA DHAM TOWERS | 1118 | 97037 | 14 Nov 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1556 | A 2801 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 47964 | 35 | 419.69 | 0 | 16787.4 | C+S GST 18% I/P RD | 3021.74 | 19809.14 | 19809.14 | Approved | 0 | 0 | 1276 | 14 Nov 2022
GANGA DHAM TOWERS | 493 | 97027 | 12 Nov 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1411 | D Bldg North Side External Plaster | External Plaster- BC | 3245.5357 | Sq.Ft | 28 | 100 | 2271.87 | 0 | 90875 | CGST 0% URD I/P | 0 | 90875 | 90875 | Approved | 0 | 0 | 909 | 12 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 12th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 23rd floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 5th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 22nd floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 10th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 17th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 1st floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 6th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 21st floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 3rd floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 4th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 8th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 7th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 13th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 14th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 19th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 15th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 20th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 2nd floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 16th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 18th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 11th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 845 | 97017 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1408 | A Eastside 9th floor External Texture Painting | Texture Paint (M) | 82.2069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 0 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 23rd floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 17th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 5th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 4th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 8th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 21st floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 6th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 10th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 12th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 2nd floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 11th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 20th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 13th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 16th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 7th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 22nd floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 1st floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 3rd floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 19th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 9th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 18th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 14th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 15th floor External Texture Painting | Scaffolding/Gondola work | 82.2857 | Sq.Ft | 3.5 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 5th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 22nd floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 3rd floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 4th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 6th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 21st floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 19th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 7th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 15th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 8th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 10th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 17th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 14th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 12th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 20th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 11th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 13th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 23rd floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 9th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 16th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 18th floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 1st floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 844 | 97016 | 11 Nov 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1409 | A Eastside 2nd floor External Texture Painting | Texture Paint (L) | 82.2069 | Sq.Ft | 7.25 | 100 | 14.9 | 0 | 596 | C+S GST 18% I/P RD | 107.28 | 703.28 | 703.28 | Approved | 0 | 0 | 203 | 11 Nov 2022
GANGA DHAM TOWERS | 1160 | 97004 | 10 Nov 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1457 | B1 1101 Tiling Work | Italian Marble Mirror Polish- BCo | 290.4615 | Sq.Ft | 65 | 100 | 472 | 0 | 18880 | C+S GST 18% I/P RD | 3398.4 | 22278.4 | 22278.4 | Approved | 0 | 0 | 378 | 10 Nov 2022
GANGA DHAM TOWERS | 1228 | 97002 | 10 Nov 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 1383 | R & D Purpose | R & D Purpose | 0.1137 | No. | 100000 | 100 | 0 | 0 | 11370 | C+S GST 18% I/P RD | 2046.6 | 13416.6 | 13416.6 | Approved | 0 | 0 | 227 | 10 Nov 2022
GANGA DHAM TOWERS | 149 | 96999 | 10 Nov 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1410 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3003 | No. | 4 | 100 | 0 | 0 | 12012 | CGST 0% URD I/P | 0 | 12012 | 12012 | Approved | 0 | 0 | 0 | 10 Nov 2022
GANGA DHAM TOWERS | 371 | 96985 | 09 Nov 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1412 | EWS Bldg RCC 11th Slab Built-up Area (L) | Hacking Work | 3118 | Sq.Ft | 2.5 | 100 | 194.88 | 0 | 7795 | CGST 0% URD I/P | 0 | 7795 | 7795 | Approved | 0 | 0 | 241 | 09 Nov 2022
GANGA DHAM TOWERS | 371 | 96985 | 09 Nov 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1412 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | Hacking Work | 1730 | Sq.Ft | 2.5 | 100 | 108.13 | 0 | 4325 | CGST 0% URD I/P | 0 | 4325 | 4325 | Approved | 0 | 0 | 241 | 09 Nov 2022
GANGA DHAM TOWERS | 371 | 96985 | 09 Nov 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1412 | EWS Bldg RCC 7th Slab Built-up Area (L) | Schedule & Quality | 2800 | Sq.Ft | 2.5 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 241 | 09 Nov 2022
GANGA DHAM TOWERS | 371 | 96985 | 09 Nov 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1412 | EWS Bldg RCC 7th Slab Built-up Area (L) | Schedule & Quality | 618.4 | Sq.Ft | 2.5 | 100 | 38.65 | 0 | 1546 | CGST 0% URD I/P | 0 | 1546 | 1546 | Approved | 0 | 0 | 241 | 09 Nov 2022
GANGA DHAM TOWERS | 371 | 96985 | 09 Nov 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1412 | EWS Bldg RCC 8th Slab Built-up Area (L) | Schedule & Quality | 1381.6 | Sq.Ft | 2.5 | 100 | 86.35 | 0 | 3454 | CGST 0% URD I/P | 0 | 3454 | 3454 | Approved | 0 | 0 | 241 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 503 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 503 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 1003 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 201 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 1002 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 901 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 403 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 504 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 902 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 303 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 203 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 701 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 1103 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 802 (Refuge area) Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 801 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 603 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 903 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 501 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 803 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 1102 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 601 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 702 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 401 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 703 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 703 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 803 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 602 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 903 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 698 | 96984 | 09 Nov 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1406 | D 603 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 31 | Sq.Ft | 4 | 100 | 3.1 | 0 | 124 | CGST 0% URD I/P | 0 | 124 | 124 | Approved | 0 | 0 | 204 | 09 Nov 2022
GANGA DHAM TOWERS | 1119 | 96983 | 09 Nov 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1452 | C Bldg 1st RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 603.373 | Sq.Ft | 170 | 100 | 2564.34 | 0 | 102573.41 | C+S GST 18% I/P RD | 18463.22 | 121036.63 | 121036.63 | Approved | 0 | 0 | 5310 | 09 Nov 2022
GANGA DHAM TOWERS | 1119 | 96983 | 09 Nov 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1452 | C Bldg 1st RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 603.3353 | Sq.Ft | 170 | 100 | 2564.18 | 0 | 102567 | C+S GST 18% I/P RD | 18462.06 | 121029.06 | 121029.06 | Approved | 0 | 0 | 5310 | 09 Nov 2022
GANGA DHAM TOWERS | 1119 | 96983 | 09 Nov 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1452 | C Bldg 3rd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 905.0595 | Sq.Ft | 180 | 100 | 4072.77 | 0 | 162910.71 | C+S GST 18% I/P RD | 29323.92 | 192234.63 | 192234.63 | Approved | 0 | 0 | 5310 | 09 Nov 2022
GANGA DHAM TOWERS | 1119 | 96983 | 09 Nov 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1452 | C Bldg 3rd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 905.061 | Sq.Ft | 180 | 100 | 4072.77 | 0 | 162910.98 | C+S GST 18% I/P RD | 29323.98 | 192234.96 | 192234.96 | Approved | 0 | 0 | 5310 | 09 Nov 2022
GANGA DHAM TOWERS | 1383 | 96982 | 08 Nov 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1359 | Professional Consultancy (Finalcial) | Professional Fees | 0.9622 | Month | 116666.666 | 100 | 0 | 0 | 112258 | C+S GST 0% I/P RD | 0 | 112258 | 112258 | Approved | 0 | 0 | 11226 | 08 Nov 2022
GANGA DHAM TOWERS | 1383 | 96981 | 08 Nov 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1360 | Professional Consultancy (Finalcial) | Professional Fees | 0.0331 | Month | 116666.666 | 100 | 0 | 0 | 3866 | C+S GST 0% I/P RD | 0 | 3866 | 3866 | Approved | 0 | 0 | 387 | 08 Nov 2022
GANGA DHAM TOWERS | 1052 | 96976 | 08 Nov 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1364 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 08 Nov 2022
GANGA DHAM TOWERS | 1208 | 96963 | 08 Nov 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 1372 | Tower Crane B-Bldg Annual Maintenance charges of lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 08 Nov 2022
GANGA DHAM TOWERS | 1207 | 96962 | 08 Nov 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 1370 | Tower Crane A & C Annual maintenance for tower crane & lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 08 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 16th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 11th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 12th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 17th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 4th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 18th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 5th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 13th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 14th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 15th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 20th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 1st Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 3rd Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 2nd Floor Texture Painting | Texture Paint (M) | 78.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.02 | C+S GST 18% I/P RD | 102.06 | 669.08 | 669.08 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 9th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 6th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 7th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 23rd Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 19th Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 21st Floor Texture Painting | Texture Paint (M) | 98.21 | Sq.Ft | 7.25 | 100 | 0 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 10th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 8th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 22nd Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1200 | 96926 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Southside 24th Floor Texture Painting | Texture Paint (M) | 78.25 | Sq.Ft | 7.25 | 100 | 0 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 |  | 0 | 0 | 0 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 9th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 2nd Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 7th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 8th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 15th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 16th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 1st Floor Texture Painting | Texture Paint (L) | 98.2069 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712 | C+S GST 18% I/P RD | 128.16 | 840.16 | 840.16 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 17th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 24th Floor Texture Painting | Texture Paint (L) | 78.21 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.02 | C+S GST 18% I/P RD | 102.06 | 669.08 | 669.08 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 5th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 23rd Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 3rd Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 4th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 20th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 12th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 14th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 13th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 6th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 10th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 19th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 21st Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 22nd Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 18th Floor Texture Painting | Texture Paint (L) | 78.25 | Sq.Ft | 7.25 | 100 | 14.18 | 0 | 567.31 | C+S GST 18% I/P RD | 102.12 | 669.43 | 669.43 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 11th Floor Texture Painting | Texture Paint (L) | 98.21 | Sq.Ft | 7.25 | 100 | 17.8 | 0 | 712.02 | C+S GST 18% I/P RD | 128.16 | 840.18 | 840.18 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 5th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 21st Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 6th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 22nd Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 9th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 23rd Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 24th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 7th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 3rd Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 8th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 11th Floor Texture Painting | Scaffolding/Gondola work | 20 | Sq.Ft | 3.5 | 100 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 11th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 20th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 4th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 1st Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 18th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 15th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 17th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 19th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 16th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 14th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 12th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 10th Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 13th Floor Texture Painting | Scaffolding/Gondola work | 98.2857 | Sq.Ft | 3.5 | 100 | 8.6 | 0 | 344 | C+S GST 18% I/P RD | 61.92 | 405.92 | 405.92 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 1199 | 96925 | 04 Nov 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1403 | B Southside 2nd Floor Texture Painting | Scaffolding/Gondola work | 78.2857 | Sq.Ft | 3.5 | 100 | 6.85 | 0 | 274 | C+S GST 18% I/P RD | 49.32 | 323.32 | 323.32 | Approved | 0 | 0 | 228 | 04 Nov 2022
GANGA DHAM TOWERS | 272 | 96923 | 04 Nov 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1418 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 236.8496 | Sq.Ft | 133 | 100 | 0 | 0 | 31501 | C+S GST 18% I/P RD | 5670.18 | 37171.18 | 37171.18 | Approved | 0 | 0 | 315 | 04 Nov 2022
GANGA DHAM TOWERS | 413 | 96896 | 03 Nov 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1636 | Sales office Garden Maintenance | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 03 Nov 2022
GANGA DHAM TOWERS | 178 | 96895 | 03 Nov 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1635 | Sales office Garden Maintenance | Garden work. | 60.915 | Day | 407.25 | 100 | 0 | 0 | 24807.63 | C+S GST 18% I/P RD | 4465.38 | 29273.01 | 29273.01 | Approved | 0 | 0 | 248 | 03 Nov 2022
GANGA DHAM TOWERS | 1433 | 96864 | 02 Nov 2022 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 2205 | RMC Pump Per Month Rental Charges | Pump Hiring for RMC | 1 | Month | 250000 | 100 | 0 | 0 | 250000 | C+S GST 18% I/P RD | 45000 | 295000 | 295000 | Approved | 0 | 0 | 5000 | 02 Nov 2022
GANGA DHAM TOWERS | 1360 | 96863 | 02 Nov 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1374 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 02 Nov 2022
GANGA DHAM TOWERS | 940 | 96862 | 02 Nov 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1375 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Nov 2022
GANGA DHAM TOWERS | 1162 | 96861 | 02 Nov 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1326 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 02 Nov 2022
GANGA DHAM TOWERS | 1340 | 96860 | 01 Nov 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1328 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 01 Nov 2022
GANGA DHAM TOWERS | 541 | 96852 | 01 Nov 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1592 | B 1501 NOC | Core Cutting Work | 10 | No. | 300 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 30 | 01 Nov 2022
GANGA DHAM TOWERS | 971 | 96851 | 01 Nov 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1536 | B 1901 NOC | Core Cutting Work | 12 | No. | 300 | 100 | 0 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 36 | 01 Nov 2022
GANGA DHAM TOWERS | 1335 | 96846 | 28 Oct 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES |  | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 |  | 0 | 0 | 0 | 28 Oct 2022
GANGA DHAM TOWERS | 1335 | 96846 | 28 Oct 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES |  | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 2 | No. | 6000 | 100 | 0 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 |  | 0 | 0 | 0 | 28 Oct 2022
GANGA DHAM TOWERS | 1228 | 96836 | 20 Oct 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1385 | Site Expenses | Site Expenses -SO | 0.1127 | Month | 30000 | 100 | 0 | 0 | 3380 | CGST 0% URD I/P | 0 | 3380 | 3380 | Approved | 0 | 0 | 0 | 20 Oct 2022
GANGA DHAM TOWERS | 1228 | 96836 | 20 Oct 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1385 | Site Expenses | Site Expenses -SO | 0.3408 | Month | 30000 | 100 | 0 | 0 | 10224 | CGST 0% URD I/P | 0 | 10224 | 10224 | Approved | 0 | 0 | 0 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 503 Marble Window Sill | Italian Marble Sill- BC- | 12.5111 | R.Ft | 45 | 100 | 14.07 | 0 | 563 | CGST 0% URD I/P | 0 | 563 | 563 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 604 Marble Window Sill | Italian Marble Sill- BC- | 22 | R.Ft | 45 | 100 | 24.75 | 0 | 990 | CGST 0% URD I/P | 0 | 990 | 990 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 403 Marble Window Sill | Italian Marble Sill- BC- | 12.5111 | R.Ft | 45 | 100 | 14.07 | 0 | 563 | CGST 0% URD I/P | 0 | 563 | 563 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 603 Marble Window Sill | Italian Marble Sill- BC- | 12.5111 | R.Ft | 45 | 100 | 14.07 | 0 | 563 | CGST 0% URD I/P | 0 | 563 | 563 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 404 Marble Window Sill | Italian Marble Sill- BC- | 22 | R.Ft | 45 | 100 | 24.75 | 0 | 990 | CGST 0% URD I/P | 0 | 990 | 990 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 504 Marble Window Sill | Italian Marble Sill- BC- | 17.3556 | R.Ft | 45 | 100 | 19.53 | 0 | 781 | CGST 0% URD I/P | 0 | 781 | 781 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 903 Marble Window Sill | Italian Marble Sill- BC- | 12.5 | R.Ft | 50 | 100 | 15.63 | 0 | 625 | CGST 0% URD I/P | 0 | 625 | 625 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 704 Marble Window Sill | Italian Marble Sill- BC- | 24.34 | R.Ft | 50 | 100 | 30.43 | 0 | 1217 | CGST 0% URD I/P | 0 | 1217 | 1217 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 703 Marble Window Sill | Italian Marble Sill- BC- | 12.5 | R.Ft | 50 | 100 | 15.63 | 0 | 625 | CGST 0% URD I/P | 0 | 625 | 625 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 803 Marble Window Sill | Italian Marble Sill- BC- | 12.5 | R.Ft | 50 | 100 | 15.63 | 0 | 625 | CGST 0% URD I/P | 0 | 625 | 625 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96835 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1334 | A 1003 Marble Window Sill | Italian Marble Sill- BC- | 12.5 | R.Ft | 50 | 100 | 15.63 | 0 | 625 | CGST 0% URD I/P | 0 | 625 | 625 | Approved | 0 | 0 | 82 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 604 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.1111 | R.Ft | 45 | 100 | 13.62 | 0 | 545 | CGST 0% URD I/P | 0 | 545 | 545 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 403 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4444 | R.Ft | 45 | 100 | 14 | 0 | 560 | CGST 0% URD I/P | 0 | 560 | 560 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 404 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.1111 | R.Ft | 45 | 100 | 24.87 | 0 | 995 | CGST 0% URD I/P | 0 | 995 | 995 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 803 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 503 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 504 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.2 | R.Ft | 45 | 100 | 19.35 | 0 | 774 | CGST 0% URD I/P | 0 | 774 | 774 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 703 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 1003 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 704 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17 | R.Ft | 45 | 100 | 19.13 | 0 | 765 | CGST 0% URD I/P | 0 | 765 | 765 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 903 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 1425 | 96834 | 20 Oct 2022 |  | Kishan Enterprises | S K ENTERPRISES (SURESH MALI) | EV - 1548 | A 603 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 12.4222 | R.Ft | 45 | 100 | 13.97 | 0 | 559 | CGST 0% URD I/P | 0 | 559 | 559 | Approved | 0 | 0 | 70 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | CGST 0% URD I/P | 0 | 312 | 312 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Children Toilet | L Groove - BCV | 30 | R.Ft | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Powder Toilet dado | L Groove - BCV | 30 | R.Ft | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Staff Toilet dado | L Groove - BCV | 16 | R.Ft | 20 | 100 | 8 | 0 | 320 | CGST 0% URD I/P | 0 | 320 | 320 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Parents Toilet dado | L Groove - BCV | 35 | R.Ft | 20 | 100 | 17.5 | 0 | 700 | CGST 0% URD I/P | 0 | 700 | 700 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 537 | 96833 | 20 Oct 2022 |  | MONIKA ENTERPRISES | S K ENTERPRISES (SURESH MALI) | EV - 1335 | A 602 Master Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | CGST 0% URD I/P | 0 | 540 | 540 | Approved | 0 | 0 | 31 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 1003 Marble Window Sill | Italian Marble Sill- BC- | 16.34 | R.Ft | 50 | 100 | 20.43 | 0 | 817 | CGST 0% URD I/P | 0 | 817 | 817 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 703 Marble Window Sill | Italian Marble Sill- BC- | 16.34 | R.Ft | 50 | 100 | 20.43 | 0 | 817 | CGST 0% URD I/P | 0 | 817 | 817 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 203 Terrace Vitrified Flooring | Vitrified Flooring -BC | 112 | Sq.Ft | 15 | 100 | 42 | 0 | 1680 | CGST 0% URD I/P | 0 | 1680 | 1680 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Marble Window Sill | Italian Marble Sill- BC- | 16.3333 | R.Ft | 45 | 100 | 18.37 | 0 | 735 | CGST 0% URD I/P | 0 | 735 | 735 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 603 Marble Window Sill | Italian Marble Sill- BC- | 16.3333 | R.Ft | 45 | 100 | 18.37 | 0 | 735 | CGST 0% URD I/P | 0 | 735 | 735 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 604 Marble Window Sill | Italian Marble Sill- BC- | 31.1556 | R.Ft | 45 | 100 | 35.05 | 0 | 1402 | CGST 0% URD I/P | 0 | 1402 | 1402 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 404 Marble Window Sill | Italian Marble Sill- BC- | 31.1556 | R.Ft | 45 | 100 | 35.05 | 0 | 1402 | CGST 0% URD I/P | 0 | 1402 | 1402 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Marble Window Sill | Italian Marble Sill- BC- | 31 | R.Ft | 45 | 100 | 34.88 | 0 | 1395 | CGST 0% URD I/P | 0 | 1395 | 1395 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 503 Marble Window Sill | Italian Marble Sill- BC- | 16.3333 | R.Ft | 45 | 100 | 18.37 | 0 | 735 | CGST 0% URD I/P | 0 | 735 | 735 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 903 Dry Balcony dado | Dado BC | 43 | Sq.Ft | 18 | 100 | 19.35 | 0 | 774 | CGST 0% URD I/P | 0 | 774 | 774 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 603 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 404 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 45 | Sq.Ft | 13 | 100 | 14.63 | 0 | 585 | CGST 0% URD I/P | 0 | 585 | 585 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | CGST 0% URD I/P | 0 | 312 | 312 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 603 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | CGST 0% URD I/P | 0 | 312 | 312 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 604 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | CGST 0% URD I/P | 0 | 312 | 312 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | CGST 0% URD I/P | 0 | 312 | 312 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 45 | Sq.Ft | 13 | 100 | 14.63 | 0 | 585 | CGST 0% URD I/P | 0 | 585 | 585 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 404 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 48 | Sq.Ft | 13 | 100 | 15.6 | 0 | 624 | CGST 0% URD I/P | 0 | 624 | 624 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 48 | Sq.Ft | 13 | 100 | 15.6 | 0 | 624 | CGST 0% URD I/P | 0 | 624 | 624 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 604 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 33 | Sq.Ft | 13 | 100 | 10.73 | 0 | 429 | CGST 0% URD I/P | 0 | 429 | 429 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 404 Dry Balcony dado | Dado BC | 89 | Sq.Ft | 14 | 100 | 31.15 | 0 | 1246 | CGST 0% URD I/P | 0 | 1246 | 1246 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 603 Dry Balcony dado | Dado BC | 86 | Sq.Ft | 14 | 100 | 30.1 | 0 | 1204 | CGST 0% URD I/P | 0 | 1204 | 1204 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Dry Balcony dado | Dado BC | 89 | Sq.Ft | 14 | 100 | 31.15 | 0 | 1246 | CGST 0% URD I/P | 0 | 1246 | 1246 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 204 Dry Balcony dado | Dado BC | 89 | Sq.Ft | 14 | 100 | 31.15 | 0 | 1246 | CGST 0% URD I/P | 0 | 1246 | 1246 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 604 Dry Balcony dado | Dado BC | 54 | Sq.Ft | 14 | 100 | 18.9 | 0 | 756 | CGST 0% URD I/P | 0 | 756 | 756 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Marble Window Sill | Italian Marble Sill- BC- | 16.34 | R.Ft | 50 | 100 | 20.43 | 0 | 817 | CGST 0% URD I/P | 0 | 817 | 817 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 903 Marble Window Sill | Italian Marble Sill- BC- | 16.34 | R.Ft | 50 | 100 | 20.43 | 0 | 817 | CGST 0% URD I/P | 0 | 817 | 817 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Terrace Vitrified Flooring | Vitrified Flooring -BC | 64 | Sq.Ft | 20 | 100 | 32 | 0 | 1280 | CGST 0% URD I/P | 0 | 1280 | 1280 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 203 Terrace Vitrified Flooring | Vitrified Skirting BC | 36 | R.Ft | 15 | 100 | 13.5 | 0 | 540 | CGST 0% URD I/P | 0 | 540 | 540 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Powder Toilet dado | L Groove - BCV | 5 | R.Ft | 20 | 100 | 2.5 | 0 | 100 | CGST 0% URD I/P | 0 | 100 | 100 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Children Toilet dado | L Groove - BCV | 43 | R.Ft | 20 | 100 | 21.5 | 0 | 860 | CGST 0% URD I/P | 0 | 860 | 860 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 603 Guest Toilet dado | L Groove - BCV | 25 | R.Ft | 20 | 100 | 12.5 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 1003 Children Toilet dado | L Groove - BCV | 30 | R.Ft | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 1003 Guest Toilet dado | L Groove - BCV | 30 | R.Ft | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Master Toilet dado | L Groove - BCV | 40 | R.Ft | 20 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 903 Dry Balcony dado | L Groove - BCV | 6 | R.Ft | 20 | 100 | 3 | 0 | 120 | CGST 0% URD I/P | 0 | 120 | 120 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Guest Toilet dado | L Groove - BCV | 27 | R.Ft | 20 | 100 | 13.5 | 0 | 540 | CGST 0% URD I/P | 0 | 540 | 540 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Master Toilet dado | L Groove - BCV | 40 | R.Ft | 20 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Children Toilet dado | L Groove - BCV | 30 | R.Ft | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 604 Parents Toilet dado | L Groove - BCV | 24 | R.Ft | 20 | 100 | 12 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Staff Toilet dado | L Groove - BCV | 20 | R.Ft | 20 | 100 | 10 | 0 | 400 | CGST 0% URD I/P | 0 | 400 | 400 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Terrace Vitrified Flooring | Vitrified Skirting BC | 36 | R.Ft | 20 | 100 | 18 | 0 | 720 | CGST 0% URD I/P | 0 | 720 | 720 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 504 Staff Toilet dado | Dado BC | 135 | Sq.Ft | 13 | 100 | 43.88 | 0 | 1755 | CGST 0% URD I/P | 0 | 1755 | 1755 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 204 Staff Toilet dado | Dado BC | 135 | Sq.Ft | 13 | 100 | 43.88 | 0 | 1755 | CGST 0% URD I/P | 0 | 1755 | 1755 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 403 Staff Toilet dado | Dado BC | 135 | Sq.Ft | 13 | 100 | 43.88 | 0 | 1755 | CGST 0% URD I/P | 0 | 1755 | 1755 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 704 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 17 | 100 | 10.2 | 0 | 408 | CGST 0% URD I/P | 0 | 408 | 408 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 704 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 23 | Sq.Ft | 17 | 100 | 9.78 | 0 | 391 | CGST 0% URD I/P | 0 | 391 | 391 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 42 | Sq.Ft | 17 | 100 | 17.85 | 0 | 714 | CGST 0% URD I/P | 0 | 714 | 714 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 704 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 33 | Sq.Ft | 17 | 100 | 14.03 | 0 | 561 | CGST 0% URD I/P | 0 | 561 | 561 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 703 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38 | Sq.Ft | 17 | 100 | 16.15 | 0 | 646 | CGST 0% URD I/P | 0 | 646 | 646 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 703 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24 | Sq.Ft | 17 | 100 | 10.2 | 0 | 408 | CGST 0% URD I/P | 0 | 408 | 408 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 1003 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 62 | Sq.Ft | 17 | 100 | 26.35 | 0 | 1054 | CGST 0% URD I/P | 0 | 1054 | 1054 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 903 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 17 | 100 | 13.6 | 0 | 544 | CGST 0% URD I/P | 0 | 544 | 544 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 1003 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38 | Sq.Ft | 17 | 100 | 16.15 | 0 | 646 | CGST 0% URD I/P | 0 | 646 | 646 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 42 | Sq.Ft | 17 | 100 | 17.85 | 0 | 714 | CGST 0% URD I/P | 0 | 714 | 714 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 551 | 96831 | 20 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S K ENTERPRISES (SURESH MALI) | EV - 1333 | A 803 Terrace Parapet Top Granite | Granite Sill-BCo | 27 | R.Ft | 45 | 100 | 30.38 | 0 | 1215 | CGST 0% URD I/P | 0 | 1215 | 1215 | Approved | 0 | 0 | 444 | 20 Oct 2022
GANGA DHAM TOWERS | 1388 | 96820 | 20 Oct 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 1369 | Tower C Podium P1 -PT Slab Work | Post Tensioning Work -BC | 0.23 | Metric Tonnes | 154000 | 10 | 0 | 0 | 3542 | C+S GST 18% I/P RD | 637.56 | 4179.56 | 4179.56 | Approved | 0 | 0 | 3767 | 20 Oct 2022
GANGA DHAM TOWERS | 1388 | 96820 | 20 Oct 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 1369 | Tower C Podium P1 -PT Slab Work | Post Tensioning Work -BC | 12 | Metric Tonnes | 154000 | 10 | 0 | 0 | 184800 | C+S GST 18% I/P RD | 33264 | 218064 | 218064 | Approved | 0 | 0 | 3767 | 20 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Tower C Architectural Consultancy | Architectural Consultancy | 284850 | Sq.Ft | 5 | 10 | 0 | 0 | 142425 | C+S GST 18% I/P RD | 25636.5 | 168061.5 | 168061.5 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Tower B Architectural Consultancy | Architectural Consultancy | 200064 | Sq.Ft | 5 | 3.33 | 0 | 0 | 33310.66 | C+S GST 18% I/P RD | 5995.92 | 39306.58 | 39306.58 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Commercial Building Architectural Consultancy | Architectural Consultancy | 16135 | Sq.Ft | 5 | 15 | 0 | 0 | 12101.25 | C+S GST 18% I/P RD | 2178.22 | 14279.47 | 14279.47 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Tower A Architectural Consultancy | Architectural Consultancy | 273950 | Sq.Ft | 5 | 3.33 | 0 | 0 | 45612.68 | C+S GST 18% I/P RD | 8210.28 | 53822.96 | 53822.96 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Tower A Architectural Consultancy | Architectural Consultancy | 273950 | Sq.Ft | 5 | 3.35 | 0 | 0 | 45886.63 | C+S GST 18% I/P RD | 8259.6 | 54146.23 | 54146.23 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | Tower B Architectural Consultancy | Architectural Consultancy | 200064 | Sq.Ft | 5 | 3.35 | 0 | 0 | 33510.72 | C+S GST 18% I/P RD | 6031.92 | 39542.64 | 39542.64 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 397 | 96817 | 19 Oct 2022 |  | DIRECTION NEXT DESIGN STUDIO | DIRECTION NEXT DESIGN STUDIO | EV - 1271 | EWS Building Architectural Consultancy | Architectural Consultancy | 37534 | Sq.Ft | 5 | 5 | 0 | 0 | 9383.5 | C+S GST 18% I/P RD | 1689.04 | 11072.54 | 11072.54 | Approved | 0 | 0 | 32223 | 19 Oct 2022
GANGA DHAM TOWERS | 372 | 96812 | 19 Oct 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1388 | B Bldg - Fire Check Slab - Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 4275.4647 | Sq.Ft | 170 | 100 | 18170.72 | 0 | 726829 | C+S GST 18% I/P RD | 130829.22 | 857658.22 | 857658.22 | Approved | 0 | 0 | 14537 | 19 Oct 2022
GANGA DHAM TOWERS | 272 | 96811 | 19 Oct 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 1389 | A Bldg Fire Check slab- Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1380 | Sq.Ft | 170 | 100 | 5865 | 0 | 234600 | C+S GST 18% I/P RD | 42228 | 276828 | 276828 | Approved | 0 | 0 | 4692 | 19 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Fire Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Regular Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Fire Staircase | Kota Champher | 43.598 | R.Ft | 7.5 | 100 | 8.17 | 0 | 326.99 | C+S GST 18% I/P RD | 58.86 | 385.85 | 385.85 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Fire Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Fire Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Regular Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Regular Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Fire Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Regular Staircase | Kota Champher | 19.818 | R.Ft | 7.5 | 100 | 3.72 | 0 | 148.64 | C+S GST 18% I/P RD | 26.76 | 175.4 | 175.4 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Regular Staircase | Kota Champher | 43.598 | R.Ft | 7.5 | 100 | 8.17 | 0 | 326.99 | C+S GST 18% I/P RD | 58.86 | 385.85 | 385.85 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Regular Staircase | Kota Skirting (L)- BCO | 15.412 | R.Ft | 30 | 100 | 11.56 | 0 | 462.36 | C+S GST 18% I/P RD | 83.22 | 545.58 | 545.58 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Fire Staircase | Kota Skirting (L)- BCO | 17.192 | R.Ft | 30 | 100 | 12.89 | 0 | 515.76 | C+S GST 18% I/P RD | 92.84 | 608.6 | 608.6 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Regular Staircase | Kota Skirting (L)- BCO | 15.412 | R.Ft | 30 | 100 | 11.56 | 0 | 462.36 | C+S GST 18% I/P RD | 83.22 | 545.58 | 545.58 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Regular Staircase | Kota Skirting (L)- BCO | 15.412 | R.Ft | 30 | 100 | 11.56 | 0 | 462.36 | C+S GST 18% I/P RD | 83.22 | 545.58 | 545.58 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Fire Staircase | Kota Skirting (L)- BCO | 17.192 | R.Ft | 30 | 100 | 12.89 | 0 | 515.76 | C+S GST 18% I/P RD | 92.84 | 608.6 | 608.6 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Fire Staircase | Kota Skirting (L)- BCO | 17.192 | R.Ft | 30 | 100 | 12.89 | 0 | 515.76 | C+S GST 18% I/P RD | 92.84 | 608.6 | 608.6 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Regular Staircase | Kota Skirting (L)- BCO | 30.756 | R.Ft | 30 | 100 | 23.07 | 0 | 922.68 | C+S GST 18% I/P RD | 166.08 | 1088.76 | 1088.76 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Fire Staircase | Kota Skirting (L)- BCO | 35.192 | R.Ft | 30 | 100 | 26.39 | 0 | 1055.76 | C+S GST 18% I/P RD | 190.04 | 1245.8 | 1245.8 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Regular Staircase | Kota Skirting (L)- BCO | 15.412 | R.Ft | 30 | 100 | 11.56 | 0 | 462.36 | C+S GST 18% I/P RD | 83.22 | 545.58 | 545.58 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Fire Staircase | Kota Skirting (L)- BCO | 17.192 | R.Ft | 30 | 100 | 12.89 | 0 | 515.76 | C+S GST 18% I/P RD | 92.84 | 608.6 | 608.6 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Regular Staircase | Kota Champher & Edge Polish | 196.191 | R.Ft | 15 | 100 | 73.57 | 0 | 2942.87 | C+S GST 18% I/P RD | 529.72 | 3472.59 | 3472.59 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Fire Staircase | Kota Champher & Edge Polish | 196.191 | R.Ft | 15 | 100 | 73.57 | 0 | 2942.87 | C+S GST 18% I/P RD | 529.72 | 3472.59 | 3472.59 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Regular Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Fire Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Regular Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Regular Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Fire Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Regular Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Regular Staircase | Kota Tread (L) - DSP | 43.598 | R.Ft | 50 | 100 | 54.5 | 0 | 2179.9 | C+S GST 18% I/P RD | 392.38 | 2572.28 | 2572.28 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Fire Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Fire Staircase | Kota Tread (L) - DSP | 19.818 | R.Ft | 50 | 100 | 24.77 | 0 | 990.9 | C+S GST 18% I/P RD | 178.36 | 1169.26 | 1169.26 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Fire Staircase | Kota Tread (L) - DSP | 43.598 | R.Ft | 50 | 100 | 54.5 | 0 | 2179.9 | C+S GST 18% I/P RD | 392.38 | 2572.28 | 2572.28 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Regular Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Fire Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Regular Staircase | Kota Riser (L)- BCO | 43.598 | R.Ft | 45 | 100 | 49.05 | 0 | 1961.91 | C+S GST 18% I/P RD | 353.14 | 2315.05 | 2315.05 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Regular Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Fire Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 2 Floor Fire Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 1 Floor Regular Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Ground Floor Regular Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Podium Floor Fire Staircase | Kota Riser (L)- BCO | 43.598 | R.Ft | 45 | 100 | 49.05 | 0 | 1961.91 | C+S GST 18% I/P RD | 353.14 | 2315.05 | 2315.05 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96802 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1697 | A Parking 3 Floor Fire Staircase | Kota Riser (L)- BCO | 19.818 | R.Ft | 45 | 100 | 22.3 | 0 | 891.81 | C+S GST 18% I/P RD | 160.52 | 1052.33 | 1052.33 | Approved | 0 | 0 | 477 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Fire Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Fire Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Regular Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Regular Staircase - 1 No. | Kota Tread (L) - DSP | 196.191 | R.Ft | 50 | 100 | 245.24 | 0 | 9809.55 | C+S GST 18% I/P RD | 1765.72 | 11575.27 | 11575.27 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Fire Staircase- - 1 No. | Kota Champher & Edge Polish | 196.191 | R.Ft | 15 | 100 | 73.57 | 0 | 2942.87 | C+S GST 18% I/P RD | 529.72 | 3472.59 | 3472.59 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Regular Staircase - 1 No. | Kota Champher & Edge Polish | 196.191 | R.Ft | 15 | 100 | 73.57 | 0 | 2942.87 | C+S GST 18% I/P RD | 529.72 | 3472.59 | 3472.59 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Regular Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Regular Staircase | Kota Skirting (L)- BCO | 59.355 | R.Ft | 30 | 100 | 44.52 | 0 | 1780.65 | C+S GST 18% I/P RD | 320.52 | 2101.17 | 2101.17 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Regular Staircase | Kota Skirting (L)- BCO | 59.355 | R.Ft | 30 | 100 | 44.52 | 0 | 1780.65 | C+S GST 18% I/P RD | 320.52 | 2101.17 | 2101.17 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Fire Staircase | Kota Skirting (L)- BCO | 75.303 | R.Ft | 30 | 100 | 56.48 | 0 | 2259.09 | C+S GST 18% I/P RD | 406.64 | 2665.73 | 2665.73 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Regular Staircase | Kota Skirting (L)- BCO | 59.355 | R.Ft | 30 | 100 | 44.52 | 0 | 1780.65 | C+S GST 18% I/P RD | 320.52 | 2101.17 | 2101.17 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Fire Staircase | Kota Skirting (L)- BCO | 75.303 | R.Ft | 30 | 100 | 56.48 | 0 | 2259.09 | C+S GST 18% I/P RD | 406.64 | 2665.73 | 2665.73 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Fire Staircase- - 1 No. | Kota Skirting (L)- BCO | 166.185 | R.Ft | 30 | 100 | 124.64 | 0 | 4985.55 | C+S GST 18% I/P RD | 897.4 | 5882.95 | 5882.95 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Regular Staircase - 1 No. | Kota Skirting (L)- BCO | 123.849 | R.Ft | 30 | 100 | 92.89 | 0 | 3715.47 | C+S GST 18% I/P RD | 668.78 | 4384.25 | 4384.25 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Regular Staircase | Kota Skirting (L)- BCO | 59.355 | R.Ft | 30 | 100 | 44.52 | 0 | 1780.65 | C+S GST 18% I/P RD | 320.52 | 2101.17 | 2101.17 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Fire Staircase | Kota Skirting (L)- BCO | 75.303 | R.Ft | 30 | 100 | 56.48 | 0 | 2259.09 | C+S GST 18% I/P RD | 406.64 | 2665.73 | 2665.73 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Fire Staircase | Kota Skirting (L)- BCO | 75.303 | R.Ft | 30 | 100 | 56.48 | 0 | 2259.09 | C+S GST 18% I/P RD | 406.64 | 2665.73 | 2665.73 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Regular Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Fire Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Regular Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Fire Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Fire Staircase- - 1 No. | Kota Tread (L) - DSP | 196.191 | R.Ft | 50 | 100 | 245.24 | 0 | 9809.55 | C+S GST 18% I/P RD | 1765.72 | 11575.27 | 11575.27 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Regular Staircase | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Fire Staircase | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Regular Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Fire Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Regular Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Fire Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Fire Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Fire Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Regular Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Regular Staircase - 1 No. | Kota Champher | 196.191 | R.Ft | 7.5 | 100 | 36.79 | 0 | 1471.43 | C+S GST 18% I/P RD | 264.86 | 1736.29 | 1736.29 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Fire Staircase- - 1 No. | Kota Champher | 196.191 | R.Ft | 7.5 | 100 | 36.79 | 0 | 1471.43 | C+S GST 18% I/P RD | 264.86 | 1736.29 | 1736.29 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Regular Staircase | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Fire Staircase- - 1 No. | Kota Riser (L)- BCO | 196.191 | R.Ft | 45 | 100 | 220.71 | 0 | 8828.6 | C+S GST 18% I/P RD | 1589.14 | 10417.74 | 10417.74 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Podium Floor Regular Staircase - 1 No. | Kota Riser (L)- BCO | 196.191 | R.Ft | 45 | 100 | 220.71 | 0 | 8828.6 | C+S GST 18% I/P RD | 1589.14 | 10417.74 | 10417.74 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Regular Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P3 Floor Fire Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Fire Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Fire Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B Ground Floor Regular Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P1 Floor Regular Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Regular Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 905 | 96801 | 18 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1650 | B P2 Floor Fire Staircase | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1548 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2302 23rd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1801 18th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2002 20th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2202 22nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1704 17th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2001 20th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2204 22nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1802 18th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2304 23rd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1904 19th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2101 21st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2004 20th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2301 23rd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1901 19th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1902 19th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2102 21st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1701 17th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2104 21st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 2201 22nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1804 18th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 779 | 96794 | 18 Oct 2022 |  | RAMDEVRA INTERIORS | ANAND LALURAM SUTHAR | EV - 1415 | A 1702 17th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 210 | 18 Oct 2022
GANGA DHAM TOWERS | 1416 | 96793 | 18 Oct 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1589 | Laser Jali removing & barricading towards Main Road | Lumpsum work- DCW | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 15 | 18 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 2 Floor Regular Staircase | Kota Flooring (L)- BCO | 32.292 | Sq.Ft | 50 | 100 | 40.37 | 0 | 1614.6 | C+S GST 18% I/P RD | 290.62 | 1905.22 | 1905.22 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Ground Floor Fire Staircase | Kota Flooring (L)- BCO | 42.248 | Sq.Ft | 50 | 100 | 52.81 | 0 | 2112.4 | C+S GST 18% I/P RD | 380.24 | 2492.64 | 2492.64 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 1 Floor Fire Staircase | Kota Flooring (L)- BCO | 42.248 | Sq.Ft | 50 | 100 | 52.81 | 0 | 2112.4 | C+S GST 18% I/P RD | 380.24 | 2492.64 | 2492.64 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 2 Floor Fire Staircase | Kota Flooring (L)- BCO | 42.24 | Sq.Ft | 50 | 100 | 52.8 | 0 | 2112 | C+S GST 18% I/P RD | 380.16 | 2492.16 | 2492.16 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 3 Floor Fire Staircase | Kota Flooring (L)- BCO | 42.248 | Sq.Ft | 50 | 100 | 52.81 | 0 | 2112.4 | C+S GST 18% I/P RD | 380.24 | 2492.64 | 2492.64 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 1 Floor Regular Staircase | Kota Flooring (L)- BCO | 32.292 | Sq.Ft | 50 | 100 | 40.37 | 0 | 1614.6 | C+S GST 18% I/P RD | 290.62 | 1905.22 | 1905.22 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Podium Floor Regular Staircase | Kota Flooring (L)- BCO | 61.334 | Sq.Ft | 50 | 100 | 76.67 | 0 | 3066.7 | C+S GST 18% I/P RD | 552 | 3618.7 | 3618.7 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Podium Floor Fire Staircase | Kota Flooring (L)- BCO | 81.192 | Sq.Ft | 50 | 100 | 101.49 | 0 | 4059.6 | C+S GST 18% I/P RD | 730.72 | 4790.32 | 4790.32 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Parking 3 Floor Regular Staircase | Kota Flooring (L)- BCO | 32.292 | Sq.Ft | 50 | 100 | 40.37 | 0 | 1614.6 | C+S GST 18% I/P RD | 290.62 | 1905.22 | 1905.22 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 908 | 96789 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1651 | A Ground Floor Regular Staircase | Kota Flooring (L)- BCO | 32.292 | Sq.Ft | 50 | 100 | 40.37 | 0 | 1614.6 | C+S GST 18% I/P RD | 290.62 | 1905.22 | 1905.22 | Approved | 0 | 0 | 220 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P3 Floor Regular Staircase | Kota Flooring (L)- BCO | 110.241 | Sq.Ft | 50 | 100 | 137.8 | 0 | 5512.05 | C+S GST 18% I/P RD | 992.16 | 6504.21 | 6504.21 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B Ground Floor Regular Staircase | Kota Flooring (L)- BCO | 110.241 | Sq.Ft | 50 | 100 | 137.8 | 0 | 5512.05 | C+S GST 18% I/P RD | 992.16 | 6504.21 | 6504.21 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P2 Floor Fire Staircase | Kota Flooring (L)- BCO | 179.316 | Sq.Ft | 50 | 100 | 224.15 | 0 | 8965.8 | C+S GST 18% I/P RD | 1613.84 | 10579.64 | 10579.64 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P3 Floor Fire Staircase | Kota Flooring (L)- BCO | 179.316 | Sq.Ft | 50 | 100 | 224.15 | 0 | 8965.8 | C+S GST 18% I/P RD | 1613.84 | 10579.64 | 10579.64 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B Ground Floor Fire Staircase | Kota Flooring (L)- BCO | 179.316 | Sq.Ft | 50 | 100 | 224.15 | 0 | 8965.8 | C+S GST 18% I/P RD | 1613.84 | 10579.64 | 10579.64 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P1 Floor Regular Staircase | Kota Flooring (L)- BCO | 110.241 | Sq.Ft | 50 | 100 | 137.8 | 0 | 5512.05 | C+S GST 18% I/P RD | 992.16 | 6504.21 | 6504.21 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B Podium Floor Regular Staircase - 1 No. | Kota Flooring (L)- BCO | 211.77 | Sq.Ft | 50 | 100 | 264.71 | 0 | 10588.5 | C+S GST 18% I/P RD | 1905.94 | 12494.44 | 12494.44 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B Podium Floor Fire Staircase- - 1 No. | Kota Flooring (L)- BCO | 254.205 | Sq.Ft | 50 | 100 | 317.76 | 0 | 12710.25 | C+S GST 18% I/P RD | 2287.84 | 14998.09 | 14998.09 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P2 Floor Regular Staircase | Kota Flooring (L)- BCO | 110.241 | Sq.Ft | 50 | 100 | 137.8 | 0 | 5512.05 | C+S GST 18% I/P RD | 992.16 | 6504.21 | 6504.21 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 905 | 96787 | 17 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1649 | B P1 Floor Fire Staircase | Kota Flooring (L)- BCO | 179.316 | Sq.Ft | 50 | 100 | 224.15 | 0 | 8965.8 | C+S GST 18% I/P RD | 1613.84 | 10579.64 | 10579.64 | Approved | 0 | 0 | 812 | 17 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 21st to 28th Floor RCC Consultancy | RCC Consultancy | 18780 | Sq.Ft | 6 | 12.5 | 0 | 0 | 14085 | C+S GST 18% I/P RD | 2535.3 | 16620.3 | 16620.3 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 21st to 28th Floor RCC Consultancy | RCC Consultancy | 87193 | Sq.Ft | 6 | 12.5 | 0 | 0 | 65394.75 | C+S GST 18% I/P RD | 11771.06 | 77165.81 | 77165.81 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 21st to 28th Floor RCC Consultancy | RCC Consultancy | 87193 | Sq.Ft | 6 | 12.5 | 0 | 0 | 65394.75 | C+S GST 18% I/P RD | 11771.06 | 77165.81 | 77165.81 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 21st to 28th Floor RCC Consultancy | RCC Consultancy | 87193 | Sq.Ft | 6 | 12.5 | 0 | 0 | 65394.75 | C+S GST 18% I/P RD | 11771.06 | 77165.81 | 77165.81 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower B 1st to 20th Floor RCC Consultancy | RCC Consultancy | 145290 | Sq.Ft | 6 | 10 | 0 | 0 | 87174 | C+S GST 18% I/P RD | 15691.32 | 102865.32 | 102865.32 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 10 | 0 | 0 | 130788.6 | C+S GST 18% I/P RD | 23541.94 | 154330.54 | 154330.54 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217981 | Sq.Ft | 6 | 5 | 0 | 0 | 65394.3 | C+S GST 18% I/P RD | 11770.98 | 77165.28 | 77165.28 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 271 | 96784 | 15 Oct 2022 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1225 | Tower B 1st to 20th Floor RCC Consultancy | RCC Consultancy | 138023.3333 | Sq.Ft | 6 | 5 | 0 | 0 | 41407 | C+S GST 18% I/P RD | 7453.26 | 48860.26 | 48860.26 | Approved | 0 | 0 | 112358 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 701 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 605 Dado (L) | Dado Fixing | 285 | Sq.Ft | 13 | 100 | 92.63 | 0 | 3705 | CGST 0% URD I/P | 0 | 3705 | 3705 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 601 Dado (L) | Dado Fixing | 285 | Sq.Ft | 13 | 100 | 92.63 | 0 | 3705 | CGST 0% URD I/P | 0 | 3705 | 3705 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 1102 Dado (L) | Dado Fixing | 278.77 | Sq.Ft | 17.49 | 100 | 121.89 | 0 | 4875.69 | CGST 0% URD I/P | 0 | 4875.69 | 4875.69 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 1104 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 901 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 805 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 1103 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 801 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 792 | 96783 | 15 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1223 | D 705 Dado (L) | Dado Fixing | 285.0117 | Sq.Ft | 17.49 | 100 | 124.62 | 0 | 4984.85 | CGST 0% URD I/P | 0 | 4984.85 | 4984.85 | Approved | 0 | 0 | 474 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 4th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 5th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 9th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 6th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 4th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 7th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 6th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 8th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 5th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 8tht Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 9th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1333 | 96781 | 15 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1740 | D 7th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.85 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.5 | C+S GST 18% I/P RD | 637.66 | 4180.16 | 4180.16 | Approved | 0 | 0 | 425 | 15 Oct 2022
GANGA DHAM TOWERS | 1099 | 96780 | 15 Oct 2022 |  | B.D. DONGARE | AVCON TECHNICS PVT LTD | EV - 1419 | D tower 12th roof slab rebarring work | Rebarring work 10mm dia- BC | 28 | No. | 110 | 100 | 77 | 0 | 3080 | C+S GST 18% I/P RD | 554.4 | 3634.4 | 3634.4 | Approved | 0 | 0 | 165 | 15 Oct 2022
GANGA DHAM TOWERS | 1099 | 96780 | 15 Oct 2022 |  | B.D. DONGARE | AVCON TECHNICS PVT LTD | EV - 1419 | D tower 12th roof slab rebarring work | Rebarring work 12mm dia- BC | 47 | No. | 110 | 100 | 129.25 | 0 | 5170 | C+S GST 18% I/P RD | 930.6 | 6100.6 | 6100.6 | Approved | 0 | 0 | 165 | 15 Oct 2022
GANGA DHAM TOWERS | 1229 | 96779 | 15 Oct 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1323 | B Fire Fighting 11 to 31 floor OUSTFIRE | Sprinkler 15mm 68 dg Pendent (M+L) | 400 | No. | 319 | 100 | 3190 | 0 | 127600 | C+S GST 18% I/P RD | 22968 | 150568 | 150568 | Approved | 0 | 0 | 12852 | 15 Oct 2022
GANGA DHAM TOWERS | 1229 | 96779 | 15 Oct 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1323 | B Fire Fighting 11 to 31 floor OUSTFIRE | Butterfly Valve 80mm (M+L) | 6.4 | No. | 2345 | 100 | 375.2 | 0 | 15008 | C+S GST 18% I/P RD | 2701.44 | 17709.44 | 17709.44 | Approved | 0 | 0 | 12852 | 15 Oct 2022
GANGA DHAM TOWERS | 1229 | 96779 | 15 Oct 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1323 | B Fire Fighting 11 to 31 floor OUSTFIRE | Flexible hose pipe 25mm dia (1.2m length) (M+L) | 400 | No. | 1250 | 100 | 0 | 0 | 500000 | C+S GST 18% I/P RD | 90000 | 590000 | 590000 | Approved | 0 | 0 | 12852 | 15 Oct 2022
GANGA DHAM TOWERS | 1228 | 96778 | 15 Oct 2022 |  | KIRAN TUKARAM DHANAWADE | OM ENGINEERING & SCIENTIFIC EQUIPMENTS | EV - 1384 | R & D Purpose | R & D Purpose | 0.0478 | No. | 100000 | 100 | 0 | 0 | 4775 | C+S GST 18% I/P RD | 859.5 | 5634.5 | 5634.5 | Approved | 0 | 0 | 48 | 15 Oct 2022
GANGA DHAM TOWERS | 45 | 96772 | 15 Oct 2022 |  | NILIMA BHOSEKAR | NILIMA BHOSEKAR | EV - 1226 | Landscape Consultancy | Landscape Consultancy. | 0.7 | No. | 2500000 | 5 | 0 | 0 | 87500 | C+S GST 18% I/P RD | 15750 | 103250 | 103250 | Approved | 0 | 0 | 46250 | 15 Oct 2022
GANGA DHAM TOWERS | 45 | 96772 | 15 Oct 2022 |  | NILIMA BHOSEKAR | NILIMA BHOSEKAR | EV - 1226 | Landscape Consultancy | Landscape Consultancy. | 1 | No. | 2500000 | 15 | 0 | 0 | 375000 | C+S GST 18% I/P RD | 67500 | 442500 | 442500 | Approved | 0 | 0 | 46250 | 15 Oct 2022
GANGA DHAM TOWERS | 798 | 96762 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1177 | D 1202 Vitrified Flooring - 348.54 Sq.Ft | Vitrified Flooring work | 348.54 | Sq.Ft | 17.49 | 100 | 152.4 | 0 | 6095.96 | CGST 0% URD I/P | 0 | 6095.96 | 6095.96 | Approved | 0 | 0 | 61 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 1002 Vitrified Flooring (L) | Vitrified Flooring work | 348.54 | Sq.Ft | 17.49 | 100 | 152.4 | 0 | 6095.96 | CGST 0% URD I/P | 0 | 6095.96 | 6095.96 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 902 Vitrified Flooring (L) | Vitrified Flooring work | 348.54 | Sq.Ft | 17.49 | 100 | 152.4 | 0 | 6095.96 | CGST 0% URD I/P | 0 | 6095.96 | 6095.96 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 604 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 504 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 603 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 503 Vitrified Flooring (L) | Vitrified Flooring work | 344.66 | Sq.Ft | 13 | 100 | 112.01 | 0 | 4480.58 | CGST 0% URD I/P | 0 | 4480.58 | 4480.58 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 702 Vitrified Flooring (L) | Vitrified Flooring work | 348.54 | Sq.Ft | 17.49 | 100 | 152.4 | 0 | 6095.96 | CGST 0% URD I/P | 0 | 6095.96 | 6095.96 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 792 | 96761 | 14 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1176 | D 1102 Vitrified Flooring (L) | Vitrified Flooring work | 348.54 | Sq.Ft | 17.49 | 100 | 152.4 | 0 | 6095.96 | CGST 0% URD I/P | 0 | 6095.96 | 6095.96 | Approved | 0 | 0 | 423 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1103 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 801 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 601 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 703 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1101 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 803 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 903 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1001 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 701 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 901 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1003 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 603 Bore Packing | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 703 IPS Waterproofing | IPS W/P | 31.7273 | Sq.Ft | 11 | 100 | 34.9 | 0 | 349 | CGST 0% URD I/P | 0 | 349 | 349 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1101 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1103 IPS Waterproofing | IPS W/P | 32.1818 | Sq.Ft | 11 | 100 | 35.4 | 0 | 354 | CGST 0% URD I/P | 0 | 354 | 354 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 801 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 603 IPS Waterproofing | IPS W/P | 32.1818 | Sq.Ft | 11 | 100 | 35.4 | 0 | 354 | CGST 0% URD I/P | 0 | 354 | 354 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1001 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1003 IPS Waterproofing | IPS W/P | 32.1818 | Sq.Ft | 11 | 100 | 35.4 | 0 | 354 | CGST 0% URD I/P | 0 | 354 | 354 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 701 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 601 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 901 IPS Waterproofing | IPS W/P | 40 | Sq.Ft | 11 | 100 | 44 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 803 IPS Waterproofing | IPS W/P | 32.1818 | Sq.Ft | 11 | 100 | 35.4 | 0 | 354 | CGST 0% URD I/P | 0 | 354 | 354 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 903 IPS Waterproofing | IPS W/P | 32.1818 | Sq.Ft | 11 | 100 | 35.4 | 0 | 354 | CGST 0% URD I/P | 0 | 354 | 354 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D903 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D1103 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D1003 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D803 Chemical Grouting | Chemical Grouting.- BC | 100 | Sq.Ft | 1 | 100 | 10 | 0 | 100 | CGST 0% URD I/P | 0 | 100 | 100 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 803 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 903 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1103 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 601 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 701 Chemical Waterproofing | Chemical Waterproofing (L) | 40.5 | Sq.Ft | 4 | 100 | 16.2 | 0 | 162 | CGST 0% URD I/P | 0 | 162 | 162 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 703 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1001 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 801 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 901 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1003 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 603 Chemical Waterproofing | Chemical Waterproofing (L) | 32.25 | Sq.Ft | 4 | 100 | 12.9 | 0 | 129 | CGST 0% URD I/P | 0 | 129 | 129 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1101 Chemical Waterproofing | Chemical Waterproofing (L) | 40 | Sq.Ft | 4 | 100 | 16 | 0 | 160 | CGST 0% URD I/P | 0 | 160 | 160 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 701 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1103 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1001 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 1003 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 801 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 603 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 703 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 901 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 903 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 803 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 653 | 96760 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1920 | D 601 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 126 | 14 Oct 2022
GANGA DHAM TOWERS | 1312 | 96753 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1916 | D1203 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 2 | 100 | 69.4 | 0 | 694 | C+S GST 0% I/P RD | 0 | 694 | 694 | Approved | 0 | 0 | 7 | 14 Oct 2022
GANGA DHAM TOWERS | 498 | 96752 | 14 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1325 | B 102 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 181 | 14 Oct 2022
GANGA DHAM TOWERS | 498 | 96752 | 14 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1325 | B 102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 181 | 14 Oct 2022
GANGA DHAM TOWERS | 498 | 96752 | 14 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1325 | B 102 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 181 | 14 Oct 2022
GANGA DHAM TOWERS | 498 | 96752 | 14 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1325 | B 102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 468.45 | Sq.Ft | 19 | 100 | 890.06 | 0 | 8900.55 | CGST 0% URD I/P | 0 | 8900.55 | 8900.55 | Approved | 0 | 0 | 181 | 14 Oct 2022
GANGA DHAM TOWERS | 498 | 96752 | 14 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1325 | B 102 Chemical & IPS Waterproofing | IPS W/P | 468.45 | Sq.Ft | 11 | 100 | 515.3 | 0 | 5152.95 | CGST 0% URD I/P | 0 | 5152.95 | 5152.95 | Approved | 0 | 0 | 181 | 14 Oct 2022
GANGA DHAM TOWERS | 1119 | 96751 | 14 Oct 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1330 | C Bldg 3rd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 4525.305 | Sq.Ft | 180 | 100 | 20363.87 | 0 | 814554.9 | C+S GST 18% I/P RD | 146619.88 | 961174.78 | 961174.78 | Approved | 0 | 0 | 16291 | 14 Oct 2022
GANGA DHAM TOWERS | 1119 | 96751 | 14 Oct 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1330 | C Bldg 3rd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 4525.2975 | Sq.Ft | 180 | 100 | 20363.84 | 0 | 814553.55 | C+S GST 18% I/P RD | 146619.64 | 961173.19 | 961173.19 | Approved | 0 | 0 | 16291 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 701 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 703 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 1003 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 603 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 803 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 1001 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 901 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 1101 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 1103 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 801 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 903 Chemical Waterproofing | Chemical Waterproofing (M) | 32.18 | Sq.Ft | 15 | 100 | 0 | 0 | 482.7 | CGST 0% URD I/P | 0 | 482.7 | 482.7 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 654 | 96750 | 14 Oct 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1921 | D 601 Chemical Waterproofing | Chemical Waterproofing (M) | 41.21 | Sq.Ft | 15 | 100 | 0 | 0 | 618.15 | CGST 0% URD I/P | 0 | 618.15 | 618.15 | Approved | 0 | 0 | 0 | 14 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 102 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5256 | Mtrs | 78 | 100 | 0 | 0 | 3551 | C+S GST 18% I/P RD | 639.18 | 4190.18 | 4190.18 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 2001 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 102 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 2001 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 8 | Mtrs | 700 | 100 | 0 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 102 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.26 | Mtrs | 700 | 100 | 0 | 0 | 15582 | C+S GST 18% I/P RD | 2804.76 | 18386.76 | 18386.76 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 2001 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 45 | Mtrs | 700 | 100 | 0 | 0 | 31500 | C+S GST 18% I/P RD | 5670 | 37170 | 37170 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 102 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 1277 | 96737 | 13 Oct 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 1405 | Tower B 2001 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 35.6111 | Mtrs | 72 | 100 | 0 | 0 | 2564 | C+S GST 18% I/P RD | 461.52 | 3025.52 | 3025.52 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 810 | 96736 | 13 Oct 2022 |  | GREENSOL TECH | GREENSOL TECH | EV - 1152 | STP 35 KLD (EWS Tower) - 1 No. | Sewage Treatment Plant (M) | 1 | No. | 406000 | 64.29 | 0 | 0 | 261001 | C+S GST 18% I/P RD | 46980.18 | 307981.18 | 307981.18 | Approved | 0 | 0 | 0 | 13 Oct 2022
GANGA DHAM TOWERS | 371 | 96734 | 13 Oct 2022 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 1151 | EWS Bldg RCC Pergola Built-up Area (L) | RCC Superstructure (B-up area) | 156.25 | Sq.Ft | 320 | 100 | 1250 | 0 | 50000 | CGST 0% URD I/P | 0 | 50000 | 50000 | Approved | 0 | 0 | 1002 | 13 Oct 2022
GANGA DHAM TOWERS | 371 | 96734 | 13 Oct 2022 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 1151 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | RCC Superstructure (B-up area) | 250.3924 | Sq.Ft | 200.665 | 100 | 1256.12 | 0 | 50245 | CGST 0% URD I/P | 0 | 50245 | 50245 | Approved | 0 | 0 | 1002 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 2001 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 35.6 | Mtrs | 20 | 100 | 17.8 | 0 | 712 | CGST 0% URD I/P | 0 | 712 | 712 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 2001 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 8 | Mtrs | 120 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 102 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 102 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 102 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5556 | Mtrs | 18 | 100 | 20.5 | 0 | 820 | CGST 0% URD I/P | 0 | 820 | 820 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 2001 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 2001 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 45 | Mtrs | 120 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 1278 | 96730 | 13 Oct 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 1404 | Tower B 102 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.2583 | Mtrs | 120 | 100 | 66.77 | 0 | 2671 | CGST 0% URD I/P | 0 | 2671 | 2671 | Approved | 0 | 0 | 138 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.466 | Sq.Ft | 21 | 100 | 24.92 | 0 | 996.79 | C+S GST 18% I/P RD | 179.42 | 1176.21 | 1176.21 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 21 | 100 | 20.6 | 0 | 823.85 | C+S GST 18% I/P RD | 148.3 | 972.15 | 972.15 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 24 | 100 | 23.54 | 0 | 941.54 | C+S GST 18% I/P RD | 169.48 | 1111.02 | 1111.02 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 35.847 | Sq.Ft | 21 | 100 | 18.82 | 0 | 752.79 | C+S GST 18% I/P RD | 135.5 | 888.29 | 888.29 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.288 | Sq.Ft | 21 | 100 | 23.78 | 0 | 951.05 | C+S GST 18% I/P RD | 171.18 | 1122.23 | 1122.23 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 21 | 100 | 20.81 | 0 | 832.55 | C+S GST 18% I/P RD | 149.86 | 982.41 | 982.41 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 24 | 100 | 32.26 | 0 | 1290.38 | C+S GST 18% I/P RD | 232.26 | 1522.64 | 1522.64 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.61 | Sq.Ft | 21 | 100 | 10.82 | 0 | 432.81 | C+S GST 18% I/P RD | 77.9 | 510.71 | 510.71 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 24 | 100 | 26.74 | 0 | 1069.42 | C+S GST 18% I/P RD | 192.5 | 1261.92 | 1261.92 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Master Toilet dado | Dado BC | 73.84 | Sq.Ft | 24 | 100 | 44.3 | 0 | 1772.16 | C+S GST 18% I/P RD | 318.98 | 2091.14 | 2091.14 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Children Toilet dado | Dado BC | 63 | Sq.Ft | 24 | 100 | 37.8 | 0 | 1512 | C+S GST 18% I/P RD | 272.16 | 1784.16 | 1784.16 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Parents Toilet dado | Dado BC | 65.14 | Sq.Ft | 24 | 100 | 39.08 | 0 | 1563.36 | C+S GST 18% I/P RD | 281.4 | 1844.76 | 1844.76 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 24 | 100 | 20.98 | 0 | 839.38 | C+S GST 18% I/P RD | 151.08 | 990.46 | 990.46 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1801 Kitchen dado | Dado BC | 36.64 | Sq.Ft | 22 | 100 | 20.15 | 0 | 806.08 | C+S GST 18% I/P RD | 145.1 | 951.18 | 951.18 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 22 | 100 | 48.19 | 0 | 1927.73 | C+S GST 18% I/P RD | 347 | 2274.73 | 2274.73 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 22 | 100 | 63.09 | 0 | 2523.71 | C+S GST 18% I/P RD | 454.26 | 2977.97 | 2977.97 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Children Toilet dado | Dado BC | 120 | Sq.Ft | 22 | 100 | 66 | 0 | 2640 | C+S GST 18% I/P RD | 475.2 | 3115.2 | 3115.2 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 22 | 100 | 73.43 | 0 | 2937.13 | C+S GST 18% I/P RD | 528.68 | 3465.81 | 3465.81 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Staff Toilet dado | Dado BC | 110.214 | Sq.Ft | 21 | 100 | 57.86 | 0 | 2314.49 | C+S GST 18% I/P RD | 416.6 | 2731.09 | 2731.09 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Children Toilet | Dado BC | 38.448 | Sq.Ft | 28 | 100 | 26.91 | 0 | 1076.54 | C+S GST 18% I/P RD | 193.78 | 1270.32 | 1270.32 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Master Toilet dado | Dado BC | 111.159 | Sq.Ft | 28 | 100 | 77.81 | 0 | 3112.45 | C+S GST 18% I/P RD | 560.24 | 3672.69 | 3672.69 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 28 | 100 | 60.01 | 0 | 2400.3 | C+S GST 18% I/P RD | 432.06 | 2832.36 | 2832.36 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1901 Kitchen dado | Dado BC | 36.64 | Sq.Ft | 28 | 100 | 25.65 | 0 | 1025.92 | C+S GST 18% I/P RD | 184.66 | 1210.58 | 1210.58 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Master Toilet dado | Dado BC | 61.002 | Sq.Ft | 28 | 100 | 42.7 | 0 | 1708.06 | C+S GST 18% I/P RD | 307.46 | 2015.52 | 2015.52 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Children Toilet | Dado BC | 188.43 | Sq.Ft | 28 | 100 | 131.9 | 0 | 5276.04 | C+S GST 18% I/P RD | 949.68 | 6225.72 | 6225.72 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Parents Toilet dado | Dado BC | 73.575 | Sq.Ft | 28 | 100 | 51.5 | 0 | 2060.1 | C+S GST 18% I/P RD | 370.82 | 2430.92 | 2430.92 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 28 | 100 | 27.06 | 0 | 1082.34 | C+S GST 18% I/P RD | 194.82 | 1277.16 | 1277.16 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Parents Toilet dado | Dado BC | 137.268 | Sq.Ft | 28 | 100 | 96.09 | 0 | 3843.5 | C+S GST 18% I/P RD | 691.84 | 4535.34 | 4535.34 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 201 Kitchen dado | Dado BC | 36.64 | Sq.Ft | 14 | 100 | 12.82 | 0 | 512.96 | C+S GST 18% I/P RD | 92.34 | 605.3 | 605.3 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Master Toilet dado | L Groove - BCV | 28.989 | R.Ft | 20 | 100 | 14.49 | 0 | 579.78 | C+S GST 18% I/P RD | 104.36 | 684.14 | 684.14 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Children Toilet dado | L Groove - BCV | 33.804 | R.Ft | 20 | 100 | 16.9 | 0 | 676.08 | C+S GST 18% I/P RD | 121.7 | 797.78 | 797.78 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Parents Toilet dado | L Groove - BCV | 38.673 | R.Ft | 20 | 100 | 19.34 | 0 | 773.46 | C+S GST 18% I/P RD | 139.22 | 912.68 | 912.68 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Children Toilet | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1801 Kitchen dado | L Groove - BCV | 13.878 | R.Ft | 20 | 100 | 6.94 | 0 | 277.56 | C+S GST 18% I/P RD | 49.96 | 327.52 | 327.52 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Master Toilet dado | L Groove - BCV | 24.885 | R.Ft | 20 | 100 | 12.44 | 0 | 497.7 | C+S GST 18% I/P RD | 89.58 | 587.28 | 587.28 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Powder Toilet dado | L Groove - BCV | 31.437 | R.Ft | 20 | 100 | 15.72 | 0 | 628.74 | C+S GST 18% I/P RD | 113.18 | 741.92 | 741.92 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1901 Kitchen dado | L Groove - BCV | 13.878 | R.Ft | 20 | 100 | 6.94 | 0 | 277.56 | C+S GST 18% I/P RD | 49.96 | 327.52 | 327.52 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Parents Toilet dado | L Groove - BCV | 36.459 | R.Ft | 20 | 100 | 18.23 | 0 | 729.18 | C+S GST 18% I/P RD | 131.26 | 860.44 | 860.44 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 1601 Staff Toilet dado | L Groove - BCV | 14.634 | R.Ft | 20 | 100 | 7.32 | 0 | 292.68 | C+S GST 18% I/P RD | 52.68 | 345.36 | 345.36 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 201 Kitchen dado | L Groove - BCV | 13.878 | R.Ft | 20 | 100 | 6.94 | 0 | 277.56 | C+S GST 18% I/P RD | 49.96 | 327.52 | 327.52 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 537 | 96727 | 13 Oct 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1241 | A 2302 Powder Toilet dado | L Groove - BCV | 29.223 | R.Ft | 20 | 100 | 14.61 | 0 | 584.46 | C+S GST 18% I/P RD | 105.2 | 689.66 | 689.66 | Approved | 0 | 0 | 565 | 13 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Main Staircase Flooring - 1 Floor | Kota Tread (L) - DSP | 70.848 | R.Ft | 50 | 100 | 88.56 | 0 | 3542.4 | C+S GST 18% I/P RD | 637.64 | 4180.04 | 4180.04 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 75 | Sq.Ft | 50 | 100 | 93.75 | 0 | 3750 | C+S GST 18% I/P RD | 675 | 4425 | 4425 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8tht Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8tht Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Main Staircase Flooring - 1 Floor | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Fire Staircase Flooring | Kota Champher | 62.976 | R.Ft | 7.5 | 100 | 11.81 | 0 | 472.32 | C+S GST 18% I/P RD | 85.02 | 557.34 | 557.34 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Main Staircase Flooring - 1 Floor | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 5th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8tht Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 70.848 | R.Ft | 15 | 100 | 26.57 | 0 | 1062.72 | C+S GST 18% I/P RD | 191.28 | 1254 | 1254 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 7th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 1st Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 141 | Sq.Ft | 50 | 100 | 176.25 | 0 | 7050 | C+S GST 18% I/P RD | 1269 | 8319 | 8319 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 9th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 11th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 8th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 2nd Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 3rd Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 12th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 4th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 10th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 1333 | 96707 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles |  | D 6th Floor Main Staircase Flooring - 1 Floor | Kota Flooring (L)- BCO | 49.41 | Sq.Ft | 50 | 100 | 61.76 | 0 | 2470.5 | C+S GST 18% I/P RD | 444.7 | 2915.2 | 2915.2 |  | 0 | 0 | 1436 | 12 Oct 2022
GANGA DHAM TOWERS | 149 | 96706 | 12 Oct 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1181 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 283 | No. | 4 | 100 | 0 | 0 | 1132 | CGST 0% URD I/P | 0 | 1132 | 1132 | Approved | 0 | 0 | 0 | 12 Oct 2022
GANGA DHAM TOWERS | 149 | 96706 | 12 Oct 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1181 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 4000 | No. | 4 | 100 | 0 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 0 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1601 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2301 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1501 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2404 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1002 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1701 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 401 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1901 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1602 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1201 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2401 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2302 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2201 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2104 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 201 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1301 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 702 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1001 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 602 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 701 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 601 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 102 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 202 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2001 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 502 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1502 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1902 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2304 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2204 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1702 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2101 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 901 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1402 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 2402 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 22.15 | R.Ft | 45 | 100 | 24.92 | 0 | 996.75 | C+S GST 18% I/P RD | 179.42 | 1176.17 | 1176.17 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 902 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 1425 | 96705 | 12 Oct 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1240 | A 1302 Marble Window Sill (Cant. Portion) | Italian Marble Double Patti -BC | 17.23 | R.Ft | 45 | 100 | 19.38 | 0 | 775.35 | C+S GST 18% I/P RD | 139.56 | 914.91 | 914.91 | Approved | 0 | 0 | 317 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 3rd Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 1st Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 3rd Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 1st Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Fire Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 3rd Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 16th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Staircase Flooring | Kota Champher & Edge Polish | 74.3175 | R.Ft | 15 | 100 | 27.87 | 0 | 1114.76 | C+S GST 18% I/P RD | 200.66 | 1315.42 | 1315.42 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 1st Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 16th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Champher | 22.2945 | R.Ft | 7.5 | 100 | 4.18 | 0 | 167.21 | C+S GST 18% I/P RD | 30.1 | 197.31 | 197.31 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 2nd Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 12th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 24th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 3rd Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 14th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 13th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 10th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | Kota Champher | 111.4725 | R.Ft | 7.5 | 100 | 20.9 | 0 | 836.04 | C+S GST 18% I/P RD | 150.48 | 986.52 | 986.52 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 22nd Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 9th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 1st Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 11th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 5th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 6th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 8th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 15th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 7th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 20th Floor Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 23rd Floor Fire Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 4th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 21st Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 18th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 19th Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 905 | 96704 | 12 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1699 | A 1st Floor Staircase Flooring | Kota Skirting (L)- BCO | 18.415 | R.Ft | 30 | 100 | 13.81 | 0 | 552.45 | C+S GST 18% I/P RD | 99.44 | 651.89 | 651.89 | Approved | 0 | 0 | 1102 | 12 Oct 2022
GANGA DHAM TOWERS | 983 | 96687 | 11 Oct 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1107 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 169 | No. | 210 | 100 | 887.25 | 0 | 35490 | C+S GST 18% I/P RD | 6388.2 | 41878.2 | 41878.2 | Approved | 0 | 0 | 355 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 16th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Riser (L)- BCO | 22.2945 | R.Ft | 45 | 100 | 25.08 | 0 | 1003.25 | C+S GST 18% I/P RD | 180.58 | 1183.83 | 1183.83 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 16th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 18th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 22.2945 | R.Ft | 45 | 100 | 25.08 | 0 | 1003.25 | C+S GST 18% I/P RD | 180.58 | 1183.83 | 1183.83 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 18th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 16th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 18th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Tread (L) - DSP | 22.2945 | R.Ft | 50 | 100 | 27.87 | 0 | 1114.73 | C+S GST 18% I/P RD | 200.66 | 1315.39 | 1315.39 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 16th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 18th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 190.116 | Sq.Ft | 50 | 100 | 237.65 | 0 | 9505.8 | C+S GST 18% I/P RD | 1711.04 | 11216.84 | 11216.84 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 16th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Staircase Flooring | Kota Flooring (L)- BCO | 145.314 | Sq.Ft | 50 | 100 | 181.64 | 0 | 7265.7 | C+S GST 18% I/P RD | 1307.82 | 8573.52 | 8573.52 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Flooring (L)- BCO | 19.9725 | Sq.Ft | 50 | 100 | 24.97 | 0 | 998.63 | C+S GST 18% I/P RD | 179.76 | 1178.39 | 1178.39 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 190.116 | Sq.Ft | 50 | 100 | 237.65 | 0 | 9505.8 | C+S GST 18% I/P RD | 1711.04 | 11216.84 | 11216.84 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 22nd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 190.116 | Sq.Ft | 50 | 100 | 237.65 | 0 | 9505.8 | C+S GST 18% I/P RD | 1711.04 | 11216.84 | 11216.84 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 23rd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 190.116 | Sq.Ft | 50 | 100 | 237.65 | 0 | 9505.8 | C+S GST 18% I/P RD | 1711.04 | 11216.84 | 11216.84 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 190.116 | Sq.Ft | 50 | 100 | 237.65 | 0 | 9505.8 | C+S GST 18% I/P RD | 1711.04 | 11216.84 | 11216.84 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 1st Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 5th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 2nd Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 15th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 12th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 19th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 7th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 18th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Staircase Flooring | Kota Flooring (L)- BCO | 24.219 | Sq.Ft | 50 | 100 | 30.27 | 0 | 1210.95 | C+S GST 18% I/P RD | 217.98 | 1428.93 | 1428.93 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 14th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 25th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 31.686 | Sq.Ft | 50 | 100 | 39.61 | 0 | 1584.3 | C+S GST 18% I/P RD | 285.18 | 1869.48 | 1869.48 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 20th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 6th Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 24th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 4th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 13th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 8th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 9th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 11th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 3rd Floor Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 21st Floor Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 905 | 96685 | 11 Oct 2022 |  | R.M.Marbles | R.M.Marbles | EV - 1698 | A 10th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 1940 | 11 Oct 2022
GANGA DHAM TOWERS | 972 | 96666 | 11 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1327 | B 1st Floor Brick bat Waterproofing - 1 Sq.Ft | Brickbat W/P 8" Sunk | 686.0667 | Sq.Ft | 15 | 100 | 0 | 0 | 10291 | CGST 0% URD I/P | 0 | 10291 | 10291 | Approved | 0 | 0 | 103 | 11 Oct 2022
GANGA DHAM TOWERS | 272 | 96665 | 11 Oct 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1105 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 419.5489 | Sq.Ft | 133 | 100 | 0 | 0 | 55800 | C+S GST 18% I/P RD | 10044 | 65844 | 65844 | Approved | 0 | 4000 | 558 | 11 Oct 2022
GANGA DHAM TOWERS | 551 | 96664 | 11 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S.K. ENTERPRISES |  | A 1003 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 8.3 | R.Ft | 50 | 100 | 10.38 | 0 | 415 | C+S GST 18% I/P RD | 74.7 | 489.7 | 489.7 |  | 0 | 0 | 8 | 11 Oct 2022
GANGA DHAM TOWERS | 551 | 96664 | 11 Oct 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | S.K. ENTERPRISES |  | A 903 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 6.84 | R.Ft | 50 | 100 | 8.55 | 0 | 342 | C+S GST 18% I/P RD | 61.56 | 403.56 | 403.56 |  | 0 | 0 | 8 | 11 Oct 2022
GANGA DHAM TOWERS | 522 | 96663 | 11 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1324 | B Bldg 2001 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 2.5 | No. | 1650 | 100 | 103.13 | 0 | 4125 | CGST 0% URD I/P | 0 | 4125 | 4125 | Approved | 0 | 0 | 116 | 11 Oct 2022
GANGA DHAM TOWERS | 522 | 96663 | 11 Oct 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1324 | B Bldg 2102 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 5 | No. | 1500 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 116 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 601 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 703 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 504 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 701 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 30 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1003 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1603 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1002 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1702 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1101 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1403 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1403 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1702 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1004 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1502 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1301 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1302 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 101 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 503 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 602 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1003 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 703 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 903 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1301 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1603 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1702 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1602 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 102 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 404 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 601 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 604 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1201 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1701 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2202 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 202 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 402 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 504 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 704 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 902 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1502 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1402 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1602 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2002 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2202 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 404 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 704 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1701 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 203 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 503 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 602 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 20 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1402 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1403 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1003 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1201 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1204 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1703 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1503 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2002 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 201 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 403 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 903 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1204 | Gyser Point BC | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1004 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1502 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 504 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 704 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1402 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1501 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 102 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 503 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1002 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1101 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1703 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 201 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1302 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1302 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1501 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1703 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 803 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 902 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 803 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1204 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 204 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 204 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 402 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 5 | 1.17 | 0 | 46.88 | C+S GST 18% I/P RD | 8.44 | 55.32 | 55.32 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1301 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 703 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 701 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 902 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 15 | 3.52 | 0 | 140.63 | C+S GST 18% I/P RD | 25.32 | 165.95 | 165.95 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1503 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1503 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1602 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 404 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 604 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1101 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1603 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 202 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 202 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 201 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 203 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 604 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 903 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1002 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 102 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 101 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 203 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 402 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 403 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1701 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 204 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 601 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 5 | 1.17 | 0 | 46.88 | C+S GST 18% I/P RD | 8.44 | 55.32 | 55.32 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1501 | Gyser Point BC | 1.248 | No. | 250 | 25 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2002 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 2202 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1004 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 101 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 403 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 602 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 701 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 803 | Gyser Point BC | 5 | No. | 250 | 20 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 359 | 96662 | 11 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1601 | A 1201 | Gyser Point BC | 5 | No. | 250 | 15 | 4.69 | 0 | 187.5 | C+S GST 18% I/P RD | 33.76 | 221.26 | 221.26 | Approved | 0 | 0 | 216 | 11 Oct 2022
GANGA DHAM TOWERS | 1296 | 96651 | 10 Oct 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1168 | Miscellaneous expenses | Marketing Operating Expenses | 7.4603 | Month | 25000 | 8.33 | 0 | 0 | 15536 | CGST 0% URD I/P | 0 | 15536 | 15536 | Approved | 0 | 0 | 155 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 16th Floor 1602- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 20th Floor 2002- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 24th Floor 2401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 15th Floor 1502- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 18th Floor 1801 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 8th Floor 801 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 13th Floor 1301 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 4th Floor 401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 8th Floor 801 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 17th Floor 1702- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 17th Floor 1702- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 5th Floor 501 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 21st Floor 2102- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 1st Floor 102- | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 12th Floor 1202- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 12th Floor 1202- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 14th Floor 1401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 7th Floor 701 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 11st Floor 1101 - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 14th Floor 1401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 21st Floor 2101 - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 7th Floor 702- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 17th Floor 1701 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 20th Floor 2001 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 3rd Floor 301 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 13th Floor 1301 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 13th Floor 1302- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 17th Floor 1701 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 22nd Floor 2202- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 3rd Floor 301 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 22nd Floor 2202- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 3rd Floor 302- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 5th Floor 501 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 10th Floor 1002- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 6th Floor 602- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 15th Floor 1502- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 18th Floor 1801 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 24th Floor 2401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 20th Floor 2001 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 1st Floor 102- | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 4th Floor 402- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 11st Floor 1102- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 13th Floor 1302- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 1st Floor 101 | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 4th Floor 402- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 9th Floor 902- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 11st Floor 1102- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 16th Floor 1602- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 20th Floor 2002- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 11st Floor 1101 - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 19th Floor 1902- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 19th Floor 1902- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 21st Floor 2101 - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 9th Floor 901 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 21st Floor 2102- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 1st Floor 101 | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 4th Floor 401 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 9th Floor 902- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 2nd Floor 201 - | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 2nd Floor 201 - | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 3rd Floor 302- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 6th Floor 602- - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 7th Floor 702- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 9th Floor 901 - 1 No. | Gyser Point BC | 7 | No. | 250 | 20 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 10th Floor 1002- - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 16th Floor 1601 - 1 No. | Gyser Point BC | 6 | No. | 250 | 15 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 16th Floor 1601 - 1 No. | Gyser Point BC | 6 | No. | 250 | 20 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 452 | 96637 | 10 Oct 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1206 | B 7th Floor 701 - 1 No. | Gyser Point BC | 7 | No. | 250 | 15 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 382 | 10 Oct 2022
GANGA DHAM TOWERS | 1052 | 96636 | 10 Oct 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1143 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 0% I/P RD | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 10 Oct 2022
GANGA DHAM TOWERS | 1383 | 96632 | 10 Oct 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 1146 | Professional Consultancy (Finalcial) | Professional Fees | 0.9328 | Month | 116666.666 | 100 | 0 | 0 | 108826 | CGST 0% URD I/P | 0 | 108826 | 108826 | Approved | 0 | 0 | 10883 | 10 Oct 2022
GANGA DHAM TOWERS | 178 | 96625 | 08 Oct 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1356 | Sales office Garden Maintenance | Garden work. | 52.4986 | Day | 420.83 | 100 | 0 | 0 | 22093 | C+S GST 18% I/P RD | 3976.74 | 26069.74 | 26069.74 | Approved | 0 | 0 | 221 | 08 Oct 2022
GANGA DHAM TOWERS | 1337 | 96622 | 08 Oct 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1260 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 80 | 08 Oct 2022
GANGA DHAM TOWERS | 1337 | 96621 | 08 Oct 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1262 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 80 | 08 Oct 2022
GANGA DHAM TOWERS | 1337 | 96620 | 08 Oct 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 1261 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 80 | 08 Oct 2022
GANGA DHAM TOWERS | 1338 | 96619 | 08 Oct 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1259 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 08 Oct 2022
GANGA DHAM TOWERS | 1338 | 96618 | 08 Oct 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1258 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 08 Oct 2022
GANGA DHAM TOWERS | 1338 | 96617 | 08 Oct 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 1257 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 08 Oct 2022
GANGA DHAM TOWERS | 493 | 96612 | 08 Oct 2022 |  | KADAVATH VENKAT ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 1239 | D Bldg East Side External Plaster | External Plaster- BC | 691.7143 | Sq.Ft | 28 | 100 | 484.2 | 0 | 19368 | CGST 0% URD I/P | 0 | 19368 | 19368 | Approved | 0 | 0 | 194 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 102 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 103 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 104 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 802 (1bhk) Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 1005 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 1105 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 1205 D Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 1001 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 105 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 101 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1386 | 96611 | 08 Oct 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1215 | D 1201 D Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 501 | 08 Oct 2022
GANGA DHAM TOWERS | 1228 | 96607 | 07 Oct 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 1210 | R & D Purpose | R & D Purpose | 0.0675 | No. | 100000 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 135 | 07 Oct 2022
GANGA DHAM TOWERS | 1228 | 96606 | 07 Oct 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 1209 | R & D Purpose | R & D Purpose | 0.0941 | No. | 100000 | 100 | 0 | 0 | 9414 | C+S GST 18% I/P RD | 1694.52 | 11108.52 | 11108.52 | Approved | 0 | 0 | 188 | 07 Oct 2022
GANGA DHAM TOWERS | 798 | 96604 | 07 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1192 | D 1203 Dado | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | C+S GST 18% I/P RD | 917.36 | 6013.77 | 6013.77 | Approved | 0 | 0 | 151 | 07 Oct 2022
GANGA DHAM TOWERS | 798 | 96604 | 07 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1192 | D 1202 Dado - 278.77 Sq.Ft | Dado Fixing | 278.77 | Sq.Ft | 17.49 | 100 | 121.89 | 0 | 4875.69 | C+S GST 18% I/P RD | 877.62 | 5753.31 | 5753.31 | Approved | 0 | 0 | 151 | 07 Oct 2022
GANGA DHAM TOWERS | 798 | 96604 | 07 Oct 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1192 | D 1204 Dado | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | C+S GST 18% I/P RD | 917.36 | 6013.77 | 6013.77 | Approved | 0 | 0 | 151 | 07 Oct 2022
GANGA DHAM TOWERS | 272 | 96595 | 07 Oct 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1250 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 172.5564 | Sq.Ft | 133 | 100 | 0 | 0 | 22950 | C+S GST 18% I/P RD | 4131 | 27081 | 27081 | Approved | 0 | 0 | 230 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 101 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 2202 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 102 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1004 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1402 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 604 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1301 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 404 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1502 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1603 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 502 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1001 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 803 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 2002 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 403 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1602 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1701 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1501 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 201 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 503 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 602 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1403 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 703 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1002 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 204 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1302 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 203 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 903 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1101 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 601 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1201 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 402 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 504 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 704 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 902 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1503 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 202 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 701 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1702 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1003 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 359 | 96593 | 07 Oct 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 1600 | A 1703 | Gyser Point BC | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 96 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 20th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 19th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 9th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 10th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 8th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 22nd Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 18th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 7th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 16th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 17th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 13th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 6th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 2nd Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 4th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 13th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 15th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 12th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 15th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 21st Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 3rd Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 14th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 21st Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 7th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 4th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 22nd Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 1st Floor Texture Painting | Texture Paint (M) | 95.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 691.29 | C+S GST 18% I/P RD | 124.44 | 815.73 | 815.73 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 2nd Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 9th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 5th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 8th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 10th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 3rd Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 17th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 18th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 23rd Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 14th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 11th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 24th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 1st Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 5th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 23rd Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 12th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 19th Floor Texture Painting | Texture Paint (M) | 76.13 | Sq.Ft | 7.25 | 100 | 0 | 0 | 551.94 | C+S GST 18% I/P RD | 99.34 | 651.28 | 651.28 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 6th Floor Texture Painting | Texture Paint (M) | 77.77 | Sq.Ft | 7.25 | 100 | 0 | 0 | 563.83 | C+S GST 18% I/P RD | 101.48 | 665.31 | 665.31 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Westside 11th Floor Texture Painting | Texture Paint (M) | 95.68 | Sq.Ft | 7.25 | 100 | 0 | 0 | 693.68 | C+S GST 18% I/P RD | 124.86 | 818.54 | 818.54 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1200 | 96590 | 07 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD |  | B Eastside 16th Floor Texture Painting | Texture Paint (M) | 98.35 | Sq.Ft | 7.25 | 100 | 0 | 0 | 713.04 | C+S GST 18% I/P RD | 128.34 | 841.38 | 841.38 |  | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 802 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1001 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 50 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1501 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 902 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1002 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 1302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 2302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 1294 | 96588 | 07 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1778 | B 702 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) (Qty Diff) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | Excavation work.- UTI | 46.875 | Mtrs | 160 | 100 | 0 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU 22 KV 3 in / 4out (L) | 1 | No. | 8000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | Transformer fixing 22KV/630kva (L) | 1.1905 | No. | 6300 | 100 | 187.5 | 0 | 7500.15 | CGST 0% URD I/P | 0 | 7500.15 | 7500.15 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | End Termination 300sqmm- UTI | 9 | No. | 1700 | 100 | 382.5 | 0 | 15300 | CGST 0% URD I/P | 0 | 15300 | 15300 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | Straight Thr. Joint 300sqmm 3C-UTI | 5 | No. | 3000 | 100 | 375 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 300 sqmm - No. | 4 | No. | 2500 | 100 | 250 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU 22kv 2in/4out (L) | 1 | No. | 8000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | Gland Plate Hole Making (L) | 9 | No. | 100 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 50x5 (M+L) -UTI | 99 | Mtrs | 235 | 100 | 581.63 | 0 | 23265 | CGST 0% URD I/P | 0 | 23265 | 23265 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 50x5 (M+L) -UTI | 92 | Mtrs | 235 | 100 | 540.5 | 0 | 21620 | CGST 0% URD I/P | 0 | 21620 | 21620 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 50x5 (M+L) -UTI | 15.32 | Mtrs | 235 | 100 | 90.01 | 0 | 3600.2 | CGST 0% URD I/P | 0 | 3600.2 | 3600.2 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU 22 kV 3 in/ 2 out (L) | 0.8 | No. | 5000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 957 | 96586 | 07 Oct 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 1224 | Electricity Infrastructure-Trnsformer,HT,LT Work | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 126 | Mtrs | 90 | 100 | 283.5 | 0 | 11340 | CGST 0% URD I/P | 0 | 11340 | 11340 | Approved | 0 | 0 | 1360 | 07 Oct 2022
GANGA DHAM TOWERS | 1180 | 96585 | 07 Oct 2022 |  | M.S. CONSTRUCTION | GODAVARI PAINT PVT LTD | EV - 1202 | B Terrcae Scaffolding Work (L | Scaffolding work | 4581.8182 | Sq.Ft | 5.5 | 100 | 630 | 0 | 25200 | C+S GST 18% I/P RD | 4536 | 29736 | 29736 | Approved | 0 | 0 | 504 | 07 Oct 2022
GANGA DHAM TOWERS | 701 | 96577 | 06 Oct 2022 |  | VEER BHADRA ENTERPRISES | BABLI ANIL MAHTO | EV - 1183 | D Lift Shaft Painting | Cement Paint (L)- BC | 1280 | Sq.Ft | 2 | 100 | 64 | 0 | 2560 | CGST 0% URD I/P | 0 | 2560 | 2560 | Approved | 0 | 0 | 26 | 06 Oct 2022
GANGA DHAM TOWERS | 1243 | 96571 | 06 Oct 2022 |  | FAST ELECTRODE | FAST ELECTRODE | EV - 1074 | Development Area Borewell Earthing Work | Earthing Work - BCo | 42.942 | No. | 6800 | 100 | 0 | 0 | 292005.6 | C+S GST 18% I/P RD | 52561 | 344566.6 | 344566.6 | Approved | 0 | 4000 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 940 | 96569 | 06 Oct 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1160 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 06 Oct 2022
GANGA DHAM TOWERS | 1360 | 96568 | 06 Oct 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1161 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 06 Oct 2022
GANGA DHAM TOWERS | 493 | 96567 | 06 Oct 2022 |  | KADAVATH VENKAT ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 1236 | D Bldg South Side External Plaster | External Plaster- BC | 470 | Sq.Ft | 35 | 100 | 411.25 | 0 | 16450 | CGST 0% URD I/P | 0 | 16450 | 16450 | Approved | 0 | 0 | 292 | 06 Oct 2022
GANGA DHAM TOWERS | 493 | 96567 | 06 Oct 2022 |  | KADAVATH VENKAT ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 1236 | D Bldg South Side External Plaster | External Plaster- BC | 363.7429 | Sq.Ft | 35 | 100 | 318.28 | 0 | 12731 | CGST 0% URD I/P | 0 | 12731 | 12731 | Approved | 0 | 0 | 292 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1502 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 202 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 902 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2201 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2402 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 302 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 901 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2202 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2301 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 601 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 701 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1401 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1402 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 801 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2102 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1801 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2401 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 802 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1002 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1802 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1301 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1702 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2101 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1101 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1902 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 402 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1302 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2002 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1201 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1602 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 502 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1501 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1102 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2001 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 702 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-2302 Terrace False Ceiling | Sherawood False Ceiling (M) | 115.661 | Sq.Ft | 140 | 100 | 0 | 0 | 16192.54 | C+S GST 18% I/P RD | 2914.66 | 19107.2 | 19107.2 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1202 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1601 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1701 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1001 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B-1901 Terrace False Ceiling | Sherawood False Ceiling (M) | 134.7214 | Sq.Ft | 140 | 100 | 0 | 0 | 18861 | C+S GST 18% I/P RD | 3394.98 | 22255.98 | 22255.98 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 814 | 96566 | 06 Oct 2022 |  | S R INFRA PROJECTS (Material) | A K INTERIOR CONTRACTOR | EV - 1179 | B 602 Terrace False Ceiling | Sherawood False Ceiling (M) | 145.649 | Sq.Ft | 140 | 100 | 0 | 0 | 20390.86 | C+S GST 18% I/P RD | 3670.36 | 24061.22 | 24061.22 | Approved | 0 | 0 | 0 | 06 Oct 2022
GANGA DHAM TOWERS | 1432 | 96562 | 05 Oct 2022 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 1055 | RMC Pump rental Charges | Rent Charges | 1 | No. | 18000 | 100 | 0 | 0 | 18000 | CGST 0% URD I/P | 0 | 18000 | 18000 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 209 | 96561 | 05 Oct 2022 |  | UNIQUE ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1085 | A Bldg 4th RCC Slab (P3 Floor) Built-up Area (L) | Hacking Work | 4090 | Sq.Ft | 5 | 100 | 511.25 | 0 | 20450 | CGST 0% URD I/P | 0 | 20450 | 20450 | Approved | 0 | 0 | 205 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Tread (L) - DSP | 89.181 | R.Ft | 50 | 100 | 111.48 | 0 | 4459.05 | C+S GST 18% I/P RD | 802.62 | 5261.67 | 5261.67 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Champher & Edge Polish | 89.181 | R.Ft | 15 | 100 | 33.44 | 0 | 1337.72 | C+S GST 18% I/P RD | 240.78 | 1578.5 | 1578.5 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 91.836 | Sq.Ft | 50 | 100 | 114.8 | 0 | 4591.8 | C+S GST 18% I/P RD | 826.52 | 5418.32 | 5418.32 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 14.8635 | R.Ft | 50 | 100 | 18.58 | 0 | 743.18 | C+S GST 18% I/P RD | 133.78 | 876.96 | 876.96 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 4th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Champher | 89.181 | R.Ft | 7.5 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Skirting (L)- BCO | 55.215 | R.Ft | 30 | 100 | 41.41 | 0 | 1656.45 | C+S GST 18% I/P RD | 298.16 | 1954.61 | 1954.61 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.9875 | R.Ft | 30 | 100 | 48.74 | 0 | 1949.63 | C+S GST 18% I/P RD | 350.94 | 2300.57 | 2300.57 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Champher | 14.8635 | R.Ft | 7.5 | 100 | 2.79 | 0 | 111.48 | C+S GST 18% I/P RD | 20.06 | 131.54 | 131.54 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 20th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 1st Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 10th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 2nd floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 14.8635 | R.Ft | 45 | 100 | 16.72 | 0 | 668.86 | C+S GST 18% I/P RD | 120.4 | 789.26 | 789.26 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 89.181 | R.Ft | 45 | 100 | 100.33 | 0 | 4013.15 | C+S GST 18% I/P RD | 722.36 | 4735.51 | 4735.51 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 14th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 6th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 23rd floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 91.836 | Sq.Ft | 50 | 100 | 114.8 | 0 | 4591.8 | C+S GST 18% I/P RD | 826.52 | 5418.32 | 5418.32 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 25th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 18th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 19th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 15th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 22nd floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 5th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 7th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 8th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 9th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 13th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 24th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 3rd floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 21st floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 11th floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 141.1125 | Sq.Ft | 50 | 100 | 176.39 | 0 | 7055.63 | C+S GST 18% I/P RD | 1270.02 | 8325.65 | 8325.65 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 12th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 907 | 96555 | 05 Oct 2022 |  | RAJESH MEHTA | R.M.Marbles | EV - 1741 | B 16th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 15.306 | Sq.Ft | 50 | 100 | 19.13 | 0 | 765.3 | C+S GST 18% I/P RD | 137.76 | 903.06 | 903.06 | Approved | 0 | 0 | 6006 | 05 Oct 2022
GANGA DHAM TOWERS | 372 | 96553 | 05 Oct 2022 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 1249 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 89.5 | Sq.Ft | 160 | 100 | 0 | 0 | 14320 | C+S GST 18% I/P RD | 2577.6 | 16897.6 | 16897.6 | Approved | 0 | 0 | 351 | 05 Oct 2022
GANGA DHAM TOWERS | 372 | 96553 | 05 Oct 2022 |  | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 1249 | B Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 134 | Sq.Ft | 155 | 100 | 0 | 0 | 20770 | C+S GST 18% I/P RD | 3738.6 | 24508.6 | 24508.6 | Approved | 0 | 0 | 351 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4923 | Kgs | 65 | 100 | 0 | 0 | 227 | C+S GST 18% I/P RD | 40.86 | 267.86 | 267.86 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 3.4914 | Kgs | 65 | 100 | 0 | 0 | 226.94 | C+S GST 18% I/P RD | 40.84 | 267.78 | 267.78 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 10.2 | Kgs | 65 | 100 | 0 | 0 | 663 | C+S GST 18% I/P RD | 119.34 | 782.34 | 782.34 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1294 | 96550 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1777 | B 1002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) (Qty Diff.) | 38.09 | Kgs | 65 | 100 | 0 | 0 | 2475.85 | C+S GST 18% I/P RD | 445.66 | 2921.51 | 2921.51 | Approved | 0 | 0 | 0 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1293 | 96548 | 05 Oct 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1779 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 3.4615 | Kgs | 26 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 21 | 05 Oct 2022
GANGA DHAM TOWERS | 1263 | 96530 | 04 Oct 2022 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 1039 | MEDIA Flex printing | Transportaion - No. | 1 | No. | 750 | 100 | 0 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 1125 | 04 Oct 2022
GANGA DHAM TOWERS | 1263 | 96530 | 04 Oct 2022 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 1039 | MEDIA Flex printing | Star Flex | 2920 | Sq.Ft | 19 | 100 | 0 | 0 | 55480 | C+S GST 18% I/P RD | 9986.4 | 65466.4 | 65466.4 | Approved | 0 | 0 | 1125 | 04 Oct 2022
GANGA DHAM TOWERS | 808 | 96526 | 04 Oct 2022 |  | GREENSOL TECH | GREENSOL TECH | EV - 1129 | STP 200 KLD(A,B,C Tower) - 1 No. | Sewage Treatment Plant (M) | 1 | No. | 1750000 | 64.29 | 0 | 0 | 1125005 | C+S GST 18% I/P RD | 202500.9 | 1327505.9 | 1327505.9 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Ceiling Painting | 2nd Coat Premium Emulsion Paint (L) | 747.38 | Sq.Ft | 1.25 | 100 | 23.36 | 0 | 934.23 | C+S GST 18% I/P RD | 168.16 | 1102.39 | 1102.39 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Wall Painting | Oil base Primer-BC | 798.6 | Sq.Ft | 1 | 100 | 19.97 | 0 | 798.6 | C+S GST 18% I/P RD | 143.74 | 942.34 | 942.34 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Ceiling Painting | 1st Coat Premium Emulsion Paint (L) | 747.38 | Sq.Ft | 1.25 | 100 | 23.36 | 0 | 934.23 | C+S GST 18% I/P RD | 168.16 | 1102.39 | 1102.39 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Wall Painting | Scrapping with 2nd Coat Putty | 798.6 | Sq.Ft | 1 | 100 | 19.97 | 0 | 798.6 | C+S GST 18% I/P RD | 143.74 | 942.34 | 942.34 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Ceiling Painting | Scrapping with 2nd Coat Putty | 747.38 | Sq.Ft | 1 | 100 | 18.68 | 0 | 747.38 | C+S GST 18% I/P RD | 134.52 | 881.9 | 881.9 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Ceiling Painting | Scrapping with 1st Coat Putty | 747.38 | Sq.Ft | 1 | 100 | 18.68 | 0 | 747.38 | C+S GST 18% I/P RD | 134.52 | 881.9 | 881.9 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Wall Painting | Scrapping with 1st Coat Putty | 798.6 | Sq.Ft | 1 | 100 | 19.97 | 0 | 798.6 | C+S GST 18% I/P RD | 143.74 | 942.34 | 942.34 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Ceiling Painting | Water Base Primer | 747.38 | Sq.Ft | 0.5 | 100 | 9.34 | 0 | 373.69 | C+S GST 18% I/P RD | 67.26 | 440.95 | 440.95 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 874 | 96524 | 04 Oct 2022 |  | CHAPLA ADE PENTING CONTRACTOR | ANIL MAHTO ENTERPRISES | EV - 1175 | A 3rd Floor Lobby Wall Painting | 1st Coat Satin Matt Paint (L) | 798.6 | Sq.Ft | 1.25 | 100 | 24.96 | 0 | 998.25 | C+S GST 18% I/P RD | 179.68 | 1177.93 | 1177.93 | Approved | 0 | 0 | 71 | 04 Oct 2022
GANGA DHAM TOWERS | 1171 | 96523 | 04 Oct 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1407 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 150 mm dia. | 45 | Mtrs | 124.355 | 100 | 0 | 0 | 5595.98 | C+S GST 18% I/P RD | 1007.28 | 6603.26 | 6603.26 | Approved | 0 | 0 | 112 | 04 Oct 2022
GANGA DHAM TOWERS | 1044 | 96522 | 04 Oct 2022 |  | SUSTAINERA SOLUTIONS PRIVATE LIMITED | SUSTAINERA SOLUTIONS PRIVATE LIMITED | EV - 1131 | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | 1 | No. | 565000 | 10 | 0 | 0 | 56500 | C+S GST 18% I/P RD | 10170 | 66670 | 66670 | Approved | 0 | 0 | 5650 | 04 Oct 2022
GANGA DHAM TOWERS | 1049 | 96521 | 04 Oct 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 1190 | Ganga Dham Main Road Planter Bed Excavation | Excavation work Lumsum-DPo | 1 | No. | 140000 | 100 | 0 | 0 | 140000 | C+S GST 18% I/P RD | 25200 | 165200 | 165200 | Approved | 0 | 0 | 1400 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 StaffToilet Dado - 1 No. | Dado BC | 115.889 | Sq.Ft | 24 | 100 | 69.53 | 0 | 2781.34 | C+S GST 18% I/P RD | 500.64 | 3281.98 | 3281.98 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 2 Vitrified Flooring | Vitrified Flooring -BC | 38.8875 | Sq.Ft | 24 | 100 | 23.33 | 0 | 933.3 | C+S GST 18% I/P RD | 168 | 1101.3 | 1101.3 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 69.3515 | Sq.Ft | 24 | 100 | 41.61 | 0 | 1664.44 | C+S GST 18% I/P RD | 299.6 | 1964.04 | 1964.04 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 1 Vitrified Flooring | Vitrified Flooring -BC | 49.589 | Sq.Ft | 24 | 100 | 29.75 | 0 | 1190.14 | C+S GST 18% I/P RD | 214.22 | 1404.36 | 1404.36 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 23.3325 | Sq.Ft | 24 | 100 | 14 | 0 | 559.98 | C+S GST 18% I/P RD | 100.8 | 660.78 | 660.78 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 1702 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 24 | 100 | 89.22 | 0 | 3568.97 | C+S GST 18% I/P RD | 642.42 | 4211.39 | 4211.39 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2202 Living Terrace Vitrified Flooing | Vitrified Flooring -BC | 186.876 | Sq.Ft | 28 | 100 | 130.81 | 0 | 5232.53 | C+S GST 18% I/P RD | 941.86 | 6174.39 | 6174.39 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2302 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 28 | 100 | 104.09 | 0 | 4163.8 | C+S GST 18% I/P RD | 749.48 | 4913.28 | 4913.28 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.713 | Sq.Ft | 28 | 100 | 103.4 | 0 | 4135.96 | C+S GST 18% I/P RD | 744.48 | 4880.44 | 4880.44 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2202 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 94.59 | R.Ft | 60 | 100 | 141.89 | 0 | 5675.4 | C+S GST 18% I/P RD | 1021.58 | 6696.98 | 6696.98 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2302 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 54.135 | R.Ft | 60 | 100 | 81.2 | 0 | 3248.1 | C+S GST 18% I/P RD | 584.66 | 3832.76 | 3832.76 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 37.8975 | R.Ft | 60 | 100 | 56.85 | 0 | 2273.85 | C+S GST 18% I/P RD | 409.3 | 2683.15 | 2683.15 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2202 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 54.135 | R.Ft | 60 | 100 | 81.2 | 0 | 3248.1 | C+S GST 18% I/P RD | 584.66 | 3832.76 | 3832.76 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 172.665 | R.Ft | 60 | 100 | 259 | 0 | 10359.9 | C+S GST 18% I/P RD | 1864.78 | 12224.68 | 12224.68 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 60 | 100 | 77.88 | 0 | 3115.35 | C+S GST 18% I/P RD | 560.76 | 3676.11 | 3676.11 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.0225 | R.Ft | 60 | 100 | 103.53 | 0 | 4141.35 | C+S GST 18% I/P RD | 745.44 | 4886.79 | 4886.79 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 203.52 | Sq.Ft | 50 | 100 | 254.4 | 0 | 10176 | C+S GST 18% I/P RD | 1831.68 | 12007.68 | 12007.68 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 50 | 100 | 336.78 | 0 | 13471 | C+S GST 18% I/P RD | 2424.78 | 15895.78 | 15895.78 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 50 | 100 | 824.45 | 0 | 32978 | C+S GST 18% I/P RD | 5936.04 | 38914.04 | 38914.04 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 2 Dado - 1 No. | Dado BC | 22.831 | Sq.Ft | 28 | 100 | 15.98 | 0 | 639.27 | C+S GST 18% I/P RD | 115.06 | 754.33 | 754.33 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Powder Toilet Dado - 1 No. | Dado BC | 33.626 | Sq.Ft | 28 | 100 | 23.54 | 0 | 941.53 | C+S GST 18% I/P RD | 169.48 | 1111.01 | 1111.01 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 2 Dado - 1 No. | Dado BC | 144.653 | Sq.Ft | 28 | 100 | 101.26 | 0 | 4050.28 | C+S GST 18% I/P RD | 729.06 | 4779.34 | 4779.34 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 1 Dado - 1 No. | Dado BC | 161.6445 | Sq.Ft | 28 | 100 | 113.15 | 0 | 4526.05 | C+S GST 18% I/P RD | 814.68 | 5340.73 | 5340.73 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Master Toilet Dado - 1 No. | Dado BC | 118.847 | Sq.Ft | 28 | 100 | 83.19 | 0 | 3327.72 | C+S GST 18% I/P RD | 598.98 | 3926.7 | 3926.7 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Powder Toilet Dado - 1 No. | Dado BC | 90.7885 | Sq.Ft | 28 | 100 | 63.55 | 0 | 2542.08 | C+S GST 18% I/P RD | 457.58 | 2999.66 | 2999.66 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Master Toilet Dado - 1 No. | Dado BC | 80.699 | Sq.Ft | 28 | 100 | 56.49 | 0 | 2259.57 | C+S GST 18% I/P RD | 406.72 | 2666.29 | 2666.29 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2401 Children Toilet 1 Dado - 1 No. | Dado BC | 34.748 | Sq.Ft | 28 | 100 | 24.32 | 0 | 972.94 | C+S GST 18% I/P RD | 175.12 | 1148.06 | 1148.06 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 20 | 100 | 74.35 | 0 | 2974.14 | C+S GST 18% I/P RD | 535.34 | 3509.48 | 3509.48 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.7 | Sq.Ft | 20 | 100 | 73.85 | 0 | 2954 | C+S GST 18% I/P RD | 531.72 | 3485.72 | 3485.72 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2202 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 42.8175 | R.Ft | 60 | 100 | 64.23 | 0 | 2569.05 | C+S GST 18% I/P RD | 462.42 | 3031.47 | 3031.47 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2302 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 42.8175 | R.Ft | 60 | 100 | 64.23 | 0 | 2569.05 | C+S GST 18% I/P RD | 462.42 | 3031.47 | 3031.47 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 2302 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 94.59 | R.Ft | 60 | 100 | 141.89 | 0 | 5675.4 | C+S GST 18% I/P RD | 1021.58 | 6696.98 | 6696.98 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 54.135 | R.Ft | 50 | 100 | 67.67 | 0 | 2706.75 | C+S GST 18% I/P RD | 487.22 | 3193.97 | 3193.97 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 94.59 | R.Ft | 50 | 100 | 118.24 | 0 | 4729.5 | C+S GST 18% I/P RD | 851.32 | 5580.82 | 5580.82 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 702 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 42.8175 | R.Ft | 50 | 100 | 53.52 | 0 | 2140.88 | C+S GST 18% I/P RD | 385.36 | 2526.24 | 2526.24 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 502 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 15 | 100 | 55.77 | 0 | 2230.61 | C+S GST 18% I/P RD | 401.5 | 2632.11 | 2632.11 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 758 | 96520 | 04 Oct 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1211 | B 602 Living Terrace Vitrified Flooring | Vitrified Flooring -BC | 186.876 | Sq.Ft | 15 | 100 | 70.08 | 0 | 2803.14 | C+S GST 18% I/P RD | 504.56 | 3307.7 | 3307.7 | Approved | 0 | 0 | 1635 | 04 Oct 2022
GANGA DHAM TOWERS | 1274 | 96519 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1244 | New Tea Canteen Fabrication work | Meta colour Sheet Fixing BC | 92 | Sq.Ft | 5 | 100 | 11.5 | 0 | 460 | CGST 0% URD I/P | 0 | 460 | 460 | Approved | 0 | 0 | 15 | 04 Oct 2022
GANGA DHAM TOWERS | 1274 | 96519 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1244 | New Tea Canteen Fabrication work | Door Making Fabrication Work | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 15 | 04 Oct 2022
GANGA DHAM TOWERS | 1274 | 96519 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1244 | New Tea Canteen Fabrication work | MS Angle. (L) | 22.54 | Kgs | 12 | 100 | 6.76 | 0 | 270.48 | CGST 0% URD I/P | 0 | 270.48 | 270.48 | Approved | 0 | 0 | 15 | 04 Oct 2022
GANGA DHAM TOWERS | 1361 | 96518 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1243 | New Electrical meter room fabrication | Door Making Fabrication Work | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 46 | 04 Oct 2022
GANGA DHAM TOWERS | 1361 | 96518 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1243 | New Electrical meter room fabrication | Meta colour Sheet Fixing BC | 472.5 | Sq.Ft | 5 | 100 | 59.06 | 0 | 2362.5 | CGST 0% URD I/P | 0 | 2362.5 | 2362.5 | Approved | 0 | 0 | 46 | 04 Oct 2022
GANGA DHAM TOWERS | 1361 | 96518 | 04 Oct 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1243 | New Electrical meter room fabrication | MS Square Pipe (L) | 120.84 | Kgs | 12 | 100 | 36.25 | 0 | 1450.08 | CGST 0% URD I/P | 0 | 1450.08 | 1450.08 | Approved | 0 | 0 | 46 | 04 Oct 2022
GANGA DHAM TOWERS | 1416 | 96517 | 04 Oct 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1201 | Laser Jali removing & barricading towards Main Road | Shifting & Fixing | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 04 Oct 2022
GANGA DHAM TOWERS | 1162 | 96516 | 04 Oct 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1120 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 04 Oct 2022
GANGA DHAM TOWERS | 1336 | 96515 | 04 Oct 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 1376 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 27000 | 100 | 0 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 540 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 23rd Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 1st Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 2nd Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 2nd Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 12th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 12th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 15th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 24th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 6th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 8th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 8th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 21st Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 11th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 9th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 10th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 5th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 5th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 9th Floor Texture Painting | Texture Paint (M) | 379.64 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752.39 | C+S GST 18% I/P RD | 495.44 | 3247.83 | 3247.83 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 3rd Floor Texture Painting | Texture Paint (M) | 379.64 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752.39 | C+S GST 18% I/P RD | 495.44 | 3247.83 | 3247.83 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 21st Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 19th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 4th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 4th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 13th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 15th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 22nd Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 18th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 18th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 20th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 17th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 3rd Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 17th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 20th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 11th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 14th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 1st Floor Texture Painting | Texture Paint (M) | 379.64 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752.39 | C+S GST 18% I/P RD | 495.44 | 3247.83 | 3247.83 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 14th Floor Texture Painting | Texture Paint (M) | 451.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 16th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 23rd Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 5th Floor Texture Painting | Texture Paint (M) | 379.64 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752.39 | C+S GST 18% I/P RD | 495.44 | 3247.83 | 3247.83 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 7th Floor Texture Painting | Texture Paint (M) | 379.64 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752.39 | C+S GST 18% I/P RD | 495.44 | 3247.83 | 3247.83 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 19th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 13th Floor Texture Painting | Texture Paint (M) | 379.5862 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 7th Floor Texture Painting | Texture Paint (M) | 116.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 10th Floor Texture Painting | Texture Paint (M) | 148.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1079 | C+S GST 18% I/P RD | 194.22 | 1273.22 | 1273.22 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 22nd Floor Texture Painting | Texture Paint (M) | 148 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1073 | C+S GST 18% I/P RD | 193.14 | 1266.14 | 1266.14 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 15th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 9th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 14th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 11th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 12th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 7th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 2nd Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 10th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 9th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 3rd Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 13th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 1st Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 6th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 19th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 4th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 8th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 20th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 16th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 5th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 23rd Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 15th Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 21st Floor Texture Painting | Water Base Primer (M) | 380 | Sq.Ft | 1 | 100 | 0 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 22nd Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 14th Floor Texture Painting | Water Base Primer (M) | 451 | Sq.Ft | 1 | 100 | 0 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 5th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 12th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 19th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 16th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 8th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 11th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 20th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 23rd Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 10th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 1st Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 3rd Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 7th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 1st Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 6th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 13th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 22nd Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 4th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Eastside 18th Floor Texture Painting | 1st Coat Acrylic Paint (M) | 451 | Sq.Ft | 2 | 100 | 0 | 0 | 902 | C+S GST 18% I/P RD | 162.36 | 1064.36 | 1064.36 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1200 | 96514 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1237 | B Westside 21st Floor Texture Painting | 1st Coat Acrylic Paint (M) | 379.5 | Sq.Ft | 2 | 100 | 0 | 0 | 759 | C+S GST 18% I/P RD | 136.62 | 895.62 | 895.62 | Approved | 0 | 0 | 2316 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 19th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 20th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 7th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 10th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 18th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 16th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 1st Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 2nd Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 3rd Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 18th Floor Texture Painting | Scaffolding/Gondola work | 95.35 | Sq.Ft | 3.5 | 100 | 8.34 | 0 | 333.73 | C+S GST 18% I/P RD | 60.08 | 393.81 | 393.81 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 11th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 13th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 15th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 4th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 5th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 12th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 8th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 9th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 20th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 12th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 13th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 22nd Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 17th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 7th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 10th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 21st Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 5th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 14th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 21st Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 23rd Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 8th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 9th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 3rd Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 4th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 6th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 22nd Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 2nd Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 11th Floor Texture Painting | Scaffolding/Gondola work | 76.13 | Sq.Ft | 3.5 | 100 | 6.66 | 0 | 266.46 | C+S GST 18% I/P RD | 47.96 | 314.42 | 314.42 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 1st Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 14th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 15th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 24th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 6th Floor Texture Painting | Scaffolding/Gondola work | 77.77 | Sq.Ft | 3.5 | 100 | 6.8 | 0 | 272.2 | C+S GST 18% I/P RD | 49 | 321.2 | 321.2 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 23rd Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Westside 17th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | C+S GST 18% I/P RD | 60.28 | 395.16 | 395.16 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96513 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1157 | B Eastside 16th Floor Texture Painting | Scaffolding/Gondola work | 98.35 | Sq.Ft | 3.5 | 100 | 8.61 | 0 | 344.23 | C+S GST 18% I/P RD | 61.96 | 406.19 | 406.19 | Approved | 0 | 0 | 140 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 15th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 7th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 2nd Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 21st Floor Texture Painting | Water Base Primer (L) | 370 | Sq.Ft | 1 | 100 | 9.25 | 0 | 370 | C+S GST 18% I/P RD | 66.6 | 436.6 | 436.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 4th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 13th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 1st Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 3rd Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 19th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 8th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 5th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 16th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 4th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 22nd Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 2nd Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 14th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 10th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 12th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 15th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 8th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 1st Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 7th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 9th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 23rd Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 20th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 21st Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 1st Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 18th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 19th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 6th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 451.3333 | Sq.Ft | 1.5 | 100 | 16.92 | 0 | 677 | C+S GST 18% I/P RD | 121.86 | 798.86 | 798.86 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 2nd Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 7th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 4th Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 15th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 2nd Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 3rd Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 9th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 19th Floor Texture Painting | Scaffolding/Gondola work | 117.7143 | Sq.Ft | 3.5 | 100 | 10.3 | 0 | 412 | C+S GST 18% I/P RD | 74.16 | 486.16 | 486.16 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 20th Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 11th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 16th Floor Texture Painting | Scaffolding/Gondola work | 148.5714 | Sq.Ft | 3.5 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 12th Floor Texture Painting | Scaffolding/Gondola work | 148.5714 | Sq.Ft | 3.5 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 10th Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 8th Floor Texture Painting | Scaffolding/Gondola work | 148.5714 | Sq.Ft | 3.5 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 24th Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 13th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 6th Floor Texture Painting | Scaffolding/Gondola work | 148.5714 | Sq.Ft | 3.5 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 22nd Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 14th Floor Texture Painting | Scaffolding/Gondola work | 148.8571 | Sq.Ft | 3.5 | 100 | 13.02 | 0 | 521 | C+S GST 18% I/P RD | 93.78 | 614.78 | 614.78 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 21st Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 23rd Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 17th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 5th Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 1st Floor Texture Painting | Scaffolding/Gondola work | 117.1429 | Sq.Ft | 3.5 | 100 | 10.25 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 18th Floor Texture Painting | Scaffolding/Gondola work | 148 | Sq.Ft | 3.5 | 100 | 12.95 | 0 | 518 | C+S GST 18% I/P RD | 93.24 | 611.24 | 611.24 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 11th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 12th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 12th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 14th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 6th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 3rd Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 4th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 13th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 11th Floor Texture Painting | 1st Coat Acrylic Paint (L) | 379.3333 | Sq.Ft | 1.5 | 100 | 14.22 | 0 | 569 | C+S GST 18% I/P RD | 102.42 | 671.42 | 671.42 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 5th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 13th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 9th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 11th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 5th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 1st Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 2nd Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 2nd Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 23rd Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 8th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 8th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 18th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 18th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 19th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 17th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 23rd Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 1st Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 16th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 7th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 9th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 17th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 22nd Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 22nd Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 21st Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 14th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 19th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 7th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 15th Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 3rd Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 13th Floor Texture Painting | Texture Paint (L) | 117.032 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.48 | C+S GST 18% I/P RD | 152.72 | 1001.2 | 1001.2 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 6th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 21st Floor Texture Painting | Texture Paint (L) | 379.5862 | Sq.Ft | 7.25 | 100 | 68.8 | 0 | 2752 | C+S GST 18% I/P RD | 495.36 | 3247.36 | 3247.36 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 4th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 15th Floor Texture Painting | Texture Paint (L) | 117.02 | Sq.Ft | 7.25 | 100 | 21.21 | 0 | 848.4 | C+S GST 18% I/P RD | 152.72 | 1001.12 | 1001.12 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 20th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 20th Floor Texture Painting | Texture Paint (L) | 148.81 | Sq.Ft | 7.25 | 100 | 26.97 | 0 | 1078.87 | C+S GST 18% I/P RD | 194.2 | 1273.07 | 1273.07 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 10th Floor Texture Painting | Texture Paint (L) | 148.02 | Sq.Ft | 7.25 | 100 | 26.83 | 0 | 1073.15 | C+S GST 18% I/P RD | 193.16 | 1266.31 | 1266.31 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 10th Floor Texture Painting | Texture Paint (L) | 451.0345 | Sq.Ft | 7.25 | 100 | 81.75 | 0 | 3270 | C+S GST 18% I/P RD | 588.6 | 3858.6 | 3858.6 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 16th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 11th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 12th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 18th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 6th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 23rd Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 9th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 20th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Westside 5th Floor Texture Painting | Water Base Primer (L) | 380 | Sq.Ft | 1 | 100 | 9.5 | 0 | 380 | C+S GST 18% I/P RD | 68.4 | 448.4 | 448.4 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 14th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96512 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1368 | B Eastside 10th Floor Texture Painting | Water Base Primer (L) | 451 | Sq.Ft | 1 | 100 | 11.28 | 0 | 451 | C+S GST 18% I/P RD | 81.18 | 532.18 | 532.18 | Approved | 0 | 0 | 2440 | 04 Oct 2022
GANGA DHAM TOWERS | 1199 | 96507 | 04 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI KRUPA ENTERPRISES |  | B Westside 19th Floor Texture Painting | Scaffolding/Gondola work | 95.68 | Sq.Ft | 3.5 | 100 | 8.37 | 0 | 334.88 | CGST 0% URD I/P | 0 | 334.88 | 334.88 |  | 0 | 0 | 3 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 2nd floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 10th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 11th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 18th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 1st floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 24th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 8th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 5th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 3rd floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 3rd floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 17th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 18th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 20th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 21st floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 24th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 13th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 15th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 22nd floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 7th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 23rd floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 5th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 17th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 9th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 19th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 4th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 11th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 22nd floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 16th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 20th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 10th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 12th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 4th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 6th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 8th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 24th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 12th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 14th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 21st floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 1st floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 19th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 9th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 7th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 2nd floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 6th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 13th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 23rd floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 14th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Westside 16th floor External Texture Painting | Texture Paint (M) | 96 | Sq.Ft | 7.25 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A South side 15th floor External Texture Painting | Texture Paint (M) | 232.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside1st floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 845 | 96501 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1186 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 52 | Sq.Ft | 7.25 | 100 | 0 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 22nd floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 6th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 9th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 10th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 17th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 11th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 22nd floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside1st floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 24th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 4th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 20th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 13th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 6th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 8th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 1st floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 18th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 19th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 8th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 21st floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 4th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 24th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 7th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 14th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 5th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 9th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 3rd floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 15th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 23rd floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 12th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 3rd floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 20th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 5th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 3rd floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 14th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 12th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 16th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 19th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 11th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 18th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 1st floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 2nd floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 24th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 21st floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 10th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 23rd floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 2nd floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 7th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 16th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 52 | Sq.Ft | 7.25 | 100 | 9.43 | 0 | 377 | C+S GST 18% I/P RD | 67.86 | 444.86 | 444.86 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 17th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A South side 15th floor External Texture Painting | Texture Paint (L) | 232.9655 | Sq.Ft | 7.25 | 100 | 42.22 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 844 | 96499 | 04 Oct 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1187 | A Westside 13th floor External Texture Painting | Texture Paint (L) | 96 | Sq.Ft | 7.25 | 100 | 17.4 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 663 | 04 Oct 2022
GANGA DHAM TOWERS | 968 | 96498 | 04 Oct 2022 |  | MAYUR ARTS & ENTERPRISES | PARTH ENTERPRISES | EV - 1207 | Safety Board Fabrication Work - 1 No. | MS Pipe (L) | 92.28 | Kgs | 12 | 100 | 27.68 | 0 | 1107.36 | CGST 0% URD I/P | 0 | 1107.36 | 1107.36 | Approved | 0 | 0 | 11 | 04 Oct 2022
GANGA DHAM TOWERS | 1399 | 96497 | 04 Oct 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1440 | Sales office PARGOLA covering work | MS Square Pipe (M) | 191 | Kgs | 71 | 100 | 0 | 0 | 13561 | C+S GST 18% I/P RD | 2440.98 | 16001.98 | 16001.98 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 1399 | 96497 | 04 Oct 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1440 | Sales office PARGOLA covering work | Silicon | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 1399 | 96497 | 04 Oct 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1440 | Sales office PARGOLA covering work | Polycarbonate Sheet (M) -AIE | 342 | Sq.Ft | 115 | 100 | 0 | 0 | 39330 | C+S GST 18% I/P RD | 7079.4 | 46409.4 | 46409.4 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 1399 | 96497 | 04 Oct 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1440 | Sales office PARGOLA covering work | Wastage, Profit & Supervision. | 1 | No. | 9425 | 100 | 0 | 0 | 9425 | C+S GST 18% I/P RD | 1696.5 | 11121.5 | 11121.5 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 1399 | 96497 | 04 Oct 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1440 | Sales office PARGOLA covering work | Lumpsum work- DCW | 1 | No. | 3500 | 100 | 0 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 0 | 04 Oct 2022
GANGA DHAM TOWERS | 1400 | 96496 | 04 Oct 2022 |  | HELIOS | HELIOS | EV - 1441 | Sales office PARGOLA covering work | Polycarbonate Sheet fixing (L) | 342 | Sq.Ft | 25 | 100 | 213.75 | 0 | 8550 | C+S GST 18% I/P RD | 1539 | 10089 | 10089 | Approved | 0 | 0 | 86 | 04 Oct 2022
GANGA DHAM TOWERS | 1340 | 96490 | 03 Oct 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1038 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 03 Oct 2022
GANGA DHAM TOWERS | 1259 | 96485 | 03 Oct 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 1439 | A 101 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.28 | Sq.Ft | 140 | 100 | 49.98 | 0 | 1999.2 | CGST 0% URD I/P | 0 | 1999.2 | 1999.2 | Approved | 0 | 0 | 30 | 03 Oct 2022
GANGA DHAM TOWERS | 1259 | 96485 | 03 Oct 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 1439 | A 102 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 7.14 | Sq.Ft | 140 | 100 | 24.99 | 0 | 999.6 | CGST 0% URD I/P | 0 | 999.6 | 999.6 | Approved | 0 | 0 | 30 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 21st Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 10th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 16th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 5th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 1st Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 3rd Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 13th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 15th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 2nd Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 17th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 6th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 17th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 1st Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 6th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 7th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 15th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 3rd Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 14th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 13th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 23rd Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 10th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 12th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 11th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 5th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 2nd Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 4th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 18th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 19th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 24th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 21st Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 16th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 8th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 23rd Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 7th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 9th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 9th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 11th Floor Texture Painting | Texture Paint (L) | 76.1379 | Sq.Ft | 7.25 | 100 | 13.8 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 22nd Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 12th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 14th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 19th Floor Texture Painting | Texture Paint (L) | 95.7241 | Sq.Ft | 7.25 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 8th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 22nd Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 20th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 20th Floor Texture Painting | Texture Paint (L) | 98.3448 | Sq.Ft | 7.25 | 100 | 17.82 | 0 | 713 | C+S GST 18% I/P RD | 128.34 | 841.34 | 841.34 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Westside 18th Floor Texture Painting | Texture Paint (L) | 77.7931 | Sq.Ft | 7.25 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 1199 | 96484 | 03 Oct 2022 |  | GODAVARI PAINT PVT LTD | SAI NIRMAL COLOURS & TEXTURES | EV - 1174 | B Eastside 4th Floor Texture Painting | Texture Paint (L) | 95.3103 | Sq.Ft | 7.25 | 100 | 17.27 | 0 | 691 | C+S GST 18% I/P RD | 124.38 | 815.38 | 815.38 | Approved | 0 | 0 | 297 | 03 Oct 2022
GANGA DHAM TOWERS | 145 | 96483 | 03 Oct 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1263 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 225 | 03 Oct 2022
GANGA DHAM TOWERS | 145 | 96483 | 03 Oct 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1263 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 225 | 03 Oct 2022
GANGA DHAM TOWERS | 145 | 96483 | 03 Oct 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1263 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 225 | 03 Oct 2022
GANGA DHAM TOWERS | 145 | 96483 | 03 Oct 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1263 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 225 | 03 Oct 2022
GANGA DHAM TOWERS | 371 | 96436 | 30 Sep 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1111 | EWS Bldg RCC 11th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 11 | Sq.Ft | 150 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 128 | 30 Sep 2022
GANGA DHAM TOWERS | 371 | 96436 | 30 Sep 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1111 | EWS Bldg RCC 11th Slab Built-up Area (L) | Hacking Work | 300 | Sq.Ft | 2.5 | 100 | 18.75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 128 | 30 Sep 2022
GANGA DHAM TOWERS | 371 | 96436 | 30 Sep 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1111 | EWS Bldg RCC 10th Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | CGST 0% URD I/P | 0 | 8547.88 | 8547.88 | Approved | 0 | 0 | 128 | 30 Sep 2022
GANGA DHAM TOWERS | 371 | 96436 | 30 Sep 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 1111 | EWS Bldg RCC Pergola Built-up Area (L) | RCC Superstructure (B-up area) | 5.7812 | Sq.Ft | 320 | 100 | 46.25 | 0 | 1850 | CGST 0% URD I/P | 0 | 1850 | 1850 | Approved | 0 | 0 | 128 | 30 Sep 2022
GANGA DHAM TOWERS | 1306 | 96428 | 30 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1084 | D 1st Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 100 | Sq.Ft | 55 | 100 | 137.5 | 0 | 5500 | CGST 0% URD I/P | 0 | 5500 | 5500 | Approved | 0 | 0 | 55 | 30 Sep 2022
GANGA DHAM TOWERS | 1395 | 96427 | 30 Sep 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 1336 | D Fire Fighting Fire Pump room equipment | SITC GI C Class Pipe 100mm dia.(L) | 1.0988 | Mtrs | 360 | 90 | 0 | 0 | 356 | C+S GST 18% I/P RD | 64.08 | 420.08 | 420.08 | Approved | 0 | 0 | 179 | 30 Sep 2022
GANGA DHAM TOWERS | 1395 | 96427 | 30 Sep 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 1336 | D Fire Fighting Internal Hydrants System | SITC GI- 150mm Dia. Heavy Grade Pipe | 39 | Mtrs | 500 | 90 | 0 | 0 | 17550 | C+S GST 18% I/P RD | 3159 | 20709 | 20709 | Approved | 0 | 0 | 179 | 30 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2104 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 250 | Sq.Ft | 19 | 100 | 475 | 0 | 4750 | CGST 0% URD I/P | 0 | 4750 | 4750 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 187 | Sq.Ft | 19 | 100 | 355.3 | 0 | 3553 | CGST 0% URD I/P | 0 | 3553 | 3553 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 104 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 72 | Sq.Ft | 19 | 100 | 136.8 | 0 | 1368 | CGST 0% URD I/P | 0 | 1368 | 1368 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 203 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 46 | Sq.Ft | 19 | 100 | 87.4 | 0 | 874 | CGST 0% URD I/P | 0 | 874 | 874 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 801 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 258 | Sq.Ft | 19 | 100 | 490.2 | 0 | 4902 | CGST 0% URD I/P | 0 | 4902 | 4902 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 1102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 271 | Sq.Ft | 19 | 100 | 514.9 | 0 | 5149 | CGST 0% URD I/P | 0 | 5149 | 5149 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2203 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 187 | Sq.Ft | 19 | 100 | 355.3 | 0 | 3553 | CGST 0% URD I/P | 0 | 3553 | 3553 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 1102 Chemical & IPS Waterproofing | IPS W/P | 271 | Sq.Ft | 11 | 100 | 298.1 | 0 | 2981 | CGST 0% URD I/P | 0 | 2981 | 2981 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2104 Chemical & IPS Waterproofing | IPS W/P | 250 | Sq.Ft | 11 | 100 | 275 | 0 | 2750 | CGST 0% URD I/P | 0 | 2750 | 2750 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 203 Chemical & IPS Waterproofing | IPS W/P | 184 | Sq.Ft | 11 | 100 | 202.4 | 0 | 2024 | CGST 0% URD I/P | 0 | 2024 | 2024 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2203 Chemical & IPS Waterproofing | IPS W/P | 187 | Sq.Ft | 11 | 100 | 205.7 | 0 | 2057 | CGST 0% URD I/P | 0 | 2057 | 2057 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 104 Chemical & IPS Waterproofing | IPS W/P | 289 | Sq.Ft | 11 | 100 | 317.9 | 0 | 3179 | CGST 0% URD I/P | 0 | 3179 | 3179 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 801 Chemical & IPS Waterproofing | IPS W/P | 258.6364 | Sq.Ft | 11 | 100 | 284.5 | 0 | 2845 | CGST 0% URD I/P | 0 | 2845 | 2845 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2103 Chemical & IPS Waterproofing | IPS W/P | 187 | Sq.Ft | 11 | 100 | 205.7 | 0 | 2057 | CGST 0% URD I/P | 0 | 2057 | 2057 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2201 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96417 | 29 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1212 | A 2402 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 540 | 29 Sep 2022
GANGA DHAM TOWERS | 1362 | 96416 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1125 | CP Sanitary Godown Work | Fabrication work- | 478.82 | Kgs | 12 | 100 | 143.65 | 0 | 5745.84 | CGST 0% URD I/P | 0 | 5745.84 | 5745.84 | Approved | 0 | 0 | 118 | 29 Sep 2022
GANGA DHAM TOWERS | 1362 | 96416 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1125 | CP Sanitary Godown Work | Meta colour Sheet Fixing BC | 1138 | Sq.Ft | 4 | 100 | 113.8 | 0 | 4552 | CGST 0% URD I/P | 0 | 4552 | 4552 | Approved | 0 | 0 | 118 | 29 Sep 2022
GANGA DHAM TOWERS | 1362 | 96416 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1125 | CP Sanitary Godown Work | M.S. Door -BCo | 1 | No. | 1500 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 118 | 29 Sep 2022
GANGA DHAM TOWERS | 1365 | 96415 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1122 | Electricity Infra | MS Door (L) | 1 | No. | 1500 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 30 | 29 Sep 2022
GANGA DHAM TOWERS | 1365 | 96415 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1122 | Electricity Infra | MS Door (L) | 1 | No. | 1500 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 30 | 29 Sep 2022
GANGA DHAM TOWERS | 1273 | 96414 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1121 | RMU Stand Fabrication work | ISMC 100 (L) | 380.87 | Kgs | 12 | 100 | 114.26 | 0 | 4570.44 | CGST 0% URD I/P | 0 | 4570.44 | 4570.44 | Approved | 0 | 0 | 61 | 29 Sep 2022
GANGA DHAM TOWERS | 1273 | 96414 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1121 | RMU Stand Fabrication work | MS Angle 50 x 50 x 5mm | 125.63 | Kgs | 12 | 100 | 37.69 | 0 | 1507.56 | CGST 0% URD I/P | 0 | 1507.56 | 1507.56 | Approved | 0 | 0 | 61 | 29 Sep 2022
GANGA DHAM TOWERS | 1361 | 96413 | 29 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1245 | Shed for Diesel storage room | Lumpsum work- DCW | 0.4 | No. | 5000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 20 | 29 Sep 2022
GANGA DHAM TOWERS | 1049 | 96412 | 29 Sep 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 1147 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Poclain Charges - BC - | 16 | Hrs | 1100 | 100 | 0 | 0 | 17600 | C+S GST 18% I/P RD | 3168 | 20768 | 20768 | Approved | 0 | 0 | 211 | 29 Sep 2022
GANGA DHAM TOWERS | 1049 | 96412 | 29 Sep 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 1147 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Transport Charges | 1 | No. | 3500 | 100 | 0 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 211 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 24th Floor 2401 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 20th Floor 2001 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 21st Floor 2102- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 8th Floor 801 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 17th Floor 1702- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 20th Floor 2002- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 7th Floor 702- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 1st Floor 102- | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 22nd Floor 2202- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 2nd Floor 201 - | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 3rd Floor 302- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 9th Floor 901 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 3rd Floor 301 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 15th Floor 1502- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 1st Floor 101 | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 5th Floor 501 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 13th Floor 1302- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 10th Floor 1002- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 16th Floor 1601 - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 16th Floor 1602- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 18th Floor 1801 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 4th Floor 401 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 9th Floor 902- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 7th Floor 701 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 19th Floor 1902- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 11st Floor 1101 - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 12th Floor 1202- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 6th Floor 602- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 11st Floor 1102- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 14th Floor 1401 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 13th Floor 1301 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 21st Floor 2101 - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 4th Floor 402- - 1 No. | Gyser Point BC | 4.8 | No. | 250 | 25 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 452 | 96411 | 29 Sep 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1195 | B 17th Floor 1701 - 1 No. | Gyser Point BC | 5.6 | No. | 250 | 25 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 218 | 29 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 17 | No. | 70 | 100 | 119 | 0 | 1190 | CGST 0% URD I/P | 0 | 1190 | 1190 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 7 | No. | 70 | 100 | 49 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1004 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 17 | No. | 70 | 100 | 119 | 0 | 1190 | CGST 0% URD I/P | 0 | 1190 | 1190 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 22 | No. | 70 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 10 | No. | 70 | 100 | 70 | 0 | 700 | CGST 0% URD I/P | 0 | 700 | 700 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2203 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2404 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2204 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1102 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1004 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 801 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 22 | No. | 70 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1102 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 801 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2203 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 1102 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2204 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 401 | 96410 | 28 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1173 | A 2404 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 490 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 12th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 8th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 6th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 11th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 10th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 9th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 9th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 7th Floor Main Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 8th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 11th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 7th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 12th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 6th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1317 | 96401 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1088 | D 10th Floor Main Staircase Railing - 22.67 R.Ft | M.S. Railing. (M) | 22.67 | R.Ft | 342 | 100 | 0 | 0 | 7753.14 | C+S GST 18% I/P RD | 1395.56 | 9148.7 | 9148.7 | Approved | 0 | 0 | 0 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 7th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 7th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 10th Floor Main Staircase Railing - 22.67 R.Ft | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 12th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 11th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 6th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 9th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 6th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 8th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 8th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 11th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 12th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 9th Floor Main Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1316 | 96400 | 28 Sep 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 1089 | D 10th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.67 | R.Ft | 120 | 100 | 68.01 | 0 | 2720.4 | C+S GST 18% I/P RD | 489.68 | 3210.08 | 3210.08 | Approved | 0 | 0 | 381 | 28 Sep 2022
GANGA DHAM TOWERS | 1259 | 96390 | 27 Sep 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 1116 | A 203 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 35.7143 | Sq.Ft | 140 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 80 | 27 Sep 2022
GANGA DHAM TOWERS | 1259 | 96390 | 27 Sep 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 1116 | A 801 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 21.4286 | Sq.Ft | 140 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 80 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 704 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5 | No. | 1200 | 100 | 45 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 1102 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3 | No. | 1200 | 100 | 90 | 0 | 3600 | CGST 0% URD I/P | 0 | 3600 | 3600 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 803 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1200 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 703 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 503 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 504 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 1601 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.5 | No. | 1400 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 1801 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1400 | 100 | 70 | 0 | 2800 | CGST 0% URD I/P | 0 | 2800 | 2800 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 455 | 96387 | 27 Sep 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 1115 | A Bldg Flat No. 1401 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3 | No. | 1400 | 100 | 105 | 0 | 4200 | CGST 0% URD I/P | 0 | 4200 | 4200 | Approved | 0 | 0 | 235 | 27 Sep 2022
GANGA DHAM TOWERS | 724 | 96368 | 26 Sep 2022 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 990 | A Ground Floor Parking Trimix work | Weld mesh fixing(L) BCo | 5871.49 | Sq.Ft | 1 | 100 | 146.79 | 0 | 5871.49 | CGST 0% URD I/P | 0 | 5871.49 | 5871.49 | Approved | 0 | 0 | 587 | 26 Sep 2022
GANGA DHAM TOWERS | 724 | 96368 | 26 Sep 2022 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 990 | A Ground Floor Parking Trimix work | Trimix Work - BC | 5871.49 | Sq.Ft | 9 | 100 | 1321.09 | 0 | 52843.41 | CGST 0% URD I/P | 0 | 52843.41 | 52843.41 | Approved | 0 | 0 | 587 | 26 Sep 2022
GANGA DHAM TOWERS | 272 | 96366 | 26 Sep 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1386 | A Bldg Fire Check slab- Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 4740 | Sq.Ft | 170 | 100 | 20145 | 0 | 805800 | C+S GST 18% I/P RD | 145044 | 950844 | 950844 | Approved | 0 | 0 | 16116 | 26 Sep 2022
GANGA DHAM TOWERS | 384 | 96364 | 26 Sep 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1113 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting rate diff.- BC | 16 | No. | 90 | 100 | 36 | 0 | 1440 | CGST 0% URD I/P | 0 | 1440 | 1440 | Approved | 0 | 0 | 14 | 26 Sep 2022
GANGA DHAM TOWERS | 1171 | 96362 | 26 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1112 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 150mm dia.(M) | 45 | Mtrs | 2090 | 100 | 0 | 0 | 94050 | C+S GST 18% I/P RD | 16929 | 110979 | 110979 | Approved | 0 | 0 | 0 | 26 Sep 2022
GANGA DHAM TOWERS | 983 | 96360 | 26 Sep 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1114 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 18 | No. | 210 | 100 | 94.5 | 0 | 3780 | CGST 0% URD I/P | 0 | 3780 | 3780 | Approved | 0 | 0 | 130 | 26 Sep 2022
GANGA DHAM TOWERS | 983 | 96360 | 26 Sep 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1114 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 3" BCE | 44 | No. | 210 | 100 | 231 | 0 | 9240 | CGST 0% URD I/P | 0 | 9240 | 9240 | Approved | 0 | 0 | 130 | 26 Sep 2022
GANGA DHAM TOWERS | 1382 | 96359 | 26 Sep 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1117 | A Bldg. Flat No. 2403 Plumbing work | Int Flat PPRC Work. | 0.75 | No. | 12000 | 100 | 225 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 270 | 26 Sep 2022
GANGA DHAM TOWERS | 1382 | 96359 | 26 Sep 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1117 | A Bldg. Flat No. 2502 Plumbing work | Int Flat PPRC Work. | 0.75 | No. | 12000 | 100 | 225 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 270 | 26 Sep 2022
GANGA DHAM TOWERS | 1382 | 96359 | 26 Sep 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 1117 | A Bldg. Flat No. 2404 Plumbing work | Int Flat PPRC Work. | 0.75 | No. | 12000 | 100 | 225 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 270 | 26 Sep 2022
GANGA DHAM TOWERS | 1282 | 96358 | 26 Sep 2022 |  | Kishan Enterprises | RAHUL ENTERPRISES (Prop Laburi) | EV - 1165 | B 2401 NOC | Italian marble Skirting - BCo | 26.2333 | R.Ft | 60 | 100 | 39.35 | 0 | 1574 | C+S GST 18% I/P RD | 283.32 | 1857.32 | 1857.32 | Approved | 0 | 0 | 86 | 26 Sep 2022
GANGA DHAM TOWERS | 1282 | 96358 | 26 Sep 2022 |  | Kishan Enterprises | RAHUL ENTERPRISES (Prop Laburi) | EV - 1165 | B 2401 NOC | Italian Marble Flooring | 117.6667 | Sq.Ft | 60 | 100 | 176.5 | 0 | 7060 | C+S GST 18% I/P RD | 1270.8 | 8330.8 | 8330.8 | Approved | 0 | 0 | 86 | 26 Sep 2022
GANGA DHAM TOWERS | 1228 | 96357 | 24 Sep 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1026 | Site Expenses | Site Expenses -SO | 0.0347 | Month | 30000 | 100 | 0 | 0 | 1042 | CGST 0% URD I/P | 0 | 1042 | 1042 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 1228 | 96357 | 24 Sep 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1026 | Site Expenses | Site Expenses -SO | 0.2417 | Month | 30000 | 100 | 0 | 0 | 7250 | CGST 0% URD I/P | 0 | 7250 | 7250 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1002 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1004 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 703 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 603 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 604 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 901 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 605 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1001 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1003 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1101 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1105 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 704 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 903 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1005 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 902 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 601 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 603 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1003 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1105 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1002 Chemical Waterproofing | Chemical Waterproofing (L) | 37.75 | Sq.Ft | 4 | 100 | 15.1 | 0 | 151 | CGST 0% URD I/P | 0 | 151 | 151 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 604 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 901 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 701 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 703 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 704 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1101 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 605 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1103 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1004 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 804 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 904 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 705 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1005 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1102 Chemical Waterproofing | Chemical Waterproofing (L) | 37.75 | Sq.Ft | 4 | 100 | 15.1 | 0 | 151 | CGST 0% URD I/P | 0 | 151 | 151 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 903 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 805 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 902 Chemical Waterproofing | Chemical Waterproofing (L) | 37.75 | Sq.Ft | 4 | 100 | 15.1 | 0 | 151 | CGST 0% URD I/P | 0 | 151 | 151 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 801 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1001 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 601 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1104 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 602 Chemical Waterproofing | Chemical Waterproofing (L) | 37.75 | Sq.Ft | 4 | 100 | 15.1 | 0 | 151 | CGST 0% URD I/P | 0 | 151 | 151 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 802 Chemical Waterproofing | Chemical Waterproofing (L) | 37.75 | Sq.Ft | 4 | 100 | 15.1 | 0 | 151 | CGST 0% URD I/P | 0 | 151 | 151 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 803 Chemical Waterproofing | Chemical Waterproofing (L) | 37 | Sq.Ft | 4 | 100 | 14.8 | 0 | 148 | CGST 0% URD I/P | 0 | 148 | 148 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 905 Chemical Waterproofing | Chemical Waterproofing (L) | 63.25 | Sq.Ft | 4 | 100 | 25.3 | 0 | 253 | CGST 0% URD I/P | 0 | 253 | 253 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 803 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1104 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1102 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 801 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 905 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 602 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 705 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 802 IPS Waterproofing | IPS W/P | 37.9091 | Sq.Ft | 11 | 100 | 41.7 | 0 | 417 | CGST 0% URD I/P | 0 | 417 | 417 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 805 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 904 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 1103 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 804 IPS Waterproofing | IPS W/P | 37 | Sq.Ft | 11 | 100 | 40.7 | 0 | 407 | CGST 0% URD I/P | 0 | 407 | 407 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 653 | 96356 | 24 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA |  | D 701 IPS Waterproofing | IPS W/P | 63.1818 | Sq.Ft | 11 | 100 | 69.5 | 0 | 695 | CGST 0% URD I/P | 0 | 695 | 695 |  | 0 | 0 | 209 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14.68 | C+S GST 18% I/P RD | 2.64 | 17.32 | 17.32 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 830 | 96354 | 24 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1053 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 592.39 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1036.68 | C+S GST 18% I/P RD | 186.6 | 1223.28 | 1223.28 | Approved | 0 | 0 | 0 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 153.86 | Sq.Ft | 150 | 100 | 0 | 0 | 23079 | C+S GST 18% I/P RD | 4154.22 | 27233.22 | 27233.22 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 121.16 | Sq.Ft | 150 | 100 | 0 | 0 | 18174 | C+S GST 18% I/P RD | 3271.32 | 21445.32 | 21445.32 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 170.72 | Sq.Ft | 150 | 100 | 0 | 0 | 25608 | C+S GST 18% I/P RD | 4609.44 | 30217.44 | 30217.44 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2.56 | Sq.Ft | 150 | 100 | 0 | 0 | 384 | C+S GST 18% I/P RD | 69.12 | 453.12 | 453.12 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 139.16 | Sq.Ft | 150 | 100 | 0 | 0 | 20874 | C+S GST 18% I/P RD | 3757.32 | 24631.32 | 24631.32 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 127.58 | Sq.Ft | 150 | 100 | 0 | 0 | 19137 | C+S GST 18% I/P RD | 3444.66 | 22581.66 | 22581.66 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 91.56 | Sq.Ft | 150 | 100 | 0 | 0 | 13734 | C+S GST 18% I/P RD | 2472.12 | 16206.12 | 16206.12 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 140.02 | Sq.Ft | 150 | 100 | 0 | 0 | 21003 | C+S GST 18% I/P RD | 3780.54 | 24783.54 | 24783.54 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 289.6 | Sq.Ft | 140 | 100 | 0 | 0 | 40544 | C+S GST 18% I/P RD | 7297.92 | 47841.92 | 47841.92 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1214 | Sq.Ft | 140 | 100 | 0 | 0 | 6317 | C+S GST 18% I/P RD | 1137.06 | 7454.06 | 7454.06 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 332.6581 | Sq.Ft | 155 | 100 | 0 | 0 | 51562 | C+S GST 18% I/P RD | 9281.16 | 60843.16 | 60843.16 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 587.5871 | Sq.Ft | 155 | 100 | 0 | 0 | 91076 | C+S GST 18% I/P RD | 16393.68 | 107469.68 | 107469.68 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 357.3613 | Sq.Ft | 155 | 100 | 0 | 0 | 55391 | C+S GST 18% I/P RD | 9970.38 | 65361.38 | 65361.38 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 562.8774 | Sq.Ft | 155 | 100 | 0 | 0 | 87246 | C+S GST 18% I/P RD | 15704.28 | 102950.28 | 102950.28 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 587.5871 | Sq.Ft | 155 | 100 | 0 | 0 | 91076 | C+S GST 18% I/P RD | 16393.68 | 107469.68 | 107469.68 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96351 | 24 Sep 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1387 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 290.7484 | Sq.Ft | 155 | 100 | 0 | 0 | 45066 | C+S GST 18% I/P RD | 8111.88 | 53177.88 | 53177.88 | Approved | 0 | 0 | 12205 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96350 | 24 Sep 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 1254 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.75 | Sq.Ft | 160 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 30 | 24 Sep 2022
GANGA DHAM TOWERS | 1170 | 96349 | 24 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1118 | A Fire Fighting 14 Floors | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | 196 | No. | 200 | 100 | 980 | 0 | 39200 | C+S GST 18% I/P RD | 7056 | 46256 | 46256 | Approved | 0 | 0 | 1353 | 24 Sep 2022
GANGA DHAM TOWERS | 1170 | 96349 | 24 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1118 | A Fire Fighting 14 Floors | Sprinkler 15mm 68 dg Pendent (L) | 160 | No. | 90 | 100 | 360 | 0 | 14400 | C+S GST 18% I/P RD | 2592 | 16992 | 16992 | Approved | 0 | 0 | 1353 | 24 Sep 2022
GANGA DHAM TOWERS | 1170 | 96349 | 24 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1118 | A Fire Fighting Extra Items | Sprinkler 15 mm 93 dg Pendent (L) | 36 | No. | 90 | 100 | 81 | 0 | 3240 | C+S GST 18% I/P RD | 583.2 | 3823.2 | 3823.2 | Approved | 0 | 0 | 1353 | 24 Sep 2022
GANGA DHAM TOWERS | 1170 | 96349 | 24 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1118 | A Fire Fighting 14 Floors | Drain Valve 50mm (L) | 36 | No. | 300 | 100 | 0 | 0 | 10800 | C+S GST 18% I/P RD | 1944 | 12744 | 12744 | Approved | 0 | 0 | 1353 | 24 Sep 2022
GANGA DHAM TOWERS | 493 | 96348 | 24 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1253 | D Bldg East Side External Plaster | External Plaster- BC | 2240.8929 | Sq.Ft | 28 | 100 | 1568.63 | 0 | 62745 | C+S GST 18% I/P RD | 11294.1 | 74039.1 | 74039.1 | Approved | 0 | 0 | 1661 | 24 Sep 2022
GANGA DHAM TOWERS | 493 | 96348 | 24 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1253 | D Bldg South Side External Plaster | External Plaster- BC | 1458.4571 | Sq.Ft | 35 | 100 | 1276.15 | 0 | 51046 | C+S GST 18% I/P RD | 9188.28 | 60234.28 | 60234.28 | Approved | 0 | 0 | 1661 | 24 Sep 2022
GANGA DHAM TOWERS | 493 | 96348 | 24 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1253 | D Bldg West Side External Plaster | External Plaster- BC | 894 | Sq.Ft | 35 | 100 | 782.25 | 0 | 31290 | C+S GST 18% I/P RD | 5632.2 | 36922.2 | 36922.2 | Approved | 0 | 0 | 1661 | 24 Sep 2022
GANGA DHAM TOWERS | 493 | 96348 | 24 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1253 | D Bldg West Side External Plaster | External Plaster- BC | 600 | Sq.Ft | 35 | 100 | 525 | 0 | 21000 | C+S GST 18% I/P RD | 3780 | 24780 | 24780 | Approved | 0 | 0 | 1661 | 24 Sep 2022
GANGA DHAM TOWERS | 372 | 96322 | 22 Sep 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR |  | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20 | Sq.Ft | 150 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 |  | 0 | 0 | 30 | 22 Sep 2022
GANGA DHAM TOWERS | 1184 | 96319 | 21 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1018 | A P3 Floor External Sand Face Plaster | External Plaster- BC | 429.64 | Sq.Ft | 20 | 100 | 214.82 | 0 | 8592.8 | CGST 0% URD I/P | 0 | 8592.8 | 8592.8 | Approved | 0 | 0 | 86 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | B - LV Duct -Single coat plaster @ lvl. 99,102.105.108-(Sq.F | Single Coat Plaster (L) | 481.42 | Sq.Ft | 20 | 100 | 240.71 | 0 | 9628.4 | CGST 0% URD I/P | 0 | 9628.4 | 9628.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | A - FIRE Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 608.58 | Sq.Ft | 20 | 100 | 304.29 | 0 | 12171.6 | CGST 0% URD I/P | 0 | 12171.6 | 12171.6 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | B - FIRE Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 208.92 | Sq.Ft | 20 | 100 | 104.46 | 0 | 4178.4 | CGST 0% URD I/P | 0 | 4178.4 | 4178.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | B - SERVICE Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 284.77 | Sq.Ft | 20 | 100 | 142.39 | 0 | 5695.4 | CGST 0% URD I/P | 0 | 5695.4 | 5695.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | A - ELECTRIC Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 512.33 | Sq.Ft | 20 | 100 | 256.17 | 0 | 10246.6 | CGST 0% URD I/P | 0 | 10246.6 | 10246.6 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | B - Duct near Driver space @ lvl.108 & nearby wall | Single Coat Plaster (L) | 249.43 | Sq.Ft | 20 | 100 | 124.72 | 0 | 4988.6 | CGST 0% URD I/P | 0 | 4988.6 | 4988.6 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | B - ELECTRIC Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 387.57 | Sq.Ft | 20 | 100 | 193.79 | 0 | 7751.4 | CGST 0% URD I/P | 0 | 7751.4 | 7751.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | A - SERVICE Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 290.67 | Sq.Ft | 20 | 100 | 145.34 | 0 | 5813.4 | CGST 0% URD I/P | 0 | 5813.4 | 5813.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1306 | 96317 | 21 Sep 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1020 | A - LV Duct -Single coat plaster @ lvl. 99,102.105.108 | Single Coat Plaster (L) | 399.67 | Sq.Ft | 20 | 100 | 199.84 | 0 | 7993.4 | CGST 0% URD I/P | 0 | 7993.4 | 7993.4 | Approved | 0 | 0 | 685 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96316 | 21 Sep 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1123 | Laser Jali removing & barricading towards Main Road | Fabrication work (L) | 138.24 | Kgs | 15 | 100 | 51.84 | 0 | 2073.6 | CGST 0% URD I/P | 0 | 2073.6 | 2073.6 | Approved | 0 | 0 | 162 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96316 | 21 Sep 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1123 | Laser Jali removing & barricading towards Main Road | G.I. Sheet Removing - SOI | 1280 | Sq.Ft | 2.5 | 100 | 0 | 0 | 3200 | CGST 0% URD I/P | 0 | 3200 | 3200 | Approved | 0 | 0 | 162 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96316 | 21 Sep 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1123 | Laser Jali removing & barricading towards Main Road | Panel Removing | 3 | No. | 800 | 100 | 0 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 162 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96316 | 21 Sep 2022 |  | PATILS FABRICATORS | PARTH ENTERPRISES | EV - 1123 | Laser Jali removing & barricading towards Main Road | G.I. Sheet Fixing - SOI | 1710 | Sq.Ft | 5 | 100 | 213.75 | 0 | 8550 | CGST 0% URD I/P | 0 | 8550 | 8550 | Approved | 0 | 0 | 162 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96315 | 21 Sep 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1456 | Laser Jali removing & barricading towards Main Road | G.I. Sheet Fixing - SOI | 472.57 | Sq.Ft | 5 | 100 | 59.07 | 0 | 2362.85 | C+S GST 18% I/P RD | 425.32 | 2788.17 | 2788.17 | Approved | 0 | 0 | 108 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96315 | 21 Sep 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1456 | Laser Jali removing & barricading towards Main Road | Panel Fixing (L) | 5 | No. | 1000 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 108 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96315 | 21 Sep 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1456 | Laser Jali removing & barricading towards Main Road | MS Square Pipe (L) | 51.24 | Kgs | 15 | 100 | 19.22 | 0 | 768.6 | C+S GST 18% I/P RD | 138.34 | 906.94 | 906.94 | Approved | 0 | 0 | 108 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96315 | 21 Sep 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1456 | Laser Jali removing & barricading towards Main Road | G.I. Sheet Removing - SOI | 472.57 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1181.43 | C+S GST 18% I/P RD | 212.66 | 1394.09 | 1394.09 | Approved | 0 | 0 | 108 | 21 Sep 2022
GANGA DHAM TOWERS | 1416 | 96315 | 21 Sep 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 1456 | Laser Jali removing & barricading towards Main Road | Lumpsum work- DCW | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 108 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 4" BCE | 21 | No. | 210 | 100 | 110.25 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 4" BCE | 11 | No. | 210 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 3" BCE | 20 | No. | 210 | 100 | 105 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 3" BCE | 3 | No. | 210 | 100 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 3" BCE | 20 | No. | 210 | 100 | 105 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting Work 5" BCE | 9 | No. | 210 | 100 | 47.25 | 0 | 1890 | C+S GST 18% I/P RD | 340.2 | 2230.2 | 2230.2 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting rate diff.- BC | 27 | No. | 90 | 100 | 0 | 0 | 2430 | C+S GST 18% I/P RD | 437.4 | 2867.4 | 2867.4 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting rate diff.- BC | 3 | No. | 90 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 885 | 96311 | 21 Sep 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1473 | D Beam Core Cutting | Core Cutting rate diff.- BC | 4 | No. | 90 | 100 | 0 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 207 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.65 | No. | 41490 | 35 | 235.97 | 0 | 9438.98 | C+S GST 18% I/P RD | 1699.02 | 11138 | 11138 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2704 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 46389 | 35 | 405.9 | 0 | 16236.15 | C+S GST 18% I/P RD | 2922.5 | 19158.65 | 19158.65 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.35 | No. | 46389 | 35 | 142.07 | 0 | 5682.65 | C+S GST 18% I/P RD | 1022.88 | 6705.53 | 6705.53 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.65 | No. | 46389 | 35 | 263.84 | 0 | 10553.5 | C+S GST 18% I/P RD | 1899.64 | 12453.14 | 12453.14 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.35 | No. | 47964 | 35 | 146.89 | 0 | 5875.59 | C+S GST 18% I/P RD | 1057.6 | 6933.19 | 6933.19 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.65 | No. | 47964 | 35 | 272.8 | 0 | 10911.81 | C+S GST 18% I/P RD | 1964.12 | 12875.93 | 12875.93 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1118 | 96310 | 21 Sep 2022 |  | VAISHALI ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1127 | A 2703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.35 | No. | 41490 | 35 | 127.06 | 0 | 5082.53 | C+S GST 18% I/P RD | 914.86 | 5997.39 | 5997.39 | Approved | 0 | 0 | 1276 | 21 Sep 2022
GANGA DHAM TOWERS | 1186 | 96309 | 21 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1022 | A & B Ground Floor Parking Gutter For Trimix Flooring - 82 | Gutter making | 135 | R.Ft | 56 | 100 | 189 | 0 | 7560 | CGST 0% URD I/P | 0 | 7560 | 7560 | Approved | 0 | 0 | 412 | 21 Sep 2022
GANGA DHAM TOWERS | 1186 | 96309 | 21 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1022 | A & B Parking Floor 3 Gutter For Trimix Flooring | Gutter making | 354.6 | R.Ft | 56 | 100 | 496.44 | 0 | 19857.6 | CGST 0% URD I/P | 0 | 19857.6 | 19857.6 | Approved | 0 | 0 | 412 | 21 Sep 2022
GANGA DHAM TOWERS | 1186 | 96309 | 21 Sep 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1022 | A & B Parking Floor 1 Gutter For Trimix Flooring | Gutter making | 245.75 | R.Ft | 56 | 100 | 344.05 | 0 | 13762 | CGST 0% URD I/P | 0 | 13762 | 13762 | Approved | 0 | 0 | 412 | 21 Sep 2022
GANGA DHAM TOWERS | 1366 | 96306 | 20 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1156 | Tower C Safety work | Barricating Work (L) - SO | 255.96 | Kgs | 12 | 100 | 76.79 | 0 | 3071.52 | CGST 0% URD I/P | 0 | 3071.52 | 3071.52 | Approved | 0 | 0 | 31 | 20 Sep 2022
GANGA DHAM TOWERS | 227 | 96296 | 20 Sep 2022 |  | MAHALAXMI ENTERPRISES | AVCON TECHNICS PVT LTD | EV - 1366 | A Bldg Tie Beams - 4th To 5th Slab Rebaring Work | Rebarring work 16mm dia- BRE | 53.8462 | No. | 130 | 100 | 175 | 0 | 7000.01 | C+S GST 18% I/P RD | 1260 | 8260.01 | 8260.01 | Approved | 0 | 0 | 140 | 20 Sep 2022
GANGA DHAM TOWERS | 473 | 96292 | 19 Sep 2022 |  | ARYA CONSULTANCY | ARYA CONSULTANCY | EV - 970 | Electricity Infrastructure | Elect Meters Installation (L)-UTI | 256.5 | No. | 3500 | 30 | 0 | 0 | 269325 | C+S GST 18% I/P RD | 48478.5 | 317803.5 | 317803.5 | Approved | 0 | 0 | 26933 | 19 Sep 2022
GANGA DHAM TOWERS | 1411 | 96291 | 19 Sep 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 971 | A Bldg Misc. Tile Repair Work | Tiling work lumpsum BC | 1 | No. | 50410 | 100 | 0 | 0 | 50410 | C+S GST 18% I/P RD | 9073.8 | 59483.8 | 59483.8 | Approved | 0 | 0 | 504 | 19 Sep 2022
GANGA DHAM TOWERS | 522 | 96267 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1024 | B Bldg 2101 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 5 | No. | 1500 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 199 | 15 Sep 2022
GANGA DHAM TOWERS | 522 | 96267 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1024 | B Bldg 2401 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 4 | No. | 1650 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 199 | 15 Sep 2022
GANGA DHAM TOWERS | 522 | 96267 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1024 | B Bldg 2001 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 3.5 | No. | 1650 | 100 | 144.38 | 0 | 5775 | CGST 0% URD I/P | 0 | 5775 | 5775 | Approved | 0 | 0 | 199 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 34.7895 | Sq.Ft | 19 | 100 | 66.1 | 0 | 661 | CGST 0% URD I/P | 0 | 661 | 661 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222.9474 | Sq.Ft | 19 | 100 | 423.6 | 0 | 4236 | CGST 0% URD I/P | 0 | 4236 | 4236 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 602 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222.9474 | Sq.Ft | 19 | 100 | 423.6 | 0 | 4236 | CGST 0% URD I/P | 0 | 4236 | 4236 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2302 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2202 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 602 Chemical & IPS Waterproofing | IPS W/P | 222.9091 | Sq.Ft | 11 | 100 | 245.2 | 0 | 2452 | CGST 0% URD I/P | 0 | 2452 | 2452 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2302 Chemical & IPS Waterproofing | IPS W/P | 165 | Sq.Ft | 11 | 100 | 181.5 | 0 | 1815 | CGST 0% URD I/P | 0 | 1815 | 1815 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2402 Chemical & IPS Waterproofing | IPS W/P | 222.9091 | Sq.Ft | 11 | 100 | 245.2 | 0 | 2452 | CGST 0% URD I/P | 0 | 2452 | 2452 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Chemical & IPS Waterproofing | IPS W/P | 287.5455 | Sq.Ft | 11 | 100 | 316.3 | 0 | 3163 | CGST 0% URD I/P | 0 | 3163 | 3163 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1402 Chemical & IPS Waterproofing | IPS W/P | 222.9091 | Sq.Ft | 11 | 100 | 245.2 | 0 | 2452 | CGST 0% URD I/P | 0 | 2452 | 2452 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 502 Chemical & IPS Waterproofing | IPS W/P | 165 | Sq.Ft | 11 | 100 | 181.5 | 0 | 1815 | CGST 0% URD I/P | 0 | 1815 | 1815 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2102 Chemical & IPS Waterproofing | IPS W/P | 165 | Sq.Ft | 11 | 100 | 181.5 | 0 | 1815 | CGST 0% URD I/P | 0 | 1815 | 1815 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2202 Chemical & IPS Waterproofing | IPS W/P | 222.9091 | Sq.Ft | 11 | 100 | 245.2 | 0 | 2452 | CGST 0% URD I/P | 0 | 2452 | 2452 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 702 Chemical & IPS Waterproofing | IPS W/P | 165 | Sq.Ft | 11 | 100 | 181.5 | 0 | 1815 | CGST 0% URD I/P | 0 | 1815 | 1815 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Chemical & IPS Waterproofing | IPS W/P | 360.1818 | Sq.Ft | 11 | 100 | 396.2 | 0 | 3962 | CGST 0% URD I/P | 0 | 3962 | 3962 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1702 Chemical & IPS Waterproofing | IPS W/P | 165 | Sq.Ft | 11 | 100 | 181.5 | 0 | 1815 | CGST 0% URD I/P | 0 | 1815 | 1815 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1802 Chemical & IPS Waterproofing | IPS W/P | 222.9091 | Sq.Ft | 11 | 100 | 245.2 | 0 | 2452 | CGST 0% URD I/P | 0 | 2452 | 2452 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1702 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2402 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1402 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 702 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 26 | No. | 70 | 100 | 182 | 0 | 1820 | CGST 0% URD I/P | 0 | 1820 | 1820 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2202 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 23 | No. | 70 | 100 | 161 | 0 | 1610 | CGST 0% URD I/P | 0 | 1610 | 1610 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2302 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1802 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2202 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222.9474 | Sq.Ft | 19 | 100 | 423.6 | 0 | 4236 | CGST 0% URD I/P | 0 | 4236 | 4236 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1802 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222.9474 | Sq.Ft | 19 | 100 | 423.6 | 0 | 4236 | CGST 0% URD I/P | 0 | 4236 | 4236 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2302 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222.9474 | Sq.Ft | 19 | 100 | 423.6 | 0 | 4236 | CGST 0% URD I/P | 0 | 4236 | 4236 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1702 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 360.2105 | Sq.Ft | 19 | 100 | 684.4 | 0 | 6844 | CGST 0% URD I/P | 0 | 6844 | 6844 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 702 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 252.7368 | Sq.Ft | 19 | 100 | 480.2 | 0 | 4802 | CGST 0% URD I/P | 0 | 4802 | 4802 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 502 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2402 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 502 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1802 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 602 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1402 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 1702 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 702 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 498 | 96266 | 15 Sep 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1023 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 986 | 15 Sep 2022
GANGA DHAM TOWERS | 1296 | 96222 | 12 Sep 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1029 | Miscellaneous expenses | Marketing Operating Expenses | 9.9342 | Month | 25000 | 8.33 | 0 | 0 | 20688 | C+S GST 0% I/P RD | 0 | 20688 | 20688 | Approved | 0 | 0 | 207 | 12 Sep 2022
GANGA DHAM TOWERS | 1052 | 96219 | 12 Sep 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 965 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 12 Sep 2022
GANGA DHAM TOWERS | 1383 | 96215 | 12 Sep 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 964 | Professional Consultancy (Finalcial) | Professional Fees | 1 | Month | 116666.666 | 100 | 0 | 0 | 116666.67 | C+S GST 0% I/P RD | 0 | 116666.67 | 116666.67 | Approved | 0 | 0 | 11667 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 17 | 100 | 10.5 | 0 | 419.99 | C+S GST 18% I/P RD | 75.6 | 495.59 | 495.59 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 17 | 100 | 8.52 | 0 | 340.88 | C+S GST 18% I/P RD | 61.36 | 402.24 | 402.24 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 17 | 100 | 8.52 | 0 | 340.88 | C+S GST 18% I/P RD | 61.36 | 402.24 | 402.24 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 73.431 | Sq.Ft | 17 | 100 | 31.21 | 0 | 1248.33 | C+S GST 18% I/P RD | 224.7 | 1473.03 | 1473.03 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 17 | 100 | 18.53 | 0 | 741.13 | C+S GST 18% I/P RD | 133.4 | 874.53 | 874.53 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 1 Vitrified Flooring | Vitrified Flooring -BC | 52.506 | Sq.Ft | 17 | 100 | 22.32 | 0 | 892.6 | C+S GST 18% I/P RD | 160.66 | 1053.26 | 1053.26 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 17 | 100 | 21.7 | 0 | 867.97 | C+S GST 18% I/P RD | 156.24 | 1024.21 | 1024.21 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 2202 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 24.147 | R.Ft | 55 | 100 | 33.2 | 0 | 1328.09 | C+S GST 18% I/P RD | 239.06 | 1567.15 | 1567.15 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 2102 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 20.394 | R.Ft | 55 | 100 | 28.04 | 0 | 1121.67 | C+S GST 18% I/P RD | 201.9 | 1323.57 | 1323.57 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 2302 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 20.394 | R.Ft | 55 | 100 | 28.04 | 0 | 1121.67 | C+S GST 18% I/P RD | 201.9 | 1323.57 | 1323.57 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 702 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.394 | R.Ft | 45 | 100 | 22.94 | 0 | 917.73 | C+S GST 18% I/P RD | 165.2 | 1082.93 | 1082.93 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1902 Granite kitchen otta | Granite Kitchen Otta BC | 17.415 | R.Ft | 375 | 100 | 163.27 | 0 | 6530.63 | C+S GST 18% I/P RD | 1175.52 | 7706.15 | 7706.15 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Guest Toilet Dado - 1 No. | Dado BC | 168.732 | Sq.Ft | 22 | 100 | 92.8 | 0 | 3712.1 | C+S GST 18% I/P RD | 668.18 | 4380.28 | 4380.28 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1701 StaffToilet Dado - 1 No. | Dado BC | 136.34 | Sq.Ft | 21 | 100 | 71.58 | 0 | 2863.14 | C+S GST 18% I/P RD | 515.36 | 3378.5 | 3378.5 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Powder Toilet Dado - 1 No. | Dado BC | 96.129 | Sq.Ft | 22 | 100 | 52.87 | 0 | 2114.84 | C+S GST 18% I/P RD | 380.68 | 2495.52 | 2495.52 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Master Toilet Dado - 1 No. | Dado BC | 212.688 | Sq.Ft | 22 | 100 | 116.98 | 0 | 4679.14 | C+S GST 18% I/P RD | 842.24 | 5521.38 | 5521.38 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Parents Toilet Dado - 1 No. | Dado BC | 132.867 | Sq.Ft | 22 | 100 | 73.08 | 0 | 2923.07 | C+S GST 18% I/P RD | 526.16 | 3449.23 | 3449.23 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Guest Toilet Dado - 1 No. | Dado BC | 35.604 | Sq.Ft | 24 | 100 | 21.36 | 0 | 854.5 | C+S GST 18% I/P RD | 153.82 | 1008.32 | 1008.32 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 502 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.394 | R.Ft | 40 | 100 | 20.39 | 0 | 815.76 | C+S GST 18% I/P RD | 146.84 | 962.6 | 962.6 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1701 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 21 | 100 | 10.53 | 0 | 421.09 | C+S GST 18% I/P RD | 75.8 | 496.89 | 496.89 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 801 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 700 | 100 | 110.78 | 0 | 4431 | C+S GST 18% I/P RD | 797.58 | 5228.58 | 5228.58 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 801 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 5.08 | R.Ft | 700 | 100 | 88.9 | 0 | 3556 | C+S GST 18% I/P RD | 640.08 | 4196.08 | 4196.08 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1202 Granite kitchen otta | Granite Kitchen Otta BC | 17.415 | R.Ft | 325 | 100 | 141.5 | 0 | 5659.88 | C+S GST 18% I/P RD | 1018.78 | 6678.66 | 6678.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1002 Granite kitchen otta - | Granite Kitchen Otta BC | 17.415 | R.Ft | 325 | 100 | 141.5 | 0 | 5659.88 | C+S GST 18% I/P RD | 1018.78 | 6678.66 | 6678.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 102 Granite kitchen otta | Granite Kitchen Otta BC | 17.415 | R.Ft | 300 | 100 | 130.61 | 0 | 5224.5 | C+S GST 18% I/P RD | 940.42 | 6164.92 | 6164.92 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 402 Granite kitchen otta - | Granite Kitchen Otta BC | 17.415 | R.Ft | 300 | 100 | 130.61 | 0 | 5224.5 | C+S GST 18% I/P RD | 940.42 | 6164.92 | 6164.92 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1102 Granite kitchen otta- - | Granite Kitchen Otta BC | 17.415 | R.Ft | 325 | 100 | 141.5 | 0 | 5659.88 | C+S GST 18% I/P RD | 1018.78 | 6678.66 | 6678.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 902 Granite kitchen otta | Granite Kitchen Otta BC | 17.415 | R.Ft | 325 | 100 | 141.5 | 0 | 5659.88 | C+S GST 18% I/P RD | 1018.78 | 6678.66 | 6678.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 2001 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 470 | Sq.Ft | 60 | 100 | 705 | 0 | 28200 | C+S GST 18% I/P RD | 5076 | 33276 | 33276 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1502Granite kitchen otta | Granite Kitchen Otta BC | 17.415 | R.Ft | 350 | 100 | 152.38 | 0 | 6095.25 | C+S GST 18% I/P RD | 1097.14 | 7192.39 | 7192.39 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1302 Granite kitchen otta - | Granite Kitchen Otta BC | 17.415 | R.Ft | 350 | 100 | 152.38 | 0 | 6095.25 | C+S GST 18% I/P RD | 1097.14 | 7192.39 | 7192.39 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Parents Toilet Dado | Dado BC | 68.121 | Sq.Ft | 20 | 100 | 34.06 | 0 | 1362.42 | C+S GST 18% I/P RD | 245.24 | 1607.66 | 1607.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Powder Toilet Dado | Dado BC | 35.604 | Sq.Ft | 20 | 100 | 17.8 | 0 | 712.08 | C+S GST 18% I/P RD | 128.18 | 840.26 | 840.26 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 1 Dado | Dado BC | 36.792 | Sq.Ft | 20 | 100 | 18.4 | 0 | 735.84 | C+S GST 18% I/P RD | 132.46 | 868.3 | 868.3 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Master Toilet Dado | Dado BC | 125.838 | Sq.Ft | 18 | 100 | 56.63 | 0 | 2265.08 | C+S GST 18% I/P RD | 407.72 | 2672.8 | 2672.8 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Guest Toilet Dado | Dado BC | 168.732 | Sq.Ft | 18 | 100 | 75.93 | 0 | 3037.18 | C+S GST 18% I/P RD | 546.7 | 3583.88 | 3583.88 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Powder Toilet Dado | Dado BC | 96.129 | Sq.Ft | 18 | 100 | 43.26 | 0 | 1730.32 | C+S GST 18% I/P RD | 311.46 | 2041.78 | 2041.78 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Master Toilet Dado | Dado BC | 212.688 | Sq.Ft | 18 | 100 | 95.71 | 0 | 3828.38 | C+S GST 18% I/P RD | 689.1 | 4517.48 | 4517.48 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Children Toilet 2 Dado | Dado BC | 153.162 | Sq.Ft | 18 | 100 | 68.92 | 0 | 2756.92 | C+S GST 18% I/P RD | 496.24 | 3253.16 | 3253.16 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 1 Dado | Dado BC | 171.153 | Sq.Ft | 18 | 100 | 77.02 | 0 | 3080.75 | C+S GST 18% I/P RD | 554.54 | 3635.29 | 3635.29 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Parents Toilet Dado | Dado BC | 132.867 | Sq.Ft | 18 | 100 | 59.79 | 0 | 2391.61 | C+S GST 18% I/P RD | 430.48 | 2822.09 | 2822.09 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Powder Toilet Dado | Dado BC | 96.129 | Sq.Ft | 18 | 100 | 43.26 | 0 | 1730.32 | C+S GST 18% I/P RD | 311.46 | 2041.78 | 2041.78 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Parents Toilet Dado | Dado BC | 132.867 | Sq.Ft | 18 | 100 | 59.79 | 0 | 2391.61 | C+S GST 18% I/P RD | 430.48 | 2822.09 | 2822.09 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Guest Toilet Dado | Dado BC | 168.732 | Sq.Ft | 18 | 100 | 75.93 | 0 | 3037.18 | C+S GST 18% I/P RD | 546.7 | 3583.88 | 3583.88 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 2 Dado | Dado BC | 153.162 | Sq.Ft | 18 | 100 | 68.92 | 0 | 2756.92 | C+S GST 18% I/P RD | 496.24 | 3253.16 | 3253.16 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1402 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 24.147 | R.Ft | 50 | 100 | 30.18 | 0 | 1207.35 | C+S GST 18% I/P RD | 217.32 | 1424.67 | 1424.67 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1802 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 24.147 | R.Ft | 50 | 100 | 30.18 | 0 | 1207.35 | C+S GST 18% I/P RD | 217.32 | 1424.67 | 1424.67 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Parents Toilet Dado - 1 No. | Dado BC | 68.121 | Sq.Ft | 24 | 100 | 40.87 | 0 | 1634.9 | C+S GST 18% I/P RD | 294.28 | 1929.18 | 1929.18 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Master Toilet Dado - 1 No. | Dado BC | 43.911 | Sq.Ft | 24 | 100 | 26.35 | 0 | 1053.86 | C+S GST 18% I/P RD | 189.7 | 1243.56 | 1243.56 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Powder Toilet Dado - 1 No. | Dado BC | 35.604 | Sq.Ft | 24 | 100 | 21.36 | 0 | 854.5 | C+S GST 18% I/P RD | 153.82 | 1008.32 | 1008.32 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 88.353 | Sq.Ft | 21 | 100 | 46.39 | 0 | 1855.41 | C+S GST 18% I/P RD | 333.98 | 2189.39 | 2189.39 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 21 | 100 | 26.8 | 0 | 1072.2 | C+S GST 18% I/P RD | 193 | 1265.2 | 1265.2 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 21 | 100 | 12.97 | 0 | 518.81 | C+S GST 18% I/P RD | 93.38 | 612.19 | 612.19 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1601 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 21 | 100 | 22.89 | 0 | 915.52 | C+S GST 18% I/P RD | 164.8 | 1080.32 | 1080.32 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 StaffToilet Dado | Dado BC | 122.706 | Sq.Ft | 17 | 100 | 52.15 | 0 | 2086 | C+S GST 18% I/P RD | 375.48 | 2461.48 | 2461.48 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 StaffToilet Dado | Dado BC | 122.706 | Sq.Ft | 17 | 100 | 52.15 | 0 | 2086 | C+S GST 18% I/P RD | 375.48 | 2461.48 | 2461.48 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Guest Toilet Dado | Dado BC | 35.604 | Sq.Ft | 20 | 100 | 17.8 | 0 | 712.08 | C+S GST 18% I/P RD | 128.18 | 840.26 | 840.26 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Powder Toilet Dado | Dado BC | 35.604 | Sq.Ft | 20 | 100 | 17.8 | 0 | 712.08 | C+S GST 18% I/P RD | 128.18 | 840.26 | 840.26 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Master Toilet Dado | Dado BC | 43.911 | Sq.Ft | 20 | 100 | 21.96 | 0 | 878.22 | C+S GST 18% I/P RD | 158.08 | 1036.3 | 1036.3 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 2 Dado | Dado BC | 24.174 | Sq.Ft | 20 | 100 | 12.09 | 0 | 483.48 | C+S GST 18% I/P RD | 87.02 | 570.5 | 570.5 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Children Toilet 2 Dado | Dado BC | 24.174 | Sq.Ft | 20 | 100 | 12.09 | 0 | 483.48 | C+S GST 18% I/P RD | 87.02 | 570.5 | 570.5 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Guest Toilet Dado | Dado BC | 35.604 | Sq.Ft | 20 | 100 | 17.8 | 0 | 712.08 | C+S GST 18% I/P RD | 128.18 | 840.26 | 840.26 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Master Toilet Dado | Dado BC | 85.446 | Sq.Ft | 20 | 100 | 42.72 | 0 | 1708.92 | C+S GST 18% I/P RD | 307.6 | 2016.52 | 2016.52 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Parents Toilet Dado | Dado BC | 68.121 | Sq.Ft | 20 | 100 | 34.06 | 0 | 1362.42 | C+S GST 18% I/P RD | 245.24 | 1607.66 | 1607.66 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 88.353 | Sq.Ft | 17 | 100 | 37.55 | 0 | 1502 | C+S GST 18% I/P RD | 270.36 | 1772.36 | 1772.36 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Children Toile 2 Vitrified Flooring | Vitrified Flooring -BC | 41.175 | Sq.Ft | 17 | 100 | 17.5 | 0 | 699.98 | C+S GST 18% I/P RD | 126 | 825.98 | 825.98 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Children Toilet 2 Vitrified Flooring | Vitrified Flooring -BC | 41.175 | Sq.Ft | 17 | 100 | 17.5 | 0 | 699.98 | C+S GST 18% I/P RD | 126 | 825.98 | 825.98 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 17 | 100 | 18.53 | 0 | 741.13 | C+S GST 18% I/P RD | 133.4 | 874.53 | 874.53 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1101 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 17 | 100 | 21.7 | 0 | 867.97 | C+S GST 18% I/P RD | 156.24 | 1024.21 | 1024.21 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 758 | 96212 | 12 Sep 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 948 | B 1001 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 17 | 100 | 10.5 | 0 | 419.99 | C+S GST 18% I/P RD | 75.6 | 495.59 | 495.59 | Approved | 0 | 0 | 1740 | 12 Sep 2022
GANGA DHAM TOWERS | 495 | 96210 | 12 Sep 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 976 | B 1201 Gypsum Plaster | Gypsum on Wall (L) | 800 | Sq.Ft | 4 | 100 | 80 | 0 | 3200 | C+S GST 18% I/P RD | 576 | 3776 | 3776 | Approved | 0 | 0 | 81 | 12 Sep 2022
GANGA DHAM TOWERS | 495 | 96210 | 12 Sep 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 976 | B 601 Gypsum Plaster (Refuge Flat) | Gypsum on Wall (L) | 930 | Sq.Ft | 4 | 100 | 93 | 0 | 3720 | C+S GST 18% I/P RD | 669.6 | 4389.6 | 4389.6 | Approved | 0 | 0 | 81 | 12 Sep 2022
GANGA DHAM TOWERS | 495 | 96210 | 12 Sep 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 976 | B 201 Gypsum Plaster | Gypsum on Wall (L) | 300 | Sq.Ft | 4 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 81 | 12 Sep 2022
GANGA DHAM TOWERS | 1405 | 96209 | 12 Sep 2022 |  | AVCON TECHNICS PVT LTD | SAROJ KUMAR PRADHAN | EV - 1170 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 34.2857 | No. | 700 | 100 | 0 | 0 | 24000 | CGST 0% URD I/P | 0 | 24000 | 24000 | Approved | 0 | 0 | 670 | 12 Sep 2022
GANGA DHAM TOWERS | 1405 | 96209 | 12 Sep 2022 |  | AVCON TECHNICS PVT LTD | SAROJ KUMAR PRADHAN | EV - 1170 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 30.7143 | No. | 700 | 100 | 0 | 0 | 21500 | CGST 0% URD I/P | 0 | 21500 | 21500 | Approved | 0 | 0 | 670 | 12 Sep 2022
GANGA DHAM TOWERS | 1405 | 96209 | 12 Sep 2022 |  | AVCON TECHNICS PVT LTD | SAROJ KUMAR PRADHAN | EV - 1170 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting 6" BCE | 30.7143 | No. | 700 | 100 | 0 | 0 | 21500 | CGST 0% URD I/P | 0 | 21500 | 21500 | Approved | 0 | 0 | 670 | 12 Sep 2022
GANGA DHAM TOWERS | 1268 | 96198 | 10 Sep 2022 |  | R.T.S. STEEL SERVICES | R.T.S. STEEL SERVICES | EV - 1087 | C Sample Flat MS Work | Fabrication Work (M) - BCo | 987.28 | Kgs | 63.5 | 100 | 1567.31 | 0 | 62692.28 | C+S GST 18% I/P RD | 11284.62 | 73976.9 | 73976.9 | Approved | 0 | 0 | 627 | 10 Sep 2022
GANGA DHAM TOWERS | 1267 | 96189 | 10 Sep 2022 |  | R.T.S. STEEL SERVICES | R.T.S. STEEL SERVICES | EV - 1086 | C Sample Flat MS Work | Fabrication Work (L) - BCo | 987.28 | Kgs | 17 | 100 | 419.59 | 0 | 16783.76 | C+S GST 18% I/P RD | 3021.08 | 19804.84 | 19804.84 | Approved | 0 | 0 | 168 | 10 Sep 2022
GANGA DHAM TOWERS | 1171 | 96185 | 09 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1047 | Towerr A& B Parking 1 Fire Fighting | Sprinkler 15mm 68 dg Upright (M) | 600 | No. | 229 | 100 | 0 | 0 | 137400 | C+S GST 18% I/P RD | 24732 | 162132 | 162132 | Approved | 0 | 0 | 0 | 09 Sep 2022
GANGA DHAM TOWERS | 1398 | 96184 | 09 Sep 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1050 | Labour Camp making | MS Angle 50 x 50 x 5mm | 656.735 | Kgs | 14 | 100 | 229.86 | 0 | 9194.29 | C+S GST 18% I/P RD | 1654.98 | 10849.27 | 10849.27 | Approved | 0 | 0 | 221 | 09 Sep 2022
GANGA DHAM TOWERS | 1398 | 96184 | 09 Sep 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1050 | Labour Camp making | M.S. Door -BCo | 8 | No. | 800 | 100 | 0 | 0 | 6400 | C+S GST 18% I/P RD | 1152 | 7552 | 7552 | Approved | 0 | 0 | 221 | 09 Sep 2022
GANGA DHAM TOWERS | 1398 | 96184 | 09 Sep 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 1050 | Labour Camp making | G.I. Sheet Fixing - BC | 1308 | Sq.Ft | 5 | 100 | 163.5 | 0 | 6540 | C+S GST 18% I/P RD | 1177.2 | 7717.2 | 7717.2 | Approved | 0 | 0 | 221 | 09 Sep 2022
GANGA DHAM TOWERS | 1173 | 96183 | 09 Sep 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 958 | Tower A& B Parking 3 Fire Fighting | Sprinkler 15mm 68 dg Upright (M) | 500 | No. | 229 | 100 | 0 | 0 | 114500 | C+S GST 18% I/P RD | 20610 | 135110 | 135110 | Approved | 0 | 0 | 0 | 09 Sep 2022
GANGA DHAM TOWERS | 1312 | 96158 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 984 | D1202 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 2 | 100 | 71.2 | 0 | 712 | CGST 0% URD I/P | 0 | 712 | 712 | Approved | 0 | 0 | 7 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D703 Chemical Grouting | Chemical Grouting.- BC | 328 | Sq.Ft | 1 | 100 | 32.8 | 0 | 328 | CGST 0% URD I/P | 0 | 328 | 328 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D1002 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D802 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D702 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D603 Chemical Grouting | Chemical Grouting.- BC | 328 | Sq.Ft | 1 | 100 | 32.8 | 0 | 328 | CGST 0% URD I/P | 0 | 328 | 328 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D902 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D1102 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D504 Chemical Grouting | Chemical Grouting.- BC | 328 | Sq.Ft | 1 | 100 | 32.8 | 0 | 328 | CGST 0% URD I/P | 0 | 328 | 328 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 653 | 96157 | 08 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 985 | D604 Chemical Grouting | Chemical Grouting.- BC | 328 | Sq.Ft | 1 | 100 | 32.8 | 0 | 328 | CGST 0% URD I/P | 0 | 328 | 328 | Approved | 0 | 0 | 31 | 08 Sep 2022
GANGA DHAM TOWERS | 401 | 96144 | 07 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 944 | A 2301 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 211 | Sq.Ft | 19 | 100 | 400.9 | 0 | 4009 | CGST 0% URD I/P | 0 | 4009 | 4009 | Approved | 0 | 0 | 81 | 07 Sep 2022
GANGA DHAM TOWERS | 401 | 96144 | 07 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 944 | A 1004 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 215 | Sq.Ft | 19 | 100 | 408.5 | 0 | 4085 | CGST 0% URD I/P | 0 | 4085 | 4085 | Approved | 0 | 0 | 81 | 07 Sep 2022
GANGA DHAM TOWERS | 178 | 96141 | 06 Sep 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1357 | Sales office Garden Maintenance | Garden work. | 60.9994 | Day | 407.25 | 100 | 0 | 0 | 24842 | C+S GST 18% I/P RD | 4471.56 | 29313.56 | 29313.56 | Approved | 0 | 0 | 248 | 06 Sep 2022
GANGA DHAM TOWERS | 401 | 96139 | 06 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 945 | A 103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 133 | Sq.Ft | 19 | 100 | 252.7 | 0 | 2527 | CGST 0% URD I/P | 0 | 2527 | 2527 | Approved | 0 | 0 | 136 | 06 Sep 2022
GANGA DHAM TOWERS | 401 | 96139 | 06 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 945 | A 203 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 138 | Sq.Ft | 19 | 100 | 262.2 | 0 | 2622 | CGST 0% URD I/P | 0 | 2622 | 2622 | Approved | 0 | 0 | 136 | 06 Sep 2022
GANGA DHAM TOWERS | 401 | 96139 | 06 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 945 | A 2401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 229 | Sq.Ft | 19 | 100 | 435.1 | 0 | 4351 | CGST 0% URD I/P | 0 | 4351 | 4351 | Approved | 0 | 0 | 136 | 06 Sep 2022
GANGA DHAM TOWERS | 401 | 96139 | 06 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 945 | A 104 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 217 | Sq.Ft | 19 | 100 | 412.3 | 0 | 4123 | CGST 0% URD I/P | 0 | 4123 | 4123 | Approved | 0 | 0 | 136 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Welding work for Aluform | 3732 | R. Inch | 14 | 100 | 1306.2 | 0 | 52248 | CGST 0% URD I/P | 0 | 52248 | 52248 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Welding work for Aluform | 128 | R. Inch | 14 | 100 | 44.8 | 0 | 1792 | CGST 0% URD I/P | 0 | 1792 | 1792 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Welding work for Aluform | 1434 | R. Inch | 14 | 100 | 501.9 | 0 | 20076 | CGST 0% URD I/P | 0 | 20076 | 20076 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Cutting work for Aluform | 288 | R. Inch | 1.5 | 100 | 10.8 | 0 | 432 | CGST 0% URD I/P | 0 | 432 | 432 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Cutting work for Aluform | 3409 | R. Inch | 1.5 | 100 | 127.84 | 0 | 5113.5 | CGST 0% URD I/P | 0 | 5113.5 | 5113.5 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1392 | 96137 | 06 Sep 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 1025 | A- Aluform Modification Work | Cutting work for Aluform | 2398 | R. Inch | 1.5 | 100 | 89.93 | 0 | 3597 | CGST 0% URD I/P | 0 | 3597 | 3597 | Approved | 0 | 0 | 833 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Welding work for Aluform | 2100 | R. Inch | 14 | 100 | 735 | 0 | 29400 | C+S GST 18% I/P RD | 5292 | 34692 | 34692 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Welding work for Aluform | 1055 | R. Inch | 14 | 100 | 369.25 | 0 | 14770 | C+S GST 18% I/P RD | 2658.6 | 17428.6 | 17428.6 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Welding work for Aluform | 454 | R. Inch | 14 | 100 | 158.9 | 0 | 6356 | C+S GST 18% I/P RD | 1144.08 | 7500.08 | 7500.08 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Cutting work for Aluform | 2841 | R. Inch | 1.5 | 100 | 106.54 | 0 | 4261.5 | C+S GST 18% I/P RD | 767.08 | 5028.58 | 5028.58 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Cutting work for Aluform | 434 | R. Inch | 1.5 | 100 | 16.28 | 0 | 651 | C+S GST 18% I/P RD | 117.18 | 768.18 | 768.18 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 1326 | 96136 | 06 Sep 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 986 | A- Aluform Modification Work | Cutting work for Aluform | 256 | R. Inch | 1.5 | 100 | 9.6 | 0 | 384 | C+S GST 18% I/P RD | 69.12 | 453.12 | 453.12 | Approved | 0 | 0 | 558 | 06 Sep 2022
GANGA DHAM TOWERS | 149 | 96134 | 06 Sep 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 969 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3868 | No. | 4 | 100 | 0 | 0 | 15472 | CGST 0% URD I/P | 0 | 15472 | 15472 | Approved | 0 | 0 | 0 | 06 Sep 2022
GANGA DHAM TOWERS | 1360 | 96132 | 06 Sep 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 966 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 06 Sep 2022
GANGA DHAM TOWERS | 940 | 96131 | 06 Sep 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 967 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 06 Sep 2022
GANGA DHAM TOWERS | 1228 | 96130 | 05 Sep 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1040 | Site Expenses | Site Expenses -SO | 0.268 | Month | 30000 | 100 | 0 | 0 | 8039 | CGST 0% URD I/P | 0 | 8039 | 8039 | Approved | 0 | 0 | 0 | 05 Sep 2022
GANGA DHAM TOWERS | 1228 | 96130 | 05 Sep 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1040 | Site Expenses | Site Expenses -SO | 0.0467 | Month | 30000 | 100 | 0 | 0 | 1400 | CGST 0% URD I/P | 0 | 1400 | 1400 | Approved | 0 | 0 | 0 | 05 Sep 2022
GANGA DHAM TOWERS | 413 | 96129 | 05 Sep 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1358 | Sales office Garden Maintenance | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 704 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 903 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 803 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 901 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 902 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 703 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 805 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 701 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 905 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 801 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 705 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 802 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 904 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 702 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96127 | 05 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1007 | D 804 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 44 | 05 Sep 2022
GANGA DHAM TOWERS | 1335 | 96125 | 05 Sep 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 983 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 2 | No. | 6000 | 100 | 0 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 660 | 05 Sep 2022
GANGA DHAM TOWERS | 1335 | 96125 | 05 Sep 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 983 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 | Approved | 0 | 0 | 660 | 05 Sep 2022
GANGA DHAM TOWERS | 1336 | 96124 | 05 Sep 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 1017 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 2 | No. | 6000 | 100 | 0 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 390 | 05 Sep 2022
GANGA DHAM TOWERS | 1336 | 96124 | 05 Sep 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 1017 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 27000 | 100 | 0 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 390 | 05 Sep 2022
GANGA DHAM TOWERS | 372 | 96123 | 05 Sep 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1094 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 125 | Sq.Ft | 150 | 100 | 0 | 0 | 18750 | C+S GST 18% I/P RD | 3375 | 22125 | 22125 | Approved | 0 | 0 | 750 | 05 Sep 2022
GANGA DHAM TOWERS | 372 | 96123 | 05 Sep 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1094 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 125 | Sq.Ft | 150 | 100 | 0 | 0 | 18750 | C+S GST 18% I/P RD | 3375 | 22125 | 22125 | Approved | 0 | 0 | 750 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 592.39 | Sq.Ft | 1.25 | 100 | 18.51 | 0 | 740.49 | C+S GST 18% I/P RD | 133.28 | 873.77 | 873.77 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 829 | 96122 | 05 Sep 2022 |  | CHAPLA ADE PENTING CONTRACTOR | GODAVARI PAINT PVT LTD | EV - 1052 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.39 | Sq.Ft | 1.25 | 100 | 0.26 | 0 | 10.49 | C+S GST 18% I/P RD | 1.88 | 12.37 | 12.37 | Approved | 0 | 0 | 346 | 05 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1104 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 601 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 103 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 605 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1101 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 105 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 104 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1001 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 101 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1003 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1004 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 602 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 603 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1103 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 102 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 604 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1105 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1005 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1002 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1102 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 604 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 702 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 105 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 802 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 103 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 904 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1002 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 903 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 604 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 701 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 605 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 602 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 705 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 104 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 101 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1103 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 102 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 704 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 905 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1005 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1102 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 804 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1001 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1003 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 801 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 803 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1004 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1105 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 901 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 805 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 903 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 101 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1004 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 105 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1101 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 805 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1104 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 603 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 703 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 601 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 902 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1101 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 702 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 703 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 904 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1103 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 602 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 803 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 603 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 102 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 605 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 905 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 104 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1002 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1104 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 701 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1102 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1105 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 804 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 601 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 902 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1003 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 801 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 901 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 103 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 802 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 704 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 705 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1005 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 653 | 96116 | 03 Sep 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 1006 | D 1001 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 279 | 03 Sep 2022
GANGA DHAM TOWERS | 1340 | 96114 | 03 Sep 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 897 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 03 Sep 2022
GANGA DHAM TOWERS | 401 | 96113 | 03 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 946 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 11 | 03 Sep 2022
GANGA DHAM TOWERS | 1361 | 96112 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1108 | Shed for Diesel storage room | MS Door (L) | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 40 | 03 Sep 2022
GANGA DHAM TOWERS | 1361 | 96112 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1108 | Shed for Diesel storage room | Meta colour Sheet Fixing BC | 487.5 | Sq.Ft | 5 | 100 | 60.94 | 0 | 2437.5 | CGST 0% URD I/P | 0 | 2437.5 | 2437.5 | Approved | 0 | 0 | 40 | 03 Sep 2022
GANGA DHAM TOWERS | 1361 | 96112 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1108 | Shed for Diesel storage room | MS Square Pipe (L) | 62.34 | Kgs | 12 | 100 | 18.7 | 0 | 748.08 | CGST 0% URD I/P | 0 | 748.08 | 748.08 | Approved | 0 | 0 | 40 | 03 Sep 2022
GANGA DHAM TOWERS | 1274 | 96110 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1124 | New DG Shed Fabrication | Meta colour Sheet Fixing BC | 792 | Sq.Ft | 5 | 100 | 99 | 0 | 3960 | CGST 0% URD I/P | 0 | 3960 | 3960 | Approved | 0 | 0 | 92 | 03 Sep 2022
GANGA DHAM TOWERS | 1274 | 96110 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1124 | New DG Shed Fabrication | MS Pipe Fixing (L) | 229.2 | Kgs | 12 | 100 | 68.76 | 0 | 2750.4 | CGST 0% URD I/P | 0 | 2750.4 | 2750.4 | Approved | 0 | 0 | 92 | 03 Sep 2022
GANGA DHAM TOWERS | 1274 | 96110 | 03 Sep 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1124 | New DG Shed Fabrication | MS Square Pipe (L) | 206.67 | Kgs | 12 | 100 | 62 | 0 | 2480.04 | CGST 0% URD I/P | 0 | 2480.04 | 2480.04 | Approved | 0 | 0 | 92 | 03 Sep 2022
GANGA DHAM TOWERS | 1162 | 96109 | 03 Sep 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 942 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 03 Sep 2022
GANGA DHAM TOWERS | 1409 | 96108 | 03 Sep 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 1064 | A -Single Coat sponge plaster for Expansion joint - 378.42 | Sponge Plaster - BC | 378.42 | Sq.Ft | 15 | 100 | 141.91 | 0 | 5676.3 | CGST 0% URD I/P | 0 | 5676.3 | 5676.3 | Approved | 0 | 0 | 75 | 03 Sep 2022
GANGA DHAM TOWERS | 1409 | 96108 | 03 Sep 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 1064 | B -Single Coat sponge plaster for Expansion joint | Sponge Plaster - BC | 120.33 | Sq.Ft | 15 | 100 | 45.12 | 0 | 1804.95 | CGST 0% URD I/P | 0 | 1804.95 | 1804.95 | Approved | 0 | 0 | 75 | 03 Sep 2022
GANGA DHAM TOWERS | 826 | 96107 | 03 Sep 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 940 | Landscape Plantation Work | Excavation in Soft Soil | 1745 | Cu.Ft | 6.5 | 100 | 0 | 0 | 11342.5 | CGST 0% URD I/P | 0 | 11342.5 | 11342.5 | Approved | 0 | 0 | 170 | 03 Sep 2022
GANGA DHAM TOWERS | 826 | 96107 | 03 Sep 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 940 | Landscape Plantation Work | Poyta Soil filling | 1745 | Cu.Ft | 6.5 | 100 | 0 | 0 | 11342.5 | CGST 0% URD I/P | 0 | 11342.5 | 11342.5 | Approved | 0 | 0 | 170 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 22nd Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 12th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 17th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 7th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 23rd Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 5th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 3rd Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 6th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 1st Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 8th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 18th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 11th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 20th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 13th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 14th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 15th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 2nd Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 9th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 4th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 16th Floor Texture Painting | Texture Paint (M) | 102.8966 | Sq.Ft | 7.25 | 100 | 0 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 10th Floor Texture Painting | Texture Paint (M) | 102.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 745 | C+S GST 18% I/P RD | 134.1 | 879.1 | 879.1 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 19th Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1200 | 96106 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1051 | B Southside 21st Floor Texture Painting | Texture Paint (M) | 122.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 0 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 15th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 12th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 14th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 18th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 13th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 10th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 2nd Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 7th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 16th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 1st Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 22nd Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 4th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 20th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 9th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 11th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 21st Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 19th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 8th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 6th Floor Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 3rd Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 17th Floor Texture Painting | Texture Paint (L) | 122.8966 | Sq.Ft | 7.25 | 100 | 22.28 | 0 | 891 | C+S GST 18% I/P RD | 160.38 | 1051.38 | 1051.38 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 5th Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 23rd Floor Texture Painting | Texture Paint (L) | 122.7586 | Sq.Ft | 7.25 | 100 | 22.25 | 0 | 890 | C+S GST 18% I/P RD | 160.2 | 1050.2 | 1050.2 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 16th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 23rd Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 9th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 15th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 7th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 6th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 22nd Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 2nd Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 14th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 18th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 8th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 10th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 1st Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 13th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 3rd Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 11th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 20th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 12th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 17th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 19th Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 4th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 5th Floor Texture Painting | Scaffolding/Gondola work | 102.8571 | Sq.Ft | 3.5 | 100 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 1199 | 96105 | 03 Sep 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1054 | B Southside 21st Floor Texture Painting | Scaffolding/Gondola work | 122.8571 | Sq.Ft | 3.5 | 100 | 10.75 | 0 | 430 | C+S GST 18% I/P RD | 77.4 | 507.4 | 507.4 | Approved | 0 | 0 | 559 | 03 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 16 | No. | 70 | 100 | 112 | 0 | 1120 | CGST 0% URD I/P | 0 | 1120 | 1120 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 16 | No. | 70 | 100 | 112 | 0 | 1120 | CGST 0% URD I/P | 0 | 1120 | 1120 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 1004 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 9 | No. | 150 | 100 | 135 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 9 | No. | 150 | 100 | 135 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 9 | No. | 150 | 100 | 135 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 9 | No. | 150 | 100 | 135 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 9 | No. | 150 | 100 | 135 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 104 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 203 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 1004 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 401 | 96091 | 02 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 949 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 198 | 02 Sep 2022
GANGA DHAM TOWERS | 1415 | 96079 | 01 Sep 2022 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 846 | RMU Servicing & Repairing Charges | RMU Servicing & Repairing | 1 | No. | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 0 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | A & B Storm Water Line Pipe Laying (L) | Chamber 36" x 18" (3ft Ht) - UDR | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | Tower A & B Drainage line Pipe Laying (L) | Chamber 36" x 18" (3ft Ht) - UDR | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | Tower A & B Drainage line Pipe Laying (L) | Chamber 36" x 18" (3ft Ht) - UDR | 7 | No. | 1000 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | Tower A & B LT & LV Line Pipie Laying (L) | Chamber 48" x 48" (3ft Ht) | 8 | No. | 1000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | A & B Storm Water Line Pipe Laying (L) | Round Chamber- UDR | 1.5 | No. | 2500 | 100 | 93.75 | 0 | 3750 | CGST 0% URD I/P | 0 | 3750 | 3750 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 439 | 96078 | 01 Sep 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 943 | A & B Storm Water Line Pipe Laying (L) | Round Chamber- UDR | 3.5 | No. | 2500 | 100 | 218.75 | 0 | 8750 | CGST 0% URD I/P | 0 | 8750 | 8750 | Approved | 0 | 0 | 315 | 01 Sep 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1205 Kitchen Otta | Granite Kitchen Otta BC | 13 | R.Ft | 400 | 100 | 130 | 0 | 5200 | CGST 0% URD I/P | 0 | 5200 | 5200 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1104 Kitchen Otta | Granite Kitchen Otta BC | 15 | R.Ft | 400 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1103 Kitchen Otta | Granite Kitchen Otta BC | 15 | R.Ft | 400 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1102 Kitchen Otta | Granite Kitchen Otta BC | 12 | R.Ft | 400 | 100 | 120 | 0 | 4800 | CGST 0% URD I/P | 0 | 4800 | 4800 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1105 Kitchen Otta | Granite Kitchen Otta BC | 13 | R.Ft | 400 | 100 | 130 | 0 | 5200 | CGST 0% URD I/P | 0 | 5200 | 5200 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1203 Kitchen Otta | Granite Kitchen Otta BC | 15 | R.Ft | 400 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1101 Kitchen Otta | Granite Kitchen Otta BC | 13 | R.Ft | 400 | 100 | 130 | 0 | 5200 | CGST 0% URD I/P | 0 | 5200 | 5200 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1201 Kitchen Otta | Granite Kitchen Otta BC | 13 | R.Ft | 400 | 100 | 130 | 0 | 5200 | CGST 0% URD I/P | 0 | 5200 | 5200 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1202 Kitchen Otta | Granite Kitchen Otta BC | 12 | R.Ft | 400 | 100 | 120 | 0 | 4800 | CGST 0% URD I/P | 0 | 4800 | 4800 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96062 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 838 | D 1204 Kitchen Otta | Granite Kitchen Otta BC | 15 | R.Ft | 400 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 544 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96061 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 837 | D 1205 Dado | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 28 | 30 Aug 2022
GANGA DHAM TOWERS | 798 | 96061 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 837 | D 1201 Dado - 366.02 Sq.Ft | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 28 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 701 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 703 Dado (L) | Dado Fixing | 200 | Sq.Ft | 17.49 | 100 | 87.45 | 0 | 3498 | CGST 0% URD I/P | 0 | 3498 | 3498 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 703 Dado (L) | Dado Fixing | 91.39 | Sq.Ft | 17.49 | 100 | 39.96 | 0 | 1598.41 | CGST 0% URD I/P | 0 | 1598.41 | 1598.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 804 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 705 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 803 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 905 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1002 Dado (L) | Dado Fixing | 278.77 | Sq.Ft | 17.49 | 100 | 121.89 | 0 | 4875.69 | CGST 0% URD I/P | 0 | 4875.69 | 4875.69 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1001 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 904 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 801 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 704 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1101 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1004 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 604 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 603 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 13 | 100 | 94.7 | 0 | 3788.07 | CGST 0% URD I/P | 0 | 3788.07 | 3788.07 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 605 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 13 | 100 | 26.4 | 0 | 1055.99 | CGST 0% URD I/P | 0 | 1055.99 | 1055.99 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 601 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 13 | 100 | 26.4 | 0 | 1055.99 | CGST 0% URD I/P | 0 | 1055.99 | 1055.99 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1005 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 702 Dado (L) | Dado Fixing | 278.77 | Sq.Ft | 17.49 | 100 | 121.89 | 0 | 4875.69 | CGST 0% URD I/P | 0 | 4875.69 | 4875.69 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1003 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 602 Dado (L) | Dado Fixing | 278.77 | Sq.Ft | 13 | 100 | 90.6 | 0 | 3624.01 | CGST 0% URD I/P | 0 | 3624.01 | 3624.01 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 901 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 902 Dado (L) | Dado Fixing | 278.77 | Sq.Ft | 17.49 | 100 | 121.89 | 0 | 4875.69 | CGST 0% URD I/P | 0 | 4875.69 | 4875.69 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 805 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 903 Dado (L) | Dado Fixing | 291.39 | Sq.Ft | 17.49 | 100 | 127.41 | 0 | 5096.41 | CGST 0% URD I/P | 0 | 5096.41 | 5096.41 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 792 | 96060 | 30 Aug 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 836 | D 1105 Dado (L) | Dado Fixing | 81.23 | Sq.Ft | 17.49 | 100 | 35.52 | 0 | 1420.71 | CGST 0% URD I/P | 0 | 1420.71 | 1420.71 | Approved | 0 | 0 | 829 | 30 Aug 2022
GANGA DHAM TOWERS | 1177 | 96056 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 973 | B Gypsum plaster on Toilet wall in M.BED up to 23rd flr | Gypsum Plaster (L) | 128.1 | Sq.Ft | 10 | 100 | 32.03 | 0 | 1281 | C+S GST 18% I/P RD | 230.58 | 1511.58 | 1511.58 | Approved | 0 | 0 | 15 | 30 Aug 2022
GANGA DHAM TOWERS | 1177 | 96056 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 973 | B plaster Removing in M.BED upto 23rd floor | Removing Gypsum - BRE | 128 | Sq.Ft | 2 | 100 | 0 | 0 | 256 | C+S GST 18% I/P RD | 46.08 | 302.08 | 302.08 | Approved | 0 | 0 | 15 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 301 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 801 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 101 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 401 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 901 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 495 | 96055 | 30 Aug 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 978 | B 701 Gypsum Plaster | Gypsum on Wall (L) | 75.25 | Sq.Ft | 4 | 100 | 7.53 | 0 | 301 | C+S GST 18% I/P RD | 54.18 | 355.18 | 355.18 | Approved | 0 | 0 | 18 | 30 Aug 2022
GANGA DHAM TOWERS | 1233 | 96054 | 30 Aug 2022 |  | KADAVATH VENKAT ENTERPRISES | A K INTERIOR CONTRACTOR | EV - 974 | B 1701 NOC | Gypsum Plaster (L) | 708.9 | Sq.Ft | 4 | 100 | 70.89 | 0 | 2835.6 | C+S GST 18% I/P RD | 510.4 | 3346 | 3346 | Approved | 0 | 0 | 28 | 30 Aug 2022
GANGA DHAM TOWERS | 1248 | 96053 | 30 Aug 2022 |  | AVCON TECHNICS PVT LTD | A K INTERIOR CONTRACTOR | EV - 977 | B 201 NOC | Gypsum Plaster (L) | 105.2632 | Sq.Ft | 9.5 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 30 Aug 2022
GANGA DHAM TOWERS | 1002 | 96052 | 30 Aug 2022 |  | AVCON TECHNICS PVT LTD | A K INTERIOR CONTRACTOR | EV - 975 | B 1201 NOC | Gypsum Plaster (L) | 636.4444 | Sq.Ft | 9 | 100 | 143.2 | 0 | 5728 | C+S GST 18% I/P RD | 1031.04 | 6759.04 | 6759.04 | Approved | 0 | 0 | 205 | 30 Aug 2022
GANGA DHAM TOWERS | 1002 | 96052 | 30 Aug 2022 |  | AVCON TECHNICS PVT LTD | A K INTERIOR CONTRACTOR | EV - 975 | B 1201 NOC | Gypsum Plaster (L) | 67 | Sq.Ft | 9 | 100 | 15.08 | 0 | 603 | C+S GST 18% I/P RD | 108.54 | 711.54 | 711.54 | Approved | 0 | 0 | 205 | 30 Aug 2022
GANGA DHAM TOWERS | 1002 | 96052 | 30 Aug 2022 |  | AVCON TECHNICS PVT LTD | A K INTERIOR CONTRACTOR | EV - 975 | B 601 NOC | Gypsum Plaster (L) | 435 | Sq.Ft | 9 | 100 | 97.88 | 0 | 3915 | C+S GST 18% I/P RD | 704.7 | 4619.7 | 4619.7 | Approved | 0 | 0 | 205 | 30 Aug 2022
GANGA DHAM TOWERS | 1239 | 96044 | 29 Aug 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 1189 | C Podium Area Murrum Shifting Work | Murum Shifting work | 3545 | Cu.Mtrs | 350 | 100 | 0 | 0 | 1240750 | C+S GST 18% I/P RD | 223335 | 1464085 | 1464085 | Approved | 0 | 0 | 12408 | 29 Aug 2022
GANGA DHAM TOWERS | 372 | 96042 | 29 Aug 2022 |  | B & B ENTERPRISES | AVCON TECHNICS PVT LTD | EV - 1639 | B Bldg 30th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 24.75 | Sq.Ft | 400 | 100 | 247.5 | 0 | 9900 | C+S GST 18% I/P RD | 1782 | 11682 | 11682 | Approved | 0 | 0 | 198 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 12th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 9th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 14th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 7th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 1st floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 8th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 15th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 4th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 6th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 11th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 18th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 21st floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 23rd floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 5th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 19th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 20th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 22nd floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 17th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 24th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 2nd floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 3rd floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 10th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 13th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 16th floor External Texture Painting | Water Base Primer (L) | 769 | Sq.Ft | 1 | 100 | 19.23 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 1st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 11th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 13th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 14th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 1st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 5th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 6th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 12th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 19th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 20th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 7th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 18th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 4th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 21st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 24th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 16th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 8th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 10th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 15th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 9th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 17th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1292 | 96041 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1019 | A Westside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 769.3333 | Sq.Ft | 1.5 | 100 | 28.85 | 0 | 1154 | C+S GST 18% I/P RD | 207.72 | 1361.72 | 1361.72 | Approved | 0 | 0 | 738 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 24th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 15th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 9th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 10th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 12th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 17th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 19th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 5th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 16th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 1st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 769.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1923 | C+S GST 18% I/P RD | 346.14 | 2269.14 | 2269.14 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 16th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 5th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 21st floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 14th floor External Texture Painting | Water Base Primer (M) | 768 | Sq.Ft | 1 | 100 | 0 | 0 | 768 | C+S GST 18% I/P RD | 138.24 | 906.24 | 906.24 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 6th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 22nd floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 24th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 2nd floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 15th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 20th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 7th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 14th floor External Texture Painting | Water Base Primer (M) | 1 | Sq.Ft | 1 | 100 | 0 | 0 | 1 | C+S GST 18% I/P RD | 0.18 | 1.18 | 1.18 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 4th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 9th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 17th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 18th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 12th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 11th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 13th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 23rd floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 1st floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 3rd floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 19th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 8th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 10th floor External Texture Painting | Water Base Primer (M) | 769 | Sq.Ft | 1 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 4th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 6th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 13th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 14th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 7th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 21st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 8th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 1st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 20th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 11th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1295 | 96039 | 29 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1021 | A Westside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 769 | Sq.Ft | 2 | 100 | 0 | 0 | 1538 | C+S GST 18% I/P RD | 276.84 | 1814.84 | 1814.84 | Approved | 0 | 0 | 0 | 29 Aug 2022
GANGA DHAM TOWERS | 1402 | 96036 | 27 Aug 2022 |  | KALPATARU CREATIONS | KALPATARU CREATIONS | EV - 822 | Event Expenses | Event Expenses | 1 | No. | 140000 | 100 | 0 | 0 | 140000 | C+S GST 18% I/P RD | 25200 | 165200 | 165200 | Approved | 0 | 0 | 2800 | 27 Aug 2022
GANGA DHAM TOWERS | 1384 | 95999 | 26 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 899 | A Fire Fighting Extra Items | Sprinkler 15 mm 93 dg Pendent (L) | 67 | No. | 170 | 100 | 284.75 | 0 | 11390 | C+S GST 18% I/P RD | 2050.2 | 13440.2 | 13440.2 | Approved | 0 | 0 | 114 | 26 Aug 2022
GANGA DHAM TOWERS | 1385 | 95998 | 26 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 902 | A Fire Fighting Extra Items | Sprinkler 15 mm 93 dg Pendent (M) | 67 | No. | 393 | 100 | 0 | 0 | 26331 | C+S GST 18% I/P RD | 4739.58 | 31070.58 | 31070.58 | Approved | 0 | 0 | 0 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 1901 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.6333 | R.Ft | 60 | 100 | 39.95 | 0 | 1598 | C+S GST 18% I/P RD | 287.64 | 1885.64 | 1885.64 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 702 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.72 | R.Ft | 50 | 100 | 34.65 | 0 | 1386 | C+S GST 18% I/P RD | 249.48 | 1635.48 | 1635.48 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 801 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 50 | 100 | 33.3 | 0 | 1332 | C+S GST 18% I/P RD | 239.76 | 1571.76 | 1571.76 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 1002 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.72 | R.Ft | 50 | 100 | 34.65 | 0 | 1386 | C+S GST 18% I/P RD | 249.48 | 1635.48 | 1635.48 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 901 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 50 | 100 | 33.3 | 0 | 1332 | C+S GST 18% I/P RD | 239.76 | 1571.76 | 1571.76 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 1502 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.7273 | R.Ft | 55 | 100 | 38.13 | 0 | 1525 | C+S GST 18% I/P RD | 274.5 | 1799.5 | 1799.5 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 537 | 95997 | 26 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 892 | A 1801 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.6364 | R.Ft | 55 | 100 | 36.63 | 0 | 1465 | C+S GST 18% I/P RD | 263.7 | 1728.7 | 1728.7 | Approved | 0 | 0 | 100 | 26 Aug 2022
GANGA DHAM TOWERS | 551 | 95996 | 26 Aug 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 894 | A 1704 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 32.3273 | R.Ft | 55 | 100 | 44.45 | 0 | 1778 | C+S GST 18% I/P RD | 320.04 | 2098.04 | 2098.04 | Approved | 0 | 0 | 36 | 26 Aug 2022
GANGA DHAM TOWERS | 551 | 95996 | 26 Aug 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 894 | A 1604 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 32.3273 | R.Ft | 55 | 100 | 44.45 | 0 | 1778 | C+S GST 18% I/P RD | 320.04 | 2098.04 | 2098.04 | Approved | 0 | 0 | 36 | 26 Aug 2022
GANGA DHAM TOWERS | 1384 | 95986 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 900 | A Fire Fighting Extra Items | SITC GI Pipe C Class 25mm dia-(L) | 136 | Mtrs | 160 | 100 | 544 | 0 | 21760 | C+S GST 18% I/P RD | 3916.8 | 25676.8 | 25676.8 | Approved | 0 | 0 | 385 | 25 Aug 2022
GANGA DHAM TOWERS | 1384 | 95986 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 900 | A Fire Fighting Extra Items | Flexible Hose Pipe 25mm Dia (1.2mtr length) (L) | 67 | No. | 250 | 100 | 418.75 | 0 | 16750 | C+S GST 18% I/P RD | 3015 | 19765 | 19765 | Approved | 0 | 0 | 385 | 25 Aug 2022
GANGA DHAM TOWERS | 1385 | 95984 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 903 | A Fire Fighting Extra Items | Flexible Hose Pipe 25mm Dia (1.2mtr length) (M) | 67 | No. | 753 | 100 | 0 | 0 | 50451 | C+S GST 18% I/P RD | 9081.18 | 59532.18 | 59532.18 | Approved | 0 | 0 | 0 | 25 Aug 2022
GANGA DHAM TOWERS | 1385 | 95984 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 903 | A Fire Fighting Extra Items | SITC GI Pipe C Class 25mm dia.(M) | 136 | Mtrs | 397 | 100 | 0 | 0 | 53992 | C+S GST 18% I/P RD | 9718.56 | 63710.56 | 63710.56 | Approved | 0 | 0 | 0 | 25 Aug 2022
GANGA DHAM TOWERS | 1385 | 95984 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 903 | A Fire Fighting Extra Items | SITC GI Pipe C Class 25mm dia.(M) | 120 | Mtrs | 397 | 100 | 0 | 0 | 47640 | C+S GST 18% I/P RD | 8575.2 | 56215.2 | 56215.2 | Approved | 0 | 0 | 0 | 25 Aug 2022
GANGA DHAM TOWERS | 1385 | 95984 | 25 Aug 2022 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 903 | A Fire Fighting Extra Items | Rossete Plate (M) | 68 | No. | 79 | 100 | 0 | 0 | 5372 | C+S GST 18% I/P RD | 966.96 | 6338.96 | 6338.96 | Approved | 0 | 0 | 0 | 25 Aug 2022
GANGA DHAM TOWERS | 1169 | 95981 | 25 Aug 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 906 | A Fire Fighting Extra Items | Sprinkler 15 mm 93 dg Pendent (M) | 36 | No. | 600 | 100 | 0 | 0 | 21600 | C+S GST 18% I/P RD | 3888 | 25488 | 25488 | Approved | 0 | 0 | 0 | 25 Aug 2022
GANGA DHAM TOWERS | 1382 | 95963 | 24 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 858 | A Bldg. Flat No. 1104 Plumbing work | Int Flat PPRC Work. | 0.07 | No. | 12000 | 100 | 21 | 0 | 840 | CGST 0% URD I/P | 0 | 840 | 840 | Approved | 0 | 0 | 8 | 24 Aug 2022
GANGA DHAM TOWERS | 1259 | 95962 | 24 Aug 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 901 | A 104 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2786 | Sq.Ft | 140 | 100 | 49.98 | 0 | 1999 | CGST 0% URD I/P | 0 | 1999 | 1999 | Approved | 0 | 0 | 80 | 24 Aug 2022
GANGA DHAM TOWERS | 1259 | 95962 | 24 Aug 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 901 | A 103 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2786 | Sq.Ft | 140 | 100 | 49.98 | 0 | 1999 | CGST 0% URD I/P | 0 | 1999 | 1999 | Approved | 0 | 0 | 80 | 24 Aug 2022
GANGA DHAM TOWERS | 1259 | 95962 | 24 Aug 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 901 | A 203 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2786 | Sq.Ft | 140 | 100 | 49.98 | 0 | 1999 | CGST 0% URD I/P | 0 | 1999 | 1999 | Approved | 0 | 0 | 80 | 24 Aug 2022
GANGA DHAM TOWERS | 1259 | 95962 | 24 Aug 2022 |  | VNE INFRA PROJECTS P LTD | SAROJ KUMAR PRADHAN | EV - 901 | A 1102 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2786 | Sq.Ft | 140 | 100 | 49.98 | 0 | 1999 | CGST 0% URD I/P | 0 | 1999 | 1999 | Approved | 0 | 0 | 80 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 902 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1200 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 702 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.25 | No. | 1200 | 100 | 67.5 | 0 | 2700 | CGST 0% URD I/P | 0 | 2700 | 2700 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 804 Internal Plumbing PPR-C | Int Flat PPRC Work. | 0.5 | No. | 1200 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 902 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 501 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 2001 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 1902 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1650 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 2002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 1903 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 2002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 455 | 95961 | 24 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 968 | A Bldg Flat No. 1901 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 228 | 24 Aug 2022
GANGA DHAM TOWERS | 1180 | 95951 | 23 Aug 2022 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 861 | A Terrace Scaffolding Work | Scaffolding work | 2688 | Sq.Ft | 5.5 | 100 | 369.6 | 0 | 14784 | CGST 0% URD I/P | 0 | 14784 | 14784 | Approved | 0 | 0 | 148 | 23 Aug 2022
GANGA DHAM TOWERS | 493 | 95933 | 20 Aug 2022 |  | KADAVATH VENKAT ENTERPRISES | RAHIMAN ABDUL SHAIKH | EV - 877 | D Bldg South Side External Plaster | External Plaster- BC | 719 | Sq.Ft | 35 | 100 | 629.13 | 0 | 25165 | CGST 0% URD I/P | 0 | 25165 | 25165 | Approved | 0 | 0 | 252 | 20 Aug 2022
GANGA DHAM TOWERS | 1382 | 95932 | 20 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 857 | A Bldg. Flat No. 1004 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 360 | 20 Aug 2022
GANGA DHAM TOWERS | 1382 | 95932 | 20 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 857 | A Bldg. Flat No. 2504 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 360 | 20 Aug 2022
GANGA DHAM TOWERS | 1382 | 95932 | 20 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 857 | A Bldg. Flat No. 2503 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 360 | 20 Aug 2022
GANGA DHAM TOWERS | 971 | 95931 | 20 Aug 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1453 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 7 | No. | 300 | 100 | 0 | 0 | 2100 | 0% | 0 | 2100 | 2100 | Approved | 0 | 0 | 81 | 20 Aug 2022
GANGA DHAM TOWERS | 971 | 95931 | 20 Aug 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 1453 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 20 | No. | 300 | 100 | 0 | 0 | 6000 | 0% | 0 | 6000 | 6000 | Approved | 0 | 0 | 81 | 20 Aug 2022
GANGA DHAM TOWERS | 1394 | 95924 | 19 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 788 | D Fire Fighting Fire Pump room equipment | SITC GI C Class Pipe 100mm dia.(M) | 2 | Mtrs | 1370 | 60 | 0 | 0 | 1644 | C+S GST 18% I/P RD | 295.92 | 1939.92 | 1939.92 | Approved | 0 | 0 | 0 | 19 Aug 2022
GANGA DHAM TOWERS | 1394 | 95924 | 19 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 788 | D Fire Fighting Internal Hydrants System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | 1.7998 | Mtrs | 964 | 60 | 0 | 0 | 1041 | C+S GST 18% I/P RD | 187.38 | 1228.38 | 1228.38 | Approved | 0 | 0 | 0 | 19 Aug 2022
GANGA DHAM TOWERS | 1394 | 95924 | 19 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 788 | D Fire Fighting Internal Hydrants System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | 15.9998 | Mtrs | 2017 | 60 | 0 | 0 | 19363 | C+S GST 18% I/P RD | 3485.34 | 22848.34 | 22848.34 | Approved | 0 | 0 | 0 | 19 Aug 2022
GANGA DHAM TOWERS | 389 | 95916 | 18 Aug 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 776 | Loading / Unloading Expenses | Unloading of tiles. | 33.5 | Metric Tonnes | 260 | 100 | 0 | 0 | 8710 | CGST 0% URD I/P | 0 | 8710 | 8710 | Approved | 0 | 0 | 87 | 18 Aug 2022
GANGA DHAM TOWERS | 1275 | 95908 | 18 Aug 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1255 | B Bldg Safety Jali Work | M.S. Jali- DPo | 136.3636 | Sq.Ft | 11 | 100 | 37.5 | 0 | 1500 | C+S GST 0% I/P RD | 0 | 1500 | 1500 | Approved | 0 | 0 | 15 | 18 Aug 2022
GANGA DHAM TOWERS | 351 | 95906 | 18 Aug 2022 |  | TECHKNOW EARTHMOVING SERVICES | PURVA ENTERPRISES | EV - 834 | A Bldg 31th SlabTower Crane Jumping Work | Tower Crane Jumping Charges | 1 | No. | 30000 | 100 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 300 | 18 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 71.1 | No. | 200 | 25 | 88.88 | 0 | 3555 | C+S GST 18% I/P RD | 639.9 | 4194.9 | 4194.9 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 71.1 | No. | 200 | 25 | 88.88 | 0 | 3555 | C+S GST 18% I/P RD | 639.9 | 4194.9 | 4194.9 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | 6 AMP Plug point (Independent) | 75.6 | No. | 200 | 25 | 94.5 | 0 | 3780 | C+S GST 18% I/P RD | 680.4 | 4460.4 | 4460.4 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | 6 AMP Plug point (Independent) | 75.6 | No. | 200 | 25 | 94.5 | 0 | 3780 | C+S GST 18% I/P RD | 680.4 | 4460.4 | 4460.4 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | TV Point | 7.2 | No. | 220 | 25 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | TV Point | 7.2 | No. | 220 | 25 | 9.9 | 0 | 396 | C+S GST 18% I/P RD | 71.28 | 467.28 | 467.28 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Exhaust Fan Point | 4.5 | No. | 200 | 25 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Exhaust Fan Point | 4.5 | No. | 200 | 25 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Secondary Light Points (Looping) | 49.5 | No. | 67 | 25 | 20.73 | 0 | 829.13 | C+S GST 18% I/P RD | 149.24 | 978.37 | 978.37 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Secondary Light Points (Looping) | 49.5 | No. | 67 | 25 | 20.73 | 0 | 829.13 | C+S GST 18% I/P RD | 149.24 | 978.37 | 978.37 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Data Point | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Data Point | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | TV/Tel DB Fixing | 0.9 | No. | 500 | 25 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Telephone Point | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Telephone Point | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | AC Point BC | 8.1 | No. | 220 | 25 | 11.14 | 0 | 445.5 | C+S GST 18% I/P RD | 80.2 | 525.7 | 525.7 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | AC Point BC | 8.1 | No. | 220 | 25 | 11.14 | 0 | 445.5 | C+S GST 18% I/P RD | 80.2 | 525.7 | 525.7 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | 8 Way TPN DB | 0.9 | No. | 1400 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | 8 Way TPN DB | 0.9 | No. | 1400 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | TV/Tel DB Fixing | 0.9 | No. | 500 | 25 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13.5 | No. | 67 | 25 | 5.65 | 0 | 226.13 | C+S GST 18% I/P RD | 40.7 | 266.83 | 266.83 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13.5 | No. | 67 | 25 | 5.65 | 0 | 226.13 | C+S GST 18% I/P RD | 40.7 | 266.83 | 266.83 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 2001 Internal Electrical Work | Fan Point | 9.9 | No. | 200 | 25 | 12.38 | 0 | 495 | C+S GST 18% I/P RD | 89.1 | 584.1 | 584.1 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 399 | 95899 | 17 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 960 | B Bldg Flat No. 201 Internal Electrical Work | Fan Point | 9.9 | No. | 200 | 25 | 12.38 | 0 | 495 | C+S GST 18% I/P RD | 89.1 | 584.1 | 584.1 | Approved | 0 | 0 | 447 | 17 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 4th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 23rd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 5th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 3rd floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 1st floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 4th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 5th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 22nd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 11th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 18th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 1st floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 24th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 12th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 8th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 19th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 9th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 17th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 19th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 2nd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 16th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 18th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 13th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 24th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 10th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 17th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 8th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 24th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 12th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 14th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 21st floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 2nd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 10th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 15th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 24th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 6th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 13th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 23rd floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 1st floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 19th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 7th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 9th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 15th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 22nd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 6th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 21st floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 12th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 3rd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 4th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 10th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 11th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 13th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 14th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 11th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 20th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 2nd floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 16th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 6th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 9th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 14th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 16th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 15th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 22nd floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 20th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 3rd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 17th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 18th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 20th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 21st floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 8th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Eastside 7th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 7th floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Westside 23rd floor External Texture Painting | Texture Paint (M) | 200 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A South side 5th floor External Texture Painting | Texture Paint (M) | 100 | Sq.Ft | 7.25 | 100 | 0 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 845 | 95883 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 827 | A Northside1st floor External Texture Painting | Texture Paint (M) | 50.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 0 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 9th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 16th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 23rd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 6th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 21st floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 24th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 14th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 21st floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 10th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 9th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 2nd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 5th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 22nd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 12th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 16th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 24th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 15th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 1st floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 16th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 21st floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 23rd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 11th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 18th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 13th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 1st floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 18th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 19th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 8th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 19th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 15th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 11th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 22nd floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 18th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 12th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 2nd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 7th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 4th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 23rd floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 12th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 3rd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 20th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 19th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 5th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 3rd floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 14th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 8th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 22nd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 6th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 13th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 11th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 10th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 17th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 24th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 17th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 15th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside1st floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 1st floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 6th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 8th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 13th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 24th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 4th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 20th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 7th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 7th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 14th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 5th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 2nd floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 50.069 | Sq.Ft | 7.25 | 100 | 9.08 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 20th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 9th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Westside 10th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A South side 17th floor External Texture Painting | Texture Paint (L) | 100 | Sq.Ft | 7.25 | 100 | 18.13 | 0 | 725 | C+S GST 18% I/P RD | 130.5 | 855.5 | 855.5 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 3rd floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 844 | 95882 | 13 Aug 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 826 | A Eastside 4th floor External Texture Painting | Texture Paint (L) | 200 | Sq.Ft | 7.25 | 100 | 36.25 | 0 | 1450 | C+S GST 18% I/P RD | 261 | 1711 | 1711 | Approved | 0 | 0 | 953 | 13 Aug 2022
GANGA DHAM TOWERS | 149 | 95881 | 13 Aug 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 863 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3216.5 | No. | 4 | 100 | 0 | 0 | 12866 | CGST 0% URD I/P | 0 | 12866 | 12866 | Approved | 0 | 0 | 129 | 13 Aug 2022
GANGA DHAM TOWERS | 1089 | 95880 | 13 Aug 2022 |  | UNIQUE ENTERPRISES | PRAKASH CONTRACTOR | EV - 874 | Lt Substation Built-up Area (L) | RCC Superstructure (B-up area) | 27.28 | Sq.Ft | 220 | 100 | 0 | 0 | 6001.6 | CGST 0% URD I/P | 0 | 6001.6 | 6001.6 | Approved | 0 | 0 | 60 | 13 Aug 2022
GANGA DHAM TOWERS | 1208 | 95879 | 13 Aug 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES |  | Tower Crane B-Bldg Annual Maintenance charges of lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 |  | 0 | 0 | 60 | 13 Aug 2022
GANGA DHAM TOWERS | 1207 | 95878 | 13 Aug 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES |  | Tower Crane A & C Annual maintenance for tower crane & lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 |  | 0 | 0 | 60 | 13 Aug 2022
GANGA DHAM TOWERS | 1334 | 95877 | 13 Aug 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 905 | A,B,D Meter Room to Substation LT Cable | End Termination 300sqmm X 3.5 core cable (M+L) | 12 | No. | 1700 | 100 | 510 | 0 | 20400 | C+S GST 18% I/P RD | 3672 | 24072 | 24072 | Approved | 0 | 0 | 290 | 13 Aug 2022
GANGA DHAM TOWERS | 1334 | 95877 | 13 Aug 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 905 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 95 | Mtrs | 90 | 100 | 213.75 | 0 | 8550 | C+S GST 18% I/P RD | 1539 | 10089 | 10089 | Approved | 0 | 0 | 290 | 13 Aug 2022
GANGA DHAM TOWERS | 1394 | 95875 | 12 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 787 | D Fire Fighting Internal Hydrants System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | 4.2 | Mtrs | 964 | 60 | 0 | 0 | 2429.28 | C+S GST 18% I/P RD | 437.28 | 2866.56 | 2866.56 | Approved | 0 | 0 | 0 | 12 Aug 2022
GANGA DHAM TOWERS | 1394 | 95875 | 12 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 787 | D Fire Fighting Fire Pump room equipment | SITC GI C Class Pipe 100mm dia.(M) | 3 | Mtrs | 1370 | 60 | 0 | 0 | 2466 | C+S GST 18% I/P RD | 443.88 | 2909.88 | 2909.88 | Approved | 0 | 0 | 0 | 12 Aug 2022
GANGA DHAM TOWERS | 1394 | 95875 | 12 Aug 2022 |  | VANGUARD ENGINEERS | VANGUARD ENGINEERS | EV - 787 | D Fire Fighting Internal Hydrants System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | 24 | Mtrs | 2017 | 60 | 0 | 0 | 29044.8 | C+S GST 18% I/P RD | 5228.06 | 34272.86 | 34272.86 | Approved | 0 | 0 | 0 | 12 Aug 2022
GANGA DHAM TOWERS | 1383 | 95874 | 11 Aug 2022 |  | GIRIRAJ DHANSHYAM MANTRI | GIRIRAJ DHANSHYAM MANTRI | EV - 694 | Professional Consultancy (Finalcial) | Professional Fees | 1 | Month | 166667 | 100 | 0 | 0 | 166667 | CGST 0% URD I/P | 0 | 166667 | 166667 | Approved | 0 | 0 | 16667 | 11 Aug 2022
GANGA DHAM TOWERS | 372 | 95869 | 11 Aug 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 871 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 75 | Sq.Ft | 150 | 100 | 0 | 0 | 11250 | C+S GST 18% I/P RD | 2025 | 13275 | 13275 | Approved | 0 | 0 | 600 | 11 Aug 2022
GANGA DHAM TOWERS | 372 | 95869 | 11 Aug 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 871 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 125 | Sq.Ft | 150 | 100 | 0 | 0 | 18750 | C+S GST 18% I/P RD | 3375 | 22125 | 22125 | Approved | 0 | 0 | 600 | 11 Aug 2022
GANGA DHAM TOWERS | 971 | 95868 | 11 Aug 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1097 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 20 | No. | 300 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 141 | 11 Aug 2022
GANGA DHAM TOWERS | 971 | 95868 | 11 Aug 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1097 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 27 | No. | 300 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 141 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1704 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 57.27 | R.Ft | 55 | 100 | 78.75 | 0 | 3149.85 | C+S GST 18% I/P RD | 566.98 | 3716.83 | 3716.83 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1801 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 53.2727 | R.Ft | 55 | 100 | 73.25 | 0 | 2930 | C+S GST 18% I/P RD | 527.4 | 3457.4 | 3457.4 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1502 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 55.4364 | R.Ft | 55 | 100 | 76.23 | 0 | 3049 | C+S GST 18% I/P RD | 548.82 | 3597.82 | 3597.82 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1604 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 57.27 | R.Ft | 55 | 100 | 78.75 | 0 | 3149.85 | C+S GST 18% I/P RD | 566.98 | 3716.83 | 3716.83 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 801 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 53.28 | R.Ft | 50 | 100 | 66.6 | 0 | 2664 | C+S GST 18% I/P RD | 479.52 | 3143.52 | 3143.52 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1002 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 55.44 | R.Ft | 50 | 100 | 69.3 | 0 | 2772 | C+S GST 18% I/P RD | 498.96 | 3270.96 | 3270.96 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 901 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 53.28 | R.Ft | 50 | 100 | 66.6 | 0 | 2664 | C+S GST 18% I/P RD | 479.52 | 3143.52 | 3143.52 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 702 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 55.44 | R.Ft | 50 | 100 | 69.3 | 0 | 2772 | C+S GST 18% I/P RD | 498.96 | 3270.96 | 3270.96 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 641 | 95867 | 11 Aug 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 893 | A 1901 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 53.2667 | R.Ft | 60 | 100 | 79.9 | 0 | 3196 | C+S GST 18% I/P RD | 575.28 | 3771.28 | 3771.28 | Approved | 0 | 0 | 263 | 11 Aug 2022
GANGA DHAM TOWERS | 537 | 95866 | 11 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 896 | A 901 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 50 | 100 | 33.3 | 0 | 1332 | C+S GST 18% I/P RD | 239.76 | 1571.76 | 1571.76 | Approved | 0 | 0 | 41 | 11 Aug 2022
GANGA DHAM TOWERS | 537 | 95866 | 11 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 896 | A 702 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.72 | R.Ft | 50 | 100 | 34.65 | 0 | 1386 | C+S GST 18% I/P RD | 249.48 | 1635.48 | 1635.48 | Approved | 0 | 0 | 41 | 11 Aug 2022
GANGA DHAM TOWERS | 537 | 95866 | 11 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 896 | A 801 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 50 | 100 | 33.3 | 0 | 1332 | C+S GST 18% I/P RD | 239.76 | 1571.76 | 1571.76 | Approved | 0 | 0 | 41 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Secondary Light Points (Looping) | 38.7 | No. | 67 | 25 | 16.21 | 0 | 648.23 | C+S GST 18% I/P RD | 116.68 | 764.91 | 764.91 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Secondary Light Points (Looping) | 38.7 | No. | 67 | 25 | 16.21 | 0 | 648.23 | C+S GST 18% I/P RD | 116.68 | 764.91 | 764.91 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Exhaust Fan Point | 7.2 | No. | 200 | 25 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Exhaust Fan Point | 7.2 | No. | 200 | 25 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | TV Point | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | TV Point | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | 8 Way TPN DB | 0.9 | No. | 1300 | 25 | 7.31 | 0 | 292.5 | C+S GST 18% I/P RD | 52.66 | 345.16 | 345.16 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | 8 Way TPN DB | 0.9 | No. | 1300 | 25 | 7.31 | 0 | 292.5 | C+S GST 18% I/P RD | 52.66 | 345.16 | 345.16 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | 6 AMP Plug point (Independent) | 47.7 | No. | 200 | 25 | 59.63 | 0 | 2385 | C+S GST 18% I/P RD | 429.3 | 2814.3 | 2814.3 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | 6 AMP Plug point (Independent) | 47.7 | No. | 200 | 25 | 59.63 | 0 | 2385 | C+S GST 18% I/P RD | 429.3 | 2814.3 | 2814.3 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11.7 | No. | 67 | 25 | 4.9 | 0 | 195.98 | C+S GST 18% I/P RD | 35.28 | 231.26 | 231.26 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Data Point | 3.6 | No. | 220 | 25 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Data Point | 3.6 | No. | 220 | 25 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 45.9 | No. | 200 | 25 | 57.38 | 0 | 2295 | C+S GST 18% I/P RD | 413.1 | 2708.1 | 2708.1 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 45.9 | No. | 200 | 25 | 57.38 | 0 | 2295 | C+S GST 18% I/P RD | 413.1 | 2708.1 | 2708.1 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | TV/Tel DB Fixing | 0.9 | No. | 500 | 25 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | AC Point BC | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | AC Point BC | 5.4 | No. | 220 | 25 | 7.43 | 0 | 297 | C+S GST 18% I/P RD | 53.46 | 350.46 | 350.46 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Telephone Point | 4.5 | No. | 220 | 25 | 6.19 | 0 | 247.5 | C+S GST 18% I/P RD | 44.56 | 292.06 | 292.06 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Telephone Point | 4.5 | No. | 220 | 25 | 6.19 | 0 | 247.5 | C+S GST 18% I/P RD | 44.56 | 292.06 | 292.06 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.7 | No. | 220 | 25 | 3.71 | 0 | 148.5 | C+S GST 18% I/P RD | 26.74 | 175.24 | 175.24 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.7 | No. | 220 | 25 | 3.71 | 0 | 148.5 | C+S GST 18% I/P RD | 26.74 | 175.24 | 175.24 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 702 Internal Electrical Work | Fan Point | 8.1 | No. | 200 | 25 | 10.13 | 0 | 405 | C+S GST 18% I/P RD | 72.9 | 477.9 | 477.9 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | Fan Point | 8.1 | No. | 200 | 25 | 10.13 | 0 | 405 | C+S GST 18% I/P RD | 72.9 | 477.9 | 477.9 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 399 | 95865 | 11 Aug 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 771 | B Bldg Flat No. 1702 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11.7 | No. | 67 | 25 | 4.9 | 0 | 195.98 | C+S GST 18% I/P RD | 35.28 | 231.26 | 231.26 | Approved | 0 | 0 | 315 | 11 Aug 2022
GANGA DHAM TOWERS | 149 | 95864 | 11 Aug 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 862 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 82.475 | No. | 4 | 100 | 0 | 0 | 329.9 | CGST 0% URD I/P | 0 | 329.9 | 329.9 | Approved | 0 | 0 | 0 | 11 Aug 2022
GANGA DHAM TOWERS | 1398 | 95859 | 10 Aug 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 855 | Labour Camp making | G.I. Sheet Fixing - BC | 3868 | Sq.Ft | 5 | 100 | 483.5 | 0 | 19340 | C+S GST 18% I/P RD | 3481.2 | 22821.2 | 22821.2 | Approved | 0 | 0 | 559 | 10 Aug 2022
GANGA DHAM TOWERS | 1398 | 95859 | 10 Aug 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 855 | Labour Camp making | M.S. Door -BCo | 16 | No. | 800 | 100 | 0 | 0 | 12800 | C+S GST 18% I/P RD | 2304 | 15104 | 15104 | Approved | 0 | 0 | 559 | 10 Aug 2022
GANGA DHAM TOWERS | 1398 | 95859 | 10 Aug 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 855 | Labour Camp making | MS Square Pipe (L) | 723.8 | Kgs | 14 | 100 | 253.33 | 0 | 10133.2 | C+S GST 18% I/P RD | 1823.98 | 11957.18 | 11957.18 | Approved | 0 | 0 | 559 | 10 Aug 2022
GANGA DHAM TOWERS | 1398 | 95859 | 10 Aug 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 855 | Labour Camp making | MS Angle 50 x 50 x 5mm | 975 | Kgs | 14 | 100 | 341.25 | 0 | 13650 | C+S GST 18% I/P RD | 2457 | 16107 | 16107 | Approved | 0 | 0 | 559 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74.59 | Sq.Ft | 1 | 100 | 1.86 | 0 | 74.59 | C+S GST 18% I/P RD | 13.42 | 88.01 | 88.01 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 79.37 | Sq.Ft | 1 | 100 | 1.98 | 0 | 79.37 | C+S GST 18% I/P RD | 14.28 | 93.65 | 93.65 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 464 | Sq.Ft | 1 | 100 | 11.6 | 0 | 464 | C+S GST 18% I/P RD | 83.52 | 547.52 | 547.52 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 79.37 | Sq.Ft | 1 | 100 | 1.98 | 0 | 79.37 | C+S GST 18% I/P RD | 14.28 | 93.65 | 93.65 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74.59 | Sq.Ft | 1 | 100 | 1.86 | 0 | 74.59 | C+S GST 18% I/P RD | 13.42 | 88.01 | 88.01 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 744 | Sq.Ft | 1 | 100 | 18.6 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | C+S GST 18% I/P RD | 18.72 | 122.72 | 122.72 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 464.55 | Sq.Ft | 1 | 100 | 11.61 | 0 | 464.55 | C+S GST 18% I/P RD | 83.62 | 548.17 | 548.17 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611 | Sq.Ft | 1 | 100 | 15.28 | 0 | 611 | C+S GST 18% I/P RD | 109.98 | 720.98 | 720.98 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611.44 | Sq.Ft | 1 | 100 | 15.29 | 0 | 611.44 | C+S GST 18% I/P RD | 110.06 | 721.5 | 721.5 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90.44 | Sq.Ft | 1 | 100 | 2.26 | 0 | 90.44 | C+S GST 18% I/P RD | 16.28 | 106.72 | 106.72 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 464.55 | Sq.Ft | 1 | 100 | 11.61 | 0 | 464.55 | C+S GST 18% I/P RD | 83.62 | 548.17 | 548.17 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74.59 | Sq.Ft | 1 | 100 | 1.86 | 0 | 74.59 | C+S GST 18% I/P RD | 13.42 | 88.01 | 88.01 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74.59 | Sq.Ft | 1 | 100 | 1.86 | 0 | 74.59 | C+S GST 18% I/P RD | 13.42 | 88.01 | 88.01 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 464.55 | Sq.Ft | 1 | 100 | 11.61 | 0 | 464.55 | C+S GST 18% I/P RD | 83.62 | 548.17 | 548.17 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 79.37 | Sq.Ft | 1 | 100 | 1.98 | 0 | 79.37 | C+S GST 18% I/P RD | 14.28 | 93.65 | 93.65 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104.65 | Sq.Ft | 1 | 100 | 2.62 | 0 | 104.65 | C+S GST 18% I/P RD | 18.84 | 123.49 | 123.49 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 744.86 | Sq.Ft | 1 | 100 | 18.62 | 0 | 744.86 | C+S GST 18% I/P RD | 134.08 | 878.94 | 878.94 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611.44 | Sq.Ft | 1 | 100 | 15.29 | 0 | 611.44 | C+S GST 18% I/P RD | 110.06 | 721.5 | 721.5 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104.65 | Sq.Ft | 1 | 100 | 2.62 | 0 | 104.65 | C+S GST 18% I/P RD | 18.84 | 123.49 | 123.49 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 79 | Sq.Ft | 1 | 100 | 1.98 | 0 | 79 | C+S GST 18% I/P RD | 14.22 | 93.22 | 93.22 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | C+S GST 18% I/P RD | 13.32 | 87.32 | 87.32 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 746 | Sq.Ft | 1 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90.44 | Sq.Ft | 1 | 100 | 2.26 | 0 | 90.44 | C+S GST 18% I/P RD | 16.28 | 106.72 | 106.72 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | C+S GST 18% I/P RD | 18.72 | 122.72 | 122.72 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 744.86 | Sq.Ft | 1 | 100 | 18.62 | 0 | 744.86 | C+S GST 18% I/P RD | 134.08 | 878.94 | 878.94 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 744.86 | Sq.Ft | 1 | 100 | 18.62 | 0 | 744.86 | C+S GST 18% I/P RD | 134.08 | 878.94 | 878.94 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611.44 | Sq.Ft | 1 | 100 | 15.29 | 0 | 611.44 | C+S GST 18% I/P RD | 110.06 | 721.5 | 721.5 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 746 | Sq.Ft | 1 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 744.86 | Sq.Ft | 1 | 100 | 18.62 | 0 | 744.86 | C+S GST 18% I/P RD | 134.08 | 878.94 | 878.94 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 746.18 | Sq.Ft | 1 | 100 | 18.65 | 0 | 746.18 | C+S GST 18% I/P RD | 134.32 | 880.5 | 880.5 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104.65 | Sq.Ft | 1 | 100 | 2.62 | 0 | 104.65 | C+S GST 18% I/P RD | 18.84 | 123.49 | 123.49 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90.44 | Sq.Ft | 1 | 100 | 2.26 | 0 | 90.44 | C+S GST 18% I/P RD | 16.28 | 106.72 | 106.72 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 1902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 746.18 | Sq.Ft | 1 | 100 | 18.65 | 0 | 746.18 | C+S GST 18% I/P RD | 134.32 | 880.5 | 880.5 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95856 | 10 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 825 | A 2103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 464.55 | Sq.Ft | 1 | 100 | 11.61 | 0 | 464.55 | C+S GST 18% I/P RD | 83.62 | 548.17 | 548.17 | Approved | 0 | 0 | 130 | 10 Aug 2022
GANGA DHAM TOWERS | 827 | 95845 | 09 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 845 | A 1802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 79.37 | Sq.Ft | 1 | 100 | 1.98 | 0 | 79.37 | C+S GST 18% I/P RD | 14.28 | 93.65 | 93.65 | Approved | 0 | 0 | 15 | 09 Aug 2022
GANGA DHAM TOWERS | 827 | 95845 | 09 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 845 | A 1801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90.44 | Sq.Ft | 1 | 100 | 2.26 | 0 | 90.44 | C+S GST 18% I/P RD | 16.28 | 106.72 | 106.72 | Approved | 0 | 0 | 15 | 09 Aug 2022
GANGA DHAM TOWERS | 827 | 95845 | 09 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 845 | A 1801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611.44 | Sq.Ft | 1 | 100 | 15.29 | 0 | 611.44 | C+S GST 18% I/P RD | 110.06 | 721.5 | 721.5 | Approved | 0 | 0 | 15 | 09 Aug 2022
GANGA DHAM TOWERS | 827 | 95845 | 09 Aug 2022 |  | CHAPLA ADE PENTING CONTRACTOR | VEER BHADRA ENTERPRISES | EV - 845 | A 1802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 746.18 | Sq.Ft | 1 | 100 | 18.65 | 0 | 746.18 | C+S GST 18% I/P RD | 134.32 | 880.5 | 880.5 | Approved | 0 | 0 | 15 | 09 Aug 2022
GANGA DHAM TOWERS | 372 | 95844 | 09 Aug 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 889 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 40 | Sq.Ft | 155 | 100 | 0 | 0 | 6200 | CGST 0% URD I/P | 0 | 6200 | 6200 | Approved | 0 | 0 | 62 | 09 Aug 2022
GANGA DHAM TOWERS | 413 | 95834 | 08 Aug 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 824 | Sales office Garden Maintenance | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 08 Aug 2022
GANGA DHAM TOWERS | 178 | 95833 | 08 Aug 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 888 | Sales office Garden Maintenance | Garden work. | 57.9948 | Day | 407.25 | 100 | 0 | 0 | 23618.38 | C+S GST 18% I/P RD | 4251.3 | 27869.68 | 27869.68 | Approved | 0 | 0 | 236 | 08 Aug 2022
GANGA DHAM TOWERS | 1296 | 95832 | 08 Aug 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 727 | Miscellaneous expenses | Marketing Operating Expenses | 7.0987 | Month | 25000 | 8.33 | 0 | 0 | 14783 | C+S GST 0% I/P RD | 0 | 14783 | 14783 | Approved | 0 | 0 | 148 | 08 Aug 2022
GANGA DHAM TOWERS | 551 | 95830 | 08 Aug 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 895 | A 1604 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 24.94 | R.Ft | 55 | 100 | 34.29 | 0 | 1371.7 | C+S GST 18% I/P RD | 246.9 | 1618.6 | 1618.6 | Approved | 0 | 0 | 27 | 08 Aug 2022
GANGA DHAM TOWERS | 551 | 95830 | 08 Aug 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 895 | A 1704 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 24.94 | R.Ft | 55 | 100 | 34.29 | 0 | 1371.7 | C+S GST 18% I/P RD | 246.9 | 1618.6 | 1618.6 | Approved | 0 | 0 | 27 | 08 Aug 2022
GANGA DHAM TOWERS | 537 | 95829 | 08 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 891 | A 1502 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.72 | R.Ft | 55 | 100 | 38.12 | 0 | 1524.6 | C+S GST 18% I/P RD | 274.42 | 1799.02 | 1799.02 | Approved | 0 | 0 | 60 | 08 Aug 2022
GANGA DHAM TOWERS | 537 | 95829 | 08 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 891 | A 1801 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 55 | 100 | 36.63 | 0 | 1465.2 | C+S GST 18% I/P RD | 263.74 | 1728.94 | 1728.94 | Approved | 0 | 0 | 60 | 08 Aug 2022
GANGA DHAM TOWERS | 537 | 95829 | 08 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 891 | A 1901 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 26.64 | R.Ft | 60 | 100 | 39.96 | 0 | 1598.4 | C+S GST 18% I/P RD | 287.72 | 1886.12 | 1886.12 | Approved | 0 | 0 | 60 | 08 Aug 2022
GANGA DHAM TOWERS | 537 | 95829 | 08 Aug 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 891 | A 1002 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 27.72 | R.Ft | 50 | 100 | 34.65 | 0 | 1386 | C+S GST 18% I/P RD | 249.48 | 1635.48 | 1635.48 | Approved | 0 | 0 | 60 | 08 Aug 2022
GANGA DHAM TOWERS | 1162 | 95828 | 08 Aug 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 677 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 08 Aug 2022
GANGA DHAM TOWERS | 1228 | 95796 | 05 Aug 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1041 | Site Expenses | Site Expenses -SO | 0.2183 | Month | 30000 | 100 | 0 | 0 | 6550 | CGST 0% URD I/P | 0 | 6550 | 6550 | Approved | 0 | 0 | 0 | 05 Aug 2022
GANGA DHAM TOWERS | 1228 | 95796 | 05 Aug 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 1041 | Site Expenses | Site Expenses -SO | 0.1752 | Month | 30000 | 100 | 0 | 0 | 5255 | CGST 0% URD I/P | 0 | 5255 | 5255 | Approved | 0 | 0 | 0 | 05 Aug 2022
GANGA DHAM TOWERS | 1052 | 95787 | 04 Aug 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 643 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 04 Aug 2022
GANGA DHAM TOWERS | 1208 | 95779 | 04 Aug 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 676 | Tower Crane B-Bldg Annual Maintenance charges of lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 04 Aug 2022
GANGA DHAM TOWERS | 1207 | 95778 | 04 Aug 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 675 | Tower Crane A & C Annual maintenance for tower crane & lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 04 Aug 2022
GANGA DHAM TOWERS | 1231 | 95777 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 697 | Tower A& B Parking 2 & 4 Fire Fighting | SITC GI Pipe C Class 80mm dia.(M+L) | 6.4 | Mtrs | 1400 | 100 | 224 | 0 | 8960 | C+S GST 18% I/P RD | 1612.8 | 10572.8 | 10572.8 | Approved | 0 | 0 | 179 | 04 Aug 2022
GANGA DHAM TOWERS | 300 | 95776 | 04 Aug 2022 |  | AMOL WATER SUPPLIERS | AMOL WATER SUPPLIERS | EV - 941 | Water Supply Water Tanker Supply | Water Tanker supply | 8 | Trips | 800 | 100 | 0 | 0 | 6400 | CGST 0% URD I/P | 0 | 6400 | 6400 | Approved | 0 | 0 | 0 | 04 Aug 2022
GANGA DHAM TOWERS | 1229 | 95775 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 696 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 80mm dia.(M+L) | 36.8 | Mtrs | 1400 | 100 | 1288 | 0 | 51520 | C+S GST 18% I/P RD | 9273.6 | 60793.6 | 60793.6 | Approved | 0 | 0 | 12523 | 04 Aug 2022
GANGA DHAM TOWERS | 1229 | 95775 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 696 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 65mm dia.(M+L) | 24 | Mtrs | 1170 | 100 | 702 | 0 | 28080 | C+S GST 18% I/P RD | 5054.4 | 33134.4 | 33134.4 | Approved | 0 | 0 | 12523 | 04 Aug 2022
GANGA DHAM TOWERS | 1229 | 95775 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 696 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 40mm dia.(M+L) | 264 | Mtrs | 760 | 100 | 5016 | 0 | 200640 | C+S GST 18% I/P URD | 36115.2 | 236755.2 | 236755.2 | Approved | 0 | 0 | 12523 | 04 Aug 2022
GANGA DHAM TOWERS | 1229 | 95775 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 696 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 25mm dia.(M+L) | 566.4 | Mtrs | 510 | 100 | 7221.6 | 0 | 288864 | C+S GST 18% I/P RD | 51995.52 | 340859.52 | 340859.52 | Approved | 0 | 0 | 12523 | 04 Aug 2022
GANGA DHAM TOWERS | 1229 | 95775 | 04 Aug 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 696 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 32mm dia.(M+L) | 86.4 | Mtrs | 660 | 100 | 1425.6 | 0 | 57024 | C+S GST 18% I/P RD | 10264.32 | 67288.32 | 67288.32 | Approved | 0 | 0 | 12523 | 04 Aug 2022
GANGA DHAM TOWERS | 1340 | 95743 | 03 Aug 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 616 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 2202 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1650 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1904 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5152 | No. | 1650 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 2004 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5152 | No. | 1650 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1901 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5152 | No. | 1650 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 2003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5152 | No. | 1650 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 801 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.0833 | No. | 1200 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1803 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7857 | No. | 1400 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1604 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1400 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1804 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1400 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1503 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1404 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1400 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1501 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1802 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7857 | No. | 1400 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 455 | 95734 | 03 Aug 2022 |  | SHWETA SURESH GOVALKAR | SAROJ KUMAR PRADHAN | EV - 684 | A Bldg Flat No. 1603 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 619 | 03 Aug 2022
GANGA DHAM TOWERS | 1382 | 95733 | 03 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN |  | A Bldg. Flat No. 1103 Plumbing work | Int Flat PPRC Work. | 0.2083 | No. | 12000 | 100 | 62.49 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 |  | 0 | 0 | 25 | 03 Aug 2022
GANGA DHAM TOWERS | 1404 | 95732 | 03 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 687 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 11.25 | Flat | 4000 | 100 | 1125 | 0 | 45000 | 0% | 0 | 45000 | 45000 | Approved | 0 | 0 | 4095 | 03 Aug 2022
GANGA DHAM TOWERS | 1404 | 95732 | 03 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 687 | A Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 11.25 | Flat | 4000 | 100 | 1125 | 0 | 45000 | 0% | 0 | 45000 | 45000 | Approved | 0 | 0 | 4095 | 03 Aug 2022
GANGA DHAM TOWERS | 1404 | 95732 | 03 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 687 | A Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 42.3436 | Flat | 3353.52 | 100 | 3550 | 0 | 142000 | 0% | 0 | 142000 | 142000 | Approved | 0 | 0 | 4095 | 03 Aug 2022
GANGA DHAM TOWERS | 1404 | 95732 | 03 Aug 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 687 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 52.9295 | Flat | 3353.52 | 100 | 4437.5 | 0 | 177500 | 0% | 0 | 177500 | 177500 | Approved | 0 | 0 | 4095 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 2nd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 17.75 | R.Ft | 7.5 | 100 | 3.33 | 0 | 133.13 | C+S GST 18% I/P RD | 23.96 | 157.09 | 157.09 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 1st Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 94.1333 | Sq.Ft | 15 | 100 | 35.3 | 0 | 1412 | C+S GST 18% I/P RD | 254.16 | 1666.16 | 1666.16 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 2nd Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 94.1333 | Sq.Ft | 15 | 100 | 35.3 | 0 | 1412 | C+S GST 18% I/P RD | 254.16 | 1666.16 | 1666.16 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 3rd Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 94.1333 | Sq.Ft | 15 | 100 | 35.3 | 0 | 1412 | C+S GST 18% I/P RD | 254.16 | 1666.16 | 1666.16 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 1st Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 17.75 | R.Ft | 7.5 | 100 | 3.33 | 0 | 133.13 | C+S GST 18% I/P RD | 23.96 | 157.09 | 157.09 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 674 | 95731 | 03 Aug 2022 |  | J K INTERIOR | J K INTERIOR | EV - 1503 | B 3rd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 17.75 | R.Ft | 7.5 | 100 | 3.33 | 0 | 133.13 | C+S GST 18% I/P RD | 23.96 | 157.09 | 157.09 | Approved | 0 | 0 | 46 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 3rd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 17.75 | R.Ft | 25 | 100 | 0 | 0 | 443.75 | C+S GST 18% I/P RD | 79.88 | 523.63 | 523.63 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 2nd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 17.75 | R.Ft | 25 | 100 | 0 | 0 | 443.75 | C+S GST 18% I/P RD | 79.88 | 523.63 | 523.63 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 1st Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 17.75 | R.Ft | 25 | 100 | 0 | 0 | 443.75 | C+S GST 18% I/P RD | 79.88 | 523.63 | 523.63 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 2nd Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 94.12 | Sq.Ft | 50 | 100 | 0 | 0 | 4706 | C+S GST 18% I/P RD | 847.08 | 5553.08 | 5553.08 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 3rd Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 94.12 | Sq.Ft | 50 | 100 | 0 | 0 | 4706 | C+S GST 18% I/P RD | 847.08 | 5553.08 | 5553.08 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 673 | 95730 | 03 Aug 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1501 | B 1st Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 94.12 | Sq.Ft | 50 | 100 | 0 | 0 | 4706 | C+S GST 18% I/P RD | 847.08 | 5553.08 | 5553.08 | Approved | 0 | 0 | 0 | 03 Aug 2022
GANGA DHAM TOWERS | 1335 | 95721 | 02 Aug 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 828 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 | Approved | 0 | 0 | 540 | 02 Aug 2022
GANGA DHAM TOWERS | 1336 | 95712 | 02 Aug 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 864 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 345 | 02 Aug 2022
GANGA DHAM TOWERS | 1336 | 95712 | 02 Aug 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 864 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Inspection Charges | 1 | No. | 2500 | 100 | 0 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 345 | 02 Aug 2022
GANGA DHAM TOWERS | 1336 | 95712 | 02 Aug 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 864 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 27000 | 100 | 0 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 345 | 02 Aug 2022
GANGA DHAM TOWERS | 940 | 95711 | 02 Aug 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 751 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Aug 2022
GANGA DHAM TOWERS | 1360 | 95710 | 02 Aug 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 752 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 02 Aug 2022
GANGA DHAM TOWERS | 1228 | 95677 | 30 Jul 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 667 | Site Expenses | Site Expenses -SO | 0.2051 | Month | 30000 | 100 | 0 | 0 | 6154 | CGST 0% URD I/P | 0 | 6154 | 6154 | Approved | 0 | 0 | 0 | 30 Jul 2022
GANGA DHAM TOWERS | 1355 | 95676 | 30 Jul 2022 |  | Kishan Enterprises | JAY BHAVANI ENTERPRISES | EV - 734 | A 1601 NOC | Blockwork 4" - BC | 44 | Sq.Ft | 20 | 100 | 22 | 0 | 880 | CGST 0% URD I/P | 0 | 880 | 880 | Approved | 0 | 0 | 9 | 30 Jul 2022
GANGA DHAM TOWERS | 1186 | 95675 | 30 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 1149 | A 2003 NOC | Blockwork 4" - BC | 17 | Sq.Ft | 22 | 100 | 9.35 | 0 | 374 | CGST 0% URD I/P | 0 | 374 | 374 | Approved | 0 | 0 | 37 | 30 Jul 2022
GANGA DHAM TOWERS | 1186 | 95675 | 30 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 1149 | A 2003 NOC | Blockwork 4" - BC | 153 | Sq.Ft | 22 | 100 | 84.15 | 0 | 3366 | C+S GST 18% I/P RD | 605.88 | 3971.88 | 3971.88 | Approved | 0 | 0 | 37 | 30 Jul 2022
GANGA DHAM TOWERS | 1261 | 95674 | 30 Jul 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 733 | A 1301 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 166 | 30 Jul 2022
GANGA DHAM TOWERS | 1261 | 95674 | 30 Jul 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 733 | A 1004 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 166 | 30 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1502 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5556 | Mtrs | 18 | 100 | 20.5 | 0 | 820 | CGST 0% URD I/P | 0 | 820 | 820 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1602 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5556 | Mtrs | 18 | 100 | 20.5 | 0 | 820 | CGST 0% URD I/P | 0 | 820 | 820 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1102 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5556 | Mtrs | 18 | 100 | 20.5 | 0 | 820 | CGST 0% URD I/P | 0 | 820 | 820 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1502 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 20.1167 | Mtrs | 120 | 100 | 60.35 | 0 | 2414 | CGST 0% URD I/P | 0 | 2414 | 2414 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1602 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 20.1167 | Mtrs | 120 | 100 | 60.35 | 0 | 2414 | CGST 0% URD I/P | 0 | 2414 | 2414 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1102 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 15.95 | Mtrs | 120 | 100 | 47.85 | 0 | 1914 | CGST 0% URD I/P | 0 | 1914 | 1914 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1102 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 4.1667 | Mtrs | 120 | 100 | 12.5 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1602 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1102 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1502 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1602 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 15.95 | Mtrs | 120 | 100 | 47.85 | 0 | 1914 | CGST 0% URD I/P | 0 | 1914 | 1914 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1502 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 15.95 | Mtrs | 120 | 100 | 47.85 | 0 | 1914 | CGST 0% URD I/P | 0 | 1914 | 1914 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1278 | 95664 | 29 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 829 | Tower B 1102 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 15.95 | Mtrs | 120 | 100 | 47.85 | 0 | 1914 | CGST 0% URD I/P | 0 | 1914 | 1914 | Approved | 0 | 0 | 171 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1502 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1602 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1102 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1102 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5385 | Mtrs | 78 | 100 | 0 | 0 | 3552 | C+S GST 18% I/P RD | 639.36 | 4191.36 | 4191.36 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1502 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5385 | Mtrs | 78 | 100 | 0 | 0 | 3552 | C+S GST 18% I/P RD | 639.36 | 4191.36 | 4191.36 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1602 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5385 | Mtrs | 78 | 100 | 0 | 0 | 3552 | C+S GST 18% I/P RD | 639.36 | 4191.36 | 4191.36 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1602 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 20.12 | Mtrs | 700 | 100 | 0 | 0 | 14084 | C+S GST 18% I/P RD | 2535.12 | 16619.12 | 16619.12 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1102 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 20.12 | Mtrs | 700 | 100 | 0 | 0 | 14084 | C+S GST 18% I/P RD | 2535.12 | 16619.12 | 16619.12 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1502 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 20.12 | Mtrs | 700 | 100 | 0 | 0 | 14084 | C+S GST 18% I/P RD | 2535.12 | 16619.12 | 16619.12 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1602 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 15.95 | Mtrs | 700 | 100 | 0 | 0 | 11165 | C+S GST 18% I/P RD | 2009.7 | 13174.7 | 13174.7 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1102 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 15.95 | Mtrs | 700 | 100 | 0 | 0 | 11165 | C+S GST 18% I/P RD | 2009.7 | 13174.7 | 13174.7 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 1277 | 95663 | 29 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 830 | Tower B 1502 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 15.95 | Mtrs | 700 | 100 | 0 | 0 | 11165 | C+S GST 18% I/P RD | 2009.7 | 13174.7 | 13174.7 | Approved | 0 | 0 | 0 | 29 Jul 2022
GANGA DHAM TOWERS | 927 | 95662 | 29 Jul 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 745 | A 21st Floor Back Coat Plaster | Back Coat Plaster | 3 | No. | 2000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 180 | 29 Jul 2022
GANGA DHAM TOWERS | 927 | 95662 | 29 Jul 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 745 | A 22nd Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 180 | 29 Jul 2022
GANGA DHAM TOWERS | 927 | 95662 | 29 Jul 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 745 | A 18th Floor Back Coat Plaster | Back Coat Plaster | 4 | No. | 2000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 180 | 29 Jul 2022
GANGA DHAM TOWERS | 1261 | 95661 | 29 Jul 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 875 | A 1802 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 38 | Sq.Ft | 55 | 100 | 52.25 | 0 | 2090 | CGST 0% URD I/P | 0 | 2090 | 2090 | Approved | 0 | 0 | 42 | 29 Jul 2022
GANGA DHAM TOWERS | 1261 | 95661 | 29 Jul 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 875 | A 1603 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 38.5455 | Sq.Ft | 55 | 100 | 53 | 0 | 2120 | CGST 0% URD I/P | 0 | 2120 | 2120 | Approved | 0 | 0 | 42 | 29 Jul 2022
GANGA DHAM TOWERS | 1382 | 95660 | 29 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 856 | A Bldg. Flat No. 104 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 240 | 29 Jul 2022
GANGA DHAM TOWERS | 1382 | 95660 | 29 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 856 | A Bldg. Flat No. 103 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 240 | 29 Jul 2022
GANGA DHAM TOWERS | 122 | 95659 | 28 Jul 2022 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 761 | C Bldg Excavation Excavtion | Excavation Work (Rate Diff) | 3685.33 | Cu.Mtrs | 285 | 100 | 0 | 0 | 1050319.05 | C+S GST 18% I/P RD | 189057.42 | 1239376.47 | 1239376.47 | Approved | 0 | 177966 | 12555 | 28 Jul 2022
GANGA DHAM TOWERS | 122 | 95659 | 28 Jul 2022 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 761 | C Bldg Excavation Excavtion | Excavation Work (Rate Diff) | 1052.21 | Cu.Mtrs | 195 | 100 | 0 | 0 | 205180.95 | C+S GST 18% I/P RD | 36932.58 | 242113.53 | 242113.53 | Approved | 0 | 177966 | 12555 | 28 Jul 2022
GANGA DHAM TOWERS | 384 | 95657 | 28 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 772 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting rate diff.- BC | 28 | No. | 90 | 100 | 63 | 0 | 2520 | CGST 0% URD I/P | 0 | 2520 | 2520 | Approved | 0 | 0 | 84 | 28 Jul 2022
GANGA DHAM TOWERS | 384 | 95657 | 28 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 772 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting Work 4" BCE | 28 | No. | 210 | 100 | 147 | 0 | 5880 | CGST 0% URD I/P | 0 | 5880 | 5880 | Approved | 0 | 0 | 84 | 28 Jul 2022
GANGA DHAM TOWERS | 631 | 95656 | 28 Jul 2022 |  | J K INTERIOR | J K INTERIOR |  | A 301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 |  | 0 | 0 | 366 | 28 Jul 2022
GANGA DHAM TOWERS | 631 | 95656 | 28 Jul 2022 |  | J K INTERIOR | J K INTERIOR |  | A 1101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 |  | 0 | 0 | 366 | 28 Jul 2022
GANGA DHAM TOWERS | 630 | 95655 | 28 Jul 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) |  | A 301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 75 | Sq.Ft | 55 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 |  | 0 | 0 | 0 | 28 Jul 2022
GANGA DHAM TOWERS | 630 | 95655 | 28 Jul 2022 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) |  | A 1101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 212.5344 | Sq.Ft | 55 | 100 | 0 | 0 | 11689.39 | C+S GST 18% I/P RD | 2104.1 | 13793.49 | 13793.49 |  | 0 | 0 | 0 | 28 Jul 2022
GANGA DHAM TOWERS | 1387 | 95654 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 706 | D Rainwater Line (L) | Rainwater Line | 18 | Flat | 1200 | 100 | 540 | 0 | 21600 | 0% | 0 | 21600 | 21600 | Approved | 0 | 0 | 420 | 27 Jul 2022
GANGA DHAM TOWERS | 1387 | 95654 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 706 | D Rainwater Line (L) | Rainwater Line | 12 | Flat | 1700 | 100 | 510 | 0 | 20400 | 0% | 0 | 20400 | 20400 | Approved | 0 | 0 | 420 | 27 Jul 2022
GANGA DHAM TOWERS | 983 | 95653 | 27 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 708 | A 1st Floor Core Cutting | Core Cutting Work 5" BCE | 15 | No. | 210 | 100 | 78.75 | 0 | 3150 | 0% | 0 | 3150 | 3150 | Approved | 0 | 0 | 189 | 27 Jul 2022
GANGA DHAM TOWERS | 983 | 95653 | 27 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 708 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 40 | No. | 210 | 100 | 210 | 0 | 8400 | 0% | 0 | 8400 | 8400 | Approved | 0 | 0 | 189 | 27 Jul 2022
GANGA DHAM TOWERS | 983 | 95653 | 27 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 708 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 2 | No. | 210 | 100 | 10.5 | 0 | 420 | 0% | 0 | 420 | 420 | Approved | 0 | 0 | 189 | 27 Jul 2022
GANGA DHAM TOWERS | 983 | 95653 | 27 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 708 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 20 | No. | 210 | 100 | 105 | 0 | 4200 | 0% | 0 | 4200 | 4200 | Approved | 0 | 0 | 189 | 27 Jul 2022
GANGA DHAM TOWERS | 983 | 95653 | 27 Jul 2022 |  | PATIL CONSTRUCTION | SAROJ KUMAR PRADHAN | EV - 708 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 13 | No. | 210 | 100 | 68.25 | 0 | 2730 | 0% | 0 | 2730 | 2730 | Approved | 0 | 0 | 189 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 904 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1202 D Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 803 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 702 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 903 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 804 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1004 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1104 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1002 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 703 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1204 D Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 603 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 602 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 704 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1203 D Int. Plumbing PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1103 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 902 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1003 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1102 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 604 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3600 | 100 | 90 | 0 | 3600 | 0% | 0 | 3600 | 3600 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 601 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 701 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 801 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 605 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 705 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 1101 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1386 | 95652 | 27 Jul 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 704 | D 805 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 5100 | 100 | 127.5 | 0 | 5100 | 0% | 0 | 5100 | 5100 | Approved | 0 | 0 | 1077 | 27 Jul 2022
GANGA DHAM TOWERS | 1126 | 95650 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2601 NOC | Steel Removing work | 140 | Kgs | 7.5 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 |  | 0 | 0 | 286 | 27 Jul 2022
GANGA DHAM TOWERS | 1126 | 95650 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2601 NOC | Deshuttering | 102 | Sq.m. | 130 | 100 | 331.5 | 0 | 13260 | C+S GST 18% I/P RD | 2386.8 | 15646.8 | 15646.8 |  | 0 | 0 | 286 | 27 Jul 2022
GANGA DHAM TOWERS | 1127 | 95648 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2301 NOC | Deshuttering | 150 | Sq.m. | 130 | 100 | 487.5 | 0 | 19500 | C+S GST 18% I/P RD | 3510 | 23010 | 23010 |  | 0 | 0 | 420 | 27 Jul 2022
GANGA DHAM TOWERS | 1127 | 95648 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2301 NOC | Steel Removing work | 200 | Kgs | 7.5 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 |  | 0 | 0 | 420 | 27 Jul 2022
GANGA DHAM TOWERS | 1125 | 95647 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2401 NOC | Steel Removing work | 165.0667 | Kgs | 7.5 | 100 | 30.95 | 0 | 1238 | C+S GST 18% I/P RD | 222.84 | 1460.84 | 1460.84 |  | 0 | 0 | 337 | 27 Jul 2022
GANGA DHAM TOWERS | 1125 | 95647 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2401 NOC | Deshuttering | 120 | Sq.m. | 130 | 100 | 390 | 0 | 15600 | C+S GST 18% I/P RD | 2808 | 18408 | 18408 |  | 0 | 0 | 337 | 27 Jul 2022
GANGA DHAM TOWERS | 1124 | 95646 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2502 NOC | Deshuttering | 35 | Sq.m. | 130 | 100 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 |  | 0 | 0 | 98 | 27 Jul 2022
GANGA DHAM TOWERS | 1124 | 95646 | 27 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B 2502 NOC | Steel Removing work | 49.0667 | Kgs | 7.5 | 100 | 9.2 | 0 | 368 | C+S GST 18% I/P RD | 66.24 | 434.24 | 434.24 |  | 0 | 0 | 98 | 27 Jul 2022
GANGA DHAM TOWERS | 1335 | 95645 | 27 Jul 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 872 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 2 | No. | 6000 | 100 | 0 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 120 | 27 Jul 2022
GANGA DHAM TOWERS | 1363 | 95644 | 26 Jul 2022 |  | DEEP MAN ENTERPRISES | DEEP MAN ENTERPRISES | EV - 579 | Borewell work | 6" Bore Well | 150 | R.Ft | 95 | 100 | 0 | 0 | 14250 | C+S GST 18% I/P RD | 2565 | 16815 | 16815 | Approved | 0 | 0 | 143 | 26 Jul 2022
GANGA DHAM TOWERS | 493 | 95643 | 26 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 713 | D Bldg South Side External Plaster | External Plaster- BC | 2047 | Sq.Ft | 35 | 100 | 1791.13 | 0 | 71645 | CGST 0% URD I/P | 0 | 71645 | 71645 | Approved | 0 | 0 | 716 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 6th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 10th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 11th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 12th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 9th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 8th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 7th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 1306 | 95642 | 26 Jul 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 739 | D 5th Floor Ledge wall BBM/ Plaster | Ledge wall Br.work, Plaster | 140.0727 | Sq.Ft | 55 | 100 | 192.6 | 0 | 7704 | CGST 0% URD I/P | 0 | 7704 | 7704 | Approved | 0 | 0 | 616 | 26 Jul 2022
GANGA DHAM TOWERS | 498 | 95641 | 26 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 716 | B 701 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 0.75 | Flat | 1300 | 100 | 97.5 | 0 | 975 | CGST 0% URD I/P | 0 | 975 | 975 | Approved | 0 | 0 | 59 | 26 Jul 2022
GANGA DHAM TOWERS | 498 | 95641 | 26 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 716 | B 1602 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 59 | 26 Jul 2022
GANGA DHAM TOWERS | 498 | 95641 | 26 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 716 | B 101 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 59 | 26 Jul 2022
GANGA DHAM TOWERS | 498 | 95641 | 26 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 716 | B 1301 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 0.75 | Flat | 1300 | 100 | 97.5 | 0 | 975 | CGST 0% URD I/P | 0 | 975 | 975 | Approved | 0 | 0 | 59 | 26 Jul 2022
GANGA DHAM TOWERS | 498 | 95641 | 26 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 716 | B 1401 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 59 | 26 Jul 2022
GANGA DHAM TOWERS | 272 | 95639 | 25 Jul 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 700 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 34.2105 | Sq.Ft | 152 | 100 | 0 | 0 | 5200 | CGST 0% URD I/P | 0 | 5200 | 5200 | Approved | 0 | 0 | 128 | 25 Jul 2022
GANGA DHAM TOWERS | 272 | 95639 | 25 Jul 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 700 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 57.1429 | Sq.Ft | 133 | 100 | 0 | 0 | 7600 | CGST 0% URD I/P | 0 | 7600 | 7600 | Approved | 0 | 0 | 128 | 25 Jul 2022
GANGA DHAM TOWERS | 1249 | 95638 | 25 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 753 | A 2101 NOC | C Groove- BCo | 27 | R.Ft | 60 | 100 | 40.5 | 0 | 1620 | C+S GST 18% I/P RD | 291.6 | 1911.6 | 1911.6 | Approved | 0 | 0 | 495 | 25 Jul 2022
GANGA DHAM TOWERS | 1249 | 95638 | 25 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 753 | A 2101 NOC | Italian marble patti | 527 | R.Ft | 60 | 100 | 790.5 | 0 | 31620 | C+S GST 18% I/P RD | 5691.6 | 37311.6 | 37311.6 | Approved | 0 | 0 | 495 | 25 Jul 2022
GANGA DHAM TOWERS | 1249 | 95638 | 25 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 753 | A 2101 NOC | Italian Marble Door Frame | 18 | R.Ft | 70 | 100 | 31.5 | 0 | 1260 | C+S GST 18% I/P RD | 226.8 | 1486.8 | 1486.8 | Approved | 0 | 0 | 495 | 25 Jul 2022
GANGA DHAM TOWERS | 1249 | 95638 | 25 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 753 | A 2101 NOC | Groove Cutting | 250 | R.Ft | 60 | 100 | 375 | 0 | 15000 | C+S GST 18% I/P RD | 2700 | 17700 | 17700 | Approved | 0 | 0 | 495 | 25 Jul 2022
GANGA DHAM TOWERS | 338 | 95618 | 23 Jul 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 738 | Mandir to Construction Gate barricating work | Excavation & Pole Grouting | 37 | No. | 200 | 100 | 0 | 0 | 7400 | CGST 0% URD I/P | 0 | 7400 | 7400 | Approved | 0 | 0 | 74 | 23 Jul 2022
GANGA DHAM TOWERS | 1130 | 95617 | 23 Jul 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 732 | New Labour Camp Toilet Shifitng & Fixing | Lumpsum work- DCW | 1 | No. | 11000 | 100 | 275 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 110 | 23 Jul 2022
GANGA DHAM TOWERS | 1180 | 95616 | 23 Jul 2022 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 860 | LT Substation rolling shutter work | Scaffolding Fixing Work - DER | 1050 | Sq.Ft | 3 | 100 | 78.75 | 0 | 3150 | CGST 0% URD I/P | 0 | 3150 | 3150 | Approved | 0 | 0 | 32 | 23 Jul 2022
GANGA DHAM TOWERS | 1049 | 95615 | 23 Jul 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 1148 | Breaking of Old Sample flat | Pocklain with Breaker- DTR | 14 | Hrs | 2200 | 100 | 0 | 0 | 30800 | C+S GST 18% I/P RD | 5544 | 36344 | 36344 | Approved | 0 | 0 | 308 | 23 Jul 2022
GANGA DHAM TOWERS | 1393 | 95614 | 23 Jul 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 835 | STP-A.B.C STP Area barrication work | Fastner (M) - SOSB | 20 | No. | 40 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 64 | 23 Jul 2022
GANGA DHAM TOWERS | 1393 | 95614 | 23 Jul 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 835 | STP-A.B.C STP Area barrication work | Meta colour Sheet Fixing BC | 690 | Sq.Ft | 5 | 100 | 86.25 | 0 | 3450 | C+S GST 18% I/P RD | 621 | 4071 | 4071 | Approved | 0 | 0 | 64 | 23 Jul 2022
GANGA DHAM TOWERS | 1393 | 95614 | 23 Jul 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 835 | STP-A.B.C STP Area barrication work | MS Square Pipe (L) | 114.65 | Kgs | 11 | 100 | 31.53 | 0 | 1261.15 | C+S GST 18% I/P RD | 227 | 1488.15 | 1488.15 | Approved | 0 | 0 | 64 | 23 Jul 2022
GANGA DHAM TOWERS | 1393 | 95614 | 23 Jul 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 835 | STP-A.B.C STP Area barrication work | MS Angle. (L) | 4.08 | Kgs | 11 | 100 | 1.12 | 0 | 44.88 | C+S GST 18% I/P RD | 8.08 | 52.96 | 52.96 | Approved | 0 | 0 | 64 | 23 Jul 2022
GANGA DHAM TOWERS | 1393 | 95614 | 23 Jul 2022 |  | MAHALAXMI FABRICATORS | MAHALAXMI FABRICATORS | EV - 835 | STP-A.B.C STP Area barrication work | M.S. Door -BCo | 1 | No. | 800 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 64 | 23 Jul 2022
GANGA DHAM TOWERS | 1391 | 95611 | 22 Jul 2022 |  | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | EV - 595 | Legal Consultancy for CGWB | Legal Consultancy.- | 1 | No. | 40000 | 20 | 0 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 4000 | 22 Jul 2022
GANGA DHAM TOWERS | 1391 | 95611 | 22 Jul 2022 |  | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | EV - 595 | Legal Consultancy for CGWB | Legal Consultancy.- | 1 | No. | 40000 | 80 | 0 | 0 | 32000 | C+S GST 18% I/P RD | 5760 | 37760 | 37760 | Approved | 0 | 0 | 4000 | 22 Jul 2022
GANGA DHAM TOWERS | 1392 | 95598 | 22 Jul 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 719 | A- Aluform Modification Work | Cutting work for Aluform | 1509.3333 | R. Inch | 1.5 | 100 | 56.6 | 0 | 2264 | CGST 0% URD I/P | 0 | 2264 | 2264 | Approved | 0 | 0 | 183 | 22 Jul 2022
GANGA DHAM TOWERS | 1392 | 95598 | 22 Jul 2022 |  | VIKASH KUMAR SINGH | VIKASH KUMAR SINGH | EV - 719 | A- Aluform Modification Work | Welding work for Aluform | 1145 | R. Inch | 14 | 100 | 400.75 | 0 | 16030 | CGST 0% URD I/P | 0 | 16030 | 16030 | Approved | 0 | 0 | 183 | 22 Jul 2022
GANGA DHAM TOWERS | 537 | 95597 | 22 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 686 | A 2001 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 145.656 | Sq.Ft | 28 | 100 | 101.96 | 0 | 4078.37 | C+S GST 18% I/P RD | 734.1 | 4812.47 | 4812.47 | Approved | 0 | 0 | 63 | 22 Jul 2022
GANGA DHAM TOWERS | 537 | 95597 | 22 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 686 | A 1501 Staff Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 63 | 22 Jul 2022
GANGA DHAM TOWERS | 537 | 95597 | 22 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 686 | A 2002 Staff Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 63 | 22 Jul 2022
GANGA DHAM TOWERS | 537 | 95597 | 22 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 686 | A 1901 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 24 | 100 | 23.79 | 0 | 951.48 | C+S GST 18% I/P RD | 171.26 | 1122.74 | 1122.74 | Approved | 0 | 0 | 63 | 22 Jul 2022
GANGA DHAM TOWERS | 537 | 95597 | 22 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 686 | A 2001 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 37.8385 | Sq.Ft | 24 | 100 | 22.7 | 0 | 908.12 | C+S GST 18% I/P RD | 163.46 | 1071.58 | 1071.58 | Approved | 0 | 0 | 63 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1604 Parents Toilet dado | L Groove - BCV | 23.95 | R.Ft | 20 | 100 | 11.98 | 0 | 479 | C+S GST 18% I/P RD | 86.22 | 565.22 | 565.22 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1604 Master Toilet dado | L Groove - BCV | 42.9 | R.Ft | 20 | 100 | 21.45 | 0 | 858 | C+S GST 18% I/P RD | 154.44 | 1012.44 | 1012.44 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1903 Guest Toilet dado | L Groove - BCV | 28.5095 | R.Ft | 20 | 100 | 14.25 | 0 | 570.19 | C+S GST 18% I/P RD | 102.64 | 672.83 | 672.83 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1604 Powder Toilet dado | L Groove - BCV | 31.8 | R.Ft | 20 | 100 | 15.9 | 0 | 636 | C+S GST 18% I/P RD | 114.48 | 750.48 | 750.48 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1903 Children Toilet dado | L Groove - BCV | 40.9165 | R.Ft | 20 | 100 | 20.46 | 0 | 818.33 | C+S GST 18% I/P RD | 147.3 | 965.63 | 965.63 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1903 Master Toilet dado | L Groove - BCV | 41.0685 | R.Ft | 20 | 100 | 20.53 | 0 | 821.37 | C+S GST 18% I/P RD | 147.84 | 969.21 | 969.21 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 551 | 95596 | 22 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 685 | A 1804 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 41.265 | Sq.Ft | 21 | 100 | 21.66 | 0 | 866.57 | C+S GST 18% I/P RD | 155.98 | 1022.55 | 1022.55 | Approved | 0 | 0 | 50 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1104 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 804 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2 | No. | 400 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1105 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 802 (Refuge) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 0.5 | No. | 400 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1204 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1203 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1201 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 805 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2.5 | No. | 400 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1202 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1103 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1101 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 803 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2 | No. | 400 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 801 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2.5 | No. | 400 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 759 | 95595 | 22 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 853 | D 1102 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 194 | 22 Jul 2022
GANGA DHAM TOWERS | 1250 | 95594 | 22 Jul 2022 |  | AVCON TECHNICS PVT LTD | SUSHANT ENTERPRISES | EV - 705 | B 1901 NOC | Bore Packing - cc | 5 | No. | 150 | 100 | 0 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 8 | 22 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 1701 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 2001 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 498 | 95585 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 717 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 149 | 21 Jul 2022
GANGA DHAM TOWERS | 522 | 95584 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 703 | B Bldg 1101 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 5 | No. | 1100 | 100 | 137.5 | 0 | 5500 | CGST 0% URD I/P | 0 | 5500 | 5500 | Approved | 0 | 0 | 274 | 21 Jul 2022
GANGA DHAM TOWERS | 522 | 95584 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 703 | B Bldg 1601 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1250 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 274 | 21 Jul 2022
GANGA DHAM TOWERS | 522 | 95584 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 703 | B Bldg 1001 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1250 | 100 | 218.75 | 0 | 8750 | CGST 0% URD I/P | 0 | 8750 | 8750 | Approved | 0 | 0 | 274 | 21 Jul 2022
GANGA DHAM TOWERS | 522 | 95584 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 703 | B Bldg 1701 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | CGST 0% URD I/P | 0 | 1400 | 1400 | Approved | 0 | 0 | 274 | 21 Jul 2022
GANGA DHAM TOWERS | 522 | 95584 | 21 Jul 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 703 | B Bldg 1701 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 3 | No. | 1400 | 100 | 105 | 0 | 4200 | CGST 0% URD I/P | 0 | 4200 | 4200 | Approved | 0 | 0 | 274 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | Int Plumbing PPRC Work. | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | 5" Bore Packing | 6 | No. | 275 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | IPS Seal Pack. | 2 | No. | 275 | 100 | 55 | 0 | 550 | CGST 0% URD I/P | 0 | 550 | 550 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | Ledge wall Br.work, Plaster | 86 | Sq.Ft | 55 | 100 | 118.25 | 0 | 4730 | CGST 0% URD I/P | 0 | 4730 | 4730 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | Lumpsum work- DCW | 1 | No. | 800 | 100 | 0 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 501 NOC | Bore Packing - cc | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | Chemical W/P (L+M) | 129.87 | Sq.Ft | 22 | 100 | 285.71 | 0 | 2857.14 | CGST 0% URD I/P | 0 | 2857.14 | 2857.14 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | Lumpsum work- DCW | 1 | No. | 400 | 100 | 0 | 0 | 400 | CGST 0% URD I/P | 0 | 400 | 400 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1302 | 95583 | 21 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 1048 | B 1501 NOC | IPS W/P | 129.87 | Sq.Ft | 15 | 100 | 194.81 | 0 | 1948.05 | CGST 0% URD I/P | 0 | 1948.05 | 1948.05 | Approved | 0 | 0 | 142 | 21 Jul 2022
GANGA DHAM TOWERS | 1002 | 95582 | 21 Jul 2022 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 726 | A 2301 NOC | Italian marble Skirting - BCo | 39.053 | R.Ft | 55 | 100 | 53.7 | 0 | 2147.92 | C+S GST 18% I/P RD | 386.62 | 2534.54 | 2534.54 | Approved | 0 | 0 | 21 | 21 Jul 2022
GANGA DHAM TOWERS | 1350 | 95581 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 683 | A 2104 NOC | Italian marble Skirting - BCo | 39.752 | R.Ft | 60 | 100 | 59.63 | 0 | 2385.12 | C+S GST 18% I/P RD | 429.32 | 2814.44 | 2814.44 | Approved | 0 | 0 | 55 | 21 Jul 2022
GANGA DHAM TOWERS | 1350 | 95581 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 683 | A 2101 NOC | Italian marble Skirting - BCo | 51.2 | R.Ft | 60 | 100 | 76.8 | 0 | 3072 | C+S GST 18% I/P RD | 552.96 | 3624.96 | 3624.96 | Approved | 0 | 0 | 55 | 21 Jul 2022
GANGA DHAM TOWERS | 1352 | 95580 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 742 | A 2404 NOC - 1 No. | Italian marble Skirting - BCo | 33.4635 | R.Ft | 60 | 100 | 50.2 | 0 | 2007.81 | C+S GST 18% I/P RD | 361.4 | 2369.21 | 2369.21 | Approved | 0 | 0 | 20 | 21 Jul 2022
GANGA DHAM TOWERS | 1251 | 95579 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 710 | A 1604 NOC - 1 No. | Italian marble Skirting - BCo | 39.752 | R.Ft | 55 | 100 | 54.66 | 0 | 2186.36 | C+S GST 18% I/P RD | 393.54 | 2579.9 | 2579.9 | Approved | 0 | 0 | 212 | 21 Jul 2022
GANGA DHAM TOWERS | 1251 | 95579 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 710 | A 2002 NOC | Italian marble Skirting - BCo | 10.64 | R.Ft | 45 | 100 | 11.97 | 0 | 478.8 | C+S GST 18% I/P RD | 86.18 | 564.98 | 564.98 | Approved | 0 | 0 | 212 | 21 Jul 2022
GANGA DHAM TOWERS | 1251 | 95579 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 710 | A 1604 NOC - 1 No. | Italian Marble Flooring | 177.4909 | Sq.Ft | 55 | 100 | 244.05 | 0 | 9762 | C+S GST 18% I/P RD | 1757.16 | 11519.16 | 11519.16 | Approved | 0 | 0 | 212 | 21 Jul 2022
GANGA DHAM TOWERS | 1251 | 95579 | 21 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 710 | A 1604 NOC - 1 No. | Italian Marble Flooring | 160 | Sq.Ft | 55 | 100 | 220 | 0 | 8800 | C+S GST 18% I/P RD | 1584 | 10384 | 10384 | Approved | 0 | 0 | 212 | 21 Jul 2022
GANGA DHAM TOWERS | 537 | 95578 | 21 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 680 | A 2001 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.6907 | R.Ft | 375 | 100 | 128.35 | 0 | 5134 | C+S GST 18% I/P RD | 924.12 | 6058.12 | 6058.12 | Approved | 0 | 0 | 236 | 21 Jul 2022
GANGA DHAM TOWERS | 537 | 95578 | 21 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 680 | A 1901 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.6907 | R.Ft | 375 | 100 | 128.35 | 0 | 5134 | C+S GST 18% I/P RD | 924.12 | 6058.12 | 6058.12 | Approved | 0 | 0 | 236 | 21 Jul 2022
GANGA DHAM TOWERS | 537 | 95578 | 21 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 680 | A 201 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.69 | R.Ft | 300 | 100 | 102.68 | 0 | 4107 | C+S GST 18% I/P RD | 739.26 | 4846.26 | 4846.26 | Approved | 0 | 0 | 236 | 21 Jul 2022
GANGA DHAM TOWERS | 537 | 95578 | 21 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 680 | A 1201 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.6892 | R.Ft | 325 | 100 | 111.22 | 0 | 4449 | C+S GST 18% I/P RD | 800.82 | 5249.82 | 5249.82 | Approved | 0 | 0 | 236 | 21 Jul 2022
GANGA DHAM TOWERS | 537 | 95578 | 21 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 680 | A 1801 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.6914 | R.Ft | 350 | 100 | 119.8 | 0 | 4792 | C+S GST 18% I/P RD | 862.56 | 5654.56 | 5654.56 | Approved | 0 | 0 | 236 | 21 Jul 2022
GANGA DHAM TOWERS | 1350 | 95561 | 20 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 737 | A 2104 NOC | Italian Marble Flooring - BCo | 177 | Sq.Ft | 60 | 100 | 265.5 | 0 | 10620 | C+S GST 18% I/P RD | 1911.6 | 12531.6 | 12531.6 | Approved | 0 | 0 | 106 | 20 Jul 2022
GANGA DHAM TOWERS | 537 | 95560 | 20 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 725 | A 2002 Staff Toilet dado | Dado BC | 122.721 | Sq.Ft | 24 | 100 | 73.63 | 0 | 2945.3 | C+S GST 18% I/P RD | 530.16 | 3475.46 | 3475.46 | Approved | 0 | 0 | 29 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Parents Toilet dado | Dado BC | 45.5417 | Sq.Ft | 24 | 100 | 27.33 | 0 | 1093 | C+S GST 18% I/P RD | 196.74 | 1289.74 | 1289.74 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Children Toilet Dado | Dado BC | 50.4167 | Sq.Ft | 24 | 100 | 30.25 | 0 | 1210 | C+S GST 18% I/P RD | 217.8 | 1427.8 | 1427.8 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Powder Toilet dado | Dado BC | 36.917 | Sq.Ft | 24 | 100 | 22.15 | 0 | 886.01 | C+S GST 18% I/P RD | 159.48 | 1045.49 | 1045.49 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Powder Toilet dado | Dado BC | 92.492 | Sq.Ft | 22 | 100 | 50.87 | 0 | 2034.82 | C+S GST 18% I/P RD | 366.26 | 2401.08 | 2401.08 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Parents Toilet dado | Dado BC | 100.7273 | Sq.Ft | 22 | 100 | 55.4 | 0 | 2216 | C+S GST 18% I/P RD | 398.88 | 2614.88 | 2614.88 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Children Toilet Dado | Dado BC | 140.714 | Sq.Ft | 22 | 100 | 77.39 | 0 | 3095.71 | C+S GST 18% I/P RD | 557.22 | 3652.93 | 3652.93 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Master Toilet dado | Dado BC | 140.714 | Sq.Ft | 22 | 100 | 77.39 | 0 | 3095.71 | C+S GST 18% I/P RD | 557.22 | 3652.93 | 3652.93 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 2104 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 132.6 | Sq.Ft | 60 | 100 | 198.9 | 0 | 7956 | C+S GST 18% I/P RD | 1432.08 | 9388.08 | 9388.08 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 2104 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.0667 | Sq.Ft | 60 | 100 | 226.6 | 0 | 9064 | C+S GST 18% I/P RD | 1631.52 | 10695.52 | 10695.52 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 2104 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 590.6 | Sq.Ft | 60 | 100 | 885.9 | 0 | 35436 | C+S GST 18% I/P RD | 6378.48 | 41814.48 | 41814.48 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 2104 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.3 | Sq.Ft | 60 | 100 | 315.45 | 0 | 12618 | C+S GST 18% I/P RD | 2271.24 | 14889.24 | 14889.24 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Children Toilet Dado | L Groove - BCV | 37.55 | R.Ft | 20 | 100 | 18.78 | 0 | 751 | C+S GST 18% I/P RD | 135.18 | 886.18 | 886.18 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Master Toilet dado | Dado BC | 51 | Sq.Ft | 24 | 100 | 30.6 | 0 | 1224 | C+S GST 18% I/P RD | 220.32 | 1444.32 | 1444.32 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.505 | Sq.Ft | 21 | 100 | 23.89 | 0 | 955.61 | C+S GST 18% I/P RD | 172 | 1127.61 | 1127.61 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.4105 | Sq.Ft | 21 | 100 | 21.74 | 0 | 869.62 | C+S GST 18% I/P RD | 156.54 | 1026.16 | 1026.16 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.077 | Sq.Ft | 21 | 100 | 25.77 | 0 | 1030.62 | C+S GST 18% I/P RD | 185.52 | 1216.14 | 1216.14 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 551 | 95559 | 20 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 682 | A 1604 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.0865 | Sq.Ft | 21 | 100 | 25.77 | 0 | 1030.82 | C+S GST 18% I/P RD | 185.54 | 1216.36 | 1216.36 | Approved | 0 | 0 | 846 | 20 Jul 2022
GANGA DHAM TOWERS | 1228 | 95558 | 19 Jul 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 854 | Site Expenses | Site Expenses -SO | 0.3313 | Month | 30000 | 100 | 0 | 0 | 9940 | CGST 0% URD I/P | 0 | 9940 | 9940 | Approved | 0 | 0 | 0 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 901 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 17 | No. | 150 | 100 | 255 | 0 | 2550 | CGST 0% URD I/P | 0 | 2550 | 2550 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 23 | No. | 70 | 100 | 161 | 0 | 1610 | CGST 0% URD I/P | 0 | 1610 | 1610 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 901 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 901 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 102 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 259 | Sq.Ft | 19 | 100 | 492.1 | 0 | 4921 | CGST 0% URD I/P | 0 | 4921 | 4921 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 301 | Sq.Ft | 19 | 100 | 571.9 | 0 | 5719 | CGST 0% URD I/P | 0 | 5719 | 5719 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 901 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 280 | Sq.Ft | 19 | 100 | 532 | 0 | 5320 | CGST 0% URD I/P | 0 | 5320 | 5320 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 401 | 95550 | 19 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 879 | A 2101 Chemical Grouting Work | Chemical Grouting.- BC | 1302.3 | Sq.Ft | 1 | 100 | 130.23 | 0 | 1302.3 | CGST 0% URD I/P | 0 | 1302.3 | 1302.3 | Approved | 0 | 0 | 316 | 19 Jul 2022
GANGA DHAM TOWERS | 1169 | 95540 | 19 Jul 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 699 | A Fire Fighting 14 Floors | Sprinkler 15mm 68 dg Pendent (M) | 180 | No. | 229 | 100 | 0 | 0 | 41220 | C+S GST 18% I/P RD | 7419.6 | 48639.6 | 48639.6 | Approved | 0 | 0 | 0 | 19 Jul 2022
GANGA DHAM TOWERS | 1169 | 95540 | 19 Jul 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 699 | A Fire Fighting 14 Floors | Flexible Hose Pipe 25mm Dia (1mtr length) (M) | 196 | No. | 950 | 100 | 0 | 0 | 186200 | C+S GST 18% I/P RD | 33516 | 219716 | 219716 | Approved | 0 | 0 | 0 | 19 Jul 2022
GANGA DHAM TOWERS | 178 | 95538 | 18 Jul 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 553 | Sales office Garden Maintenance | Garden work. | 89.28 | Day | 407.25 | 100 | 0 | 0 | 36359.28 | C+S GST 18% I/P RD | 6544.68 | 42903.96 | 42903.96 | Approved | 0 | 0 | 713 | 18 Jul 2022
GANGA DHAM TOWERS | 178 | 95538 | 18 Jul 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 553 | Sales office Garden Maintenance | Garden work. | 77.49 | Day | 450.89 | 100 | 0 | 0 | 34939.47 | C+S GST 18% I/P RD | 6289.1 | 41228.57 | 41228.57 | Approved | 0 | 0 | 713 | 18 Jul 2022
GANGA DHAM TOWERS | 272 | 95537 | 18 Jul 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 554 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 35.0877 | Sq.Ft | 142.5 | 100 | 0 | 0 | 5000 | C+S GST 0% I/P RD | 0 | 5000 | 5000 | Approved | 0 | 0 | 100 | 18 Jul 2022
GANGA DHAM TOWERS | 272 | 95537 | 18 Jul 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 554 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 35.0877 | Sq.Ft | 142.5 | 100 | 0 | 0 | 5000 | C+S GST 0% I/P RD | 0 | 5000 | 5000 | Approved | 0 | 0 | 100 | 18 Jul 2022
GANGA DHAM TOWERS | 1213 | 95534 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 959 | Tower-B Ceiling Parking Painting work (L) | Primer First Coat | 13939 | Sq.Ft | 0.75 | 100 | 261.36 | 0 | 10454.25 | C+S GST 18% I/P RD | 1881.76 | 12336.01 | 12336.01 | Approved | 0 | 0 | 279 | 18 Jul 2022
GANGA DHAM TOWERS | 1213 | 95534 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 959 | Tower-B Ceiling Parking Painting work (L) | Primer First Coat | 13939 | Sq.Ft | 0.75 | 100 | 261.36 | 0 | 10454.25 | C+S GST 18% I/P RD | 1881.76 | 12336.01 | 12336.01 | Approved | 0 | 0 | 279 | 18 Jul 2022
GANGA DHAM TOWERS | 1213 | 95534 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 959 | Tower-B Ceiling Parking Painting work (L) | Putty with Touchup | 13939 | Sq.Ft | 0.25 | 100 | 87.12 | 0 | 3484.75 | C+S GST 18% I/P RD | 627.26 | 4112.01 | 4112.01 | Approved | 0 | 0 | 279 | 18 Jul 2022
GANGA DHAM TOWERS | 1213 | 95534 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 959 | Tower-B Ceiling Parking Painting work (L) | Putty with Touchup | 13939 | Sq.Ft | 0.25 | 100 | 87.12 | 0 | 3484.75 | C+S GST 18% I/P RD | 627.26 | 4112.01 | 4112.01 | Approved | 0 | 0 | 279 | 18 Jul 2022
GANGA DHAM TOWERS | 1214 | 95533 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 672 | Tower-A Parking Painting work of Ceiling (L) | Primer First Coat | 5960 | Sq.Ft | 0.75 | 100 | 111.75 | 0 | 4470 | C+S GST 18% I/P RD | 804.6 | 5274.6 | 5274.6 | Approved | 0 | 0 | 119 | 18 Jul 2022
GANGA DHAM TOWERS | 1214 | 95533 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 672 | Tower-A Parking Painting work of Ceiling (L) | Primer First Coat | 5960 | Sq.Ft | 0.75 | 100 | 111.75 | 0 | 4470 | C+S GST 18% I/P RD | 804.6 | 5274.6 | 5274.6 | Approved | 0 | 0 | 119 | 18 Jul 2022
GANGA DHAM TOWERS | 1214 | 95533 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 672 | Tower-A Parking Painting work of Ceiling (L) | Putty with Touchup | 5960 | Sq.Ft | 0.25 | 100 | 37.25 | 0 | 1490 | C+S GST 18% I/P RD | 268.2 | 1758.2 | 1758.2 | Approved | 0 | 0 | 119 | 18 Jul 2022
GANGA DHAM TOWERS | 1214 | 95533 | 18 Jul 2022 |  | HINDUSTAN MAINTENANCE COMPANY | VEER BHADRA ENTERPRISES | EV - 672 | Tower-A Parking Painting work of Ceiling (L) | Putty with Touchup | 5960 | Sq.Ft | 0.25 | 100 | 37.25 | 0 | 1490 | C+S GST 18% I/P RD | 268.2 | 1758.2 | 1758.2 | Approved | 0 | 0 | 119 | 18 Jul 2022
GANGA DHAM TOWERS | 634 | 95532 | 18 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 728 | A 25th Floor Lift cladding | Dado Work - BC | 30 | Sq.Ft | 70 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 667 | 18 Jul 2022
GANGA DHAM TOWERS | 634 | 95532 | 18 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 728 | A 25th Floor Lobbby Flooring | Vitrified Flooring -Bco | 649 | Sq.Ft | 45 | 100 | 730.13 | 0 | 29205 | C+S GST 18% I/P RD | 5256.9 | 34461.9 | 34461.9 | Approved | 0 | 0 | 667 | 18 Jul 2022
GANGA DHAM TOWERS | 634 | 95532 | 18 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 728 | A 25th Floor Lobbby Flooring | Vitrified Skirting -Bco | 45 | R.Ft | 45 | 100 | 50.63 | 0 | 2025 | C+S GST 18% I/P RD | 364.5 | 2389.5 | 2389.5 | Approved | 0 | 0 | 667 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 2202 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 60 | 100 | 404.13 | 0 | 16165.2 | C+S GST 18% I/P RD | 2909.74 | 19074.94 | 19074.94 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 2202 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 203.5333 | Sq.Ft | 60 | 100 | 305.3 | 0 | 12212 | C+S GST 18% I/P RD | 2198.16 | 14410.16 | 14410.16 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 2202 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 60 | 100 | 989.34 | 0 | 39573.6 | C+S GST 18% I/P RD | 7123.24 | 46696.84 | 46696.84 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 21 | 100 | 10.53 | 0 | 421.09 | C+S GST 18% I/P RD | 75.8 | 496.89 | 496.89 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.798 | Sq.Ft | 21 | 100 | 11.44 | 0 | 457.76 | C+S GST 18% I/P RD | 82.4 | 540.16 | 540.16 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 21 | 100 | 24.26 | 0 | 970.33 | C+S GST 18% I/P RD | 174.66 | 1144.99 | 1144.99 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Children Toile Vitrified Flooring | Vitrified Flooring -BC | 45.243 | Sq.Ft | 21 | 100 | 23.75 | 0 | 950.1 | C+S GST 18% I/P RD | 171.02 | 1121.12 | 1121.12 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 21 | 100 | 28.23 | 0 | 1129.09 | C+S GST 18% I/P RD | 203.24 | 1332.33 | 1332.33 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 38.457 | Sq.Ft | 21 | 100 | 20.19 | 0 | 807.6 | C+S GST 18% I/P RD | 145.36 | 952.96 | 952.96 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 21 | 100 | 22.3 | 0 | 892.08 | C+S GST 18% I/P RD | 160.58 | 1052.66 | 1052.66 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.667 | Sq.Ft | 21 | 100 | 28.18 | 0 | 1127.01 | C+S GST 18% I/P RD | 202.86 | 1329.87 | 1329.87 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 758 | 95531 | 18 Jul 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 621 | B 1502 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 21 | 100 | 29.14 | 0 | 1165.75 | C+S GST 18% I/P RD | 209.84 | 1375.59 | 1375.59 | Approved | 0 | 0 | 759 | 18 Jul 2022
GANGA DHAM TOWERS | 436 | 95524 | 15 Jul 2022 |  | TANGENT SURVEYORS | VECTOR SURVEYORS | EV - 623 | C Total Station Survey Point Marking | Total Station Point marking- | 1 | Day | 4500 | 100 | 0 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 45 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 3rd Floor Main Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 5th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 2nd Floor Main Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 2nd Floor Fire Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 1st Floor Fire Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 5th Floor Main Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 3rd Floor Fire Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 4th Floor Fire Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 1st Floor Main Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1317 | 95521 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 627 | D 4th Floor Main Staircase Railing | M.S. Railing. (M) | 22.6696 | R.Ft | 342 | 100 | 0 | 0 | 7753 | C+S GST 18% I/P RD | 1395.54 | 9148.54 | 9148.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 5th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 3rd Floor Fire Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 2nd Floor Main Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 4th Floor Main Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 5th Floor Main Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 4th Floor Fire Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 3rd Floor Main Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 1st Floor Fire Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 1st Floor Main Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 1316 | 95520 | 15 Jul 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 714 | D 2nd Floor Fire Staircase Railing | M.S. Railing. (L) | 22.6667 | R.Ft | 120 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 272 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1102 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 42 | Mtrs | 105 | 100 | 0 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1902 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 42 | Mtrs | 105 | 100 | 0 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.8 | Mtrs | 105 | 100 | 0 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1903 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.8 | Mtrs | 105 | 100 | 0 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 901 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 801 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 42 | Mtrs | 105 | 100 | 0 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1501 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1901 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41 | Mtrs | 105 | 100 | 0 | 0 | 4305 | C+S GST 18% I/P RD | 774.9 | 5079.9 | 5079.9 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 40.2 | Mtrs | 105 | 100 | 0 | 0 | 4221 | C+S GST 18% I/P RD | 759.78 | 4980.78 | 4980.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 101 AC Installation & Commissioning | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 37.2 | Mtrs | 105 | 100 | 0 | 0 | 3906 | C+S GST 18% I/P RD | 703.08 | 4609.08 | 4609.08 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 201 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1801 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1501 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1902 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 48 | Mtrs | 19.5 | 100 | 0 | 0 | 936 | C+S GST 18% I/P RD | 168.48 | 1104.48 | 1104.48 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 101 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 38.3077 | Mtrs | 19.5 | 100 | 0 | 0 | 747 | C+S GST 18% I/P RD | 134.46 | 881.46 | 881.46 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 48 | Mtrs | 19.5 | 100 | 0 | 0 | 936 | C+S GST 18% I/P RD | 168.48 | 1104.48 | 1104.48 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 801 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 201 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1801 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 35.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1102 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 48 | Mtrs | 19.5 | 100 | 0 | 0 | 936 | C+S GST 18% I/P RD | 168.48 | 1104.48 | 1104.48 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 35.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 45.2821 | Mtrs | 19.5 | 100 | 0 | 0 | 883 | C+S GST 18% I/P RD | 158.94 | 1041.94 | 1041.94 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 901 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1901 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 201 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1901 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 801 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1801 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 25.9048 | Mtrs | 21 | 100 | 0 | 0 | 544 | C+S GST 18% I/P RD | 97.92 | 641.92 | 641.92 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 901 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1102 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1902 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 23.0952 | Mtrs | 21 | 100 | 0 | 0 | 485 | C+S GST 18% I/P RD | 87.3 | 572.3 | 572.3 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1501 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 1903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 532 | 95519 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 629 | A 101 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 770 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28.8 | Mtrs | 345 | 100 | 0 | 0 | 9936 | C+S GST 18% I/P RD | 1788.48 | 11724.48 | 11724.48 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 42 | Mtrs | 345 | 100 | 0 | 0 | 14490 | C+S GST 18% I/P RD | 2608.2 | 17098.2 | 17098.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1901 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 8.928 | Mtrs | 345 | 100 | 0 | 0 | 3080.16 | C+S GST 18% I/P RD | 554.42 | 3634.58 | 3634.58 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 42 | Mtrs | 345 | 100 | 0 | 0 | 14490 | C+S GST 18% I/P RD | 2608.2 | 17098.2 | 17098.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 38.998 | Mtrs | 345 | 100 | 0 | 0 | 13454.31 | C+S GST 18% I/P RD | 2421.78 | 15876.09 | 15876.09 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1301 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 203 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1401 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1203 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1404 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 28 | Mtrs | 23 | 100 | 0 | 0 | 644 | C+S GST 18% I/P RD | 115.92 | 759.92 | 759.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1303 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1304 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 28 | Mtrs | 23 | 100 | 0 | 0 | 644 | C+S GST 18% I/P RD | 115.92 | 759.92 | 759.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1202 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1201 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1403 AC Installation & Commissioning - 1 No. | Rate Difference for Drain Pipe with Installation (M) | 18 | Mtrs | 23 | 100 | 0 | 0 | 414 | C+S GST 18% I/P RD | 74.52 | 488.52 | 488.52 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1201 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1403 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 35.6129 | Mtrs | 15.5 | 100 | 0 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1901 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1401 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1404 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 46.129 | Mtrs | 15.5 | 100 | 0 | 0 | 715 | C+S GST 18% I/P RD | 128.7 | 843.7 | 843.7 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 203 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 32.9032 | Mtrs | 15.5 | 100 | 0 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1301 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1303 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 35.6129 | Mtrs | 15.5 | 100 | 0 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1701 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 50.5161 | Mtrs | 15.5 | 100 | 0 | 0 | 783 | C+S GST 18% I/P RD | 140.94 | 923.94 | 923.94 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 35.6129 | Mtrs | 15.5 | 100 | 0 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1203 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 35.6129 | Mtrs | 15.5 | 100 | 0 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1304 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 46.129 | Mtrs | 15.5 | 100 | 0 | 0 | 715 | C+S GST 18% I/P RD | 128.7 | 843.7 | 843.7 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1202 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 48 | Mtrs | 15.5 | 100 | 0 | 0 | 744 | C+S GST 18% I/P RD | 133.92 | 877.92 | 877.92 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | 35.6129 | Mtrs | 15.5 | 100 | 0 | 0 | 552 | C+S GST 18% I/P RD | 99.36 | 651.36 | 651.36 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 42 | Mtrs | 345 | 100 | 0 | 0 | 14490 | C+S GST 18% I/P RD | 2608.2 | 17098.2 | 17098.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 42 | Mtrs | 345 | 100 | 0 | 0 | 14490 | C+S GST 18% I/P RD | 2608.2 | 17098.2 | 17098.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 48 | Mtrs | 60.5 | 100 | 0 | 0 | 2904 | C+S GST 18% I/P RD | 522.72 | 3426.72 | 3426.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1901 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.7055 | Mtrs | 60.5 | 100 | 0 | 0 | 2160.18 | C+S GST 18% I/P RD | 388.84 | 2549.02 | 2549.02 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 48 | Mtrs | 60.5 | 100 | 0 | 0 | 2904 | C+S GST 18% I/P RD | 522.72 | 3426.72 | 3426.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 48 | Mtrs | 60.5 | 100 | 0 | 0 | 2904 | C+S GST 18% I/P RD | 522.72 | 3426.72 | 3426.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 48 | Mtrs | 60.5 | 100 | 0 | 0 | 2904 | C+S GST 18% I/P RD | 522.72 | 3426.72 | 3426.72 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1901 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18.6939 | Mtrs | 49 | 100 | 0 | 0 | 916 | C+S GST 18% I/P RD | 164.88 | 1080.88 | 1080.88 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1403 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 28.8 | Mtrs | 355 | 100 | 0 | 0 | 10224 | C+S GST 18% I/P RD | 1840.32 | 12064.32 | 12064.32 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1203 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 28.8 | Mtrs | 355 | 100 | 0 | 0 | 10224 | C+S GST 18% I/P RD | 1840.32 | 12064.32 | 12064.32 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1303 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 28.8 | Mtrs | 355 | 100 | 0 | 0 | 10224 | C+S GST 18% I/P RD | 1840.32 | 12064.32 | 12064.32 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1801 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 502 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1701 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 37.9014 | Mtrs | 355 | 100 | 0 | 0 | 13455 | C+S GST 18% I/P RD | 2421.9 | 15876.9 | 15876.9 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1301 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1304 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 38 | Mtrs | 355 | 100 | 0 | 0 | 13490 | C+S GST 18% I/P RD | 2428.2 | 15918.2 | 15918.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 203 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 27.6 | Mtrs | 355 | 100 | 0 | 0 | 9798 | C+S GST 18% I/P RD | 1763.64 | 11561.64 | 11561.64 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1401 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1201 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1202 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1901 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 28.8 | Mtrs | 355 | 100 | 0 | 0 | 10224 | C+S GST 18% I/P RD | 1840.32 | 12064.32 | 12064.32 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 42 | Mtrs | 355 | 100 | 0 | 0 | 14910 | C+S GST 18% I/P RD | 2683.8 | 17593.8 | 17593.8 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 201 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1404 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 38 | Mtrs | 355 | 100 | 0 | 0 | 13490 | C+S GST 18% I/P RD | 2428.2 | 15918.2 | 15918.2 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 41.1014 | Mtrs | 355 | 100 | 0 | 0 | 14591 | C+S GST 18% I/P RD | 2626.38 | 17217.38 | 17217.38 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1503 AC Installation & Commissioning - 1 No. | Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | 28.8 | Mtrs | 355 | 100 | 0 | 0 | 10224 | C+S GST 18% I/P RD | 1840.32 | 12064.32 | 12064.32 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 801 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 901 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1102 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1501 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.4898 | Mtrs | 49 | 100 | 0 | 0 | 1053 | C+S GST 18% I/P RD | 189.54 | 1242.54 | 1242.54 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1902 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 1502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 101 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 530 | 95518 | 15 Jul 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 630 | A 702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 24.4898 | Mtrs | 49 | 100 | 0 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 0 | 15 Jul 2022
GANGA DHAM TOWERS | 384 | 95511 | 14 Jul 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 540 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting rate diff.- BC | 78 | No. | 90 | 100 | 175.5 | 0 | 7020 | CGST 0% URD I/P | 0 | 7020 | 7020 | Approved | 0 | 0 | 101 | 14 Jul 2022
GANGA DHAM TOWERS | 384 | 95511 | 14 Jul 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 540 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting rate diff.- BC | 34 | No. | 90 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 101 | 14 Jul 2022
GANGA DHAM TOWERS | 407 | 95501 | 14 Jul 2022 |  | SHANKAR VILAS GAIKWAD | SHANKAR VILAS GAIKWAD |  | Drainage Line Manual Excavation & Filling work | Excavation (manually)- Dld | 2488.43 | Cu.Ft | 7 | 100 | 0 | 0 | 17419.01 | CGST 0% URD I/P | 0 | 17419.01 | 17419.01 |  | 0 | 0 | 174 | 14 Jul 2022
GANGA DHAM TOWERS | 407 | 95500 | 14 Jul 2022 |  | SHANKAR VILAS GAIKWAD | PRAKASH CONTRACTOR | EV - 741 | Fire Fighting Line Excavation & Filling | Excavation (manually)- Dld | 1000 | Cu.Ft | 7 | 100 | 0 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 70 | 14 Jul 2022
GANGA DHAM TOWERS | 957 | 95499 | 14 Jul 2022 |  | LAXMI ELECTRICALS | PRAKASH CONTRACTOR | EV - 698 | Electricity Infrastructure-Trnsformer,HT,LT Work | Excavation work.- UTI | 30.625 | Mtrs | 160 | 100 | 0 | 0 | 4900 | CGST 0% URD I/P | 0 | 4900 | 4900 | Approved | 0 | 0 | 49 | 14 Jul 2022
GANGA DHAM TOWERS | 1224 | 95498 | 14 Jul 2022 |  | DURGARAM CHANDURAM BHATEE | PRAKASH CONTRACTOR | EV - 731 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 13 | Day | 466.67 | 100 | 0 | 0 | 6066.71 | CGST 0% URD I/P | 0 | 6066.71 | 6066.71 | Approved | 0 | 0 | 61 | 14 Jul 2022
GANGA DHAM TOWERS | 634 | 95497 | 14 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 729 | A 25th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 3033 | 14 Jul 2022
GANGA DHAM TOWERS | 634 | 95497 | 14 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 729 | A 25th Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 3033 | 14 Jul 2022
GANGA DHAM TOWERS | 634 | 95497 | 14 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 729 | A 25th Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 3033 | 14 Jul 2022
GANGA DHAM TOWERS | 634 | 95497 | 14 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 729 | A 25th Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 3033 | 14 Jul 2022
GANGA DHAM TOWERS | 634 | 95497 | 14 Jul 2022 |  | R K INTERIOR | R K INTERIOR | EV - 729 | A 25th Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 3033 | 14 Jul 2022
GANGA DHAM TOWERS | 724 | 95492 | 13 Jul 2022 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 718 | A Ground Floor Parking Trimix work | Trimix Work - BC | 7687 | Sq.Ft | 9 | 100 | 1729.58 | 0 | 69183 | CGST 0% URD I/P | 0 | 69183 | 69183 | Approved | 0 | 0 | 769 | 13 Jul 2022
GANGA DHAM TOWERS | 724 | 95492 | 13 Jul 2022 |  | MUKESH CONSTRUCTIONS | HOLE ENTERPRISES | EV - 718 | A Parking Floor 1 Trimix work (L) - | Weld mesh fixing(L) BCo | 7687 | Sq.Ft | 1 | 100 | 192.18 | 0 | 7687 | CGST 0% URD I/P | 0 | 7687 | 7687 | Approved | 0 | 0 | 769 | 13 Jul 2022
GANGA DHAM TOWERS | 957 | 95489 | 13 Jul 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 744 | Electricity Infrastructure-Trnsformer,HT,LT Work | Earthing work(m+l)- BC | 13 | No. | 4000 | 100 | 1300 | 0 | 52000 | CGST 0% URD I/P | 0 | 52000 | 52000 | Approved | 0 | 0 | 1062 | 13 Jul 2022
GANGA DHAM TOWERS | 957 | 95489 | 13 Jul 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 744 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 50x5 (M+L) -UTI | 43 | Mtrs | 235 | 100 | 252.63 | 0 | 10105 | CGST 0% URD I/P | 0 | 10105 | 10105 | Approved | 0 | 0 | 1062 | 13 Jul 2022
GANGA DHAM TOWERS | 957 | 95489 | 13 Jul 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 744 | Electricity Infrastructure-Trnsformer,HT,LT Work | Earthing Pits exc.- UDG | 26 | No. | 1000 | 100 | 650 | 0 | 26000 | CGST 0% URD I/P | 0 | 26000 | 26000 | Approved | 0 | 0 | 1062 | 13 Jul 2022
GANGA DHAM TOWERS | 957 | 95489 | 13 Jul 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 744 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 32x6 fixing. -UTI | 70 | Mtrs | 180 | 100 | 315 | 0 | 12600 | CGST 0% URD I/P | 0 | 12600 | 12600 | Approved | 0 | 0 | 1062 | 13 Jul 2022
GANGA DHAM TOWERS | 957 | 95489 | 13 Jul 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 744 | Electricity Infrastructure-Trnsformer,HT,LT Work | XLPE Cable laying 95sqmm 3C 22kv (L) | 50 | Mtrs | 110 | 100 | 137.5 | 0 | 5500 | CGST 0% URD I/P | 0 | 5500 | 5500 | Approved | 0 | 0 | 1062 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 901 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 603 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 604 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 905 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1105 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 605 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1001 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1101 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 601 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 902 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 803 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 703 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 802 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 701 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1003 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 903 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1005 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1102 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 704 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 804 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 602 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 801 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1103 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 702 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 805 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 904 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1104 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1002 Window Box IPS Waterproofing | IPS W/P | 35.8182 | Sq.Ft | 11 | 100 | 39.4 | 0 | 394 | CGST 0% URD I/P | 0 | 394 | 394 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 705 Window Box IPS Waterproofing | IPS W/P | 55.1818 | Sq.Ft | 11 | 100 | 60.7 | 0 | 607 | CGST 0% URD I/P | 0 | 607 | 607 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 770 | 95486 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 695 | D 1004 Window Box IPS Waterproofing | IPS W/P | 19.3636 | Sq.Ft | 11 | 100 | 21.3 | 0 | 213 | CGST 0% URD I/P | 0 | 213 | 213 | Approved | 0 | 0 | 122 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1204 Window Box IPS Waterproofing | IPS W/P | 19.3333 | Sq.Ft | 15 | 100 | 29 | 0 | 290 | C+S GST 0% I/P RD | 0 | 290 | 290 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1201 Window Box IPS Waterproofing | IPS W/P | 55.2 | Sq.Ft | 15 | 100 | 82.8 | 0 | 828 | C+S GST 0% I/P RD | 0 | 828 | 828 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1205 Window Box IPS Waterproofing | IPS W/P | 55.2 | Sq.Ft | 15 | 100 | 82.8 | 0 | 828 | C+S GST 0% I/P RD | 0 | 828 | 828 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1202 Window Box IPS Waterproofing | IPS W/P | 35.8 | Sq.Ft | 15 | 100 | 53.7 | 0 | 537 | C+S GST 0% I/P RD | 0 | 537 | 537 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1203 Window Box IPS Waterproofing | IPS W/P | 19.3333 | Sq.Ft | 15 | 100 | 29 | 0 | 290 | C+S GST 0% I/P RD | 0 | 290 | 290 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1202 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 37.8636 | Sq.Ft | 22 | 100 | 83.3 | 0 | 833 | C+S GST 0% I/P RD | 0 | 833 | 833 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1204 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 37 | Sq.Ft | 22 | 100 | 81.4 | 0 | 814 | C+S GST 0% I/P RD | 0 | 814 | 814 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1203 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 37 | Sq.Ft | 22 | 100 | 81.4 | 0 | 814 | C+S GST 0% I/P RD | 0 | 814 | 814 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1201 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 63.1818 | Sq.Ft | 22 | 100 | 139 | 0 | 1390 | C+S GST 0% I/P RD | 0 | 1390 | 1390 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1320 | 95485 | 13 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 711 | D 1205 Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 63.1818 | Sq.Ft | 22 | 100 | 139 | 0 | 1390 | C+S GST 0% I/P RD | 0 | 1390 | 1390 | Approved | 0 | 0 | 80 | 13 Jul 2022
GANGA DHAM TOWERS | 1340 | 95476 | 12 Jul 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 501 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 12 Jul 2022
GANGA DHAM TOWERS | 1320 | 95471 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 890 | D 1205 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 55.1818 | Sq.Ft | 22 | 100 | 121.4 | 0 | 1214 | C+S GST 0% I/P RD | 0 | 1214 | 1214 | Approved | 0 | 0 | 41 | 12 Jul 2022
GANGA DHAM TOWERS | 1320 | 95471 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 890 | D 1203 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 19.3636 | Sq.Ft | 22 | 100 | 42.6 | 0 | 426 | C+S GST 0% I/P RD | 0 | 426 | 426 | Approved | 0 | 0 | 41 | 12 Jul 2022
GANGA DHAM TOWERS | 1320 | 95471 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 890 | D 1202 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 35.8182 | Sq.Ft | 22 | 100 | 78.8 | 0 | 788 | C+S GST 0% I/P RD | 0 | 788 | 788 | Approved | 0 | 0 | 41 | 12 Jul 2022
GANGA DHAM TOWERS | 1320 | 95471 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 890 | D 1204 Window Box Chemical Waterproofing | Chemical Waterproofing (M+L).Sq.ft | 19.3636 | Sq.Ft | 22 | 100 | 42.6 | 0 | 426 | C+S GST 0% I/P RD | 0 | 426 | 426 | Approved | 0 | 0 | 41 | 12 Jul 2022
GANGA DHAM TOWERS | 1320 | 95471 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 890 | D 1201 Window Box Chemical Waterproofing - | Chemical Waterproofing (M+L).Sq.ft | 55.1818 | Sq.Ft | 22 | 100 | 121.4 | 0 | 1214 | C+S GST 0% I/P RD | 0 | 1214 | 1214 | Approved | 0 | 0 | 41 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 901 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 802 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 705 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 605 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.7895 | Sq.Ft | 9.5 | 100 | 53 | 0 | 530 | CGST 0% URD I/P | 0 | 530 | 530 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1105 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 701 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 803 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 804 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1003 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 703 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 601 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1005 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 904 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 604 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 801 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 902 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 702 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 805 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1002 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1001 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1004 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1104 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 603 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 903 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 704 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 602 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 905 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1101 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 55.1579 | Sq.Ft | 9.5 | 100 | 52.4 | 0 | 524 | CGST 0% URD I/P | 0 | 524 | 524 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1102 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 35.7895 | Sq.Ft | 9.5 | 100 | 34 | 0 | 340 | CGST 0% URD I/P | 0 | 340 | 340 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 770 | 95470 | 12 Jul 2022 |  | SUSHANT ENTERPRISES | AJAY KUMAR GUPTA | EV - 833 | D 1103 Window Box Chemical Waterproofing | Chemical Waterproofing (L) | 19.3684 | Sq.Ft | 9.5 | 100 | 18.4 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 105 | 12 Jul 2022
GANGA DHAM TOWERS | 1326 | 95454 | 09 Jul 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 987 | A- Aluform Modification Work | Cutting work for Aluform | 1200 | R. Inch | 1.5 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 321 | 09 Jul 2022
GANGA DHAM TOWERS | 1326 | 95454 | 09 Jul 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 987 | A- Aluform Modification Work | Cutting work for Aluform | 1500 | R. Inch | 1.5 | 100 | 56.25 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 321 | 09 Jul 2022
GANGA DHAM TOWERS | 1326 | 95454 | 09 Jul 2022 |  | REY ENTERPRISES | REY ENTERPRISES | EV - 987 | A- Aluform Modification Work | Welding work for Aluform | 2000 | R. Inch | 14 | 100 | 700 | 0 | 28000 | C+S GST 18% I/P RD | 5040 | 33040 | 33040 | Approved | 0 | 0 | 321 | 09 Jul 2022
GANGA DHAM TOWERS | 468 | 95453 | 09 Jul 2022 |  | ANJALI ENTERPRISES | ANAND LALURAM SUTHAR | EV - 1461 | Tower-A Temporary Doors Upto 26th Floor | Temporary Door Fixing | 18 | No. | 200 | 100 | 90 | 0 | 3600 | CGST 0% URD I/P | 0 | 3600 | 3600 | Approved | 0 | 0 | 36 | 09 Jul 2022
GANGA DHAM TOWERS | 1012 | 95452 | 09 Jul 2022 |  | LALURAM B SHARMA | ANAND LALURAM SUTHAR | EV - 1462 | A Temporary Door Maintanance Work | Door Repairing Work | 4 | No. | 200 | 100 | 0 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 8 | 09 Jul 2022
GANGA DHAM TOWERS | 1184 | 95451 | 09 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 587 | D 11th to 12th Floor Staircase 1 & 2 Riser Plaster - 1 No | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 80 | 09 Jul 2022
GANGA DHAM TOWERS | 1184 | 95451 | 09 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 587 | D 10th to 11th Floor Staircase 1 & 2 Riser Plaster - 1 No | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 80 | 09 Jul 2022
GANGA DHAM TOWERS | 493 | 95450 | 09 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 555 | D Bldg South Side External Plaster | External Plaster- BC | 4780 | Sq.Ft | 35 | 100 | 4182.5 | 0 | 167300 | CGST 0% URD I/P | 0 | 167300 | 167300 | Approved | 0 | 0 | 1923 | 09 Jul 2022
GANGA DHAM TOWERS | 493 | 95450 | 09 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 555 | D Bldg South Side External Plaster | External Plaster- BC | 445.6 | Sq.Ft | 35 | 100 | 389.9 | 0 | 15596 | CGST 0% URD I/P | 0 | 15596 | 15596 | Approved | 0 | 0 | 1923 | 09 Jul 2022
GANGA DHAM TOWERS | 493 | 95450 | 09 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 555 | D Bldg North Side External Plaster | External Plaster- BC | 337 | Sq.Ft | 28 | 100 | 235.9 | 0 | 9436 | CGST 0% URD I/P | 0 | 9436 | 9436 | Approved | 0 | 0 | 1923 | 09 Jul 2022
GANGA DHAM TOWERS | 371 | 95449 | 09 Jul 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 873 | EWS Bldg RCC 11th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 35 | Sq.Ft | 150 | 100 | 131.25 | 0 | 5250 | CGST 0% URD I/P | 0 | 5250 | 5250 | Approved | 0 | 0 | 290 | 09 Jul 2022
GANGA DHAM TOWERS | 371 | 95449 | 09 Jul 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 873 | EWS Bldg RCC 9th Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | CGST 0% URD I/P | 0 | 8547.88 | 8547.88 | Approved | 0 | 0 | 290 | 09 Jul 2022
GANGA DHAM TOWERS | 371 | 95449 | 09 Jul 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 873 | EWS Bldg RCC 8th Slab Built-up Area (L) | Hacking Work | 2567.2 | Sq.Ft | 2.5 | 100 | 160.45 | 0 | 6418 | CGST 0% URD I/P | 0 | 6418 | 6418 | Approved | 0 | 0 | 290 | 09 Jul 2022
GANGA DHAM TOWERS | 371 | 95449 | 09 Jul 2022 |  | CONSTROGENESIS | JAY GANESH ENTERPRISES | EV - 873 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 55 | Sq.Ft | 160 | 100 | 220 | 0 | 8800 | CGST 0% URD I/P | 0 | 8800 | 8800 | Approved | 0 | 0 | 290 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 1202 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.5583 | Mtrs | 120 | 100 | 67.67 | 0 | 2707 | CGST 0% URD I/P | 0 | 2707 | 2707 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 902 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.5583 | Mtrs | 120 | 100 | 67.67 | 0 | 2707 | CGST 0% URD I/P | 0 | 2707 | 2707 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 902 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5556 | Mtrs | 18 | 100 | 20.5 | 0 | 820 | CGST 0% URD I/P | 0 | 820 | 820 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 1202 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 20.9484 | Mtrs | 18 | 100 | 9.43 | 0 | 377.07 | CGST 0% URD I/P | 0 | 377.07 | 377.07 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 1202 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 24.4444 | Mtrs | 18 | 100 | 11 | 0 | 440 | CGST 0% URD I/P | 0 | 440 | 440 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 902 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 1202 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 902 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1278 | 95448 | 09 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 832 | Tower B 1202 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.4 | Mtrs | 20 | 100 | 14.2 | 0 | 568 | CGST 0% URD I/P | 0 | 568 | 568 | Approved | 0 | 0 | 114 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 1202 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 902 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 1202 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.26 | Mtrs | 700 | 100 | 0 | 0 | 15582 | C+S GST 18% I/P RD | 2804.76 | 18386.76 | 18386.76 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 902 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.56 | Mtrs | 700 | 100 | 0 | 0 | 15792 | C+S GST 18% I/P RD | 2842.56 | 18634.56 | 18634.56 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 902 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 1202 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 902 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5385 | Mtrs | 78 | 100 | 0 | 0 | 3552 | C+S GST 18% I/P RD | 639.36 | 4191.36 | 4191.36 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1277 | 95447 | 09 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 831 | Tower B 1202 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5385 | Mtrs | 78 | 100 | 0 | 0 | 3552 | C+S GST 18% I/P RD | 639.36 | 4191.36 | 4191.36 | Approved | 0 | 0 | 0 | 09 Jul 2022
GANGA DHAM TOWERS | 1228 | 95437 | 08 Jul 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 527 | Site Expenses | Site Expenses -SO | 0.0073 | Month | 15000 | 100 | 0 | 0 | 110 | C+S GST 0% I/P RD | 0 | 110 | 110 | Approved | 0 | 0 | 0 | 08 Jul 2022
GANGA DHAM TOWERS | 1228 | 95437 | 08 Jul 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 527 | Site Expenses | Site Expenses -SO | 0.0437 | Month | 30000 | 100 | 0 | 0 | 1310 | CGST 0% URD I/P | 0 | 1310 | 1310 | Approved | 0 | 0 | 0 | 08 Jul 2022
GANGA DHAM TOWERS | 1228 | 95437 | 08 Jul 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 527 | Site Expenses | Site Expenses -SO | 0.2138 | Month | 30000 | 100 | 0 | 0 | 6415 | CGST 0% URD I/P | 0 | 6415 | 6415 | Approved | 0 | 0 | 0 | 08 Jul 2022
GANGA DHAM TOWERS | 1052 | 95433 | 08 Jul 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 474 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 08 Jul 2022
GANGA DHAM TOWERS | 1162 | 95429 | 08 Jul 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 590 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 0.9666 | Month | 5000 | 100 | 0 | 0 | 4833 | CGST 0% URD I/P | 0 | 4833 | 4833 | Approved | 0 | 0 | 48 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Staff Room Vitrified Flooring | Vitrified Skirting BC | 16.207 | R.Ft | 17 | 100 | 6.89 | 0 | 275.52 | C+S GST 18% I/P RD | 49.6 | 325.12 | 325.12 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 28 | 100 | 84.54 | 0 | 3381.59 | C+S GST 18% I/P RD | 608.68 | 3990.27 | 3990.27 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 28 | 100 | 80.3 | 0 | 3211.99 | C+S GST 18% I/P RD | 578.16 | 3790.15 | 3790.15 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 28 | 100 | 41.04 | 0 | 1641.53 | C+S GST 18% I/P RD | 295.48 | 1937.01 | 1937.01 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 28 | 100 | 93.45 | 0 | 3738.17 | C+S GST 18% I/P RD | 672.88 | 4411.05 | 4411.05 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 28 | 100 | 44.53 | 0 | 1781.14 | C+S GST 18% I/P RD | 320.6 | 2101.74 | 2101.74 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 28 | 100 | 24.48 | 0 | 979.27 | C+S GST 18% I/P RD | 176.26 | 1155.53 | 1155.53 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 28 | 100 | 46.52 | 0 | 1860.77 | C+S GST 18% I/P RD | 334.94 | 2195.71 | 2195.71 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 24 | 100 | 35.18 | 0 | 1407.02 | C+S GST 18% I/P RD | 253.26 | 1660.28 | 1660.28 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 24 | 100 | 39.87 | 0 | 1594.94 | C+S GST 18% I/P RD | 287.08 | 1882.02 | 1882.02 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 24 | 100 | 20.98 | 0 | 839.38 | C+S GST 18% I/P RD | 151.08 | 990.46 | 990.46 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Staff Toilet dado | Dado BC | 110.214 | Sq.Ft | 17 | 100 | 46.84 | 0 | 1873.64 | C+S GST 18% I/P RD | 337.26 | 2210.9 | 2210.9 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.103 | Sq.Ft | 21 | 100 | 26.3 | 0 | 1052.16 | C+S GST 18% I/P RD | 189.38 | 1241.54 | 1241.54 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.804 | Sq.Ft | 21 | 100 | 25.1 | 0 | 1003.88 | C+S GST 18% I/P RD | 180.7 | 1184.58 | 1184.58 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Children Toilet Flooring | Vitrified Flooring -BC | 46.626 | Sq.Ft | 21 | 100 | 24.48 | 0 | 979.15 | C+S GST 18% I/P RD | 176.24 | 1155.39 | 1155.39 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Children Toilet Flooring | Vitrified Flooring -BC | 46.626 | Sq.Ft | 24 | 100 | 27.98 | 0 | 1119.02 | C+S GST 18% I/P RD | 201.42 | 1320.44 | 1320.44 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.103 | Sq.Ft | 24 | 100 | 30.06 | 0 | 1202.47 | C+S GST 18% I/P RD | 216.44 | 1418.91 | 1418.91 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.804 | Sq.Ft | 24 | 100 | 28.68 | 0 | 1147.3 | C+S GST 18% I/P RD | 206.52 | 1353.82 | 1353.82 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.4105 | Sq.Ft | 21 | 100 | 21.74 | 0 | 869.62 | C+S GST 18% I/P RD | 156.54 | 1026.16 | 1026.16 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.4105 | Sq.Ft | 24 | 100 | 24.85 | 0 | 993.85 | C+S GST 18% I/P RD | 178.9 | 1172.75 | 1172.75 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Children Toilet | L Groove - BCV | 30.8465 | R.Ft | 20 | 100 | 15.42 | 0 | 616.93 | C+S GST 18% I/P RD | 111.04 | 727.97 | 727.97 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Master Toilet dado | L Groove - BCV | 30.5995 | R.Ft | 20 | 100 | 15.3 | 0 | 611.99 | C+S GST 18% I/P RD | 110.16 | 722.15 | 722.15 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Parents Toilet dado | L Groove - BCV | 38.4845 | R.Ft | 20 | 100 | 19.24 | 0 | 769.69 | C+S GST 18% I/P RD | 138.54 | 908.23 | 908.23 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Children Toilet dado | L Groove - BCV | 35.682 | R.Ft | 20 | 100 | 17.84 | 0 | 713.64 | C+S GST 18% I/P RD | 128.46 | 842.1 | 842.1 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Powder Toilet dado | L Groove - BCV | 33.1835 | R.Ft | 20 | 100 | 16.59 | 0 | 663.67 | C+S GST 18% I/P RD | 119.46 | 783.13 | 783.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Parents Toilet dado | L Groove - BCV | 40.8215 | R.Ft | 20 | 100 | 20.41 | 0 | 816.43 | C+S GST 18% I/P RD | 146.96 | 963.39 | 963.39 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Powder Toilet dado | L Groove - BCV | 33.1835 | R.Ft | 20 | 100 | 16.59 | 0 | 663.67 | C+S GST 18% I/P RD | 119.46 | 783.13 | 783.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Parents Toilet dado | L Groove - BCV | 40.8215 | R.Ft | 20 | 100 | 20.41 | 0 | 816.43 | C+S GST 18% I/P RD | 146.96 | 963.39 | 963.39 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Parents Toilet dado | L Groove - BCV | 40.8215 | R.Ft | 20 | 100 | 20.41 | 0 | 816.43 | C+S GST 18% I/P RD | 146.96 | 963.39 | 963.39 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Master Toilet dado | L Groove - BCV | 30.5995 | R.Ft | 20 | 100 | 15.3 | 0 | 611.99 | C+S GST 18% I/P RD | 110.16 | 722.15 | 722.15 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Children Toilet dado | L Groove - BCV | 35.682 | R.Ft | 20 | 100 | 17.84 | 0 | 713.64 | C+S GST 18% I/P RD | 128.46 | 842.1 | 842.1 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Parents Toilet dado | L Groove - BCV | 40.8215 | R.Ft | 20 | 100 | 20.41 | 0 | 816.43 | C+S GST 18% I/P RD | 146.96 | 963.39 | 963.39 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Powder Toilet dado | L Groove - BCV | 33.1835 | R.Ft | 20 | 100 | 16.59 | 0 | 663.67 | C+S GST 18% I/P RD | 119.46 | 783.13 | 783.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Master Toilet dado | L Groove - BCV | 26.2675 | R.Ft | 20 | 100 | 13.13 | 0 | 525.35 | C+S GST 18% I/P RD | 94.56 | 619.91 | 619.91 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Staff Toilet dado | L Groove - BCV | 15.447 | R.Ft | 20 | 100 | 7.72 | 0 | 308.94 | C+S GST 18% I/P RD | 55.6 | 364.54 | 364.54 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 20 | 100 | 33.23 | 0 | 1329.12 | C+S GST 18% I/P RD | 239.24 | 1568.36 | 1568.36 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Children Toilet | Dado BC | 42.72 | Sq.Ft | 20 | 100 | 21.36 | 0 | 854.4 | C+S GST 18% I/P RD | 153.8 | 1008.2 | 1008.2 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 20 | 100 | 29.31 | 0 | 1172.52 | C+S GST 18% I/P RD | 211.06 | 1383.58 | 1383.58 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 20 | 100 | 31.81 | 0 | 1272.24 | C+S GST 18% I/P RD | 229 | 1501.24 | 1501.24 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 20 | 100 | 17.49 | 0 | 699.48 | C+S GST 18% I/P RD | 125.9 | 825.38 | 825.38 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 20 | 100 | 33.89 | 0 | 1355.6 | C+S GST 18% I/P RD | 244 | 1599.6 | 1599.6 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Powder Toilet dado | Dado BC | 38.655 | Sq.Ft | 20 | 100 | 19.33 | 0 | 773.1 | C+S GST 18% I/P RD | 139.16 | 912.26 | 912.26 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Parents Toilet dado | Dado BC | 58.626 | Sq.Ft | 20 | 100 | 29.31 | 0 | 1172.52 | C+S GST 18% I/P RD | 211.06 | 1383.58 | 1383.58 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 20 | 100 | 33.23 | 0 | 1329.12 | C+S GST 18% I/P RD | 239.24 | 1568.36 | 1568.36 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 20 | 100 | 31.81 | 0 | 1272.24 | C+S GST 18% I/P RD | 229 | 1501.24 | 1501.24 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Powder Toilet dado | Dado BC | 34.974 | Sq.Ft | 20 | 100 | 17.49 | 0 | 699.48 | C+S GST 18% I/P RD | 125.9 | 825.38 | 825.38 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Parents Toilet dado | Dado BC | 81.75 | Sq.Ft | 20 | 100 | 40.88 | 0 | 1635 | C+S GST 18% I/P RD | 294.3 | 1929.3 | 1929.3 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Children Toilet dado | Dado BC | 63.612 | Sq.Ft | 24 | 100 | 38.17 | 0 | 1526.69 | C+S GST 18% I/P RD | 274.8 | 1801.49 | 1801.49 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Powder Toilet dado | L Groove - BCV | 30.8465 | R.Ft | 20 | 100 | 15.42 | 0 | 616.93 | C+S GST 18% I/P RD | 111.04 | 727.97 | 727.97 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Dry Balcony dado | L Groove - BCV | 4.2085 | R.Ft | 20 | 100 | 2.1 | 0 | 84.17 | C+S GST 18% I/P RD | 15.16 | 99.33 | 99.33 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Master Toilet dado | L Groove - BCV | 30.5995 | R.Ft | 20 | 100 | 15.3 | 0 | 611.99 | C+S GST 18% I/P RD | 110.16 | 722.15 | 722.15 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Children Toilet dado | L Groove - BCV | 35.682 | R.Ft | 20 | 100 | 17.84 | 0 | 713.64 | C+S GST 18% I/P RD | 128.46 | 842.1 | 842.1 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Master Toilet dado | L Groove - BCV | 30.5995 | R.Ft | 20 | 100 | 15.3 | 0 | 611.99 | C+S GST 18% I/P RD | 110.16 | 722.15 | 722.15 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Powder Toilet dado | L Groove - BCV | 33.1835 | R.Ft | 20 | 100 | 16.59 | 0 | 663.67 | C+S GST 18% I/P RD | 119.46 | 783.13 | 783.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Children Toilet dado | L Groove - BCV | 35.682 | R.Ft | 20 | 100 | 17.84 | 0 | 713.64 | C+S GST 18% I/P RD | 128.46 | 842.1 | 842.1 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 22 | 100 | 48.19 | 0 | 1927.73 | C+S GST 18% I/P RD | 347 | 2274.73 | 2274.73 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 22 | 100 | 63.09 | 0 | 2523.71 | C+S GST 18% I/P RD | 454.26 | 2977.97 | 2977.97 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 22 | 100 | 73.43 | 0 | 2937.13 | C+S GST 18% I/P RD | 528.68 | 3465.81 | 3465.81 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1801 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 22 | 100 | 66.42 | 0 | 2656.96 | C+S GST 18% I/P RD | 478.26 | 3135.22 | 3135.22 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 1901 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 28 | 100 | 61.34 | 0 | 2453.47 | C+S GST 18% I/P RD | 441.62 | 2895.09 | 2895.09 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.804 | Sq.Ft | 17 | 100 | 20.32 | 0 | 812.67 | C+S GST 18% I/P RD | 146.28 | 958.95 | 958.95 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.4105 | Sq.Ft | 17 | 100 | 17.6 | 0 | 703.98 | C+S GST 18% I/P RD | 126.72 | 830.7 | 830.7 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.103 | Sq.Ft | 17 | 100 | 21.29 | 0 | 851.75 | C+S GST 18% I/P RD | 153.32 | 1005.07 | 1005.07 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Children Toilet Flooring | Vitrified Flooring -BC | 46.626 | Sq.Ft | 17 | 100 | 19.82 | 0 | 792.64 | C+S GST 18% I/P RD | 142.68 | 935.32 | 935.32 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.0345 | Sq.Ft | 17 | 100 | 19.99 | 0 | 799.59 | C+S GST 18% I/P RD | 143.92 | 943.51 | 943.51 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 56.753 | Sq.Ft | 17 | 100 | 24.12 | 0 | 964.8 | C+S GST 18% I/P RD | 173.66 | 1138.46 | 1138.46 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 37.8385 | Sq.Ft | 17 | 100 | 16.08 | 0 | 643.25 | C+S GST 18% I/P RD | 115.78 | 759.03 | 759.03 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.61 | Sq.Ft | 17 | 100 | 8.76 | 0 | 350.37 | C+S GST 18% I/P RD | 63.06 | 413.43 | 413.43 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 17 | 100 | 16.67 | 0 | 666.93 | C+S GST 18% I/P RD | 120.04 | 786.97 | 786.97 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.103 | Sq.Ft | 17 | 100 | 21.29 | 0 | 851.75 | C+S GST 18% I/P RD | 153.32 | 1005.07 | 1005.07 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.288 | Sq.Ft | 17 | 100 | 19.25 | 0 | 769.9 | C+S GST 18% I/P RD | 138.58 | 908.48 | 908.48 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Dry Balcony dado | Dado BC | 71.055 | Sq.Ft | 18 | 100 | 31.97 | 0 | 1278.99 | C+S GST 18% I/P RD | 230.22 | 1509.21 | 1509.21 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 18 | 100 | 60.08 | 0 | 2403.11 | C+S GST 18% I/P RD | 432.56 | 2835.67 | 2835.67 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Master Toilet dado | Dado BC | 123.51 | Sq.Ft | 18 | 100 | 55.58 | 0 | 2223.18 | C+S GST 18% I/P RD | 400.18 | 2623.36 | 2623.36 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 18 | 100 | 39.43 | 0 | 1577.23 | C+S GST 18% I/P RD | 283.9 | 1861.13 | 1861.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 18 | 100 | 54.35 | 0 | 2173.88 | C+S GST 18% I/P RD | 391.3 | 2565.18 | 2565.18 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 18 | 100 | 51.62 | 0 | 2064.85 | C+S GST 18% I/P RD | 371.68 | 2436.53 | 2436.53 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Powder Toilet dado | Dado BC | 87.624 | Sq.Ft | 18 | 100 | 39.43 | 0 | 1577.23 | C+S GST 18% I/P RD | 283.9 | 1861.13 | 1861.13 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 18 | 100 | 51.62 | 0 | 2064.85 | C+S GST 18% I/P RD | 371.68 | 2436.53 | 2436.53 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Children Toilet dado | Dado BC | 120.771 | Sq.Ft | 18 | 100 | 54.35 | 0 | 2173.88 | C+S GST 18% I/P RD | 391.3 | 2565.18 | 2565.18 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Parents Toilet dado | Dado BC | 152.52 | Sq.Ft | 18 | 100 | 68.63 | 0 | 2745.36 | C+S GST 18% I/P RD | 494.16 | 3239.52 | 3239.52 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Powder Toilet dado | Dado BC | 85.725 | Sq.Ft | 18 | 100 | 38.58 | 0 | 1543.05 | C+S GST 18% I/P RD | 277.74 | 1820.79 | 1820.79 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Children Toilet | Dado BC | 188.43 | Sq.Ft | 18 | 100 | 84.79 | 0 | 3391.74 | C+S GST 18% I/P RD | 610.52 | 4002.26 | 4002.26 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Parents Toilet dado | Dado BC | 133.506 | Sq.Ft | 18 | 100 | 60.08 | 0 | 2403.11 | C+S GST 18% I/P RD | 432.56 | 2835.67 | 2835.67 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Children Toilet Flooring | Vitrified Flooring -BC | 46.626 | Sq.Ft | 17 | 100 | 19.82 | 0 | 792.64 | C+S GST 18% I/P RD | 142.68 | 935.32 | 935.32 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 702 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 56.753 | Sq.Ft | 17 | 100 | 24.12 | 0 | 964.8 | C+S GST 18% I/P RD | 173.66 | 1138.46 | 1138.46 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 901 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 17 | 100 | 16.85 | 0 | 673.97 | C+S GST 18% I/P RD | 121.32 | 795.29 | 795.29 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 537 | 95428 | 08 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 622 | A 801 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.4105 | Sq.Ft | 17 | 100 | 17.6 | 0 | 703.98 | C+S GST 18% I/P RD | 126.72 | 830.7 | 830.7 | Approved | 0 | 0 | 1117 | 08 Jul 2022
GANGA DHAM TOWERS | 1302 | 95427 | 08 Jul 2022 |  | SHREE GURUDATTA ENTERPRISES | PATIL CONSTRUCTION | EV - 1098 | B 1901 NOC | Core Cutting Work | 10 | No. | 300 | 100 | 75 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 08 Jul 2022
GANGA DHAM TOWERS | 1335 | 95426 | 07 Jul 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 721 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 650 | 07 Jul 2022
GANGA DHAM TOWERS | 1335 | 95426 | 07 Jul 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 721 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 | Approved | 0 | 0 | 650 | 07 Jul 2022
GANGA DHAM TOWERS | 1335 | 95426 | 07 Jul 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 721 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 650 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95420 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS | EV - 1443 | A 1st Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95420 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS | EV - 1443 | A 1st Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 27.5 | Sq.Ft | 150 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 27.5 | Sq.Ft | 150 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 27.5 | Sq.Ft | 150 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 27.5 | Sq.Ft | 150 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 29.4643 | Sq.Ft | 140 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 372 | 95418 | 07 Jul 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 870 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 26.6129 | Sq.Ft | 155 | 100 | 0 | 0 | 4125 | C+S GST 18% I/P RD | 742.5 | 4867.5 | 4867.5 | Approved | 0 | 0 | 495 | 07 Jul 2022
GANGA DHAM TOWERS | 493 | 95417 | 07 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 556 | D Bldg South Side External Plaster | External Plaster- BC | 445.6 | Sq.Ft | 35 | 100 | 389.9 | 0 | 15596 | CGST 0% URD I/P | 0 | 15596 | 15596 | Approved | 0 | 0 | 250 | 07 Jul 2022
GANGA DHAM TOWERS | 493 | 95417 | 07 Jul 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 556 | D Bldg North Side External Plaster | External Plaster- BC | 337 | Sq.Ft | 28 | 100 | 235.9 | 0 | 9436 | CGST 0% URD I/P | 0 | 9436 | 9436 | Approved | 0 | 0 | 250 | 07 Jul 2022
GANGA DHAM TOWERS | 1234 | 95416 | 07 Jul 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 720 | A 1601 NOC | Concrete Cutting Work | 30.99 | R.Ft | 525 | 100 | 0 | 0 | 16269.75 | C+S GST 18% I/P RD | 2928.56 | 19198.31 | 19198.31 | Approved | 0 | 0 | 353 | 07 Jul 2022
GANGA DHAM TOWERS | 1234 | 95416 | 07 Jul 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 720 | A 1601 NOC | Concrete wall Crushing work | 0.192 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 1382.4 | C+S GST 18% I/P RD | 248.84 | 1631.24 | 1631.24 | Approved | 0 | 0 | 353 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A Ground Floor Staircase 2 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P1 Parking Staircase 2 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P2 Parking Staircase 2 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P1 Parking Staircase 1 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P2 Parking Staircase 1 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A Podium Floor Staircase 1 Railling | SS Railing (M) | 66.87 | R.Ft | 931 | 100 | 0 | 0 | 62255.97 | C+S GST 18% I/P RD | 11206.08 | 73462.05 | 73462.05 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P3 Parking Staircase 2 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A P3 Parking Staircase 1 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A Ground Floor Staircase 1 Railling | SS Railing (M) | 32.22 | R.Ft | 931 | 100 | 0 | 0 | 29996.82 | C+S GST 18% I/P RD | 5399.42 | 35396.24 | 35396.24 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 681 | 95415 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1444 | A Podium Floor Staircase 2 Railling | SS Railing (M) | 66.87 | R.Ft | 931 | 100 | 0 | 0 | 62255.97 | C+S GST 18% I/P RD | 11206.08 | 73462.05 | 73462.05 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-16th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-23rd Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 4th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-11th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 6th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-22nd Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-21th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-23rd Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-10th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-26th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 2nd Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 9th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 2nd Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 3rd Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-17th Floor Staircase 1 Railling | SS Railing (M) | 36.26 | R.Ft | 931 | 100 | 0 | 0 | 33758.06 | C+S GST 18% I/P RD | 6076.46 | 39834.52 | 39834.52 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 4th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-13th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-13th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-18th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-22nd Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-16th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-11th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-12th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-20th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 9th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 3rd Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-21th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-20th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 7th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 8th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-14th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-18th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-26th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-12th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-19th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 5th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 5th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 6th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-15th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-17th Floor Staircase 2 Railling | SS Railing (M) | 36.26 | R.Ft | 931 | 100 | 0 | 0 | 33758.06 | C+S GST 18% I/P RD | 6076.46 | 39834.52 | 39834.52 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-25th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 8th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A 7th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-10th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-25th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-15th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-14th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-24th Floor Staircase 1 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-24th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 960 | 95414 | 07 Jul 2022 |  | HELIOS (Material) | HELIOS (Material) | EV - 1615 | A-19th Floor Staircase 2 Railling | SS Railing (M) | 32.81 | R.Ft | 931 | 100 | 0 | 0 | 30546.11 | C+S GST 18% I/P RD | 5498.3 | 36044.41 | 36044.41 | Approved | 0 | 0 | 0 | 07 Jul 2022
GANGA DHAM TOWERS | 178 | 95412 | 06 Jul 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 597 | Sales office Garden Maintenance | Garden work. | 58.995 | Day | 420.83 | 100 | 0 | 0 | 24826.87 | C+S GST 18% I/P RD | 4468.84 | 29295.71 | 29295.71 | Approved | 0 | 0 | 248 | 06 Jul 2022
GANGA DHAM TOWERS | 149 | 95407 | 06 Jul 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 591 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 4000 | No. | 4 | 100 | 0 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 0 | 06 Jul 2022
GANGA DHAM TOWERS | 551 | 95396 | 06 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 572 | A 104 Terrace Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 15 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 83 | 06 Jul 2022
GANGA DHAM TOWERS | 551 | 95396 | 06 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 572 | A 2303 Terrace Vitrified Flooring | Vitrified Flooring -BC | 96 | Sq.Ft | 28 | 100 | 67.2 | 0 | 2688 | C+S GST 18% I/P RD | 483.84 | 3171.84 | 3171.84 | Approved | 0 | 0 | 83 | 06 Jul 2022
GANGA DHAM TOWERS | 551 | 95396 | 06 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 572 | A 2203 Terrace Vitrified Flooring | Vitrified Flooring -BC | 96 | Sq.Ft | 28 | 100 | 67.2 | 0 | 2688 | C+S GST 18% I/P RD | 483.84 | 3171.84 | 3171.84 | Approved | 0 | 0 | 83 | 06 Jul 2022
GANGA DHAM TOWERS | 551 | 95396 | 06 Jul 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 572 | A 2103 Terrace Vitrified Flooring | Vitrified Flooring -BC | 96 | Sq.Ft | 28 | 100 | 67.2 | 0 | 2688 | C+S GST 18% I/P RD | 483.84 | 3171.84 | 3171.84 | Approved | 0 | 0 | 83 | 06 Jul 2022
GANGA DHAM TOWERS | 1249 | 95395 | 06 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 573 | A 2403 NOC | Italian Marble Flooring | 170 | Sq.Ft | 55 | 100 | 233.75 | 0 | 9350 | C+S GST 18% I/P RD | 1683 | 11033 | 11033 | Approved | 0 | 0 | 94 | 06 Jul 2022
GANGA DHAM TOWERS | 1350 | 95394 | 06 Jul 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 574 | A 2101 NOC | Italian Marble Flooring - BCo | 416.62 | Sq.Ft | 60 | 100 | 624.93 | 0 | 24997.2 | C+S GST 18% I/P RD | 4499.5 | 29496.7 | 29496.7 | Approved | 0 | 0 | 250 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 2301 Marble Window Sill | Italian Marble Sill- BC- | 47.4 | R.Ft | 60 | 100 | 71.1 | 0 | 2844 | C+S GST 18% I/P RD | 511.92 | 3355.92 | 3355.92 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 2201 Marble Window Sill | Italian Marble Sill- BC- | 52.32 | R.Ft | 60 | 100 | 78.48 | 0 | 3139.2 | C+S GST 18% I/P RD | 565.06 | 3704.26 | 3704.26 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1602 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 55 | 100 | 73.29 | 0 | 2931.5 | C+S GST 18% I/P RD | 527.68 | 3459.18 | 3459.18 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 902 Marble Window Sill | Italian Marble Sill- BC- | 48.38 | R.Ft | 50 | 100 | 60.48 | 0 | 2419 | C+S GST 18% I/P RD | 435.42 | 2854.42 | 2854.42 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 2401 Terrace Vitrified Flooring | Vitrified Flooring -BC | 17.75 | Sq.Ft | 28 | 100 | 12.43 | 0 | 497 | C+S GST 18% I/P RD | 89.46 | 586.46 | 586.46 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1301 Marble Window Sill | Italian Marble Sill- BC- | 47.4 | R.Ft | 55 | 100 | 65.18 | 0 | 2607 | C+S GST 18% I/P RD | 469.26 | 3076.26 | 3076.26 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 702 Marble Window Sill | Italian Marble Sill- BC- | 22 | R.Ft | 50 | 100 | 27.5 | 0 | 1100 | C+S GST 18% I/P RD | 198 | 1298 | 1298 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 601 Marble Window Sill | Italian Marble Sill- BC- | 27 | R.Ft | 45 | 100 | 30.38 | 0 | 1215 | C+S GST 18% I/P RD | 218.7 | 1433.7 | 1433.7 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 101 Marble Window Sill | Italian Marble Sill- BC- | 47.4 | R.Ft | 45 | 100 | 53.33 | 0 | 2133 | C+S GST 18% I/P RD | 383.94 | 2516.94 | 2516.94 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 901 Marble Window Sill | Italian Marble Sill- BC- | 22.58 | R.Ft | 50 | 100 | 28.23 | 0 | 1129 | C+S GST 18% I/P RD | 203.22 | 1332.22 | 1332.22 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 801 Marble Window Sill | Italian Marble Sill- BC- | 41 | R.Ft | 50 | 100 | 51.25 | 0 | 2050 | C+S GST 18% I/P RD | 369 | 2419 | 2419 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1502 Marble Window Sill | Italian Marble Sill- BC- | 48.38 | R.Ft | 55 | 100 | 66.52 | 0 | 2660.9 | C+S GST 18% I/P RD | 478.96 | 3139.86 | 3139.86 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 802 Marble Window Sill | Italian Marble Sill- BC- | 47.97 | R.Ft | 50 | 100 | 59.96 | 0 | 2398.5 | C+S GST 18% I/P RD | 431.74 | 2830.24 | 2830.24 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1001 Marble Window Sill | Italian Marble Sill- BC- | 52.32 | R.Ft | 50 | 100 | 65.4 | 0 | 2616 | C+S GST 18% I/P RD | 470.88 | 3086.88 | 3086.88 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 402 Marble Window Sill | Italian Marble Sill- BC- | 23 | R.Ft | 45 | 100 | 25.88 | 0 | 1035 | C+S GST 18% I/P RD | 186.3 | 1221.3 | 1221.3 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 502 Marble Window Sill | Italian Marble Sill- BC- | 48.38 | R.Ft | 45 | 100 | 54.43 | 0 | 2177.1 | C+S GST 18% I/P RD | 391.88 | 2568.98 | 2568.98 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 202 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 45 | 100 | 59.96 | 0 | 2398.5 | C+S GST 18% I/P RD | 431.74 | 2830.24 | 2830.24 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1002 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 50 | 100 | 66.63 | 0 | 2665 | C+S GST 18% I/P RD | 479.7 | 3144.7 | 3144.7 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1102 Marble Window Sill | Italian Marble Sill- BC- | 48.38 | R.Ft | 50 | 100 | 60.48 | 0 | 2419 | C+S GST 18% I/P RD | 435.42 | 2854.42 | 2854.42 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1201 Marble Window Sill | Italian Marble Sill- BC- | 52.32 | R.Ft | 50 | 100 | 65.4 | 0 | 2616 | C+S GST 18% I/P RD | 470.88 | 3086.88 | 3086.88 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 102 Marble Window Sill | Italian Marble Sill- BC- | 22 | R.Ft | 45 | 100 | 24.75 | 0 | 990 | C+S GST 18% I/P RD | 178.2 | 1168.2 | 1168.2 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1101 Marble Window Sill | Italian Marble Sill- BC- | 47.4 | R.Ft | 50 | 100 | 59.25 | 0 | 2370 | C+S GST 18% I/P RD | 426.6 | 2796.6 | 2796.6 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1302 Marble Window Sill | Italian Marble Sill- BC- | 48.38 | R.Ft | 55 | 100 | 66.52 | 0 | 2660.9 | C+S GST 18% I/P RD | 478.96 | 3139.86 | 3139.86 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 701 Marble Window Sill | Italian Marble Sill- BC- | 22 | R.Ft | 50 | 100 | 27.5 | 0 | 1100 | C+S GST 18% I/P RD | 198 | 1298 | 1298 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1402 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 55 | 100 | 73.29 | 0 | 2931.5 | C+S GST 18% I/P RD | 527.68 | 3459.18 | 3459.18 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1501 Marble Window Sill | Italian Marble Sill- BC- | 47.4 | R.Ft | 55 | 100 | 65.18 | 0 | 2607 | C+S GST 18% I/P RD | 469.26 | 3076.26 | 3076.26 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 537 | 95393 | 06 Jul 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 707 | A 1601 Marble Window Sill | Italian Marble Sill- BC- | 52.32 | R.Ft | 55 | 100 | 71.94 | 0 | 2877.6 | C+S GST 18% I/P RD | 517.96 | 3395.56 | 3395.56 | Approved | 0 | 0 | 586 | 06 Jul 2022
GANGA DHAM TOWERS | 1296 | 95380 | 05 Jul 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 520 | Miscellaneous expenses | Marketing Operating Expenses | 6.0778 | Month | 25000 | 8.33 | 0 | 0 | 12657 | CGST 0% URD I/P | 0 | 12657 | 12657 | Approved | 0 | 0 | 127 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 10th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 17th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 6th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 21st floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 1st floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside1st floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 15th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 24th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 2nd floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 16th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 18th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 3rd floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 5th floor External Texture Painting | Texture Paint (M) | 56.5517 | Sq.Ft | 7.25 | 100 | 0 | 0 | 410 | C+S GST 18% I/P RD | 73.8 | 483.8 | 483.8 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 22nd floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 20th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 7th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 23rd floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 8th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 24th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 12th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 9th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 19th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 11th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 13th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 14th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Eastside 4th floor External Texture Painting | Texture Paint (M) | 56.6897 | Sq.Ft | 7.25 | 100 | 0 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 845 | 95378 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 566 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 116.8276 | Sq.Ft | 7.25 | 100 | 0 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 14th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 8th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 12th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 4th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 18th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 21st floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 8th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 10th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 5th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 5th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 3rd floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 11th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 2nd floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 19th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 17th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 8th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 20th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 16th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside1st floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 9th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 13th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 18th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 6th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 6th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 24th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 19th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 1st floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 3rd floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 21st floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 10th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 12th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 4th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 11th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 17th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 7th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 23rd floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 24th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 22nd floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 9th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 20th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 2nd floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 23rd floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 15th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 14th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 15th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 16th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 18th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 24th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 17th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 10th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 13th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 7th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 3rd floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 19th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 11th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 3rd floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 21st floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 6th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 4th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 20th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 2nd floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 24th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 15th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 12th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 22nd floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 5th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 1st floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside1st floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 116.8276 | Sq.Ft | 7.25 | 100 | 21.18 | 0 | 847 | C+S GST 18% I/P RD | 152.46 | 999.46 | 999.46 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 23rd floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 9th floor External Texture Painting | Texture Paint (L) | 56.6897 | Sq.Ft | 7.25 | 100 | 10.28 | 0 | 411 | C+S GST 18% I/P RD | 73.98 | 484.98 | 484.98 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 13th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 16th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 7th floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Eastside 22nd floor External Texture Painting | Scaffolding/Gondola work | 56.5714 | Sq.Ft | 3.5 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 844 | 95377 | 05 Jul 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 565 | A Northside 14th floor External Texture Painting | Scaffolding/Gondola work | 116.8571 | Sq.Ft | 3.5 | 100 | 10.22 | 0 | 409 | C+S GST 18% I/P RD | 73.62 | 482.62 | 482.62 | Approved | 0 | 0 | 448 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.8045 | Sq.Ft | 133 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.8045 | Sq.Ft | 133 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.8045 | Sq.Ft | 133 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.8045 | Sq.Ft | 133 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.6842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.6842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.6842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.6842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 40.9539 | Sq.Ft | 152 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95376 | 05 Jul 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 869 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 40.9539 | Sq.Ft | 152 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 623 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-19th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-17th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-24th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-26th Floor-Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 1st Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 5th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 7th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 9th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 1st Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-10th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-26th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-18th Floor Staircase 2 Railing | SS Railing (M) | 25 | R.Ft | 931 | 100 | 0 | 0 | 23275 | C+S GST 18% I/P RD | 4189.5 | 27464.5 | 27464.5 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-22nd Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-25th Floor-Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 6th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-15th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 3rd Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-20th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-22nd Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 2nd Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 5th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-12th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-13th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 3rd Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 4th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-11th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 8th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 2nd Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-12th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 8th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-15th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-23rd Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-18th Floor Staircase 1 Railing | SS Railing (M) | 25 | R.Ft | 931 | 100 | 0 | 0 | 23275 | C+S GST 18% I/P RD | 4189.5 | 27464.5 | 27464.5 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 7th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-16th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-16th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-10th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-25th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 6th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-11th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-20th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-21st Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 4th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-23rd Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-14th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-17th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-24th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-21st Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-19th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-13th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B-14th Floor Staircase 2 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 963 | 95375 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1785 | B 9th Floor Staircase 1 Railing | SS Railing (M) | 22.31 | R.Ft | 931 | 100 | 0 | 0 | 20770.61 | C+S GST 18% I/P RD | 3738.7 | 24509.31 | 24509.31 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P1 Parking Floor Staircase 2 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P2 Parking Floor Staircase 2 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B Ground Floor Floor Staircase 2 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P1 Parking Floor Staircase 1 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B Podium Floor Staircase 1 Railing | SS Railing (M) | 44.62 | R.Ft | 931 | 100 | 0 | 0 | 41541.22 | C+S GST 18% I/P RD | 7477.42 | 49018.64 | 49018.64 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B Ground Floor Staircase 1 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P3 Parking Floor Staircase 1 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P2 Parking Floor Staircase 1 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B Podium Floor Staircase 2 Railing | SS Railing (M) | 44.62 | R.Ft | 931 | 100 | 0 | 0 | 41541.22 | C+S GST 18% I/P RD | 7477.42 | 49018.64 | 49018.64 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 980 | 95374 | 05 Jul 2022 |  | DIVINE ENTERPRISES | HELIOS | EV - 1442 | B P3 Parking Floor Staircase 2 Railing | SS Railing (M) | 21.79 | R.Ft | 931 | 100 | 0 | 0 | 20286.49 | C+S GST 18% I/P RD | 3651.56 | 23938.05 | 23938.05 | Approved | 0 | 0 | 0 | 05 Jul 2022
GANGA DHAM TOWERS | 272 | 95365 | 04 Jul 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 606 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1823.9989 | Sq.Ft | 181.3 | 100 | 0 | 0 | 330691 | C+S GST 18% I/P RD | 59524.38 | 390215.38 | 390215.38 | Approved | 0 | 0 | 6614 | 04 Jul 2022
GANGA DHAM TOWERS | 272 | 95364 | 04 Jul 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 947 | A Bldg 32nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2000 | Sq.Ft | 181.3 | 100 | 0 | 0 | 362600 | C+S GST 18% I/P RD | 65268 | 427868 | 427868 | Approved | 0 | 0 | 7252 | 04 Jul 2022
GANGA DHAM TOWERS | 272 | 95363 | 04 Jul 2022 |  | GOURI INFRA | B & B ENTERPRISES | EV - 605 | A Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1823.9989 | Sq.Ft | 181.3 | 100 | 0 | 0 | 330691 | C+S GST 18% I/P RD | 59524.38 | 390215.38 | 390215.38 | Approved | 0 | 0 | 6614 | 04 Jul 2022
GANGA DHAM TOWERS | 372 | 95362 | 04 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 607 | B Bldg 25th Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 218.552 | Sq.Ft | 400 | 100 | 2185.52 | 0 | 87420.8 | C+S GST 18% I/P RD | 15735.74 | 103156.54 | 103156.54 | Approved | 0 | 0 | 4689 | 04 Jul 2022
GANGA DHAM TOWERS | 372 | 95362 | 04 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 607 | B Bldg 20th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 186.256 | Sq.Ft | 160 | 100 | 745.02 | 0 | 29800.96 | C+S GST 18% I/P RD | 5364.18 | 35165.14 | 35165.14 | Approved | 0 | 0 | 4689 | 04 Jul 2022
GANGA DHAM TOWERS | 372 | 95362 | 04 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 607 | B Bldg 25th Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 186.256 | Sq.Ft | 160 | 100 | 745.02 | 0 | 29800.96 | C+S GST 18% I/P RD | 5364.18 | 35165.14 | 35165.14 | Approved | 0 | 0 | 4689 | 04 Jul 2022
GANGA DHAM TOWERS | 372 | 95362 | 04 Jul 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 607 | B Bldg 20th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 218.552 | Sq.Ft | 400 | 100 | 2185.52 | 0 | 87420.8 | C+S GST 18% I/P RD | 15735.74 | 103156.54 | 103156.54 | Approved | 0 | 0 | 4689 | 04 Jul 2022
GANGA DHAM TOWERS | 371 | 95349 | 04 Jul 2022 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 612 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | RCC Superstructure (B-up area) | 625.0019 | Sq.Ft | 200.665 | 100 | 3135.4 | 0 | 125416 | CGST 0% URD I/P | 0 | 125416 | 125416 | Approved | 0 | 0 | 1254 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 1302 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 702 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 2202 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 13.5083 | Mtrs | 120 | 100 | 40.52 | 0 | 1621 | CGST 0% URD I/P | 0 | 1621 | 1621 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 2202 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.35 | Mtrs | 20 | 100 | 14.18 | 0 | 567 | CGST 0% URD I/P | 0 | 567 | 567 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 1302 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.35 | Mtrs | 20 | 100 | 14.18 | 0 | 567 | CGST 0% URD I/P | 0 | 567 | 567 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 702 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 28.35 | Mtrs | 20 | 100 | 14.18 | 0 | 567 | CGST 0% URD I/P | 0 | 567 | 567 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 2202 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.5583 | Mtrs | 120 | 100 | 67.67 | 0 | 2707 | CGST 0% URD I/P | 0 | 2707 | 2707 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 1302 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.5583 | Mtrs | 120 | 100 | 67.67 | 0 | 2707 | CGST 0% URD I/P | 0 | 2707 | 2707 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 702 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 22.5583 | Mtrs | 120 | 100 | 67.67 | 0 | 2707 | CGST 0% URD I/P | 0 | 2707 | 2707 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 702 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5 | Mtrs | 18 | 100 | 20.48 | 0 | 819 | CGST 0% URD I/P | 0 | 819 | 819 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 2202 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5 | Mtrs | 18 | 100 | 20.48 | 0 | 819 | CGST 0% URD I/P | 0 | 819 | 819 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1278 | 95348 | 04 Jul 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 528 | Tower B 1302 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 45.5 | Mtrs | 18 | 100 | 20.48 | 0 | 819 | CGST 0% URD I/P | 0 | 819 | 819 | Approved | 0 | 0 | 171 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 702 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.56 | Mtrs | 700 | 100 | 0 | 0 | 15792 | C+S GST 18% I/P RD | 2842.56 | 18634.56 | 18634.56 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 2202 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.56 | Mtrs | 700 | 100 | 0 | 0 | 15792 | C+S GST 18% I/P RD | 2842.56 | 18634.56 | 18634.56 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 1302 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 22.56 | Mtrs | 700 | 100 | 0 | 0 | 15792 | C+S GST 18% I/P RD | 2842.56 | 18634.56 | 18634.56 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 702 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 2202 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 1302 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 13.51 | Mtrs | 700 | 100 | 0 | 0 | 9457 | C+S GST 18% I/P RD | 1702.26 | 11159.26 | 11159.26 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 2202 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5 | Mtrs | 78 | 100 | 0 | 0 | 3549 | C+S GST 18% I/P RD | 638.82 | 4187.82 | 4187.82 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 702 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5 | Mtrs | 78 | 100 | 0 | 0 | 3549 | C+S GST 18% I/P RD | 638.82 | 4187.82 | 4187.82 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 1302 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 45.5 | Mtrs | 78 | 100 | 0 | 0 | 3549 | C+S GST 18% I/P RD | 638.82 | 4187.82 | 4187.82 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 2202 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 702 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1277 | 95347 | 04 Jul 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 529 | Tower B 1302 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 28.375 | Mtrs | 72 | 100 | 0 | 0 | 2043 | C+S GST 18% I/P RD | 367.74 | 2410.74 | 2410.74 | Approved | 0 | 0 | 0 | 04 Jul 2022
GANGA DHAM TOWERS | 1360 | 95346 | 04 Jul 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 535 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 150 | 04 Jul 2022
GANGA DHAM TOWERS | 940 | 95345 | 04 Jul 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 534 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 04 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 1701 Chemical & IPS Waterproofing | IPS W/P | 345.1818 | Sq.Ft | 11 | 100 | 379.7 | 0 | 3797 | CGST 0% URD I/P | 0 | 3797 | 3797 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2401 Chemical & IPS Waterproofing | IPS W/P | 107.4545 | Sq.Ft | 11 | 100 | 118.2 | 0 | 1182 | CGST 0% URD I/P | 0 | 1182 | 1182 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12.98 | No. | 150 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2202 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 1701 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 345.2105 | Sq.Ft | 19 | 100 | 655.9 | 0 | 6559 | CGST 0% URD I/P | 0 | 6559 | 6559 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 498 | 95326 | 02 Jul 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 876 | B 2401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 107.4211 | Sq.Ft | 19 | 100 | 204.1 | 0 | 2041 | CGST 0% URD I/P | 0 | 2041 | 2041 | Approved | 0 | 0 | 202 | 02 Jul 2022
GANGA DHAM TOWERS | 1287 | 95325 | 02 Jul 2022 |  | SANTOSH HMMAT CHAVHAN | PRAKASH CONTRACTOR | EV - 760 | B 2101 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 58.4727 | Sq.Ft | 55 | 100 | 80.4 | 0 | 3216 | C+S GST 0% I/P RD | 0 | 3216 | 3216 | Approved | 0 | 0 | 32 | 02 Jul 2022
GANGA DHAM TOWERS | 971 | 95324 | 02 Jul 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1096 | B-Bldg Core cutting work for AC & Fire fighting | Core Cutting Work 3" BCE | 150 | No. | 300 | 100 | 1125 | 0 | 45000 | C+S GST 18% I/P URD | 8100 | 53100 | 53100 | Approved | 0 | 0 | 450 | 02 Jul 2022
GANGA DHAM TOWERS | 1338 | 95318 | 01 Jul 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 490 | HO Expensess (L) | Toner refilling | 12 | Month | 4000 | 8.33 | 0 | 0 | 3999.98 | CGST 0% URD I/P | 0 | 3999.98 | 3999.98 | Approved | 0 | 0 | 40 | 01 Jul 2022
GANGA DHAM TOWERS | 1338 | 95317 | 01 Jul 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 489 | HO Expensess (L) | Toner refilling | 12 | Month | 4000 | 8.33 | 0 | 0 | 3999.98 | CGST 0% URD I/P | 0 | 3999.98 | 3999.98 | Approved | 0 | 0 | 40 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 102 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 801 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 104 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 103 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 203 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 101 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 1259 | 95316 | 01 Jul 2022 |  | VNE INFRA PROJECTS P LTD | PRAKASH CONTRACTOR | EV - 868 | A 1102 Ledge Wall RCC Work (L) | RCC Ledge Wall - DCW - Sq.Ft | 14.2857 | Sq.Ft | 140 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 140 | 01 Jul 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 19th Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 20th Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 23rd Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 22nd Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 18th Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 21st Floor Lobby Gypsum | Gypsum on Wall (M) | 798.98 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2796.43 | C+S GST 18% I/P RD | 503.36 | 3299.79 | 3299.79 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 543 | 95310 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 549 | A 24th Floor Lobby Gypsum | Gypsum on Wall (M) | 523.7143 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1833 | C+S GST 18% I/P RD | 329.94 | 2162.94 | 2162.94 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 632 | 95305 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 512 | A 2203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 197 | 30 Jun 2022
GANGA DHAM TOWERS | 632 | 95305 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 512 | A 2203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 197 | 30 Jun 2022
GANGA DHAM TOWERS | 629 | 95304 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 515 | A 2203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 629 | 95304 | 30 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 515 | A 2203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 18th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 16th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 15th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 7th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 3rd Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 8th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 10th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 4th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 5th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 21st Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 1st Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 6th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 22nd Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 11th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 20th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 19th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 2nd Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 13th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 14th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 12th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 17th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 23rd Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 24th Floor Texture Painting | Scaffolding/Gondola work | 253.4286 | Sq.Ft | 3.5 | 100 | 22.18 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 1199 | 95302 | 30 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 576 | B Southside 9th Floor Texture Painting | Scaffolding/Gondola work | 386.8571 | Sq.Ft | 3.5 | 100 | 33.85 | 0 | 1354 | C+S GST 18% I/P RD | 243.72 | 1597.72 | 1597.72 | Approved | 0 | 0 | 538 | 30 Jun 2022
GANGA DHAM TOWERS | 797 | 95279 | 29 Jun 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 496 | D 10th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 431.5556 | Sq.Ft | 9 | 100 | 97.1 | 0 | 3884 | CGST 0% URD I/P | 0 | 3884 | 3884 | Approved | 0 | 0 | 39 | 29 Jun 2022
GANGA DHAM TOWERS | 1313 | 95278 | 29 Jun 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 497 | D 1201 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.1053 | Sq.Ft | 9.5 | 100 | 217.58 | 0 | 8703 | CGST 0% URD I/P | 0 | 8703 | 8703 | Approved | 0 | 0 | 369 | 29 Jun 2022
GANGA DHAM TOWERS | 1313 | 95278 | 29 Jun 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 497 | D 1205 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.1053 | Sq.Ft | 9.5 | 100 | 217.58 | 0 | 8703 | CGST 0% URD I/P | 0 | 8703 | 8703 | Approved | 0 | 0 | 369 | 29 Jun 2022
GANGA DHAM TOWERS | 1313 | 95278 | 29 Jun 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 497 | D 1202 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 783.3684 | Sq.Ft | 9.5 | 100 | 186.05 | 0 | 7442 | CGST 0% URD I/P | 0 | 7442 | 7442 | Approved | 0 | 0 | 369 | 29 Jun 2022
GANGA DHAM TOWERS | 1313 | 95278 | 29 Jun 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 497 | D 1203 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.3158 | Sq.Ft | 9.5 | 100 | 150.65 | 0 | 6026 | CGST 0% URD I/P | 0 | 6026 | 6026 | Approved | 0 | 0 | 369 | 29 Jun 2022
GANGA DHAM TOWERS | 1313 | 95278 | 29 Jun 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 497 | D 1204 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.3158 | Sq.Ft | 9.5 | 100 | 150.65 | 0 | 6026 | CGST 0% URD I/P | 0 | 6026 | 6026 | Approved | 0 | 0 | 369 | 29 Jun 2022
GANGA DHAM TOWERS | 983 | 95277 | 29 Jun 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 730 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting 6" BCE | 23 | No. | 210 | 100 | 120.75 | 0 | 4830 | CGST 0% URD I/P | 0 | 4830 | 4830 | Approved | 0 | 0 | 206 | 29 Jun 2022
GANGA DHAM TOWERS | 983 | 95277 | 29 Jun 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 730 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 3" BCE | 75 | No. | 210 | 100 | 393.75 | 0 | 15750 | CGST 0% URD I/P | 0 | 15750 | 15750 | Approved | 0 | 0 | 206 | 29 Jun 2022
GANGA DHAM TOWERS | 1248 | 95276 | 29 Jun 2022 |  | AVCON TECHNICS PVT LTD | RAM GUNAJI MANDLIK | EV - 736 | A 1104 NOC | Core Cutting - BCo | 8 | No. | 300 | 100 | 0 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 24 | 29 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 294.5385 | Sq.Ft | 130 | 100 | 0 | 0 | 38290.01 | C+S GST 18% I/P RD | 6892.2 | 45182.21 | 45182.21 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 84.6 | Sq.Ft | 130 | 100 | 0 | 0 | 10998 | C+S GST 18% I/P RD | 1979.64 | 12977.64 | 12977.64 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.8231 | Sq.Ft | 130 | 100 | 0 | 0 | 7127 | C+S GST 18% I/P RD | 1282.86 | 8409.86 | 8409.86 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 317.6 | Sq.Ft | 130 | 100 | 0 | 0 | 41288 | C+S GST 18% I/P RD | 7431.84 | 48719.84 | 48719.84 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 332.3 | Sq.Ft | 130 | 100 | 0 | 0 | 43199 | C+S GST 18% I/P RD | 7775.82 | 50974.82 | 50974.82 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 352.5 | Sq.Ft | 130 | 100 | 0 | 0 | 45825 | C+S GST 18% I/P RD | 8248.5 | 54073.5 | 54073.5 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 332.3308 | Sq.Ft | 130 | 100 | 0 | 0 | 43203 | C+S GST 18% I/P RD | 7776.54 | 50979.54 | 50979.54 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 332.3231 | Sq.Ft | 130 | 100 | 0 | 0 | 43202 | C+S GST 18% I/P RD | 7776.36 | 50978.36 | 50978.36 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 330.6333 | Sq.Ft | 120 | 100 | 0 | 0 | 39676 | C+S GST 18% I/P RD | 7141.68 | 46817.68 | 46817.68 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 7th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 298.4833 | Sq.Ft | 120 | 100 | 0 | 0 | 35818 | C+S GST 18% I/P RD | 6447.24 | 42265.24 | 42265.24 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 7th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 298.4833 | Sq.Ft | 120 | 100 | 0 | 0 | 35818 | C+S GST 18% I/P RD | 6447.24 | 42265.24 | 42265.24 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 193.4583 | Sq.Ft | 120 | 100 | 0 | 0 | 23215 | C+S GST 18% I/P RD | 4178.7 | 27393.7 | 27393.7 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 315.9333 | Sq.Ft | 120 | 100 | 0 | 0 | 37912 | C+S GST 18% I/P RD | 6824.16 | 44736.16 | 44736.16 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 279 | Sq.Ft | 120 | 100 | 0 | 0 | 33480 | C+S GST 18% I/P RD | 6026.4 | 39506.4 | 39506.4 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 164.1167 | Sq.Ft | 120 | 100 | 0 | 0 | 19694 | C+S GST 18% I/P RD | 3544.92 | 23238.92 | 23238.92 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 315.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 37913 | C+S GST 18% I/P RD | 6824.34 | 44737.34 | 44737.34 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 319 | Sq.Ft | 140 | 100 | 0 | 0 | 44660 | C+S GST 18% I/P RD | 8038.8 | 52698.8 | 52698.8 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 333.7 | Sq.Ft | 140 | 100 | 0 | 0 | 46718 | C+S GST 18% I/P RD | 8409.24 | 55127.24 | 55127.24 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 333.7 | Sq.Ft | 140 | 100 | 0 | 0 | 46718 | C+S GST 18% I/P RD | 8409.24 | 55127.24 | 55127.24 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 213.3 | Sq.Ft | 140 | 100 | 0 | 0 | 29862 | C+S GST 18% I/P RD | 5375.16 | 35237.16 | 35237.16 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 266.4571 | Sq.Ft | 140 | 100 | 0 | 0 | 37304 | C+S GST 18% I/P RD | 6714.72 | 44018.72 | 44018.72 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 372 | 95257 | 28 Jun 2022 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1015 | B Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 352.5 | Sq.Ft | 140 | 100 | 0 | 0 | 49350 | C+S GST 18% I/P RD | 8883 | 58233 | 58233 | Approved | 0 | 0 | 15825 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 220 | Sq.Ft | 10 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 211.5 | Sq.Ft | 10 | 100 | 52.88 | 0 | 2115 | C+S GST 18% I/P RD | 380.7 | 2495.7 | 2495.7 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 23.5 | Sq.Ft | 10 | 100 | 5.88 | 0 | 235 | C+S GST 18% I/P RD | 42.3 | 277.3 | 277.3 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 229.5 | Sq.Ft | 10 | 100 | 57.38 | 0 | 2295 | C+S GST 18% I/P RD | 413.1 | 2708.1 | 2708.1 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 25.5 | Sq.Ft | 10 | 100 | 6.38 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1345 | 95256 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 475 | B 1602 NOC | Dado Rate Diff.-Mkt | 275 | Sq.Ft | 10 | 100 | 68.75 | 0 | 2750 | C+S GST 18% I/P RD | 495 | 3245 | 3245 | Approved | 0 | 0 | 99 | 28 Jun 2022
GANGA DHAM TOWERS | 1146 | 95255 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 567 | B 1902 NOC | Italian Marble Flooring - BCo | 156.12 | Sq.Ft | 55 | 100 | 214.67 | 0 | 8586.6 | C+S GST 18% I/P RD | 1545.58 | 10132.18 | 10132.18 | Approved | 0 | 0 | 86 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 StaffToilet Dado - 1 No. | Dado BC | 122.805 | Sq.Ft | 21 | 100 | 64.47 | 0 | 2578.91 | C+S GST 18% I/P RD | 464.2 | 3043.11 | 3043.11 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 22 | 100 | 80.57 | 0 | 3222.85 | C+S GST 18% I/P RD | 580.12 | 3802.97 | 3802.97 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 22 | 100 | 66.75 | 0 | 2670.03 | C+S GST 18% I/P RD | 480.6 | 3150.63 | 3150.63 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Powder Toilet Dado - 1 No. | Dado BC | 85.446 | Sq.Ft | 22 | 100 | 47 | 0 | 1879.81 | C+S GST 18% I/P RD | 338.36 | 2218.17 | 2218.17 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Dry Balcony Dado - 1 No. | Dado BC | 73.242 | Sq.Ft | 22 | 100 | 40.28 | 0 | 1611.32 | C+S GST 18% I/P RD | 290.04 | 1901.36 | 1901.36 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 22 | 100 | 89.6 | 0 | 3583.8 | C+S GST 18% I/P RD | 645.08 | 4228.88 | 4228.88 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Parents Toilet Dado - 1 No. | Dado BC | 162.9 | Sq.Ft | 22 | 100 | 89.6 | 0 | 3583.8 | C+S GST 18% I/P RD | 645.08 | 4228.88 | 4228.88 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 22 | 100 | 85.94 | 0 | 3437.48 | C+S GST 18% I/P RD | 618.74 | 4056.22 | 4056.22 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Master Toilet Dado - 1 No. | Dado BC | 156.249 | Sq.Ft | 22 | 100 | 85.94 | 0 | 3437.48 | C+S GST 18% I/P RD | 618.74 | 4056.22 | 4056.22 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Children Toilet 1 Dado - 1 No. | Dado BC | 146.493 | Sq.Ft | 22 | 100 | 80.57 | 0 | 3222.85 | C+S GST 18% I/P RD | 580.12 | 3802.97 | 3802.97 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Guest Toilet Dado - 1 No. | Dado BC | 121.365 | Sq.Ft | 22 | 100 | 66.75 | 0 | 2670.03 | C+S GST 18% I/P RD | 480.6 | 3150.63 | 3150.63 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 StaffToilet Dado - 1 No. | Dado BC | 122.805 | Sq.Ft | 21 | 100 | 64.47 | 0 | 2578.91 | C+S GST 18% I/P RD | 464.2 | 3043.11 | 3043.11 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 2401 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 193.15 | Sq.Ft | 60 | 100 | 289.73 | 0 | 11589 | C+S GST 18% I/P RD | 2086.02 | 13675.02 | 13675.02 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 2401 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 60 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 2401 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 60 | 100 | 364.5 | 0 | 14580 | C+S GST 18% I/P RD | 2624.4 | 17204.4 | 17204.4 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 2401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1154 | Sq.Ft | 60 | 100 | 1731 | 0 | 69240 | C+S GST 18% I/P RD | 12463.2 | 81703.2 | 81703.2 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Parents Toilet Dado - 1 No. | Dado BC | 48.654 | Sq.Ft | 24 | 100 | 29.19 | 0 | 1167.7 | C+S GST 18% I/P RD | 210.18 | 1377.88 | 1377.88 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 24 | 100 | 26.77 | 0 | 1070.93 | C+S GST 18% I/P RD | 192.76 | 1263.69 | 1263.69 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 24 | 100 | 30.62 | 0 | 1224.72 | C+S GST 18% I/P RD | 220.44 | 1445.16 | 1445.16 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Powder Toilet Dado - 1 No. | Dado BC | 34.893 | Sq.Ft | 24 | 100 | 20.94 | 0 | 837.43 | C+S GST 18% I/P RD | 150.74 | 988.17 | 988.17 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Parents Toilet Dado - 1 No. | Dado BC | 48.654 | Sq.Ft | 24 | 100 | 29.19 | 0 | 1167.7 | C+S GST 18% I/P RD | 210.18 | 1377.88 | 1377.88 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Master Toilet Dado - 1 No. | Dado BC | 51.03 | Sq.Ft | 24 | 100 | 30.62 | 0 | 1224.72 | C+S GST 18% I/P RD | 220.44 | 1445.16 | 1445.16 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 24 | 100 | 35.6 | 0 | 1424.09 | C+S GST 18% I/P RD | 256.34 | 1680.43 | 1680.43 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1502 Children Toilet 1 Dado - 1 No. | Dado BC | 44.622 | Sq.Ft | 24 | 100 | 26.77 | 0 | 1070.93 | C+S GST 18% I/P RD | 192.76 | 1263.69 | 1263.69 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 758 | 95254 | 28 Jun 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 568 | B 1602 Guest Toilet Dado - 1 No. | Dado BC | 59.337 | Sq.Ft | 24 | 100 | 35.6 | 0 | 1424.09 | C+S GST 18% I/P RD | 256.34 | 1680.43 | 1680.43 | Approved | 0 | 0 | 1588 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 704 | Sq.Ft | 152 | 100 | 0 | 0 | 107008 | C+S GST 18% I/P RD | 19261.44 | 126269.44 | 126269.44 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 484.0132 | Sq.Ft | 152 | 100 | 0 | 0 | 73570 | C+S GST 18% I/P RD | 13242.6 | 86812.6 | 86812.6 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 163.5461 | Sq.Ft | 152 | 100 | 0 | 0 | 24859 | C+S GST 18% I/P RD | 4474.62 | 29333.62 | 29333.62 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 700 | Sq.Ft | 171 | 100 | 0 | 0 | 119700 | C+S GST 18% I/P RD | 21546 | 141246 | 141246 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 403 | Sq.Ft | 152 | 100 | 0 | 0 | 61256 | C+S GST 18% I/P RD | 11026.08 | 72282.08 | 72282.08 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1051.4605 | Sq.Ft | 152 | 100 | 0 | 0 | 159822 | C+S GST 18% I/P RD | 28767.96 | 188589.96 | 188589.96 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 844.2982 | Sq.Ft | 171 | 100 | 0 | 0 | 144375 | C+S GST 18% I/P RD | 25987.5 | 170362.5 | 170362.5 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 932.2982 | Sq.Ft | 171 | 100 | 0 | 0 | 159423 | C+S GST 18% I/P RD | 28696.14 | 188119.14 | 188119.14 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 500 | Sq.Ft | 171 | 100 | 0 | 0 | 85500 | C+S GST 18% I/P RD | 15390 | 100890 | 100890 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 27th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1200 | Sq.Ft | 171 | 100 | 0 | 0 | 205200 | C+S GST 18% I/P RD | 36936 | 242136 | 242136 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 497.076 | Sq.Ft | 171 | 100 | 0 | 0 | 85000 | C+S GST 18% I/P RD | 15300 | 100300 | 100300 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 42.75 | Sq.Ft | 152 | 100 | 0 | 0 | 6498 | C+S GST 18% I/P RD | 1169.64 | 7667.64 | 7667.64 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 392.4334 | Sq.Ft | 161.5 | 100 | 0 | 0 | 63378 | C+S GST 18% I/P RD | 11408.04 | 74786.04 | 74786.04 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 713.5604 | Sq.Ft | 161.5 | 100 | 0 | 0 | 115240 | C+S GST 18% I/P RD | 20743.2 | 135983.2 | 135983.2 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 606.5333 | Sq.Ft | 142.5 | 100 | 0 | 0 | 86431 | C+S GST 18% I/P RD | 15557.58 | 101988.58 | 101988.58 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 400 | Sq.Ft | 161.5 | 100 | 0 | 0 | 64600 | C+S GST 18% I/P RD | 11628 | 76228 | 76228 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 308.0867 | Sq.Ft | 161.5 | 100 | 0 | 0 | 49756 | C+S GST 18% I/P RD | 8956.08 | 58712.08 | 58712.08 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 424.5139 | Sq.Ft | 161.5 | 100 | 0 | 0 | 68559 | C+S GST 18% I/P RD | 12340.62 | 80899.62 | 80899.62 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 423.1158 | Sq.Ft | 142.5 | 100 | 0 | 0 | 60294 | C+S GST 18% I/P RD | 10852.92 | 71146.92 | 71146.92 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 316.0351 | Sq.Ft | 142.5 | 100 | 0 | 0 | 45035 | C+S GST 18% I/P RD | 8106.3 | 53141.3 | 53141.3 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 500.0842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 71262 | C+S GST 18% I/P RD | 12827.16 | 84089.16 | 84089.16 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 272 | 95252 | 28 Jun 2022 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 735 | A Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 995.7088 | Sq.Ft | 181.3 | 100 | 0 | 0 | 180522 | C+S GST 18% I/P RD | 32493.96 | 213015.96 | 213015.96 | Approved | 0 | 0 | 40746 | 28 Jun 2022
GANGA DHAM TOWERS | 452 | 95247 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) |  | D Bldg Flat No.1002 Electrical Work - 0 No. | TV Point | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 |  | 0 | 0 | 2 | 27 Jun 2022
GANGA DHAM TOWERS | 1261 | 95246 | 27 Jun 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 485 | A 1104 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 18.1818 | Sq.Ft | 55 | 100 | 25 | 0 | 1000 | C+S GST 0% I/P RD | 0 | 1000 | 1000 | Approved | 0 | 0 | 23 | 27 Jun 2022
GANGA DHAM TOWERS | 1261 | 95246 | 27 Jun 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 485 | A 2204 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 24 | Sq.Ft | 55 | 100 | 33 | 0 | 1320 | C+S GST 0% I/P RD | 0 | 1320 | 1320 | Approved | 0 | 0 | 23 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 8th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 9th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 20th Floor Back Coat Plaster | Back Coat Plaster | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 21st Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 22nd Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 19th Floor Back Coat Plaster | Back Coat Plaster | 0.1 | No. | 2000 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 927 | 95245 | 27 Jun 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 904 | A 19th Floor Back Coat Plaster | Back Coat Plaster | 0.9 | No. | 2000 | 100 | 45 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 220 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 22nd Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 17th Floor Fire Staircase Air Pressurization Shaft B | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 19th Floor Fire Staircase Air Pressurization Shaft B | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 9th Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 24 Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 13th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 20th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 3rd Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 7th Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 16th Floor Fire Staircase Air Pressurization Shaft B | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 2nd Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 4th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 8th Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 11th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 12th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 23rd Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 14th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 18th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 5th Floor Fire Staircase Air Pressurization Shaft BBM | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 21st Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 10th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 6th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 766 | 95244 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 491 | A Bldg 15th Floor Fire Staircase Air Pressurization Shaft BB | Blockwork/ Plaster-BC | 0.5 | No. | 2500 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 488 | 27 Jun 2022
GANGA DHAM TOWERS | 1355 | 95243 | 27 Jun 2022 |  | Kishan Enterprises | JAY BHAVANI ENTERPRISES | EV - 493 | A 1601 NOC | Blockwork 4" - BC | 132.0225 | Sq.Ft | 20 | 100 | 66.01 | 0 | 2640.45 | CGST 0% URD I/P | 0 | 2640.45 | 2640.45 | Approved | 0 | 0 | 26 | 27 Jun 2022
GANGA DHAM TOWERS | 1002 | 95242 | 27 Jun 2022 |  | AVCON TECHNICS PVT LTD | JAY BHAVANI ENTERPRISES |  | A 1902 NOC | Blockwork 4" - BC | 27.53 | Sq.Ft | 24 | 100 | 16.52 | 0 | 660.72 | CGST 0% URD I/P | 0 | 660.72 | 660.72 |  | 0 | 0 | 7 | 27 Jun 2022
GANGA DHAM TOWERS | 1287 | 95241 | 27 Jun 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 495 | B 2202 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 30.3455 | Sq.Ft | 55 | 100 | 41.73 | 0 | 1669 | CGST 0% URD I/P | 0 | 1669 | 1669 | Approved | 0 | 0 | 34 | 27 Jun 2022
GANGA DHAM TOWERS | 1287 | 95241 | 27 Jun 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 495 | B 2101 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 30.7273 | Sq.Ft | 55 | 100 | 42.25 | 0 | 1690 | CGST 0% URD I/P | 0 | 1690 | 1690 | Approved | 0 | 0 | 34 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1400 | 25 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.4 | No. | 220 | 25 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.6 | No. | 220 | 25 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Secondary Light Points (Looping) | 49.5 | No. | 67 | 25 | 20.73 | 0 | 829.13 | C+S GST 18% I/P RD | 149.24 | 978.37 | 978.37 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | AC Point BC | 1.8 | No. | 220 | 25 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | AC Point BC | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | 6 AMP Plug point (Independent) | 75.6 | No. | 200 | 25 | 94.5 | 0 | 3780 | C+S GST 18% I/P RD | 680.4 | 4460.4 | 4460.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | 6 AMP Plug point (Independent) | 47.7 | No. | 200 | 25 | 59.63 | 0 | 2385 | C+S GST 18% I/P RD | 429.3 | 2814.3 | 2814.3 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1001 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | 6 AMP Plug point (Independent) | 16.8 | No. | 200 | 25 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | TV/Tel DB Fixing | 0.2 | No. | 500 | 25 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11.7 | No. | 67 | 25 | 4.9 | 0 | 195.98 | C+S GST 18% I/P RD | 35.28 | 231.26 | 231.26 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Exhaust Fan Point | 1.6 | No. | 200 | 25 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Data Point | 3.6 | No. | 220 | 25 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | 8 Way TPN DB | 0.2 | No. | 1300 | 25 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.6 | No. | 200 | 25 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | 6 AMP Plug point (Independent) | 47.7 | No. | 200 | 25 | 59.63 | 0 | 2385 | C+S GST 18% I/P RD | 429.3 | 2814.3 | 2814.3 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Video Door Phone (L)- BC | 0.9 | No. | 200 | 25 | 1.13 | 0 | 45 | C+S GST 18% I/P RD | 8.1 | 53.1 | 53.1 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Video Door Phone (L)- BC | 0.2 | No. | 200 | 25 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 200 | 25 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 67 | 25 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Secondary Light Points (Looping) | 8.6 | No. | 67 | 25 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11.7 | No. | 67 | 25 | 4.9 | 0 | 195.98 | C+S GST 18% I/P RD | 35.28 | 231.26 | 231.26 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11.7 | No. | 67 | 25 | 4.9 | 0 | 195.98 | C+S GST 18% I/P RD | 35.28 | 231.26 | 231.26 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13.5 | No. | 67 | 25 | 5.65 | 0 | 226.13 | C+S GST 18% I/P RD | 40.7 | 266.83 | 266.83 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13.5 | No. | 67 | 25 | 5.65 | 0 | 226.13 | C+S GST 18% I/P RD | 40.7 | 266.83 | 266.83 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13.5 | No. | 67 | 25 | 5.65 | 0 | 226.13 | C+S GST 18% I/P RD | 40.7 | 266.83 | 266.83 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3 | No. | 67 | 25 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.6 | No. | 67 | 25 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Telephone Point | 1 | No. | 220 | 25 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Telephone Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | TV Point | 1.6 | No. | 220 | 25 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | TV Point | 1.2 | No. | 220 | 25 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 71.1 | No. | 200 | 25 | 88.88 | 0 | 3555 | C+S GST 18% I/P RD | 639.9 | 4194.9 | 4194.9 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.8 | No. | 200 | 25 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10.2 | No. | 200 | 25 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Data Point | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Data Point | 0.8 | No. | 220 | 25 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 901 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2102 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 202 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1401 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1602 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 501 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2002 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 801 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1002 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1202 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1801 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1601 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2101 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1302 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 302 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 701 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1502 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 101 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 402 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1902 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 102 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 401 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 902 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1101 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1102 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2401 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 2202 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 301 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1301 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 1701 Internal Electrical Work | Fan Point | 2.2 | No. | 200 | 25 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 399 | 95239 | 27 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 712 | B Bldg Flat No. 602 Internal Electrical Work | Fan Point | 1.8 | No. | 200 | 25 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 1531 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 16th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 9th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 7th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 24th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 25th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 23rd Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 2nd Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 15th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 4th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 17th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 1st Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 19th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 18th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 3rd Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 5th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 12th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 10th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 11th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 22nd Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 14th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 21st Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 6th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 13th Floor Pressurization shaft & Garbage Chute BBM | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 20thFloor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 767 | 95235 | 27 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY BHAVANI ENTERPRISES | EV - 492 | B Bldg 8th Floor Pressurization shaft & Garbage Chute BBM & | Blockwork/ Plaster-BC | 0.475 | No. | 2500 | 100 | 29.69 | 0 | 1187.5 | CGST 0% URD I/P | 0 | 1187.5 | 1187.5 | Approved | 0 | 0 | 297 | 27 Jun 2022
GANGA DHAM TOWERS | 804 | 95220 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 581 | B-1101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 520.752 | R.Ft | 55 | 100 | 0 | 0 | 28641.36 | C+S GST 18% I/P RD | 5155.44 | 33796.8 | 33796.8 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 804 | 95220 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 581 | B-1101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1366.974 | Sq.Ft | 55 | 100 | 0 | 0 | 75183.57 | C+S GST 18% I/P RD | 13533.04 | 88716.61 | 88716.61 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 804 | 95220 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 581 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 237.8727 | Sq.Ft | 55 | 100 | 0 | 0 | 13083 | C+S GST 18% I/P RD | 2354.94 | 15437.94 | 15437.94 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 804 | 95220 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 581 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 94.535 | R.Ft | 55 | 100 | 0 | 0 | 5199.43 | C+S GST 18% I/P RD | 935.9 | 6135.33 | 6135.33 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 805 | 95219 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 582 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 94.535 | R.Ft | 20 | 100 | 47.27 | 0 | 1890.7 | C+S GST 18% I/P RD | 340.32 | 2231.02 | 2231.02 | Approved | 0 | 0 | 444 | 25 Jun 2022
GANGA DHAM TOWERS | 805 | 95219 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 582 | B-1101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 520.752 | R.Ft | 20 | 100 | 260.38 | 0 | 10415.04 | C+S GST 18% I/P RD | 1874.7 | 12289.74 | 12289.74 | Approved | 0 | 0 | 444 | 25 Jun 2022
GANGA DHAM TOWERS | 805 | 95219 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 582 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 237.9 | Sq.Ft | 20 | 100 | 118.95 | 0 | 4758 | C+S GST 18% I/P RD | 856.44 | 5614.44 | 5614.44 | Approved | 0 | 0 | 444 | 25 Jun 2022
GANGA DHAM TOWERS | 805 | 95219 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 582 | B-1101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1366.974 | Sq.Ft | 20 | 100 | 683.49 | 0 | 27339.48 | C+S GST 18% I/P RD | 4921.1 | 32260.58 | 32260.58 | Approved | 0 | 0 | 444 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 2nd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 26th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 5th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 1st Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 19th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 14th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 3rd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 22nd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 24th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 25th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 7th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 4th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 17th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 970.08 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3395.28 | C+S GST 18% I/P RD | 611.16 | 4006.44 | 4006.44 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 16th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 21st Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 15th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 9th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 397.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1391 | C+S GST 18% I/P RD | 250.38 | 1641.38 | 1641.38 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 20th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 6th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 8th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 23rd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 710 | 95218 | 25 Jun 2022 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 551 | A 18th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (M) | 667.92 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2337.72 | C+S GST 18% I/P RD | 420.78 | 2758.5 | 2758.5 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 22nd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 17th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 1024.33 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3585.16 | C+S GST 18% I/P RD | 645.32 | 4230.48 | 4230.48 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 18tth Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 20th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 19th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 16th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 23rd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 21st Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 15th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 13th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 24th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 325.7143 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1140 | C+S GST 18% I/P RD | 205.2 | 1345.2 | 1345.2 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 711 | 95216 | 25 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 550 | A 14th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (M) | 618.47 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2164.65 | C+S GST 18% I/P RD | 389.64 | 2554.29 | 2554.29 | Approved | 0 | 0 | 0 | 25 Jun 2022
GANGA DHAM TOWERS | 1368 | 95210 | 24 Jun 2022 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 536 | A Podium 108 Level Expansion Joint | Expansion Joint (L) | 106 | Mtrs | 354 | 100 | 3752.4 | 0 | 37524 | CGST 0% URD I/P | 0 | 37524 | 37524 | Approved | 0 | 0 | 375 | 24 Jun 2022
GANGA DHAM TOWERS | 1367 | 95209 | 24 Jun 2022 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 537 | A Podium 108 Level Expansion Joint | Expansion Joint (M) | 106 | Mtrs | 459 | 100 | 0 | 0 | 48654 | CGST 0% URD I/P | 0 | 48654 | 48654 | Approved | 0 | 0 | 0 | 24 Jun 2022
GANGA DHAM TOWERS | 389 | 95208 | 24 Jun 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 406 | Loading / Unloading Expenses | Unloading of GYpsum- | 10 | Metric Tonnes | 200 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 24 Jun 2022
GANGA DHAM TOWERS | 998 | 95204 | 23 Jun 2022 |  | VENKAT RATHOD | JAY GANESH ENTERPRISES | EV - 533 | Ganga Business Centre Shop 32 Plaster Work | Labour lumpsum | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 60 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2302 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2103 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2402 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2301 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 203 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2203 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2104 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 102 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 1503 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2303 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 101 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 901 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2401 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2201 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1382 | 95203 | 23 Jun 2022 |  | SAROJ KUMAR PRADHAN | SAROJ KUMAR PRADHAN | EV - 402 | A Bldg. Flat No. 2204 Plumbing work | Int Flat PPRC Work. | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | IGST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 1800 | 23 Jun 2022
GANGA DHAM TOWERS | 1337 | 95202 | 23 Jun 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 433 | HO Expensess (L) | Printer Repairing- | 11.9985 | Month | 8000 | 8.33 | 0 | 0 | 7999 | C+S GST 18% I/P RD | 1439.82 | 9438.82 | 9438.82 | Approved | 0 | 0 | 80 | 23 Jun 2022
GANGA DHAM TOWERS | 1337 | 95201 | 23 Jun 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 432 | HO Expensess (L) | Printer Repairing- | 5.775 | Month | 8000 | 8.33 | 0 | 0 | 3850 | C+S GST 18% I/P RD | 693 | 4543 | 4543 | Approved | 0 | 0 | 39 | 23 Jun 2022
GANGA DHAM TOWERS | 1337 | 95200 | 23 Jun 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 431 | HO Expensess (L) | Printer Repairing- | 6 | Month | 8000 | 8.33 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 40 | 23 Jun 2022
GANGA DHAM TOWERS | 363 | 95197 | 23 Jun 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | Stamping Charges | 1 | No. | 18500 | 100 | 0 | 0 | 18500 | C+S GST 18% I/P RD | 3330 | 21830 | 21830 |  | 0 | 0 | 0 | 23 Jun 2022
GANGA DHAM TOWERS | 1224 | 95185 | 22 Jun 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE | EV - 480 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 21.9989 | Day | 451.613 | 100 | 0 | 0 | 9935 | CGST 0% URD I/P | 0 | 9935 | 9935 | Approved | 0 | 0 | 99 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Granite Border- Dld | 19.92 | R.Ft | 90 | 100 | 44.82 | 0 | 1792.8 | C+S GST 18% I/P RD | 322.7 | 2115.5 | 2115.5 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Granite Buffing | 134.21 | Sq.Ft | 45 | 100 | 150.99 | 0 | 6039.45 | C+S GST 18% I/P RD | 1087.1 | 7126.55 | 7126.55 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Brush Polish on Granite- BCE | 466.93 | Sq.Ft | 65 | 100 | 758.76 | 0 | 30350.45 | C+S GST 18% I/P RD | 5463.08 | 35813.53 | 35813.53 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Mason - SOS | 7.5 | Day | 1100 | 100 | 206.25 | 0 | 8250 | C+S GST 18% I/P RD | 1485 | 9735 | 9735 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Helper - SM | 4 | Day | 550 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Marble Mirror Polish Wrk | 35.25 | R.Ft | 65 | 100 | 57.28 | 0 | 2291.25 | C+S GST 18% I/P RD | 412.42 | 2703.67 | 2703.67 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Zero Point Joint Making | 63.84 | R.Ft | 200 | 100 | 319.2 | 0 | 12768 | C+S GST 18% I/P RD | 2298.24 | 15066.24 | 15066.24 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1284 | 95180 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 526 | B1 1101 Tiling Work | Drill Hole | 37 | No. | 130 | 100 | 120.25 | 0 | 4810 | C+S GST 18% I/P RD | 865.8 | 5675.8 | 5675.8 | Approved | 0 | 0 | 1370 | 22 Jun 2022
GANGA DHAM TOWERS | 1286 | 95179 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 525 | B1 1101 Tiling Work | Granite Leather Polish | 2620.18 | Sq.Ft | 65 | 100 | 4257.79 | 0 | 170311.7 | C+S GST 18% I/P RD | 30656.1 | 200967.8 | 200967.8 | Approved | 0 | 0 | 3723 | 22 Jun 2022
GANGA DHAM TOWERS | 1286 | 95179 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 525 | B1 1101 Tiling Work | Marble Mirror Polish | 203.68 | Sq.Ft | 65 | 100 | 330.98 | 0 | 13239.2 | C+S GST 18% I/P RD | 2383.06 | 15622.26 | 15622.26 | Approved | 0 | 0 | 3723 | 22 Jun 2022
GANGA DHAM TOWERS | 1286 | 95179 | 22 Jun 2022 |  | R K INTERIOR | R K INTERIOR | EV - 525 | B1 1101 Tiling Work | Marble Mirror Polish Wrk | 39.98 | R.Ft | 65 | 100 | 64.97 | 0 | 2598.7 | C+S GST 18% I/P RD | 467.76 | 3066.46 | 3066.46 | Approved | 0 | 0 | 3723 | 22 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1601 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1901 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 701 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 902 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1202 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2301 Kitchen HOB & Geyser Conduit Box Fixing work - 1 | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1002 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1304 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 602 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1201 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1204 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2401 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 303 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 603 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1801 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1102 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1504 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1902 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1001 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2101 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1104 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 903 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1401 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1402 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1802 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2104 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 904 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 202 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 502 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2102 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2201 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 504 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2202 Kitchen HOB & Geyser Conduit Box Fixing work - 1 | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 401 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 403 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 802 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1501 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1702 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1101 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2404 Kitchen HOB & Geyser Conduit Box Fixing work - 1 | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 404 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 703 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1701 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2302 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1604 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 901 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1602 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2002 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 704 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 402 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1704 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 601 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1904 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 604 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1302 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2001 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 702 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1502 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 201 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 2402 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 1301 Kitchen HOB & Geyser Conduit Box Fixing work - 1 N | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 301 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1270 | 95170 | 20 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 421 | A 801 Kitchen HOB & Geyser Conduit Box Fixing work - 1 No | 2 Module Box Fixing | 2 | No. | 150 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 189 | 20 Jun 2022
GANGA DHAM TOWERS | 1205 | 95169 | 20 Jun 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 388 | MS Frame Making,Fixing at A-Bldg 105 level parking. | MS Frame Making & Fixing | 280.49 | Sq.Ft | 8 | 100 | 56.1 | 0 | 2243.92 | CGST 0% URD I/P | 0 | 2243.92 | 2243.92 | Approved | 0 | 0 | 22 | 20 Jun 2022
GANGA DHAM TOWERS | 441 | 95168 | 20 Jun 2022 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION | EV - 389 | Tower-B Terrace Safety Railing 1st Floor to 26th Floor | Fabrication Work (L) - BCo | 218.1818 | Kgs | 11 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 24 | 20 Jun 2022
GANGA DHAM TOWERS | 368 | 95167 | 20 Jun 2022 |  | VATSA ENGINEERING | SAURABH FABRICATION | EV - 390 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Fabrication Work (L) - BCo | 218.1818 | Kgs | 11 | 100 | 60 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 24 | 20 Jun 2022
GANGA DHAM TOWERS | 126 | 95158 | 18 Jun 2022 |  | SANDIP VAMANRAO RUPNAWAR | KIRAN TUKARAM DHANAWADE | EV - 364 | Site Expenses | Site Expenses -SO | 0.4793 | Month | 15000 | 100 | 0 | 0 | 7190 | CGST 0% URD I/P | 0 | 7190 | 7190 | Approved | 0 | 0 | 0 | 18 Jun 2022
GANGA DHAM TOWERS | 126 | 95157 | 18 Jun 2022 |  | SANDIP VAMANRAO RUPNAWAR | KIRAN TUKARAM DHANAWADE | EV - 363 | Site Expenses | Site Expenses -SO | 0.0964 | Month | 15000 | 100 | 0 | 0 | 1446 | CGST 0% URD I/P | 0 | 1446 | 1446 | Approved | 0 | 0 | 0 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1501 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1301 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 2202 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 202 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 902 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1302 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 2002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 504 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1118 | 95140 | 18 Jun 2022 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL |  | A 1503 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 40 | 232.37 | 0 | 9294.8 | C+S GST 18% I/P RD | 1673.06 | 10967.86 | 10967.86 | Approved | 0 | 0 | 575 | 18 Jun 2022
GANGA DHAM TOWERS | 1180 | 95139 | 18 Jun 2022 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 500 | A Terrace Scaffolding Work | Scaffolding work | 6200 | Sq.Ft | 5.5 | 100 | 852.5 | 0 | 34100 | CGST 0% URD I/P | 0 | 34100 | 34100 | Approved | 0 | 0 | 341 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | CGST 0% URD I/P | 0 | 346.5 | 346.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | CGST 0% URD I/P | 0 | 346.5 | 346.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | CGST 0% URD I/P | 0 | 87.5 | 87.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | CGST 0% URD I/P | 0 | 87.5 | 87.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | CGST 0% URD I/P | 0 | 87.5 | 87.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | CGST 0% URD I/P | 0 | 87.5 | 87.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | CGST 0% URD I/P | 0 | 504.18 | 504.18 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | CGST 0% URD I/P | 0 | 644.88 | 644.88 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | CGST 0% URD I/P | 0 | 504.18 | 504.18 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | CGST 0% URD I/P | 0 | 115.5 | 115.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | CGST 0% URD I/P | 0 | 115.5 | 115.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | CGST 0% URD I/P | 0 | 308 | 308 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | CGST 0% URD I/P | 0 | 308 | 308 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | CGST 0% URD I/P | 0 | 245 | 245 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | CGST 0% URD I/P | 0 | 245 | 245 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | CGST 0% URD I/P | 0 | 154 | 154 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | CGST 0% URD I/P | 0 | 269.5 | 269.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | CGST 0% URD I/P | 0 | 269.5 | 269.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | CGST 0% URD I/P | 0 | 154 | 154 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | CGST 0% URD I/P | 0 | 2765 | 2765 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | CGST 0% URD I/P | 0 | 1785 | 1785 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | CGST 0% URD I/P | 0 | 1785 | 1785 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | CGST 0% URD I/P | 0 | 175 | 175 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | CGST 0% URD I/P | 0 | 175 | 175 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | CGST 0% URD I/P | 0 | 152.43 | 152.43 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | CGST 0% URD I/P | 0 | 175.88 | 175.88 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | CGST 0% URD I/P | 0 | 152.43 | 152.43 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | CGST 0% URD I/P | 0 | 227.5 | 227.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | CGST 0% URD I/P | 0 | 227.5 | 227.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | CGST 0% URD I/P | 0 | 175.88 | 175.88 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | CGST 0% URD I/P | 0 | 192.5 | 192.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | CGST 0% URD I/P | 0 | 192.5 | 192.5 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | CGST 0% URD I/P | 0 | 231 | 231 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2401 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | CGST 0% URD I/P | 0 | 385 | 385 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2002 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | CGST 0% URD I/P | 0 | 315 | 315 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 501 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | CGST 0% URD I/P | 0 | 385 | 385 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 399 | 95138 | 18 Jun 2022 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS | EV - 518 | B Bldg Flat No. 2202 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | CGST 0% URD I/P | 0 | 315 | 315 | Approved | 0 | 0 | 163 | 18 Jun 2022
GANGA DHAM TOWERS | 1224 | 95129 | 17 Jun 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE | EV - 476 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 11 | Day | 466.67 | 100 | 0 | 0 | 5133.37 | CGST 0% URD I/P | 0 | 5133.37 | 5133.37 | Approved | 0 | 0 | 51 | 17 Jun 2022
GANGA DHAM TOWERS | 1354 | 95127 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 702 | LT Substation External Painting work | Water Base Primer (M) | 3946.7 | Sq.Ft | 1 | 100 | 0 | 0 | 3946.7 | C+S GST 18% I/P RD | 710.4 | 4657.1 | 4657.1 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1354 | 95127 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 702 | LT Substation External Painting work | 1st Coat Acrylic Paint (M) | 3946.7 | Sq.Ft | 2 | 100 | 0 | 0 | 7893.4 | C+S GST 18% I/P RD | 1420.82 | 9314.22 | 9314.22 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1353 | 95126 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 701 | LT Substation External Painting work | 1st Coat Acrylic Paint (L) | 3946.7 | Sq.Ft | 1.5 | 100 | 148 | 0 | 5920.05 | C+S GST 18% I/P RD | 1065.6 | 6985.65 | 6985.65 | Approved | 0 | 0 | 197 | 17 Jun 2022
GANGA DHAM TOWERS | 1353 | 95126 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 701 | LT Substation External Painting work | Water Base Primer (L) | 3946.7 | Sq.Ft | 1 | 100 | 98.67 | 0 | 3946.7 | C+S GST 18% I/P RD | 710.4 | 4657.1 | 4657.1 | Approved | 0 | 0 | 197 | 17 Jun 2022
GANGA DHAM TOWERS | 1224 | 95125 | 17 Jun 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE |  | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 22 | Day | 451.613 | 100 | 0 | 0 | 9935.49 | CGST 0% URD I/P | 0 | 9935.49 | 9935.49 |  | 0 | 0 | 99 | 17 Jun 2022
GANGA DHAM TOWERS | 1375 | 95124 | 17 Jun 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 498 | MS Frame Making For Media Advertisemen | Fabrication work (L) | 700 | Sq.Ft | 2.5 | 100 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 115 | 17 Jun 2022
GANGA DHAM TOWERS | 1375 | 95124 | 17 Jun 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 498 | MS Frame Making For Media Advertisemen | GI Sheet Fixing (L) | 700 | Sq.Ft | 5 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 115 | 17 Jun 2022
GANGA DHAM TOWERS | 1375 | 95124 | 17 Jun 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 498 | MS Frame Making For Media Advertisemen | Taping Screw (M+L) | 200 | No. | 2.5 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 115 | 17 Jun 2022
GANGA DHAM TOWERS | 1375 | 95124 | 17 Jun 2022 |  | SHRUSHTI GLASS & ALUMINIUM | SHRUSHTI GLASS & ALUMINIUM | EV - 498 | MS Frame Making For Media Advertisemen | Fabrication work (L) | 250 | Kgs | 23 | 100 | 143.75 | 0 | 5750 | C+S GST 18% I/P RD | 1035 | 6785 | 6785 | Approved | 0 | 0 | 115 | 17 Jun 2022
GANGA DHAM TOWERS | 1309 | 95123 | 17 Jun 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 740 | C Drainage Line Laying work (L) | Round chamber 2ft dia (1.2m ht) - No. | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 25 | 17 Jun 2022
GANGA DHAM TOWERS | 1322 | 95121 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 477 | Compound Fabrication near Substation | Removing Work | 472 | Sq.Ft | 2 | 100 | 0 | 0 | 944 | CGST 0% URD I/P | 0 | 944 | 944 | Approved | 0 | 0 | 36 | 17 Jun 2022
GANGA DHAM TOWERS | 1322 | 95121 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 477 | Compound Fabrication near Substation | Removing Work | 240 | Sq.Ft | 2 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 36 | 17 Jun 2022
GANGA DHAM TOWERS | 1322 | 95121 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 477 | Compound Fabrication near Substation | Fabrication Work | 240 | Sq.Ft | 4 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 36 | 17 Jun 2022
GANGA DHAM TOWERS | 1322 | 95121 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 477 | Compound Fabrication near Substation | Meta colour Sheet Fixing BC | 134.67 | Sq.Ft | 5 | 100 | 16.83 | 0 | 673.35 | CGST 0% URD I/P | 0 | 673.35 | 673.35 | Approved | 0 | 0 | 36 | 17 Jun 2022
GANGA DHAM TOWERS | 1322 | 95121 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 477 | Compound Fabrication near Substation | Fabrication work- | 44.2 | Kgs | 12 | 100 | 13.26 | 0 | 530.4 | CGST 0% URD I/P | 0 | 530.4 | 530.4 | Approved | 0 | 0 | 36 | 17 Jun 2022
GANGA DHAM TOWERS | 1366 | 95119 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 479 | Fire M.S. Stand Fabrication | J Hook - AIE | 30 | No. | 20 | 100 | 15 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 26 | 17 Jun 2022
GANGA DHAM TOWERS | 1366 | 95119 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 479 | Fire M.S. Stand Fabrication | Fabrication Work-(L) | 166.4 | Kgs | 12 | 100 | 49.92 | 0 | 1996.8 | CGST 0% URD I/P | 0 | 1996.8 | 1996.8 | Approved | 0 | 0 | 26 | 17 Jun 2022
GANGA DHAM TOWERS | 1274 | 95118 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 478 | Store Plumbing material Godown | G.I. Sheet Fixing - BC | 220 | Sq.Ft | 5 | 100 | 27.5 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 35 | 17 Jun 2022
GANGA DHAM TOWERS | 1274 | 95118 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 478 | Store Plumbing material Godown | Fabrication work- | 64.64 | Kgs | 12 | 100 | 19.39 | 0 | 775.68 | CGST 0% URD I/P | 0 | 775.68 | 775.68 | Approved | 0 | 0 | 35 | 17 Jun 2022
GANGA DHAM TOWERS | 1274 | 95118 | 17 Jun 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 478 | Store Plumbing material Godown | MS Door (L) | 2 | No. | 800 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 35 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1604 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.13 | R.Ft | 55 | 100 | 79.93 | 0 | 3197.15 | C+S GST 18% I/P RD | 575.48 | 3772.63 | 3772.63 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1604 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 21.49 | R.Ft | 55 | 100 | 29.55 | 0 | 1181.95 | C+S GST 18% I/P RD | 212.76 | 1394.71 | 1394.71 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1601 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 55 | 100 | 45.11 | 0 | 1804.55 | C+S GST 18% I/P RD | 324.82 | 2129.37 | 2129.37 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1601 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 55 | 100 | 21.71 | 0 | 868.45 | C+S GST 18% I/P RD | 156.32 | 1024.77 | 1024.77 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1601 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 55 | 100 | 80.81 | 0 | 3232.35 | C+S GST 18% I/P RD | 581.82 | 3814.17 | 3814.17 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1601 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 55 | 100 | 42.86 | 0 | 1714.35 | C+S GST 18% I/P RD | 308.58 | 2022.93 | 2022.93 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 101 Living,Dining,Passa. Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 45 | 100 | 66.12 | 0 | 2644.65 | C+S GST 18% I/P RD | 476.04 | 3120.69 | 3120.69 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 101 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 45 | 100 | 36.91 | 0 | 1476.45 | C+S GST 18% I/P RD | 265.76 | 1742.21 | 1742.21 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 101 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 49.872 | R.Ft | 45 | 100 | 56.11 | 0 | 2244.24 | C+S GST 18% I/P RD | 403.96 | 2648.2 | 2648.2 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 1604 Master Bed Marble Flooring | Italian Marble Champher & Polish | 28.71 | R.Ft | 55 | 100 | 39.48 | 0 | 1579.05 | C+S GST 18% I/P RD | 284.22 | 1863.27 | 1863.27 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2401 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2404 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.13 | R.Ft | 60 | 100 | 87.2 | 0 | 3487.8 | C+S GST 18% I/P RD | 627.8 | 4115.6 | 4115.6 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2404 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 21.49 | R.Ft | 60 | 100 | 32.24 | 0 | 1289.4 | C+S GST 18% I/P RD | 232.1 | 1521.5 | 1521.5 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2404 Master Bed Marble Flooring | Italian Marble Champher & Polish | 28.71 | R.Ft | 60 | 100 | 43.07 | 0 | 1722.6 | C+S GST 18% I/P RD | 310.06 | 2032.66 | 2032.66 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2401 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 641 | 95117 | 17 Jun 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 510 | A 2401 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 338 | 17 Jun 2022
GANGA DHAM TOWERS | 1355 | 95116 | 17 Jun 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 506 | A 1601 NOC | Italian marble Skirting - BCo | 81.378 | R.Ft | 55 | 100 | 111.89 | 0 | 4475.79 | C+S GST 18% I/P RD | 805.64 | 5281.43 | 5281.43 | Approved | 0 | 0 | 45 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1403 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.89 | Sq.Ft | 21 | 100 | 13.07 | 0 | 522.69 | C+S GST 18% I/P RD | 94.08 | 616.77 | 616.77 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2003 Terrace Vitrified Flooring | Vitrified Flooring -BC | 132.07 | Sq.Ft | 28 | 100 | 92.45 | 0 | 3697.96 | C+S GST 18% I/P RD | 665.64 | 4363.6 | 4363.6 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2404 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2303 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2004 Terrace Vitrified Flooring | Vitrified Flooring -BC | 177.61 | Sq.Ft | 28 | 100 | 124.33 | 0 | 4973.08 | C+S GST 18% I/P RD | 895.16 | 5868.24 | 5868.24 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2103 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2104 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2203 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2304 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1903 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1904 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2403 Terrace Vitrified Flooring | Vitrified Flooring -BC | 35.7143 | Sq.Ft | 28 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1403 Staff Toilet dado | Dado BC | 135.37 | Sq.Ft | 21 | 100 | 71.07 | 0 | 2842.77 | C+S GST 18% I/P RD | 511.7 | 3354.47 | 3354.47 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1604 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.384 | R.Ft | 55 | 100 | 47.28 | 0 | 1891.12 | C+S GST 18% I/P RD | 340.4 | 2231.52 | 2231.52 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1604 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 93.008 | R.Ft | 55 | 100 | 127.89 | 0 | 5115.44 | C+S GST 18% I/P RD | 920.78 | 6036.22 | 6036.22 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1604 Master Bed Marble Flooring | Italian marble Skirting - BCo | 45.936 | R.Ft | 55 | 100 | 63.16 | 0 | 2526.48 | C+S GST 18% I/P RD | 454.76 | 2981.24 | 2981.24 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1503 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1704 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1304 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1504 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1403 Terrace Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 24 | 100 | 19.2 | 0 | 768 | C+S GST 18% I/P RD | 138.24 | 906.24 | 906.24 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1603 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1404 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1804 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2404 Master Bed Marble Flooring | Italian marble Skirting - BCo | 45.936 | R.Ft | 60 | 100 | 68.9 | 0 | 2756.16 | C+S GST 18% I/P RD | 496.1 | 3252.26 | 3252.26 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2404 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 93.008 | R.Ft | 60 | 100 | 139.51 | 0 | 5580.48 | C+S GST 18% I/P RD | 1004.48 | 6584.96 | 6584.96 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2404 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.384 | R.Ft | 60 | 100 | 51.58 | 0 | 2063.04 | C+S GST 18% I/P RD | 371.34 | 2434.38 | 2434.38 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 804 Terrace Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 20 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1103 Terrace Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1104 Terrace Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 904 Terrace Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 903 Terrace Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 20 | 100 | 16 | 0 | 640 | C+S GST 18% I/P RD | 115.2 | 755.2 | 755.2 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 803 Terrace Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1203 Terrace Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 20 | 100 | 16 | 0 | 640 | C+S GST 18% I/P RD | 115.2 | 755.2 | 755.2 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1204 Terrace Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 20 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 2404 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 60 | 100 | 79.95 | 0 | 3198 | C+S GST 18% I/P RD | 575.64 | 3773.64 | 3773.64 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1604 Terrace Vitrified Flooring | Vitrified Flooring -BC | 177.61 | Sq.Ft | 24 | 100 | 106.57 | 0 | 4262.64 | C+S GST 18% I/P RD | 767.28 | 5029.92 | 5029.92 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 551 | 95115 | 17 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 511 | A 1303 Terrace Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 24 | 100 | 19.2 | 0 | 768 | C+S GST 18% I/P RD | 138.24 | 906.24 | 906.24 | Approved | 0 | 0 | 638 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 602 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 45 | 100 | 59.96 | 0 | 2398.5 | C+S GST 18% I/P RD | 431.74 | 2830.24 | 2830.24 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 201 Marble Window Sill | Italian Marble Sill- BC- | 27 | R.Ft | 45 | 100 | 30.38 | 0 | 1215 | C+S GST 18% I/P RD | 218.7 | 1433.7 | 1433.7 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 401 Marble Window Sill | Italian Marble Sill- BC- | 27 | R.Ft | 45 | 100 | 30.38 | 0 | 1215 | C+S GST 18% I/P RD | 218.7 | 1433.7 | 1433.7 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1601 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 55 | 100 | 68.57 | 0 | 2742.96 | C+S GST 18% I/P RD | 493.74 | 3236.7 | 3236.7 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 101 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 45 | 100 | 59.06 | 0 | 2362.32 | C+S GST 18% I/P RD | 425.22 | 2787.54 | 2787.54 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 101 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 45 | 100 | 56.11 | 0 | 2244.24 | C+S GST 18% I/P RD | 403.96 | 2648.2 | 2648.2 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 101 Living,Dining,Passa. Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 45 | 100 | 105.79 | 0 | 4231.44 | C+S GST 18% I/P RD | 761.66 | 4993.1 | 4993.1 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1501 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.9 | Sq.Ft | 21 | 100 | 12.02 | 0 | 480.9 | C+S GST 18% I/P RD | 86.56 | 567.46 | 567.46 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 2401 Marble Window Sill | Italian Marble Sill- BC- | 52.32 | R.Ft | 60 | 100 | 78.48 | 0 | 3139.2 | C+S GST 18% I/P RD | 565.06 | 3704.26 | 3704.26 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 2402 Marble Window Sill | Italian Marble Sill- BC- | 53.3 | R.Ft | 60 | 100 | 79.95 | 0 | 3198 | C+S GST 18% I/P RD | 575.64 | 3773.64 | 3773.64 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1601 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 55 | 100 | 129.29 | 0 | 5171.76 | C+S GST 18% I/P RD | 930.92 | 6102.68 | 6102.68 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1601 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 25.264 | R.Ft | 55 | 100 | 34.74 | 0 | 1389.52 | C+S GST 18% I/P RD | 250.12 | 1639.64 | 1639.64 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1601 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 55 | 100 | 72.18 | 0 | 2887.28 | C+S GST 18% I/P RD | 519.72 | 3407 | 3407 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 1501 Staff Toilet dado | Dado BC | 122.46 | Sq.Ft | 21 | 100 | 64.29 | 0 | 2571.66 | C+S GST 18% I/P RD | 462.9 | 3034.56 | 3034.56 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 2402 Master Bed Marble Flooring | Italian marble Skirting - BCo | 53.52 | R.Ft | 60 | 100 | 80.28 | 0 | 3211.2 | C+S GST 18% I/P RD | 578.02 | 3789.22 | 3789.22 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 2402 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.736 | R.Ft | 60 | 100 | 59.6 | 0 | 2384.16 | C+S GST 18% I/P RD | 429.14 | 2813.3 | 2813.3 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 537 | 95114 | 17 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 507 | A 2402 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 57.295 | R.Ft | 60 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 443 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 7th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 23rd Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 12th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 17th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 2nd Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 9th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 13th Floor Texture Painting | Texture Paint (M) | 386.4828 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2802 | C+S GST 18% I/P RD | 504.36 | 3306.36 | 3306.36 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 14th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 1st Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 19th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 21st Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 22nd Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 24th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 10th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 3rd Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 8th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 4th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 18th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 11th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 20th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 15th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 16th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 6th Floor Texture Painting | Texture Paint (M) | 253.5172 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1200 | 95113 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 514 | B Southside 5th Floor Texture Painting | Texture Paint (M) | 386.7586 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 0 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 3rd Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 6th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 5th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 23rd Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 7th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 22nd Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 18th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 16th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 17th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 24th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 21st Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 2nd Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 9th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 11th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 8th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 15th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 13th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 4th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 20th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 12th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 14th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 10th Floor Texture Painting | Texture Paint (L) | 253.5172 | Sq.Ft | 7.25 | 100 | 45.95 | 0 | 1838 | C+S GST 18% I/P RD | 330.84 | 2168.84 | 2168.84 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 19th Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1199 | 95112 | 17 Jun 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 513 | B Southside 1st Floor Texture Painting | Texture Paint (L) | 386.7586 | Sq.Ft | 7.25 | 100 | 70.1 | 0 | 2804 | C+S GST 18% I/P RD | 504.72 | 3308.72 | 3308.72 | Approved | 0 | 0 | 1114 | 17 Jun 2022
GANGA DHAM TOWERS | 1352 | 95099 | 16 Jun 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 427 | A 2404 NOC - 1 No. | Italian Marble Flooring - BCo | 337 | Sq.Ft | 60 | 100 | 505.5 | 0 | 20220 | C+S GST 18% I/P RD | 3639.6 | 23859.6 | 23859.6 | Approved | 0 | 0 | 202 | 16 Jun 2022
GANGA DHAM TOWERS | 1355 | 95097 | 16 Jun 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 426 | A 1601 NOC | Italian Marble Flooring - BCo | 335 | Sq.Ft | 55 | 100 | 460.63 | 0 | 18425 | C+S GST 18% I/P RD | 3316.5 | 21741.5 | 21741.5 | Approved | 0 | 0 | 184 | 16 Jun 2022
GANGA DHAM TOWERS | 551 | 95096 | 16 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 509 | A 2404 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 584.9811 | Sq.Ft | 60 | 100 | 877.47 | 0 | 35098.87 | C+S GST 18% I/P RD | 6317.8 | 41416.67 | 41416.67 | Approved | 0 | 0 | 693 | 16 Jun 2022
GANGA DHAM TOWERS | 551 | 95096 | 16 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 509 | A 2404 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 60 | 100 | 315.66 | 0 | 12626.4 | C+S GST 18% I/P RD | 2272.76 | 14899.16 | 14899.16 | Approved | 0 | 0 | 693 | 16 Jun 2022
GANGA DHAM TOWERS | 551 | 95096 | 16 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 509 | A 2404 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 132.5115 | Sq.Ft | 60 | 100 | 198.77 | 0 | 7950.69 | C+S GST 18% I/P RD | 1431.12 | 9381.81 | 9381.81 | Approved | 0 | 0 | 693 | 16 Jun 2022
GANGA DHAM TOWERS | 551 | 95096 | 16 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 509 | A 2404 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 60 | 100 | 227.99 | 0 | 9119.4 | C+S GST 18% I/P RD | 1641.5 | 10760.9 | 10760.9 | Approved | 0 | 0 | 693 | 16 Jun 2022
GANGA DHAM TOWERS | 551 | 95096 | 16 Jun 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 509 | A 2204 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 160.3206 | Sq.Ft | 28 | 100 | 112.22 | 0 | 4488.98 | C+S GST 18% I/P RD | 808.02 | 5297 | 5297 | Approved | 0 | 0 | 693 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Tiling Below Wooden Flooring | Ceramic Flooring work | 180 | Sq.Ft | 21 | 100 | 94.5 | 0 | 3780 | C+S GST 18% I/P RD | 680.4 | 4460.4 | 4460.4 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 150.97 | Sq.Ft | 28 | 100 | 105.68 | 0 | 4227.16 | C+S GST 18% I/P RD | 760.88 | 4988.04 | 4988.04 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 28 | 100 | 111.89 | 0 | 4475.77 | C+S GST 18% I/P RD | 805.64 | 5281.41 | 5281.41 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 225.918 | Sq.Ft | 45 | 100 | 254.16 | 0 | 10166.31 | C+S GST 18% I/P RD | 1829.94 | 11996.25 | 11996.25 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Living,Dining,Passa. Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 45 | 100 | 644.29 | 0 | 25771.5 | C+S GST 18% I/P RD | 4638.88 | 30410.38 | 30410.38 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 1601 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 55 | 100 | 290.08 | 0 | 11603.35 | C+S GST 18% I/P RD | 2088.6 | 13691.95 | 13691.95 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 38.1333 | Sq.Ft | 45 | 100 | 42.9 | 0 | 1716 | C+S GST 18% I/P RD | 308.88 | 2024.88 | 2024.88 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 1601 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 55 | 100 | 313.78 | 0 | 12551 | C+S GST 18% I/P RD | 2259.18 | 14810.18 | 14810.18 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 1601 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 132.5115 | Sq.Ft | 55 | 100 | 182.2 | 0 | 7288.13 | C+S GST 18% I/P RD | 1311.86 | 8599.99 | 8599.99 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 45 | 100 | 237.34 | 0 | 9493.65 | C+S GST 18% I/P RD | 1708.86 | 11202.51 | 11202.51 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 1601 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 566.973 | Sq.Ft | 55 | 100 | 779.59 | 0 | 31183.52 | C+S GST 18% I/P RD | 5613.04 | 36796.56 | 36796.56 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 132.5115 | Sq.Ft | 60 | 100 | 198.77 | 0 | 7950.69 | C+S GST 18% I/P RD | 1431.12 | 9381.81 | 9381.81 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 60 | 100 | 315.98 | 0 | 12639 | C+S GST 18% I/P RD | 2275.02 | 14914.02 | 14914.02 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 60 | 100 | 273.68 | 0 | 10947 | C+S GST 18% I/P RD | 1970.46 | 12917.46 | 12917.46 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 2402 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 60 | 100 | 859.22 | 0 | 34368.6 | C+S GST 18% I/P RD | 6186.34 | 40554.94 | 40554.94 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Tiling Below Wooden Flooring | Ceramic Flooring work | 169.5474 | Sq.Ft | 13 | 100 | 55.1 | 0 | 2204.12 | C+S GST 18% I/P RD | 396.74 | 2600.86 | 2600.86 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 160.2216 | Sq.Ft | 15 | 100 | 60.08 | 0 | 2403.32 | C+S GST 18% I/P RD | 432.6 | 2835.92 | 2835.92 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 537 | 95094 | 16 Jun 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 508 | A 101 Terrace Vitrified Flooring | Vitrified Flooring -BC | 89 | Sq.Ft | 15 | 100 | 33.38 | 0 | 1335 | C+S GST 18% I/P RD | 240.3 | 1575.3 | 1575.3 | Approved | 0 | 0 | 1941 | 16 Jun 2022
GANGA DHAM TOWERS | 971 | 95075 | 13 Jun 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 715 | B-Bldg Core cutting work for AC & Fire fighting | Core Cutting Work 3" BCE | 11 | No. | 300 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 33 | 13 Jun 2022
GANGA DHAM TOWERS | 1228 | 95072 | 11 Jun 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 387 | Site Expenses | Site Expenses -SO | 0.5532 | Month | 15000 | 100 | 0 | 0 | 8298 | C+S GST 0% I/P RD | 0 | 8298 | 8298 | Approved | 0 | 0 | 0 | 11 Jun 2022
GANGA DHAM TOWERS | 1228 | 95072 | 11 Jun 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 387 | Site Expenses | Site Expenses -SO | 0.1718 | Month | 15000 | 100 | 0 | 0 | 2577 | C+S GST 0% I/P RD | 0 | 2577 | 2577 | Approved | 0 | 0 | 0 | 11 Jun 2022
GANGA DHAM TOWERS | 1184 | 95071 | 11 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 386 | B Fire Check Floor Steps BBM/ Plaster | Plaster Work -Dld | 58.85 | Sq.Ft | 15 | 100 | 22.07 | 0 | 882.75 | CGST 0% URD I/P | 0 | 882.75 | 882.75 | Approved | 0 | 0 | 53 | 11 Jun 2022
GANGA DHAM TOWERS | 1184 | 95071 | 11 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 386 | B Fire Check Floor Steps BBM/ Plaster | Plaster Work -Dld | 58.85 | Sq.Ft | 15 | 100 | 22.07 | 0 | 882.75 | CGST 0% URD I/P | 0 | 882.75 | 882.75 | Approved | 0 | 0 | 53 | 11 Jun 2022
GANGA DHAM TOWERS | 1184 | 95071 | 11 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 386 | B Fire Check Floor Steps BBM/ Plaster | Brickwork 4" -DLd | 99.38 | Sq.Ft | 18 | 100 | 44.72 | 0 | 1788.84 | CGST 0% URD I/P | 0 | 1788.84 | 1788.84 | Approved | 0 | 0 | 53 | 11 Jun 2022
GANGA DHAM TOWERS | 1184 | 95071 | 11 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 386 | B Fire Check Floor Steps BBM/ Plaster | Brickwork 4" -DLd | 99.38 | Sq.Ft | 18 | 100 | 44.72 | 0 | 1788.84 | CGST 0% URD I/P | 0 | 1788.84 | 1788.84 | Approved | 0 | 0 | 53 | 11 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU 22 kV 3 in/ 2 out (L) | 1 | No. | 5000 | 100 | 125 | 0 | 5000 | C+S GST 0% I/P RD | 0 | 5000 | 5000 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | Earthing work(m+l)- BC | 13 | No. | 4000 | 100 | 1300 | 0 | 52000 | C+S GST 0% I/P RD | 0 | 52000 | 52000 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 50x5 (M+L) -UTI | 20 | Mtrs | 235 | 100 | 117.5 | 0 | 4700 | C+S GST 0% I/P RD | 0 | 4700 | 4700 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 300 sqmm - No. | 2 | No. | 2500 | 100 | 125 | 0 | 5000 | C+S GST 0% I/P RD | 0 | 5000 | 5000 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | 22/95 Sqmm. I.D. Joint -UTI | 2 | No. | 6300 | 100 | 315 | 0 | 12600 | C+S GST 0% I/P RD | 0 | 12600 | 12600 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | Feeder Pillar fixing (L)-LC | 2 | No. | 3000 | 100 | 150 | 0 | 6000 | C+S GST 0% I/P RD | 0 | 6000 | 6000 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | End Termination 300sqmm- UTI | 12 | No. | 1700 | 100 | 510 | 0 | 20400 | C+S GST 0% I/P RD | 0 | 20400 | 20400 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | XLPE Cable laying 95sqmm 3C 22kv (L) | 50 | Mtrs | 110 | 100 | 137.5 | 0 | 5500 | C+S GST 0% I/P RD | 0 | 5500 | 5500 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | Transformer fixing 22KV/630kva (L) | 1.4286 | No. | 6300 | 100 | 225 | 0 | 9000 | C+S GST 0% I/P RD | 0 | 9000 | 9000 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 95 sqmm | 1 | No. | 2500 | 100 | 62.5 | 0 | 2500 | C+S GST 0% I/P RD | 0 | 2500 | 2500 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | G.I. Strip 32x6 fixing. -UTI | 30 | Mtrs | 180 | 100 | 135 | 0 | 5400 | C+S GST 0% I/P RD | 0 | 5400 | 5400 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | Gland Plate Hole Making (L) | 12 | No. | 100 | 100 | 30 | 0 | 1200 | C+S GST 0% I/P RD | 0 | 1200 | 1200 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 957 | 95055 | 09 Jun 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 304 | Electricity Infrastructure-Trnsformer,HT,LT Work | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 114 | Mtrs | 90 | 100 | 256.5 | 0 | 10260 | C+S GST 0% I/P RD | 0 | 10260 | 10260 | Approved | 0 | 0 | 1396 | 09 Jun 2022
GANGA DHAM TOWERS | 1196 | 95037 | 08 Jun 2022 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 1322 | MEDIA Flex printing | Star Flex | 2640 | Sq.Ft | 19 | 100 | 0 | 0 | 50160 | C+S GST 18% I/P RD | 9028.8 | 59188.8 | 59188.8 | Approved | 0 | 0 | 1003 | 08 Jun 2022
GANGA DHAM TOWERS | 372 | 95036 | 08 Jun 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 370 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 23.0769 | Sq.Ft | 130 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 105 | 08 Jun 2022
GANGA DHAM TOWERS | 372 | 95036 | 08 Jun 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 370 | B Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.1429 | Sq.Ft | 140 | 100 | 0 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 105 | 08 Jun 2022
GANGA DHAM TOWERS | 372 | 95036 | 08 Jun 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 370 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 25 | Sq.Ft | 120 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 105 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | B Grond Floor External Sand Face Plaster | External Plaster- BC | 726 | Sq.Ft | 20 | 100 | 363 | 0 | 14520 | CGST 0% URD I/P | 0 | 14520 | 14520 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | A P3 Floor External Sand Face Plaster | External Plaster- BC | 1325 | Sq.Ft | 20 | 100 | 662.5 | 0 | 26500 | CGST 0% URD I/P | 0 | 26500 | 26500 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | A Podium Floor External Sand Face Plaster | External Plaster- BC | 622 | Sq.Ft | 20 | 100 | 311 | 0 | 12440 | CGST 0% URD I/P | 0 | 12440 | 12440 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | B P1 Floor External Sand Face Plaster | External Plaster- BC | 31 | Sq.Ft | 20 | 100 | 15.5 | 0 | 620 | CGST 0% URD I/P | 0 | 620 | 620 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | B Podium Floor External Sand Face Plaster | External Plaster- BC | 585 | Sq.Ft | 20 | 100 | 292.5 | 0 | 11700 | CGST 0% URD I/P | 0 | 11700 | 11700 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | A Ground Floor External Sand Face Plaster | External Plaster- BC | 217 | Sq.Ft | 20 | 100 | 108.5 | 0 | 4340 | CGST 0% URD I/P | 0 | 4340 | 4340 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | A P2 Floor External Sand Face Plaster | External Plaster- BC | 2108 | Sq.Ft | 20 | 100 | 1054 | 0 | 42160 | CGST 0% URD I/P | 0 | 42160 | 42160 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | B P2 Floor External Sand Face Plaster | External Plaster- BC | 268 | Sq.Ft | 20 | 100 | 134 | 0 | 5360 | CGST 0% URD I/P | 0 | 5360 | 5360 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 1184 | 95035 | 08 Jun 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 488 | A P1 Floor External Sand Face Plaster | External Plaster- BC | 937 | Sq.Ft | 20 | 100 | 468.5 | 0 | 18740 | CGST 0% URD I/P | 0 | 18740 | 18740 | Approved | 0 | 0 | 1364 | 08 Jun 2022
GANGA DHAM TOWERS | 209 | 95034 | 08 Jun 2022 |  | UNIQUE ENTERPRISES | JAY GANESH ENTERPRISES | EV - 440 | A Bldg 3rd RCC Slab (P2 Floor) Built-up Area (L) | Hacking Work | 4000 | Sq.Ft | 5 | 100 | 500 | 0 | 20000 | CGST 0% URD I/P | 0 | 20000 | 20000 | Approved | 0 | 0 | 200 | 08 Jun 2022
GANGA DHAM TOWERS | 1052 | 95031 | 07 Jun 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 284 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 18% RCM | 5397.84 | 35385.84 | 35385.84 | Approved | 0 | 0 | 2999 | 07 Jun 2022
GANGA DHAM TOWERS | 1340 | 95027 | 07 Jun 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 283 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 07 Jun 2022
GANGA DHAM TOWERS | 1335 | 95001 | 06 Jun 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 352 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Shifting Charges-SO | 6 | No. | 6000 | 100 | 0 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 1490 | 06 Jun 2022
GANGA DHAM TOWERS | 1335 | 95001 | 06 Jun 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 352 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 | Approved | 0 | 0 | 1490 | 06 Jun 2022
GANGA DHAM TOWERS | 1335 | 95001 | 06 Jun 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 352 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Hiring of Gondola | 1 | Month | 54000 | 100 | 0 | 0 | 54000 | C+S GST 18% I/P RD | 9720 | 63720 | 63720 | Approved | 0 | 0 | 1490 | 06 Jun 2022
GANGA DHAM TOWERS | 1335 | 95001 | 06 Jun 2022 |  | KAUSHAL CRADLE SERVICES | KAUSHAL CRADLE SERVICES | EV - 352 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | Material Shifting | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 1490 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 702 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 6 | No. | 20 | 100 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1902 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2001 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1002 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 802 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1501 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2002 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 50 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 902 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 2101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 1001 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 4 | No. | 20 | 100 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1293 | 94992 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 375 | B 502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 70 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1002 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 902 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 702 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1502 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 50 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1302 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 2 | No. | 40 | 100 | 0 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 602 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1501 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2001 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2102 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1001 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 802 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1402 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1601 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1801 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1202 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1902 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2201 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 901 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2002 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2101 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2401 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 701 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 1301 Duct Platform Fabration Work - - 1 No. | Mechanical Fastner (M) | 4 | No. | 40 | 100 | 0 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 1294 | 94991 | 06 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 374 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (M) | 9.7538 | Kgs | 65 | 100 | 0 | 0 | 634 | C+S GST 18% I/P RD | 114.12 | 748.12 | 748.12 | Approved | 0 | 0 | 0 | 06 Jun 2022
GANGA DHAM TOWERS | 145 | 94990 | 06 Jun 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 381 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 06 Jun 2022
GANGA DHAM TOWERS | 145 | 94989 | 06 Jun 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 379 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 06 Jun 2022
GANGA DHAM TOWERS | 145 | 94988 | 06 Jun 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 380 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 06 Jun 2022
GANGA DHAM TOWERS | 272 | 94987 | 04 Jun 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 274 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 49.1228 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 70 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 204 Duct Platform Fabration Work | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 701 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1004 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1501 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1804 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1901 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2304 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2403 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 603 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 604 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1101 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1403 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1903 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2301 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 801 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1201 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1304 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1601 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1401 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2201 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 503 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1001 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 403 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1604 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1701 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2103 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 704 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 903 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1303 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1904 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1103 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1503 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1704 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1003 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1404 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1104 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 201 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 203 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2204 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2303 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 803 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1703 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2404 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 404 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 401 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 501 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1801 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1803 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1203 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2101 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 804 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 901 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1204 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1301 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1603 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2004 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 104 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 904 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2001 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2401 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 301 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 303 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 504 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 703 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2003 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2104 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 503 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 504 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 904 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1303 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 901 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 803 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2304 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1501 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1604 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 204 Duct Platform Fabration Work | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2003 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 403 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 501 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 604 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1701 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1001 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1304 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 704 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1104 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 301 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 404 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1003 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 701 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1204 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 201 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 601 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1401 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1403 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2201 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1801 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2103 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 101 Duct Platform Fabration Work | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 104 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1504 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2001 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 103 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 903 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1803 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2204 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1301 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2101 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2404 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1004 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 303 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1103 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2303 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 203 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 804 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1101 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1903 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1203 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1901 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1704 Duct Platform Fabration Work - | Fabrication work (L) | 22.5385 | Kgs | 26 | 100 | 14.65 | 0 | 586 | C+S GST 18% I/P RD | 105.48 | 691.48 | 691.48 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2203 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 603 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2104 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2301 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1404 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1703 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1804 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2401 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 703 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1904 Duct Platform Fabration Work - | Fabrication work (L) | 22.5385 | Kgs | 26 | 100 | 14.65 | 0 | 586 | C+S GST 18% I/P RD | 105.48 | 691.48 | 691.48 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2004 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2403 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1503 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 304 Duct Platform Fabration Work - | Fabrication work (L) | 22.5769 | Kgs | 26 | 100 | 14.67 | 0 | 587 | C+S GST 18% I/P RD | 105.66 | 692.66 | 692.66 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 401 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 801 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1601 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1603 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1201 Duct Platform Fabration Work - | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 1504 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 2203 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 103 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 601 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 101 Duct Platform Fabration Work | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 1290 | 94985 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 376 | A 304 Duct Platform Fabration Work - | Mechanical Fastner (L) | 12 | No. | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 645 | 04 Jun 2022
GANGA DHAM TOWERS | 632 | 94984 | 04 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 377 | A 1503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 197 | 04 Jun 2022
GANGA DHAM TOWERS | 632 | 94984 | 04 Jun 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 377 | A 1503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 197 | 04 Jun 2022
GANGA DHAM TOWERS | 629 | 94983 | 04 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 578 | A 1503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 629 | 94983 | 04 Jun 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 578 | A 1503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 2002 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.5 | No. | 1500 | 100 | 56.25 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 2002 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.5 | No. | 1500 | 100 | 56.25 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 802 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.5 | No. | 1100 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 802 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.5 | No. | 1100 | 100 | 41.25 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 1901 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.75 | No. | 1650 | 100 | 72.19 | 0 | 2887.5 | CGST 0% URD I/P | 0 | 2887.5 | 2887.5 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 522 | 94980 | 04 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 434 | B Bldg 1901 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.75 | No. | 1650 | 100 | 72.19 | 0 | 2887.5 | CGST 0% URD I/P | 0 | 2887.5 | 2887.5 | Approved | 0 | 0 | 136 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1002 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 802 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 50 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 601 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 902 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1501 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1602 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2002 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 201 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2301 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2102 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2401 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1502 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 402 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 502 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1701 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1801 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 602 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1302 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1901 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1402 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1902 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2001 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 2202 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 1101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 702 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 26.52 | Kgs | 26 | 100 | 17.24 | 0 | 689.52 | C+S GST 18% I/P RD | 124.12 | 813.64 | 813.64 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 1293 | 94979 | 04 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 372 | B 101 Duct Platform Fabration Work - - 1 No. | Fabrication work (L) | 9.7692 | Kgs | 26 | 100 | 6.35 | 0 | 254 | C+S GST 18% I/P RD | 45.72 | 299.72 | 299.72 | Approved | 0 | 0 | 206 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1393 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1393 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1393 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.1579 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.1579 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.1579 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9605 | Sq.Ft | 152 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9605 | Sq.Ft | 152 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9605 | Sq.Ft | 152 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94978 | 04 Jun 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 437 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9605 | Sq.Ft | 152 | 100 | 0 | 0 | 7290 | C+S GST 18% I/P RD | 1312.2 | 8602.2 | 8602.2 | Approved | 0 | 0 | 729 | 04 Jun 2022
GANGA DHAM TOWERS | 272 | 94977 | 04 Jun 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 371 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 90.2256 | Sq.Ft | 133 | 100 | 0 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 120 | 04 Jun 2022
GANGA DHAM TOWERS | 372 | 94976 | 04 Jun 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 444 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45 | Sq.Ft | 150 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 675 | 04 Jun 2022
GANGA DHAM TOWERS | 372 | 94976 | 04 Jun 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 444 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45 | Sq.Ft | 150 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 675 | 04 Jun 2022
GANGA DHAM TOWERS | 372 | 94976 | 04 Jun 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 444 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.5484 | Sq.Ft | 155 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 675 | 04 Jun 2022
GANGA DHAM TOWERS | 372 | 94976 | 04 Jun 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 444 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.5484 | Sq.Ft | 155 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 675 | 04 Jun 2022
GANGA DHAM TOWERS | 372 | 94976 | 04 Jun 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 444 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.5484 | Sq.Ft | 155 | 100 | 0 | 0 | 6750 | C+S GST 18% I/P RD | 1215 | 7965 | 7965 | Approved | 0 | 0 | 675 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 16th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 12th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 11th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 2nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 15th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 18th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 21st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside1st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 10th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 16th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 17th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 6th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 10th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 23rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 15th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 24th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 12th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 1st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 7th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 3rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 19th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 4th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 4th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 8th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 9th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 24th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 7th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 13th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 14th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 14th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 19th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 5th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 21st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 8th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 13th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 20th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 9th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 18th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 17th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 5th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 6th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 22nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 225 | Sq.Ft | 2 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 11th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 20th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 211 | Sq.Ft | 2 | 100 | 0 | 0 | 422 | C+S GST 18% I/P RD | 75.96 | 497.96 | 497.96 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 9th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 16th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 1st floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 4th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 3rd floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 10th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 17th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 8th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 19th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 10th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 21st floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 14th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 18th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 16th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 6th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 11th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 20th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 9th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 2nd floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 4th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 13th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 22nd floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 2nd floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 20th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 22nd floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 3rd floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 13th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 5th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 19th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 14th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 21st floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 24th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 8th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 23rd floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 24th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 12th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 15th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 6th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 7th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 12th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 5th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside1st floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 15th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 17th floor External Texture Painting | Water Base Primer (M) | 225 | Sq.Ft | 1 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 7th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 23rd floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 11th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 18th floor External Texture Painting | Water Base Primer (M) | 211 | Sq.Ft | 1 | 100 | 0 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 14th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 19th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 6th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 4th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 20th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside1st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 1st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 8th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 9th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 16th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 18th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 5th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 21st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 24th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 11th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 13th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 15th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 7th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 17th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 12th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A South side 10th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 225.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 563 | C+S GST 18% I/P RD | 101.34 | 664.34 | 664.34 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1295 | 94975 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 679 | A Northside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 211.2 | Sq.Ft | 2.5 | 100 | 0 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 0 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 9th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 10th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 6th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 8th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 15th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 14th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 24th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 18th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 21st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 16th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 7th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 11th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 5th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 12th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 13th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 17th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside1st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 16th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 6th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 8th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 21st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 13th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 20th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 10th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 19th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 20th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 1st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 8th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 15th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 2nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 3rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 17th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 9th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 10th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 9th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 23rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 5th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 5th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 12th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 18th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 8th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 12th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 12th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 18th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 19th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 20th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 6th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 11th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 22nd floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 7th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 9th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 16th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 4th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 22nd floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 23rd floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 7th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 9th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 10th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 2nd floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 17th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 5th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 19th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 14th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 18th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 5th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 13th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside1st floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 21st floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 8th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 16th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 17th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 14th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 3rd floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 10th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 3rd floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 21st floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 23rd floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 6th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 13th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 20th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 1st floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 2nd floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 24th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 4th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 15th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 11th floor External Texture Painting | Water Base Primer (L) | 225 | Sq.Ft | 1 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 15th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 24th floor External Texture Painting | Water Base Primer (L) | 211 | Sq.Ft | 1 | 100 | 5.28 | 0 | 211 | C+S GST 18% I/P RD | 37.98 | 248.98 | 248.98 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside1st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 16th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 18th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 17th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 4th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 24th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 14th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 19th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 14th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 15th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 22nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 12th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 6th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 11th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 7th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 19th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 20th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 1st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 4th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 7th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 13th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 24th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 11th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A South side 21st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 225.3333 | Sq.Ft | 1.5 | 100 | 8.45 | 0 | 338 | C+S GST 18% I/P RD | 60.84 | 398.84 | 398.84 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 4th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1292 | 94974 | 04 Jun 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 681 | A Northside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 211.3333 | Sq.Ft | 1.5 | 100 | 7.92 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 419 | 04 Jun 2022
GANGA DHAM TOWERS | 1359 | 94972 | 03 Jun 2022 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4199.98 | C+S GST 18% I/P RD | 756 | 4955.98 | 4955.98 |  | 0 | 0 | 84 | 03 Jun 2022
GANGA DHAM TOWERS | 1359 | 94972 | 03 Jun 2022 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4199.98 | C+S GST 18% I/P RD | 756 | 4955.98 | 4955.98 |  | 0 | 0 | 84 | 03 Jun 2022
GANGA DHAM TOWERS | 413 | 94971 | 03 Jun 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 589 | Sales office Garden Maintenance | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 03 Jun 2022
GANGA DHAM TOWERS | 178 | 94970 | 03 Jun 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 598 | Sales office Garden Maintenance | Garden work. | 58.9992 | Day | 407.25 | 100 | 0 | 0 | 24027.42 | C+S GST 18% I/P RD | 4324.94 | 28352.36 | 28352.36 | Approved | 0 | 0 | 240 | 03 Jun 2022
GANGA DHAM TOWERS | 1297 | 94969 | 03 Jun 2022 |  | MANALI HEMANT PHARATE | MANALI HEMANT PHARATE | EV - 325 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 1 | Month | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 149 | 94968 | 03 Jun 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 341 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3609 | No. | 4 | 100 | 0 | 0 | 14436 | CGST 0% URD I/P | 0 | 14436 | 14436 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1360 | 94966 | 03 Jun 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 411 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 300 | 03 Jun 2022
GANGA DHAM TOWERS | 1360 | 94966 | 03 Jun 2022 |  | GREEN GARDEN DEVLOPERS AND MENTENANCE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 411 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 15000 | 100 | 0 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 300 | 03 Jun 2022
GANGA DHAM TOWERS | 940 | 94965 | 03 Jun 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 412 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 440 | 03 Jun 2022
GANGA DHAM TOWERS | 940 | 94965 | 03 Jun 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 412 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 440 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 504 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1503 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1904 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2003 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 303 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 704 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 801 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1104 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1504 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1301 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1701 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2401 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2403 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 401 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1201 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1601 Duct Platform Fabration Work - | Fabrication work (M) | 17.6615 | Kgs | 65 | 100 | 0 | 0 | 1148 | C+S GST 18% I/P RD | 206.64 | 1354.64 | 1354.64 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1601 Duct Platform Fabration Work - | Fabrication work (M) | 8.8462 | Kgs | 65 | 100 | 0 | 0 | 575 | C+S GST 18% I/P RD | 103.5 | 678.5 | 678.5 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2001 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2301 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 304 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 703 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1103 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 301 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1604 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1803 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1901 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2404 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 603 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 701 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 203 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2104 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 403 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 901 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1003 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 204 Duct Platform Fabration Work | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 501 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2204 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2303 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2004 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2304 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1004 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1804 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 201 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1303 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 903 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1101 Duct Platform Fabration Work - | Fabrication work (M) | 16.7692 | Kgs | 65 | 100 | 0 | 0 | 1090 | C+S GST 18% I/P RD | 196.2 | 1286.2 | 1286.2 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1101 Duct Platform Fabration Work - | Fabrication work (M) | 9 | Kgs | 65 | 100 | 0 | 0 | 585 | C+S GST 18% I/P RD | 105.3 | 690.3 | 690.3 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1304 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1401 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1703 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1801 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1704 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2101 Duct Platform Fabration Work - | Fabrication work (M) | 17.6615 | Kgs | 65 | 100 | 0 | 0 | 1148 | C+S GST 18% I/P RD | 206.64 | 1354.64 | 1354.64 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2101 Duct Platform Fabration Work - | Fabrication work (M) | 8.8462 | Kgs | 65 | 100 | 0 | 0 | 575 | C+S GST 18% I/P RD | 103.5 | 678.5 | 678.5 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2103 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 503 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 904 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 104 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1501 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2201 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 404 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 804 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1001 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1203 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1404 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1603 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 604 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 803 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 103 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1204 Duct Platform Fabration Work - | Fabrication work (M) | 22.5538 | Kgs | 65 | 100 | 0 | 0 | 1466 | C+S GST 18% I/P RD | 263.88 | 1729.88 | 1729.88 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1403 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1903 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2203 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 601 Duct Platform Fabration Work - | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 101 Duct Platform Fabration Work | Fabrication work (M) | 26.52 | Kgs | 65 | 100 | 0 | 0 | 1723.8 | C+S GST 18% I/P RD | 310.28 | 2034.08 | 2034.08 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2004 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2401 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 304 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 401 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 801 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 703 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1101 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 504 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1704 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 204 Duct Platform Fabration Work | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1303 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1404 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1703 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1001 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 501 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 103 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1403 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1803 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2103 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2104 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1901 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2301 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2404 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 603 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 701 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 104 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 101 Duct Platform Fabration Work | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1401 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1801 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1804 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2201 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1003 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1204 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2203 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 301 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 404 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 804 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1603 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1201 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2001 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2303 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1104 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 403 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 903 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1203 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1504 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1601 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1604 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2003 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2304 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2101 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 604 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 803 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1301 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1701 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2204 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 904 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1501 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1503 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1903 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 201 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 203 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 303 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 704 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1004 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1304 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 503 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 601 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1904 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 2403 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 901 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1291 | 94964 | 03 Jun 2022 |  | PATILS FABRICATORS | PATILS FABRICATORS | EV - 373 | A 1103 Duct Platform Fabration Work - | Mechanical Fastner (M) | 12 | No. | 40 | 100 | 0 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 0 | 03 Jun 2022
GANGA DHAM TOWERS | 1296 | 94954 | 01 Jun 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 343 | Miscellaneous expenses | Marketing Operating Expenses | 6.0394 | Month | 25000 | 8.33 | 0 | 0 | 12577 | CGST 0% URD I/P | 0 | 12577 | 12577 | Approved | 0 | 0 | 0 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Chemical & IPS Waterproofing | IPS W/P | 345.1818 | Sq.Ft | 11 | 100 | 379.7 | 0 | 3797 | CGST 0% URD I/P | 0 | 3797 | 3797 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Chemical & IPS Waterproofing | IPS W/P | 345.1818 | Sq.Ft | 11 | 100 | 379.7 | 0 | 3797 | CGST 0% URD I/P | 0 | 3797 | 3797 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 2401 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1901 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 345.2105 | Sq.Ft | 19 | 100 | 655.9 | 0 | 6559 | CGST 0% URD I/P | 0 | 6559 | 6559 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 498 | 94944 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 499 | B 1801 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 345.2105 | Sq.Ft | 19 | 100 | 655.9 | 0 | 6559 | CGST 0% URD I/P | 0 | 6559 | 6559 | Approved | 0 | 0 | 437 | 01 Jun 2022
GANGA DHAM TOWERS | 522 | 94943 | 01 Jun 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 324 | B Bldg 1801 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1400 | 100 | 245 | 0 | 9800 | CGST 0% URD I/P | 0 | 9800 | 9800 | Approved | 0 | 0 | 98 | 01 Jun 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 6.31 | Kgs | 26.4 | 100 | 4.16 | 0 | 166.58 | CGST 0% URD I/P | 0 | 166.58 | 166.58 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 8.8 | Kgs | 26.4 | 100 | 5.81 | 0 | 232.32 | CGST 0% URD I/P | 0 | 232.32 | 232.32 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 107.98 | Kgs | 22.8 | 100 | 61.55 | 0 | 2461.94 | CGST 0% URD I/P | 0 | 2461.94 | 2461.94 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 7.71 | Kgs | 26.4 | 100 | 5.09 | 0 | 203.54 | CGST 0% URD I/P | 0 | 203.54 | 203.54 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fastner (L) - SOSB | 23 | No. | 10 | 100 | 5.75 | 0 | 230 | CGST 0% URD I/P | 0 | 230 | 230 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 80 | Kgs | 22.8 | 100 | 45.6 | 0 | 1824 | CGST 0% URD I/P | 0 | 1824 | 1824 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 14.92 | Kgs | 26.4 | 100 | 9.85 | 0 | 393.89 | CGST 0% URD I/P | 0 | 393.89 | 393.89 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1374 | 94929 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 367 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (L) | 100.72 | Kgs | 22.8 | 100 | 57.41 | 0 | 2296.42 | CGST 0% URD I/P | 0 | 2296.42 | 2296.42 | Approved | 0 | 0 | 78 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 100.72 | Kgs | 57 | 100 | 0 | 0 | 5741.04 | CGST 0% URD I/P | 0 | 5741.04 | 5741.04 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 107.98 | Kgs | 57 | 100 | 0 | 0 | 6154.86 | CGST 0% URD I/P | 0 | 6154.86 | 6154.86 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 80 | Kgs | 57 | 100 | 0 | 0 | 4560 | CGST 0% URD I/P | 0 | 4560 | 4560 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 6.31 | Kgs | 66 | 100 | 0 | 0 | 416.46 | CGST 0% URD I/P | 0 | 416.46 | 416.46 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fastner (M) - SOSB | 23 | No. | 25 | 100 | 0 | 0 | 575 | CGST 0% URD I/P | 0 | 575 | 575 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 8.8 | Kgs | 66 | 100 | 0 | 0 | 580.8 | CGST 0% URD I/P | 0 | 580.8 | 580.8 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 14.92 | Kgs | 66 | 100 | 0 | 0 | 984.72 | CGST 0% URD I/P | 0 | 984.72 | 984.72 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1373 | 94928 | 31 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 368 | Ganga Business Centre Shop 32 Loft Fabrication work | Fabrication Work (M) | 7.71 | Kgs | 66 | 100 | 0 | 0 | 508.86 | CGST 0% URD I/P | 0 | 508.86 | 508.86 | Approved | 0 | 0 | 0 | 31 May 2022
GANGA DHAM TOWERS | 1162 | 94925 | 31 May 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 353 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 31 May 2022
GANGA DHAM TOWERS | 537 | 94924 | 31 May 2022 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 588 | A 202 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.26 | R.Ft | 650 | 100 | 101.73 | 0 | 4069 | C+S GST 18% I/P RD | 732.42 | 4801.42 | 4801.42 | Approved | 0 | 0 | 115 | 31 May 2022
GANGA DHAM TOWERS | 537 | 94924 | 31 May 2022 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 588 | A 202 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 650 | 100 | 99.13 | 0 | 3965 | C+S GST 18% I/P RD | 713.7 | 4678.7 | 4678.7 | Approved | 0 | 0 | 115 | 31 May 2022
GANGA DHAM TOWERS | 537 | 94924 | 31 May 2022 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 588 | A 202 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.87 | R.Ft | 650 | 100 | 46.64 | 0 | 1865.5 | C+S GST 18% I/P RD | 335.8 | 2201.3 | 2201.3 | Approved | 0 | 0 | 115 | 31 May 2022
GANGA DHAM TOWERS | 537 | 94924 | 31 May 2022 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 588 | A 202 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.4908 | R.Ft | 650 | 100 | 40.48 | 0 | 1619 | C+S GST 18% I/P RD | 291.42 | 1910.42 | 1910.42 | Approved | 0 | 0 | 115 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Powder Toilet dado | Dado BC | 76.707 | Sq.Ft | 22 | 100 | 42.19 | 0 | 1687.55 | C+S GST 18% I/P RD | 303.76 | 1991.31 | 1991.31 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Guest Toilet dado | Dado BC | 117.918 | Sq.Ft | 22 | 100 | 64.85 | 0 | 2594.2 | C+S GST 18% I/P RD | 466.96 | 3061.16 | 3061.16 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Children Toilet dado | Dado BC | 130.698 | Sq.Ft | 22 | 100 | 71.88 | 0 | 2875.36 | C+S GST 18% I/P RD | 517.56 | 3392.92 | 3392.92 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Guest Toilet dado | L Groove - BCV | 27.009 | R.Ft | 20 | 100 | 13.5 | 0 | 540.18 | C+S GST 18% I/P RD | 97.24 | 637.42 | 637.42 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Master Toilet dado | L Groove - BCV | 38.907 | R.Ft | 20 | 100 | 19.45 | 0 | 778.14 | C+S GST 18% I/P RD | 140.06 | 918.2 | 918.2 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Children Toilet dado | L Groove - BCV | 38.763 | R.Ft | 20 | 100 | 19.38 | 0 | 775.26 | C+S GST 18% I/P RD | 139.54 | 914.8 | 914.8 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Powder Toilet dado | L Groove - BCV | 5.74 | R.Ft | 20 | 100 | 2.87 | 0 | 114.8 | C+S GST 18% I/P RD | 20.66 | 135.46 | 135.46 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Master Toilet dado | Dado BC | 130.698 | Sq.Ft | 22 | 100 | 71.88 | 0 | 2875.36 | C+S GST 18% I/P RD | 517.56 | 3392.92 | 3392.92 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Master Toilet dado | Dado BC | 60.048 | Sq.Ft | 24 | 100 | 36.03 | 0 | 1441.15 | C+S GST 18% I/P RD | 259.4 | 1700.55 | 1700.55 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Children Toilet dado | Dado BC | 60.048 | Sq.Ft | 24 | 100 | 36.03 | 0 | 1441.15 | C+S GST 18% I/P RD | 259.4 | 1700.55 | 1700.55 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Guest Toilet dado | Dado BC | 52.452 | Sq.Ft | 24 | 100 | 31.47 | 0 | 1258.85 | C+S GST 18% I/P RD | 226.6 | 1485.45 | 1485.45 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Powder Toilet dado | Dado BC | 35.361 | Sq.Ft | 24 | 100 | 21.22 | 0 | 848.66 | C+S GST 18% I/P RD | 152.76 | 1001.42 | 1001.42 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 21 | 100 | 11.83 | 0 | 473.07 | C+S GST 18% I/P RD | 85.16 | 558.23 | 558.23 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 21 | 100 | 24.01 | 0 | 960.31 | C+S GST 18% I/P RD | 172.86 | 1133.17 | 1133.17 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 21 | 100 | 24.01 | 0 | 960.31 | C+S GST 18% I/P RD | 172.86 | 1133.17 | 1133.17 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 21 | 100 | 19.71 | 0 | 788.32 | C+S GST 18% I/P RD | 141.9 | 930.22 | 930.22 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 551 | 94923 | 31 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | RAHUL ENTERPRISES (Prop Laburi) | EV - 575 | A 1703 Terrace Vitrified Flooring | Vitrified Flooring -BC | 118.863 | Sq.Ft | 24 | 100 | 71.32 | 0 | 2852.71 | C+S GST 18% I/P RD | 513.48 | 3366.19 | 3366.19 | Approved | 0 | 0 | 233 | 31 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 2101 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (M) | 46.9444 | Mtrs | 72 | 100 | 0 | 0 | 3380 | C+S GST 18% I/P RD | 608.4 | 3988.4 | 3988.4 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1101 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (M) | 46.9444 | Mtrs | 72 | 100 | 0 | 0 | 3380 | C+S GST 18% I/P RD | 608.4 | 3988.4 | 3988.4 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1801 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 39.0139 | Mtrs | 72 | 100 | 0 | 0 | 2809 | C+S GST 18% I/P RD | 505.62 | 3314.62 | 3314.62 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1801 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 2101 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 48.8 | Mtrs | 78 | 100 | 0 | 0 | 3806.4 | C+S GST 18% I/P RD | 685.16 | 4491.56 | 4491.56 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1101 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 48.8 | Mtrs | 78 | 100 | 0 | 0 | 3806.4 | C+S GST 18% I/P RD | 685.16 | 4491.56 | 4491.56 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 2101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 8 | Mtrs | 700 | 100 | 0 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 8 | Mtrs | 700 | 100 | 0 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1801 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 700 | 100 | 0 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 2101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 38.1 | Mtrs | 700 | 100 | 0 | 0 | 26670 | C+S GST 18% I/P RD | 4800.6 | 31470.6 | 31470.6 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 38.1 | Mtrs | 700 | 100 | 0 | 0 | 26670 | C+S GST 18% I/P RD | 4800.6 | 31470.6 | 31470.6 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1277 | 94912 | 30 May 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 339 | Tower B 1801 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 40.38 | Mtrs | 700 | 100 | 0 | 0 | 28266 | C+S GST 18% I/P RD | 5087.88 | 33353.88 | 33353.88 | Approved | 0 | 0 | 1207 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1801 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 120 | 100 | 27 | 0 | 1080 | CGST 0% URD I/P | 0 | 1080 | 1080 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 2101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 8 | Mtrs | 120 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1801 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1101 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 48.8 | Mtrs | 18 | 100 | 21.96 | 0 | 878.4 | CGST 0% URD I/P | 0 | 878.4 | 878.4 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 2101 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 48.8 | Mtrs | 18 | 100 | 21.96 | 0 | 878.4 | CGST 0% URD I/P | 0 | 878.4 | 878.4 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 2101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 38.1 | Mtrs | 120 | 100 | 114.3 | 0 | 4572 | CGST 0% URD I/P | 0 | 4572 | 4572 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 38.1 | Mtrs | 120 | 100 | 114.3 | 0 | 4572 | CGST 0% URD I/P | 0 | 4572 | 4572 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1801 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 40.3833 | Mtrs | 120 | 100 | 121.15 | 0 | 4846 | CGST 0% URD I/P | 0 | 4846 | 4846 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1801 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 39 | Mtrs | 20 | 100 | 19.5 | 0 | 780 | CGST 0% URD I/P | 0 | 780 | 780 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1101 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (L) | 46.95 | Mtrs | 20 | 100 | 23.48 | 0 | 939 | CGST 0% URD I/P | 0 | 939 | 939 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 2101 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (L) | 46.95 | Mtrs | 20 | 100 | 23.48 | 0 | 939 | CGST 0% URD I/P | 0 | 939 | 939 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 1278 | 94906 | 30 May 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 338 | Tower B 1101 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 8 | Mtrs | 120 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 224 | 30 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Soil Analysis Test- SOS | 16 | No. | 1500 | 25 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Water Testing report - SOS | 8 | No. | 1000 | 25 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Noise Test Night SOS | 32 | No. | 175 | 25 | 0 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Stack Monitoring Report SOS | 8 | No. | 900 | 25 | 0 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Air Test SOS | 16 | No. | 1500 | 25 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | NOise Test Day SOS | 32 | No. | 125 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Effluent Sample | 4 | No. | 1000 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 799 | 94875 | 27 May 2022 |  | INSTA POLLUTECH LABS | INSTA POLLUTECH LABS | EV - 349 | Test Report ( 2020-21) - | Effluent Sample | 4 | No. | 1000 | 25 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 202 | 27 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 7000.01 | C+S GST 18% I/P RD | 1260 | 8260.01 | 8260.01 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 7000.01 | C+S GST 18% I/P RD | 1260 | 8260.01 | 8260.01 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 7000.01 | C+S GST 18% I/P RD | 1260 | 8260.01 | 8260.01 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1613 | Sq.Ft | 155 | 100 | 0 | 0 | 7000 | C+S GST 18% I/P RD | 1260 | 8260 | 8260 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1613 | Sq.Ft | 155 | 100 | 0 | 0 | 7000 | C+S GST 18% I/P RD | 1260 | 8260 | 8260 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 372 | 94857 | 25 May 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 487 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.1613 | Sq.Ft | 155 | 100 | 0 | 0 | 7000 | C+S GST 18% I/P RD | 1260 | 8260 | 8260 | Approved | 0 | 0 | 420 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2002 Chemical & IPS Waterproofing | IPS W/P | 279 | Sq.Ft | 11 | 100 | 306.9 | 0 | 3069 | CGST 0% URD I/P | 0 | 3069 | 3069 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2102 Chemical & IPS Waterproofing | IPS W/P | 306 | Sq.Ft | 11 | 100 | 336.6 | 0 | 3366 | CGST 0% URD I/P | 0 | 3366 | 3366 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 1503 Chemical & IPS Waterproofing | IPS W/P | 222 | Sq.Ft | 11 | 100 | 244.2 | 0 | 2442 | CGST 0% URD I/P | 0 | 2442 | 2442 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2302 Chemical & IPS Waterproofing | IPS W/P | 306 | Sq.Ft | 11 | 100 | 336.6 | 0 | 3366 | CGST 0% URD I/P | 0 | 3366 | 3366 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2002 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 279 | Sq.Ft | 19 | 100 | 530.1 | 0 | 5301 | CGST 0% URD I/P | 0 | 5301 | 5301 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2302 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 306 | Sq.Ft | 19 | 100 | 581.4 | 0 | 5814 | CGST 0% URD I/P | 0 | 5814 | 5814 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 1503 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 222 | Sq.Ft | 19 | 100 | 421.8 | 0 | 4218 | CGST 0% URD I/P | 0 | 4218 | 4218 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 306 | Sq.Ft | 19 | 100 | 581.4 | 0 | 5814 | CGST 0% URD I/P | 0 | 5814 | 5814 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 1503 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2302 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 1503 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2302 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 1503 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 19 | No. | 70 | 100 | 133 | 0 | 1330 | CGST 0% URD I/P | 0 | 1330 | 1330 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2302 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 21 | No. | 70 | 100 | 147 | 0 | 1470 | CGST 0% URD I/P | 0 | 1470 | 1470 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2002 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 22 | No. | 70 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 401 | 94856 | 25 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 709 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 22 | No. | 70 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 519 | 25 May 2022
GANGA DHAM TOWERS | 1261 | 94855 | 25 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 298 | A 1104 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 53 | Sq.Ft | 55 | 100 | 72.88 | 0 | 2915 | C+S GST 0% I/P RD | 0 | 2915 | 2915 | Approved | 0 | 0 | 186 | 25 May 2022
GANGA DHAM TOWERS | 1261 | 94855 | 25 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 298 | A 1103 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 138.6 | Sq.Ft | 55 | 100 | 190.58 | 0 | 7623 | C+S GST 0% I/P RD | 0 | 7623 | 7623 | Approved | 0 | 0 | 186 | 25 May 2022
GANGA DHAM TOWERS | 1261 | 94855 | 25 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 298 | A 501 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 67 | Sq.Ft | 55 | 100 | 92.13 | 0 | 3685 | C+S GST 0% I/P RD | 0 | 3685 | 3685 | Approved | 0 | 0 | 186 | 25 May 2022
GANGA DHAM TOWERS | 1261 | 94855 | 25 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 298 | A 2501 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 80 | Sq.Ft | 55 | 100 | 110 | 0 | 4400 | C+S GST 0% I/P RD | 0 | 4400 | 4400 | Approved | 0 | 0 | 186 | 25 May 2022
GANGA DHAM TOWERS | 804 | 94849 | 24 May 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 584 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 472.5273 | R.Ft | 55 | 100 | 0 | 0 | 25989 | C+S GST 18% I/P RD | 4678.02 | 30667.02 | 30667.02 | Approved | 0 | 0 | 0 | 24 May 2022
GANGA DHAM TOWERS | 804 | 94849 | 24 May 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 584 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1184 | Sq.Ft | 55 | 100 | 0 | 0 | 65120 | C+S GST 18% I/P RD | 11721.6 | 76841.6 | 76841.6 | Approved | 0 | 0 | 0 | 24 May 2022
GANGA DHAM TOWERS | 805 | 94848 | 24 May 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 378 | B-1801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1184 | Sq.Ft | 20 | 100 | 592 | 0 | 23680 | C+S GST 18% I/P RD | 4262.4 | 27942.4 | 27942.4 | Approved | 0 | 0 | 331 | 24 May 2022
GANGA DHAM TOWERS | 805 | 94848 | 24 May 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 378 | B-1801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 472.55 | R.Ft | 20 | 100 | 236.28 | 0 | 9451 | C+S GST 18% I/P RD | 1701.18 | 11152.18 | 11152.18 | Approved | 0 | 0 | 331 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2104 Chemical & IPS Waterproofing | IPS W/P | 156 | Sq.Ft | 11 | 100 | 171.6 | 0 | 1716 | CGST 0% URD I/P | 0 | 1716 | 1716 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2303 Chemical & IPS Waterproofing | IPS W/P | 125 | Sq.Ft | 11 | 100 | 137.5 | 0 | 1375 | CGST 0% URD I/P | 0 | 1375 | 1375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2403 Chemical & IPS Waterproofing | IPS W/P | 125 | Sq.Ft | 11 | 100 | 137.5 | 0 | 1375 | CGST 0% URD I/P | 0 | 1375 | 1375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2404 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2003 Chemical & IPS Waterproofing | IPS W/P | 125 | Sq.Ft | 11 | 100 | 137.5 | 0 | 1375 | CGST 0% URD I/P | 0 | 1375 | 1375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2204 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2204 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2203 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 125 | Sq.Ft | 19 | 100 | 237.5 | 0 | 2375 | CGST 0% URD I/P | 0 | 2375 | 2375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2404 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2003 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 125 | Sq.Ft | 19 | 100 | 237.5 | 0 | 2375 | CGST 0% URD I/P | 0 | 2375 | 2375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2403 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 125 | Sq.Ft | 19 | 100 | 237.5 | 0 | 2375 | CGST 0% URD I/P | 0 | 2375 | 2375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2104 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 156 | Sq.Ft | 19 | 100 | 296.4 | 0 | 2964 | CGST 0% URD I/P | 0 | 2964 | 2964 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 125 | Sq.Ft | 19 | 100 | 237.5 | 0 | 2375 | CGST 0% URD I/P | 0 | 2375 | 2375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2303 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 125 | Sq.Ft | 19 | 100 | 237.5 | 0 | 2375 | CGST 0% URD I/P | 0 | 2375 | 2375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2304 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 156 | Sq.Ft | 19 | 100 | 296.4 | 0 | 2964 | CGST 0% URD I/P | 0 | 2964 | 2964 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2401 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 101 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2402 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2304 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2103 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2204 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2104 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2303 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2403 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2404 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2304 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 3 | No. | 150 | 100 | 45 | 0 | 450 | CGST 0% URD I/P | 0 | 450 | 450 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2203 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2203 Chemical & IPS Waterproofing | IPS W/P | 125 | Sq.Ft | 11 | 100 | 137.5 | 0 | 1375 | CGST 0% URD I/P | 0 | 1375 | 1375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2103 Chemical & IPS Waterproofing | IPS W/P | 125 | Sq.Ft | 11 | 100 | 137.5 | 0 | 1375 | CGST 0% URD I/P | 0 | 1375 | 1375 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2304 Chemical & IPS Waterproofing | IPS W/P | 156 | Sq.Ft | 11 | 100 | 171.6 | 0 | 1716 | CGST 0% URD I/P | 0 | 1716 | 1716 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2402 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 2401 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 401 | 94847 | 24 May 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 743 | A 101 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 518 | 24 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 2003 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 138.6 | Sq.Ft | 55 | 100 | 190.58 | 0 | 7623 | C+S GST 0% I/P RD | 0 | 7623 | 7623 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 2004 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 1902 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 35 | Sq.Ft | 55 | 100 | 48.13 | 0 | 1925 | C+S GST 0% I/P RD | 0 | 1925 | 1925 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 901 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 1904 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1261 | 94829 | 21 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 299 | A 1303 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 387 | 21 May 2022
GANGA DHAM TOWERS | 1218 | 94818 | 20 May 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 326 | B-Bldg Rebaring work for ledge wall | Rebarring work 8mm dia- BC | 34 | No. | 80 | 100 | 68 | 0 | 2720 | C+S GST 18% I/P RD | 489.6 | 3209.6 | 3209.6 | Approved | 0 | 0 | 54 | 20 May 2022
GANGA DHAM TOWERS | 1219 | 94817 | 20 May 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 323 | A-Bldg Rebaring Work in Flat-1,2,3,4 | Rebaring work 8mm dia.- DTR | 64 | No. | 80 | 100 | 128 | 0 | 5120 | C+S GST 18% I/P RD | 921.6 | 6041.6 | 6041.6 | Approved | 0 | 0 | 102 | 20 May 2022
GANGA DHAM TOWERS | 149 | 94812 | 19 May 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 266 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3282 | No. | 4 | 100 | 0 | 0 | 13128 | CGST 0% URD I/P | 0 | 13128 | 13128 | Approved | 0 | 0 | 0 | 19 May 2022
GANGA DHAM TOWERS | 371 | 94806 | 18 May 2022 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 362 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | RCC Superstructure (B-up area) | 500.0025 | Sq.Ft | 200.665 | 100 | 2508.33 | 0 | 100333 | CGST 0% URD I/P | 0 | 100333 | 100333 | Approved | 0 | 0 | 1253 | 18 May 2022
GANGA DHAM TOWERS | 371 | 94806 | 18 May 2022 |  | CONSTROGENESIS | VYANKAT SAI CONSTRUCTION | EV - 362 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | RCC Superstructure (B-up area) | 124.6007 | Sq.Ft | 200.665 | 100 | 625.07 | 0 | 25003 | CGST 0% URD I/P | 0 | 25003 | 25003 | Approved | 0 | 0 | 1253 | 18 May 2022
GANGA DHAM TOWERS | 1228 | 94801 | 17 May 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 358 | R & D Purpose | R & D Purpose | 0.0022 | No. | 100000 | 100 | 0 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 5 | 17 May 2022
GANGA DHAM TOWERS | 983 | 94793 | 16 May 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 503 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 3" BCE | 65 | No. | 210 | 100 | 341.25 | 0 | 13650 | CGST 0% URD I/P | 0 | 13650 | 13650 | Approved | 0 | 0 | 372 | 16 May 2022
GANGA DHAM TOWERS | 983 | 94793 | 16 May 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 503 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 112 | No. | 210 | 100 | 588 | 0 | 23520 | CGST 0% URD I/P | 0 | 23520 | 23520 | Approved | 0 | 0 | 372 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 2202 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 2102 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 701 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 804 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 803 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 1202 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1200 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 1404 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 1401 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 1604 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 1504 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 455 | 94792 | 16 May 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE |  | A Bldg Flat No. 201 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 |  | 0 | 0 | 147 | 16 May 2022
GANGA DHAM TOWERS | 389 | 94782 | 13 May 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK |  | Loading / Unloading Expenses | Unloading work-SO | 3 | No. | 1000 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 |  | 0 | 0 | 0 | 13 May 2022
GANGA DHAM TOWERS | 389 | 94782 | 13 May 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK |  | Loading / Unloading Expenses | Unloading of AAC Blocks | 2062 | No. | 2 | 100 | 0 | 0 | 4124 | CGST 0% URD I/P | 0 | 4124 | 4124 |  | 0 | 0 | 0 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.7895 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.6966 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.7895 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.6966 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.7895 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.6966 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.5526 | Sq.Ft | 152 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.5526 | Sq.Ft | 152 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.5526 | Sq.Ft | 152 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 272 | 94781 | 13 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 136 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.5526 | Sq.Ft | 152 | 100 | 0 | 0 | 7380 | C+S GST 18% I/P RD | 1328.4 | 8708.4 | 8708.4 | Approved | 0 | 29661 | 738 | 13 May 2022
GANGA DHAM TOWERS | 971 | 94780 | 13 May 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 214 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 22 | No. | 210 | 100 | 115.5 | 0 | 4620 | C+S GST 18% I/P RD | 831.6 | 5451.6 | 5451.6 | Approved | 0 | 0 | 65 | 13 May 2022
GANGA DHAM TOWERS | 971 | 94780 | 13 May 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 214 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 9 | No. | 210 | 100 | 47.25 | 0 | 1890 | C+S GST 18% I/P RD | 340.2 | 2230.2 | 2230.2 | Approved | 0 | 0 | 65 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 203 Terrace Parapet Top Granite | Granite Sill-BCo | 24.675 | R.Ft | 40 | 100 | 24.68 | 0 | 987 | C+S GST 18% I/P RD | 177.66 | 1164.66 | 1164.66 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 504 Terrace Parapet Top Granite | Granite Sill-BCo | 20.625 | R.Ft | 40 | 100 | 20.63 | 0 | 825 | C+S GST 18% I/P RD | 148.5 | 973.5 | 973.5 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 403 Terrace Parapet Top Granite | Granite Sill-BCo | 24.675 | R.Ft | 40 | 100 | 24.68 | 0 | 987 | C+S GST 18% I/P RD | 177.66 | 1164.66 | 1164.66 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1403 Terrace Parapet Top Granite | Granite Sill-BCo | 11.68 | R.Ft | 50 | 100 | 14.6 | 0 | 584 | C+S GST 18% I/P RD | 105.12 | 689.12 | 689.12 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1604 Terrace Parapet Top Granite | Granite Sill-BCo | 20.62 | R.Ft | 50 | 100 | 25.78 | 0 | 1031 | C+S GST 18% I/P RD | 185.58 | 1216.58 | 1216.58 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1303 Terrace Parapet Top Granite | Granite Sill-BCo | 24.68 | R.Ft | 50 | 100 | 30.85 | 0 | 1234 | C+S GST 18% I/P RD | 222.12 | 1456.12 | 1456.12 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1104 Terrace Parapet Top Granite | Granite Sill-BCo | 20.6222 | R.Ft | 45 | 100 | 23.2 | 0 | 928 | C+S GST 18% I/P RD | 167.04 | 1095.04 | 1095.04 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 903 Terrace Parapet Top Granite | Granite Sill-BCo | 11.6667 | R.Ft | 45 | 100 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1103 Terrace Parapet Top Granite | Granite Sill-BCo | 24.6667 | R.Ft | 45 | 100 | 27.75 | 0 | 1110 | C+S GST 18% I/P RD | 199.8 | 1309.8 | 1309.8 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 704 Terrace Parapet Top Granite | Granite Sill-BCo | 7.6222 | R.Ft | 45 | 100 | 8.57 | 0 | 343 | C+S GST 18% I/P RD | 61.74 | 404.74 | 404.74 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1203 Terrace Parapet Top Granite | Granite Sill-BCo | 11 | R.Ft | 45 | 100 | 12.38 | 0 | 495 | C+S GST 18% I/P RD | 89.1 | 584.1 | 584.1 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Children Toilet dado | Dado BC | 120 | Sq.Ft | 28 | 100 | 84 | 0 | 3360 | C+S GST 18% I/P RD | 604.8 | 3964.8 | 3964.8 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Master Toilet dado | Dado BC | 62 | Sq.Ft | 28 | 100 | 43.4 | 0 | 1736 | C+S GST 18% I/P RD | 312.48 | 2048.48 | 2048.48 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Guest Toilet dado | Dado BC | 108 | Sq.Ft | 28 | 100 | 75.6 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Master Toilet dado | Dado BC | 125 | Sq.Ft | 28 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Children Toilet dado | Dado BC | 55 | Sq.Ft | 28 | 100 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 551 | 94779 | 13 May 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 198 | A 1903 Guest Toilet dado | Dado BC | 48 | Sq.Ft | 28 | 100 | 33.6 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 236 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A-1102 Parents Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 24.835 | R.Ft | 50 | 100 | 31.04 | 0 | 1241.75 | C+S GST 18% I/P RD | 223.52 | 1465.27 | 1465.27 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A-1102 Master Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 33.45 | R.Ft | 50 | 100 | 41.81 | 0 | 1672.5 | C+S GST 18% I/P RD | 301.06 | 1973.56 | 1973.56 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A-1102 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Champher & Polish | 57.295 | R.Ft | 50 | 100 | 71.62 | 0 | 2864.75 | C+S GST 18% I/P RD | 515.66 | 3380.41 | 3380.41 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A 2402 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 57.295 | R.Ft | 60 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A 2402 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 24.835 | R.Ft | 60 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 641 | 94778 | 13 May 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 445 | A 2402 Master Bed Marble Flooring | Italian Marble Champher & Polish | 33.45 | R.Ft | 60 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 127 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.26 | Sq.Ft | 21 | 100 | 89.91 | 0 | 3596.46 | C+S GST 18% I/P RD | 647.36 | 4243.82 | 4243.82 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 50 | 100 | 228.06 | 0 | 9122.5 | C+S GST 18% I/P RD | 1642.06 | 10764.56 | 10764.56 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 567.0819 | Sq.Ft | 50 | 100 | 708.85 | 0 | 28354.1 | C+S GST 18% I/P RD | 5103.74 | 33457.84 | 33457.84 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Guest Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 50 | 100 | 163.97 | 0 | 6558.65 | C+S GST 18% I/P RD | 1180.56 | 7739.21 | 7739.21 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Master Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 50 | 100 | 263.31 | 0 | 10532.5 | C+S GST 18% I/P RD | 1895.86 | 12428.36 | 12428.36 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 60 | 100 | 78.74 | 0 | 3149.76 | C+S GST 18% I/P RD | 566.96 | 3716.72 | 3716.72 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 60 | 100 | 141.05 | 0 | 5641.92 | C+S GST 18% I/P RD | 1015.54 | 6657.46 | 6657.46 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 1102 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140.472 | Sq.Ft | 20 | 100 | 70.24 | 0 | 2809.44 | C+S GST 18% I/P RD | 505.7 | 3315.14 | 3315.14 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 1102 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 135.873 | Sq.Ft | 20 | 100 | 67.94 | 0 | 2717.46 | C+S GST 18% I/P RD | 489.14 | 3206.6 | 3206.6 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 161.84 | Sq.Ft | 28 | 100 | 113.29 | 0 | 4531.52 | C+S GST 18% I/P RD | 815.68 | 5347.2 | 5347.2 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 28 | 100 | 111.89 | 0 | 4475.77 | C+S GST 18% I/P RD | 805.64 | 5281.41 | 5281.41 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 1102 Tiling Below Wooden Flooring | Ceramic Flooring work | 151 | Sq.Ft | 16 | 100 | 60.4 | 0 | 2416 | C+S GST 18% I/P RD | 434.88 | 2850.88 | 2850.88 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 60 | 100 | 316.46 | 0 | 12658.2 | C+S GST 18% I/P RD | 2278.48 | 14936.68 | 14936.68 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 60 | 100 | 342.3 | 0 | 13692 | C+S GST 18% I/P RD | 2464.56 | 16156.56 | 16156.56 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 60 | 100 | 196.76 | 0 | 7870.38 | C+S GST 18% I/P RD | 1416.66 | 9287.04 | 9287.04 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A 2401 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 566.973 | Sq.Ft | 60 | 100 | 850.46 | 0 | 34018.38 | C+S GST 18% I/P RD | 6123.3 | 40141.68 | 40141.68 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 39.736 | R.Ft | 50 | 100 | 49.67 | 0 | 1986.8 | C+S GST 18% I/P RD | 357.62 | 2344.42 | 2344.42 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Master Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 53.52 | R.Ft | 50 | 100 | 66.9 | 0 | 2676 | C+S GST 18% I/P RD | 481.68 | 3157.68 | 3157.68 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 537 | 94777 | 13 May 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 199 | A-1102 Living,Dining,Passa. Marble Flooring - 1 No. | Italian marble Skirting - BCo | 91.672 | R.Ft | 50 | 100 | 114.59 | 0 | 4583.6 | C+S GST 18% I/P RD | 825.04 | 5408.64 | 5408.64 | Approved | 0 | 0 | 1644 | 13 May 2022
GANGA DHAM TOWERS | 541 | 94776 | 13 May 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1103 | B Core Cutting Work | Core Cutting Work 3" BCE | 5 | No. | 210 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 11 | 13 May 2022
GANGA DHAM TOWERS | 1252 | 94775 | 13 May 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | PATIL CONSTRUCTION | EV - 1102 | B 1001 NOC | Core Cutting Work 3" BCE | 3 | No. | 300 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 9 | 13 May 2022
GANGA DHAM TOWERS | 993 | 94774 | 13 May 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | PATIL CONSTRUCTION | EV - 1100 | B 701 NOC | Core Cutting Work 3" BCE | 2 | No. | 300 | 100 | 0 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 0 | 6 | 13 May 2022
GANGA DHAM TOWERS | 1248 | 94773 | 13 May 2022 |  | AVCON TECHNICS PVT LTD | PATIL CONSTRUCTION | EV - 1101 | B 201 NOC | Core Cutting Work 3" BCE | 3 | No. | 300 | 100 | 0 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 9 | 13 May 2022
GANGA DHAM TOWERS | 1250 | 94772 | 13 May 2022 |  | AVCON TECHNICS PVT LTD | PATIL CONSTRUCTION | EV - 1099 | B 1901 NOC | Core Cutting Work 5" -DER | 5 | No. | 210 | 100 | 0 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 11 | 13 May 2022
GANGA DHAM TOWERS | 971 | 94771 | 13 May 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1104 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 10 | No. | 210 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 231 | 13 May 2022
GANGA DHAM TOWERS | 971 | 94771 | 13 May 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1104 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 100 | No. | 210 | 100 | 525 | 0 | 21000 | C+S GST 18% I/P RD | 3780 | 24780 | 24780 | Approved | 0 | 0 | 231 | 13 May 2022
GANGA DHAM TOWERS | 616 | 94763 | 12 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 180 | B P3 Parking Floor Blockwork 5" (108 Level) | Blockwork 5" - BC - | 167.6923 | Sq.Ft | 13 | 100 | 54.5 | 0 | 2180 | CGST 0% URD I/P | 0 | 2180 | 2180 | Approved | 0 | 0 | 22 | 12 May 2022
GANGA DHAM TOWERS | 615 | 94762 | 12 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 179 | A Ground Floor Blockwork 5" (99 Level) | Blockwork 5" - BC - | 187.6154 | Sq.Ft | 13 | 100 | 60.98 | 0 | 2439 | CGST 0% URD I/P | 0 | 2439 | 2439 | Approved | 0 | 0 | 91 | 12 May 2022
GANGA DHAM TOWERS | 615 | 94762 | 12 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 179 | A P2 Parking Floor Blockwork 4" (105 Level) | Blockwork 4" - BC | 169.6154 | Sq.Ft | 13 | 100 | 55.13 | 0 | 2205 | CGST 0% URD I/P | 0 | 2205 | 2205 | Approved | 0 | 0 | 91 | 12 May 2022
GANGA DHAM TOWERS | 615 | 94762 | 12 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 179 | A P1 Parking Floor Blockwork 4" (102 Level) | Blockwork 4" - BC | 169.6154 | Sq.Ft | 13 | 100 | 55.13 | 0 | 2205 | CGST 0% URD I/P | 0 | 2205 | 2205 | Approved | 0 | 0 | 91 | 12 May 2022
GANGA DHAM TOWERS | 615 | 94762 | 12 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 179 | A P3 Parking Floor Blockwork 4" (108 Level) | Blockwork 4" - BC | 169.6154 | Sq.Ft | 13 | 100 | 55.13 | 0 | 2205 | CGST 0% URD I/P | 0 | 2205 | 2205 | Approved | 0 | 0 | 91 | 12 May 2022
GANGA DHAM TOWERS | 477 | 94761 | 12 May 2022 |  | ANJALI ENTERPRISES | ANAND LALURAM SUTHAR | EV - 1463 | Tower B-Temporary Door Fixing Upto 20 Floors | Temporary Door Fixing | 8 | No. | 200 | 100 | 40 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 112 | 12 May 2022
GANGA DHAM TOWERS | 477 | 94761 | 12 May 2022 |  | ANJALI ENTERPRISES | ANAND LALURAM SUTHAR | EV - 1463 | Tower B-Temporary Door Fixing Upto 20 Floors | Door Shutter fixing - | 16 | No. | 600 | 100 | 240 | 0 | 9600 | CGST 0% URD I/P | 0 | 9600 | 9600 | Approved | 0 | 0 | 112 | 12 May 2022
GANGA DHAM TOWERS | 1012 | 94760 | 12 May 2022 |  | LALURAM B SHARMA | ANAND LALURAM SUTHAR | EV - 1460 | B Temporary Door - 1 No. | Department Labour- BC | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 13 | 12 May 2022
GANGA DHAM TOWERS | 1012 | 94760 | 12 May 2022 |  | LALURAM B SHARMA | ANAND LALURAM SUTHAR | EV - 1460 | B Temporary Door - 1 No. | Department Labour- BC | 1 | No. | 800 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 13 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.5132 | Sq.Ft | 152 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.5132 | Sq.Ft | 152 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.5132 | Sq.Ft | 152 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 51.5132 | Sq.Ft | 152 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.483 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.483 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.483 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.9474 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.9474 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 272 | 94759 | 12 May 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 486 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.9474 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7830 | C+S GST 18% I/P RD | 1409.4 | 9239.4 | 9239.4 | Approved | 0 | 0 | 783 | 12 May 2022
GANGA DHAM TOWERS | 1210 | 94748 | 11 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 369 | A-Bldg at lift fabrication frame for Advertise board | Fabrication work (L) | 184.48 | Kgs | 11 | 100 | 50.73 | 0 | 2029.28 | CGST 0% URD I/P | 0 | 2029.28 | 2029.28 | Approved | 0 | 0 | 133 | 11 May 2022
GANGA DHAM TOWERS | 1210 | 94748 | 11 May 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 369 | A-Bldg at lift fabrication frame for Advertise board | Fabrication work (L) | 1028.03 | Kgs | 11 | 100 | 282.71 | 0 | 11308.33 | CGST 0% URD I/P | 0 | 11308.33 | 11308.33 | Approved | 0 | 0 | 133 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 3rd floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 17th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 18th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 20th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 21st floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 2nd floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 14th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 16th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 9th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 6th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 12th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 10th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 11th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 5th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 13th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 4th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 15th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 22nd floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 8th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 24th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 7th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 23rd floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 1st floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 845 | 94747 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 296 | A Westside 19th floor External Texture Painting | Texture Paint (M) | 564.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 0 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 6th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 21st floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 3rd floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 20th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 22nd floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 4th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 12th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 11th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 10th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 5th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 9th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 18th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 13th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 15th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 24th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 7th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 23rd floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 14th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 2nd floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 1st floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 8th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 17th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 19th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 16th floor External Texture Painting | Scaffolding/Gondola work | 565.1429 | Sq.Ft | 3.5 | 100 | 49.45 | 0 | 1978 | C+S GST 18% I/P RD | 356.04 | 2334.04 | 2334.04 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 12th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 1st floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 18th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 19th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 22nd floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 5th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 10th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 11th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 3rd floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 20th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 15th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 13th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 24th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 14th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 7th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 6th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 8th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 23rd floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 17th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 2nd floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 4th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 21st floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 16th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 844 | 94746 | 11 May 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 297 | A Westside 9th floor External Texture Painting | Texture Paint (L) | 564.9655 | Sq.Ft | 7.25 | 100 | 102.4 | 0 | 4096 | C+S GST 18% I/P RD | 737.28 | 4833.28 | 4833.28 | Approved | 0 | 0 | 1458 | 11 May 2022
GANGA DHAM TOWERS | 1296 | 94743 | 31 Mar 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2338 | Miscellaneous expenses | Marketing Operating Expenses | 1.4406 | Month | 25000 | 8.33 | 0 | 0 | 3000 | C+S GST 0% I/P RD | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 300 | 94741 | 10 May 2022 |  | AMOL WATER SUPPLIERS | AMOL WATER SUPPLIERS | EV - 517 | Water Supply Water Tanker Supply | Water Tanker supply | 60 | Trips | 800 | 100 | 0 | 0 | 48000 | CGST 0% URD I/P | 0 | 48000 | 48000 | Approved | 0 | 0 | 0 | 10 May 2022
GANGA DHAM TOWERS | 300 | 94741 | 10 May 2022 |  | AMOL WATER SUPPLIERS | AMOL WATER SUPPLIERS | EV - 517 | Water Supply Water Tanker Supply | Water Tanker supply | 8 | Trips | 800 | 100 | 0 | 0 | 6400 | CGST 0% URD I/P | 0 | 6400 | 6400 | Approved | 0 | 0 | 0 | 10 May 2022
GANGA DHAM TOWERS | 696 | 94740 | 10 May 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 270 | B P2 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 194 | Sq.Ft | 5 | 100 | 24.25 | 0 | 970 | CGST 0% URD I/P | 0 | 970 | 970 | Approved | 0 | 0 | 17 | 10 May 2022
GANGA DHAM TOWERS | 696 | 94740 | 10 May 2022 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 270 | B P2 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 194 | Sq.Ft | 4 | 100 | 19.4 | 0 | 776 | CGST 0% URD I/P | 0 | 776 | 776 | Approved | 0 | 0 | 17 | 10 May 2022
GANGA DHAM TOWERS | 1065 | 94739 | 10 May 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 218 | A Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 513 | Sq.Ft | 9 | 100 | 115.43 | 0 | 4617 | CGST 0% URD I/P | 0 | 4617 | 4617 | Approved | 0 | 0 | 46 | 10 May 2022
GANGA DHAM TOWERS | 1067 | 94738 | 10 May 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 217 | B Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 291 | Sq.Ft | 9 | 100 | 65.48 | 0 | 2619 | CGST 0% URD I/P | 0 | 2619 | 2619 | Approved | 0 | 0 | 26 | 10 May 2022
GANGA DHAM TOWERS | 1133 | 94736 | 10 May 2022 |  | BASSAPPA CHAVAN | NAMANNA RATHOD | EV - 361 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 18 | No. | 800 | 100 | 0 | 0 | 14400 | CGST 0% URD I/P | 0 | 14400 | 14400 | Approved | 0 | 0 | 144 | 10 May 2022
GANGA DHAM TOWERS | 1334 | 94735 | 10 May 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 203 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 680 | Mtrs | 90 | 100 | 1530 | 0 | 61200 | C+S GST 18% I/P RD | 11016 | 72216 | 72216 | Approved | 0 | 0 | 1373 | 10 May 2022
GANGA DHAM TOWERS | 1334 | 94735 | 10 May 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 203 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 628 | Mtrs | 90 | 100 | 1413 | 0 | 56520 | C+S GST 18% I/P RD | 10173.6 | 66693.6 | 66693.6 | Approved | 0 | 0 | 1373 | 10 May 2022
GANGA DHAM TOWERS | 1334 | 94735 | 10 May 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 203 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 120sqmm-UTI | 186 | Mtrs | 65 | 100 | 302.25 | 0 | 12090 | C+S GST 18% I/P RD | 2176.2 | 14266.2 | 14266.2 | Approved | 0 | 0 | 1373 | 10 May 2022
GANGA DHAM TOWERS | 1334 | 94735 | 10 May 2022 |  | ADITI POWER CARE AND ENTERPRISES | ADITI POWER CARE AND ENTERPRISES | EV - 203 | A,B,D Meter Room to Substation LT Cable | Al. Arm. Cable laying 3.5C 95sqmm-DCH | 136 | Mtrs | 55 | 100 | 187 | 0 | 7480 | C+S GST 18% I/P RD | 1346.4 | 8826.4 | 8826.4 | Approved | 0 | 0 | 1373 | 10 May 2022
GANGA DHAM TOWERS | 1296 | 94729 | 09 May 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 148 | Miscellaneous expenses | Marketing Operating Expenses | 6.8591 | Month | 25000 | 8.33 | 0 | 0 | 14284 | C+S GST 0% I/P RD | 0 | 14284 | 14284 | Approved | 0 | 0 | 0 | 09 May 2022
GANGA DHAM TOWERS | 1250 | 94711 | 09 May 2022 |  | AVCON TECHNICS PVT LTD | JAY GANESH ENTERPRISES | EV - 197 | B 1901 NOC | Blockwork 4" - BC | 210.15 | Sq.Ft | 20 | 100 | 105.08 | 0 | 4203 | CGST 0% URD I/P | 0 | 4203 | 4203 | Approved | 0 | 0 | 42 | 09 May 2022
GANGA DHAM TOWERS | 1340 | 94706 | 07 May 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 94 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 07 May 2022
GANGA DHAM TOWERS | 1356 | 94702 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 195 | D Building 1202 Rough Plaster | Rough Plaster rate diff. | 374.84 | Sq.Ft | 5 | 100 | 46.86 | 0 | 1874.2 | CGST 0% URD I/P | 0 | 1874.2 | 1874.2 | Approved | 0 | 0 | 117 | 07 May 2022
GANGA DHAM TOWERS | 1356 | 94702 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 195 | D Building 1201 Rough Plaster | Rough Plaster rate diff. | 553.55 | Sq.Ft | 5 | 100 | 69.19 | 0 | 2767.75 | CGST 0% URD I/P | 0 | 2767.75 | 2767.75 | Approved | 0 | 0 | 117 | 07 May 2022
GANGA DHAM TOWERS | 1356 | 94702 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 195 | D Building 1203 Rough Plaster | Rough Plaster rate diff. | 425.39 | Sq.Ft | 5 | 100 | 53.17 | 0 | 2126.95 | CGST 0% URD I/P | 0 | 2126.95 | 2126.95 | Approved | 0 | 0 | 117 | 07 May 2022
GANGA DHAM TOWERS | 1356 | 94702 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 195 | D Building 1204 Rough Plaster | Rough Plaster rate diff. | 425.39 | Sq.Ft | 5 | 100 | 53.17 | 0 | 2126.95 | CGST 0% URD I/P | 0 | 2126.95 | 2126.95 | Approved | 0 | 0 | 117 | 07 May 2022
GANGA DHAM TOWERS | 1356 | 94702 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 195 | D Building 1205 Rough Plaster | Rough Plaster rate diff. | 553.55 | Sq.Ft | 5 | 100 | 69.19 | 0 | 2767.75 | CGST 0% URD I/P | 0 | 2767.75 | 2767.75 | Approved | 0 | 0 | 117 | 07 May 2022
GANGA DHAM TOWERS | 1315 | 94699 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 204 | D Building 1201 Rough Plaster | Rough Plaster | 553.55 | Sq.Ft | 15 | 100 | 207.58 | 0 | 8303.25 | C+S GST 0% I/P RD | 0 | 8303.25 | 8303.25 | Approved | 0 | 0 | 350 | 07 May 2022
GANGA DHAM TOWERS | 1315 | 94699 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 204 | D Building 1203 Rough Plaster | Rough Plaster | 425.39 | Sq.Ft | 15 | 100 | 159.52 | 0 | 6380.85 | C+S GST 0% I/P RD | 0 | 6380.85 | 6380.85 | Approved | 0 | 0 | 350 | 07 May 2022
GANGA DHAM TOWERS | 1315 | 94699 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 204 | D Building 1204 Rough Plaster | Rough Plaster | 425.39 | Sq.Ft | 15 | 100 | 159.52 | 0 | 6380.85 | C+S GST 0% I/P RD | 0 | 6380.85 | 6380.85 | Approved | 0 | 0 | 350 | 07 May 2022
GANGA DHAM TOWERS | 1315 | 94699 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 204 | D Building 1202 Rough Plaster | Rough Plaster | 374.84 | Sq.Ft | 15 | 100 | 140.57 | 0 | 5622.6 | C+S GST 0% I/P RD | 0 | 5622.6 | 5622.6 | Approved | 0 | 0 | 350 | 07 May 2022
GANGA DHAM TOWERS | 1315 | 94699 | 07 May 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 204 | D Building 1205 Rough Plaster | Rough Plaster | 553.55 | Sq.Ft | 15 | 100 | 207.58 | 0 | 8303.25 | C+S GST 0% I/P RD | 0 | 8303.25 | 8303.25 | Approved | 0 | 0 | 350 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1102 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | CGST 0% URD I/P | 0 | 722.1 | 722.1 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1104 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | CGST 0% URD I/P | 0 | 1152.75 | 1152.75 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1101 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | CGST 0% URD I/P | 0 | 1817.1 | 1817.1 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1105 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | CGST 0% URD I/P | 0 | 1817.1 | 1817.1 | Approved | 0 | 0 | 293 | 07 May 2022